## Sheet1
Step # | Description | Location | Estimator | Duration (days)
1 | Lock up and tag out the TMA horizon pointing. Daily safety check for each step forward. | TMA |  | 0.1
2 | Warming up the camera - cold and cryo semi sequentially (still under vacuum) - 24hrs Prep and deploy platform at the same time while warming up - 24 hrs Add the L1 cover while warming up - 8hrs | TMA at horizon |  | 1 | Use case 1: Camera comes off when M2 gets re-coated
3 | Vent and purge with N2 the Cryostat, Hex Ca | TMA at horizon |  | 0.25 | Use case 2: Camera service time that cannot be addressed on TMA
4 | Remove the Calibration screen reflector (need a place to put it) | TMA at horizon |  | 0.5
5 | Preparation for refrigeration Cryo disconnection - up to 3 days if full recovery can we leave the liquid refrigerant in or need to recover? Is recovery before or after disconneting | TMA at horizon |  | 3
6 | Preparation for pumped coolant disconnection - 1 day or less for the pumped coolant | TMA at horizon |  | 1
7 | Disconnect all camera utilities, power and fibers | TMA at horizon | Reil | 2
8 | Disconnect all Integrator utilities | TMA at horizon | Andrew | 1
9 | Preparation for the lift - Install scaffolding in front and back (2 days) - Add guide rails and rollers (0.5 days) - needs the scaffolding for part of it - Bring the lift fixture from 5 to 8 (1 day) in parallel with scaffolding - Bring Cart from 3 to 8 (1 day), sequential with lift fixture but in parallel with scaffolding | TMA at horizon | Barr | 3
10 | Extract camera integrating structure and load on cart | Level 8 |  | 1
11 | Move lifting fixture back to level 5 | Level 5 |  | 1
12 | Bring camera integrating structure to level 3 | Level 3 |  | 1
13 | Service Time - includes camera disconnected and ready on the cart at level 3 - assumes the TMA remains locked During servicing, the cryo lines should be kept dry using dry N2. (How to get the N2 is not clear)
14 | Move lifting fixture from level 5 to 8 | Level 8 |  | 1
15 | Bring camera integrating structure from level 3 to 8 | Level 8 |  | 1
16 | Insert camera integrating structure on TMA | Level 8 |  | 1
17 | Connect all Integrator utilities and re-start and check for leaks and functional check | TMA at horizon | Andrew | 2
18 | Connect all camera utilities, power and fibers (clean fibers) and bring the pump cart to the extended platform | TMA at horizon | Reil | 2
19 | Camera turn on an testing of camera functionality (dynalene was checked at time of integrator) - Phase 1: Protection, dynalene, power distribution, Environmental core control (purge) - 2 days - Start Pumping down while Path 2 occurs (1 day) - Phase 2: Funtional testing of sub-systems except CCDs (Carousel, shutter, auto-changer) - 1 day | TMA at horizon | Marshall | 3
20 | Connect Pumped coolant lines and N2 purge and pressure test and fill at room temperature | TMA at horizon | Nordby | 1
21 | Turn pumped coolant on and cool down the cold plate In parallel connect the cryo lines. | TMA at horizon | Marshall | 1
22 | Dry down the cryo lines (need additional system to help parallel processing) to ensure the dew point temperature is correct. Review durations with Boyd. Conduct REB aliveness test in parallel | TMA at horizon |  | 3
23 | Charge the cryo systems (2 circuits per day) - Check duration with Boyd | TMA at horizon |  | 3
24 | Cool down Cryo plate - Pre-Conductioning (35C step) - 0.5 day - Conditioning (40C) sequence and actual cool down - 2 days | TMA at horizon | Utsumi | 3
25 | Turn on the CCDs | TMA at horizon | Utsumi | 1
26 | Remount calibration screen projector and check initial alignment | TMA at horizon |  | 1
27 | Remove scaffolding | TMA at horizon | Reil | 1
28 | Remove L1 cover (0.5) and return TMA to operational state (includes retracting the platform, pump cart, etc.) | TMA at horizon |  | 2
29 | Run deluxe daily calibration | TMA at horizon | Roodman | 3
| TOTAL |  |  | 43.85