## Slide 1: Camera Summit Reverification Travis Lange Camera I&T Engineer NSF/DOE LSST Commissioning Review August 2, 2018

## Slide 2: Outline
Schedule, Budget, Risks and Hazards
Reassembling the Camera
Re-Verification of Requirements

## Slide 3: Schedule, Budget, Risks, and Hazards

## Slide 4: Schedule
Scope
  This WBS takes the LSSTCam from delivery at the summit to ready for installation on the telescope
Duration
  June 2020  November 2020

## Slide 5: Budget
Reverification-related FTEs
  7.2 FTEs average per month during reverification process
    Primarily DOE
Procurements - $5k (all DOE)
  Miscellaneous tools and hardware

## Slide 6: Risks
Inherited from Camera I&T
  IT-035 Refrigeration expertise required
  IT-036 Optical engineer expertise required
DOEC-004, Accelerated Camera MIE rolloff
DOEC-010, Refrigeration preparation time
DOEC-012, Optical filter delays (affects ability to perform throughput testing)
DOEC-013 / CRYO-057, Refrigeration ICD mismatch
DOEC-015, Refrigeration Technician training

## Slide 7: Hazards
Inherited from I&T during their verification process
DOE personnel on summit for first time will require additional training

## Slide 8: Camera Assembly and Re-verification

## Slide 9: Introduction
The LSST Camera needs to be delivered from SLAC to the Cerro Pachon Summit
  See presentation by Margaux Lopez
  To mitigate hazards to the Camera hardware, the optics are being removed and shipped separately
Plan for reassembly at the summit is required
Subset of camera requirements need to be re-verified

## Slide 10: Reassembly of the Camera after shipping

## Slide 11: 3rd Floor Camera Maintenance Facility
Clean Room
White Room
Camera Staging and Test Area
Utility Area
Mirror Coating Facility
Walkway

## Slide 12: Receiving the Camera and Prepping for Install
Camera Integration Stand
BOT
Camera Staging and Test Area
White Room (class 100,000)
Clean Room (class 10,000)

## Slide 13: Receiving the Camera—LCA-13420
Remove Camera from Shipping Container and move into White Room

## Slide 14: Camera Staging and Test Area
Camera Integration Stand

## Slide 15: Receive Camera from SLAC on Saddle Stand
Camera on Support Stand

## Slide 16: Move Camera Into White Room

## Slide 17: Camera in White Room
Camera in Support Stand
L1-L2 Support Stand

## Slide 18: Bring L1-L2 Container into White Room
L1-L2 Shipping Container
L1-L2 Support Stand

## Slide 19: Prep L1-L2
L1-L2 Shipping Container
L1-L2 on Support Stand

## Slide 20: Remove L1-L2 Shipping Container

## Slide 21: Integrate L1-L2 and Shroud to Camera

## Slide 22: Move Camera into Staging Area

## Slide 23: Prep Filters for Camera
Bench Top Stand
Filter Loader on Cart
Filter Clean Storage Box
Holds 6 filter assemblies
Manually move filters from individual shipping container into bench top stand.
Use filter loader to move filters from bench top stand to filter storage box, fully automated.

## Slide 24: Prep Camera for Move to Integration Stand

## Slide 25: Install Filters in Camera
Filter Clean Storage Box

## Slide 26: Camera Testing & Alignment

## Slide 27: Prep Hexapod/Rotator Assembly
Camera Integration Assembly Stand/Cart

## Slide 28
Camera Integration Assembly on Cart

## Slide 29: Integrate Camera on Hexapod/Rotator Assembly
Complete Camera Integration Assembly on cart, ready for move to telescope

## Slide 30: Re-Verification of the Camera Requirements

## Slide 31: Functional and Performance Tests
Subset of functional tests re-verified before L1-L2 assembly is installed
  CCS Control
  Hardware Protection System
  Shutter
  Auto Changer
  Filter Exchange with Carousel (no filter present)
  Cryostat vacuum—leak check
After Camera reassembly:
  Refrigeration temperature control
  Camera body temperature control (purge air system)
  Data Acquisition

## Slide 32: Alignment and Performance—After Reassembly
  Survey and Alignment
  Placement and verification of Best Fit Optical Axis
Darks
  Noise Level
  Bad Pixels
  Traps (potentially)
Flat Field (photon transfer)
  Gain
  Linearity
  Full Well
Calibrated Optical Beam Projector (CCOB) Narrow Beam
  Optical filter throughput (for new filters)
  Optical alignment re-verification
  Focal Plane metrology check—relative height of raft CCDs

## Slide 33: Re-verification Equipment
Throughput Measurements on CCOB Narrow Beam
Survey and Alignment on Camera Integration Stand

## Slide 34: Summary
Extensive planning has been completed for logistics of camera reassembly
  Flow Diagrams for high level details
  CAD layouts to verify movement logistics
  Requirements from these plans are flowed to camera fixture hardware
Re-verification plan (LCA-14954) has been created to identify what tests need to be reconfirmed at the Cerro Pachon summit

## Slide 35: End of Presentation

## Slide 36: Re-verification Contingency
The Camera will be outfitted with shock monitor data loggers during shipping
If shock loads are recorded at values higher than allowable, there are concerns about the integrity of the focal plane
  Will require re-verification of focal plane flatness requirement
  Significant task would require:
    removing cryostat from camera body (leave UT attached to cryostat)
    constructing clean tent in staging area
    setting up BOT in clean tent to verify focal plane metrology requirement

## Slide 37: Long term RAFT Maintenance
We expect to never need to replace a RAFT tower
  MIE provides one spare RAFT
If spare RAFT is installed then the removed RAFT will be shipped back to SLAC for repair
  All RAFT construction fixtures will be maintained at SLAC
  Skills needed for refurbishment will be transferred from BNL to SLAC personnel as part of commissioning budget
  Both commissioning and operations would need contingent funding to rebuild a RAFT
Note:
  SLAC plans to maintain camera expertise by retaining key personnel on new projects

## Slide 38: Camera Maintenance (Receiving the Camera from the Telescope)

## Slide 39: Maintenance Flow Diagram: Disassembly

## Slide 40: Maintenance Flow Diagram: Raft Integration

## Slide 41: Maintenance Flow Diagram: Cryostat and Camera Integration

## Slide 42: Maintenance Flow Diagram: Final Integration and Test

## Slide 43: Prep for Camera Removal from Integrated Assembly
Prep Camera Support Assembly for transfer of camera to saddle stand

## Slide 44: Remove Filters from Camera & Store in Clean Box
Filter Storage Clean Box

## Slide 45: Move Camera into White Room

## Slide 46: Camera in White Room

## Slide 47: Remove Camera Shroud, Auto Changer and Shutter
Utility Trunk Support Stand
Cryo Support Stand

## Slide 48: Move Cryostat Assembly to Cryo Support Stand
Auto Changer in Clean Box on Cart
Cryo Support Stand

## Slide 49: Move Utility Trunk to UT Support Stand
Utility Trunk Support Stand

## Slide 50: Move Cryostat into Clean Room

## Slide 51: Move Cryostat into Clean Room

## Slide 52: Clean Room Layout
BOT
Single-bay Raft Metrology
TS8
Portable Crane
Not Shown:
Alum-a-lift
Utility Trunk-in-a-rack
Computers for BOT, Raft Integration, TS8 & Single-bay Raft Metrology stands
TS8 cryostat cart
Parts storage / Shelving

## Slide 53: Prep Cryo for move to Raft Integration Stand

## Slide 54: Remove Raft from Cryostat
Utilities Needed:
Power for temporary Utility Trunk
Power for stages/pumps/compressors
DAQ Fibers
Refrigeration
Nitrogen gas
Compressed dry air

## Slide 55: Camera Equipment Storage Needs

## Slide 56: Storage Needs In Camera Maintenance Facility
Remains in Camera Staging & Test Area
Camera Integration Stand
Remains in White Room
Saddle Stand
Cryo Support Stand
Shutter Service Stand (2m x 1m)
Auto Changer Service Stand
Remains in Clean Room
Raft Integration Stand
Bench for Optical Testing (BOT)
Single-bay Raft Metrology Stand
Single-bay Raft Electro Optical Test Stand (TS8)
Crane

## Slide 57: Storage Needs Outside of Camera Maintenance Facility
Used During Telescope Operations
Filter Loader with cart, 2x (1.2m x .75m)
Filter Storage Clean Box (1.7m x 1.2m)
Filter Bench Top Stand
Spare Auto Changer (in clean box)
Auto Changer Clean Box Cart, 2x (1.7m x 1.7m)
Auto Changer Lift Fixture
Filter Shipping Container, 6x
Filter Covers, 12x
Spare Shutter (in clean storage box)
Shutter Installation Rails
Shutter Lift Fixture

## Slide 58: Storage Needs Outside of Camera Maintenance Facility, cont’d
Used Only During Camera Maintenance
UT Support Stand (2m x 2m)
Camera Lift Fixture
Cryo Lift Fixture
Cryo Spreader Bar
Seldom Used (Only for Receiving the Camera from SLAC)
L1-L2 Shipping Container (3.2m x 3.2m)
L1-L2 Support Stand (2.75m x 2.2m)
L1-L2 Lift Fixture (on support stand)
Camera Shipping Container (6m x 2.5m)