## Ribbon View
Fuse® Analyst Report
Workbook: Workbook1 - 8168 Activities
Schedule Quality
Created on: 8/5/2019
Created by: brackett
Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality | Schedule Quality
|  | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line
|  | 2010 | 2010 | 2011 | 2011 | 2012 | 2012 | 2013 | 2013 | 2014 | 2014 | 2015 | 2015 | 2016 | 2016 | 2017 | 2017 | 2018 | 2018 | 2019 | 2019 | 2020 | 2020 | 2021 | 2021 | Missing Logic | Logic Density™ | Critical | Hard Constraints | Negative Float | Insufficient Detail™ | Number of Lags | Number of Leads | Merge Hotspot | Score
Ribbons | LSST Forecast - B57 - B1 | [24 empty] | 7 | 3.06 | 106 | 0 | 136 | 43 | 464 | 0 | 761 | 84
Ribbons | LSST Forecast - B57 - B1 | [24 empty] | 0% |  | 15% | 0% | 19% | 1% | 6% | 0% | 9%
Phase Analyzer | Missing Logic | 0 | 0% | 1 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 2 | 0% | 2 | 1% | 2 | 25%
Phase Analyzer | Logic Density™ | 2.82 |  | 2.97 |  | 2.53 |  | 2.81 |  | 2.87 |  | 3.1 |  | 2.99 |  | 3.02 |  | 2.87 |  | 2.98 |  | 6.14 |  | 4
Phase Analyzer | Critical | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 1 | 1% | 47 | 8% | 53 | 33% | 8 | 100%
Phase Analyzer | Hard Constraints | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Phase Analyzer | Negative Float | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 85 | 15% | 51 | 32% | 0 | 0%
Phase Analyzer | Insufficient Detail™ | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Phase Analyzer | Number of Lags | 0 | 0% | 0 | 0% | 0 | 0% | 1 | 0% | 25 | 2% | 65 | 5% | 84 | 7% | 121 | 8% | 108 | 8% | 56 | 7% | 3 | 2% | 1 | 14%
Phase Analyzer | Number of Leads | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Phase Analyzer | Merge Hotspot | 1 | 1% | 12 | 5% | 1 | 1% | 13 | 5% | 61 | 6% | 127 | 10% | 116 | 10% | 153 | 10% | 136 | 11% | 106 | 13% | 34 | 25% | 1 | 14%
Phase Analyzer | Score | 99 |  | 96 |  | 100 |  | 96 |  | 93 |  | 88 |  | 88 |  | 86 |  | 86 |  | 79 |  | 56 |  | 75

## Ribbon Analysis
Fuse® Analyst Report
Workbook: Workbook1 - 8168 Activities
Schedule Quality
Created on: 8/5/2019
Created by: brackett
Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis
Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis
|  | Missing Logic | Logic Density™ | Critical | Hard Constraints | Negative Float | Insufficient Detail™ | Number of Lags | Number of Leads | Merge Hotspot | Score
Ribbons | LSST Forecast - B57 - B1 | 7 | 3.06 | 106 | 0 | 136 | 43 | 464 | 0 | 761 | 84
Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis
|  | Missing Logic | Logic Density™ | Critical | Hard Constraints | Negative Float | Insufficient Detail™ | Number of Lags | Number of Leads | Merge Hotspot | Score
Ribbons | LSST Forecast - B57 - B1 | 0% |  | 15% | 0% | 19% | 1% | 6% | 0% | 9%

## LSST-Forecast---B57---B11
Fuse® Analyst Report
Workbook: Workbook1 - 8168 Activities
Schedule Quality
Created on: 8/5/2019
Created by: brackett
LSST Forecast - B57 - B1: Detailed View | LSST Forecast - B57 - B1: Detailed View | LSST Forecast - B57 - B1: Detailed View | LSST Forecast - B57 - B1: Detailed View | LSST Forecast - B57 - B1: Detailed View | LSST Forecast - B57 - B1: Detailed View | LSST Forecast - B57 - B1: Detailed View
Missing Logic
Total number of activities that are missing a predecessor, a successor, or both. This number should not exceed 5%.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | Previous Start | Previous Finish | Percent Complete | Previous Remaining Duration | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | IsLevelOfEffort | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | Global_Basis of Estimate | Global_Cobra Cost Class | Cobra PMT (EV Method)_Global | Global_Color of Money | Global_Control Account Manager | Global_Design Maturity | Global_Judgement Factor | Global_Milestone Levels | Global_Project Phase | Global_Funding Source | Global_EDIA Survey | Global_MS Type | Phase | NSF Milestones | Loading Curve | Sensor Vendor | LSST_CA | Summary Schedule | ICD for NSF Input | LSST Camera Critical Paths | CD2 Budget Changes | DOE Reviews | Critical Path (CD Reviews) | LSST WP Summary | Critical Path (Camera Delivery) | AWARD / NEED Sub-System | Final Design Key Links | CP - CAMM2100 | CP - CAMM2130 | CP - CAMM2160 | BNL Work Org | Last ETC Update | BNL WBS | LSST Story List | Sum Sch 01 (Camera) | Sum Sch 02 (IT w/Needs) | Sum Sch 03 (Sensors_RTM_IT) | LSST Raft Particulate Mitigation | LSST RTM
FALSE |  | CAMM1010 | COMP: CD-0, Approve Mission Need | LSST Forecast - B57 - B1 | 0 | 0 | 2011-06-20 | 2011-06-20 | 0 | 2011-06-20 | 2011-06-20 | 0 | 2019-06-01 | 2019-06-01 | 2018-09-07 | 2018-09-07 | 0 | 0 | 0 | 0 | 0 | 72 | FALSE | Finish Milestone | FALSE | 2011-06-20 | 2011-06-20 |  |  |  |  | 1 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 0 | 71 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.01 | DOE Project Milestones | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 1 Milestone | Management/Administration
FALSE |  | CAMF669240 | Remove Carousel Proto & 1st Dummy Back Flange - Carousel | LSST Forecast - B57 - B1 | 5 | 0 | 2019-01-07 | 2019-01-14 | 0 | 2019-01-07 | 2019-01-14 | 0 | 2019-06-01 | 2019-06-01 | 2018-10-24 | 2018-10-24 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-02-07 | 2019-02-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 5 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Fabrication/Assembly
FALSE |  | CAMC8000 | COMP: Partial Camera Image data for Data Management | LSST Forecast - B57 - B1 | 0 | 0 | 2019-10-11 | 2019-10-11 | 595 |  |  | 343 | 2019-10-11 | 2019-10-11 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 0 | FALSE | Finish Milestone | FALSE | 2019-10-11 | 2019-10-11 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01 | Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 3 Milestone | Management/Administration |  |  |  |  | Partial Camera Image Data for DM
FALSE |  | CAMM6050 | APPROVED: CD-4 - Project Completion - Camera | LSST Forecast - B57 - B1 | 0 | 0 | 2020-12-17 | 2020-12-17 | 305 |  |  | 53 | 2020-12-17 | 2020-12-17 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 0 | FALSE | Finish Milestone | FALSE | 2020-12-17 | 2020-12-17 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 149 | 0 | 149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.02 | NSF Watched Milestones | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration |  |  |  |  | CD-4 Project Close
FALSE |  | CAMC8700 | COMP: Project Level of Effort Support | LSST Forecast - B57 - B1 | 0 | 0 | 2020-12-18 | 2020-12-18 | 304 |  |  | 52 | 2020-12-18 | 2020-12-18 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 0 | FALSE | Finish Milestone | FALSE | 2020-12-18 | 2020-12-18 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 151 | 0 | 151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01 | Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 3 Milestone | Management/Administration
FALSE |  | CAMM1060 | COMP: CD-4, Approve Project Completion | LSST Forecast - B57 - B1 | 0 | 0 | 2021-03-17 | 2021-03-17 | 252 |  |  | 0 | 2021-03-17 | 2021-03-17 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 0 | FALSE | Finish Milestone | TRUE | 2021-03-17 | 2021-03-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | FinishOnOrBefore | 2022-03-31 | None | [6 empty] | 17 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  |  | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.01 | DOE Project Milestones | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 1 Milestone | Management/Administration
FALSE |  | CAMM6120 | DECISION: Reduce Effective Area of the Focal Plane (3) | LSST Forecast - B57 - B1 | 0 | 0 | 2021-03-17 | 2021-03-17 | 252 |  |  | 0 | 2021-03-17 | 2021-03-17 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 0 | FALSE | Finish Milestone | TRUE | 2021-03-17 | 2021-03-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.05 | Upscope/Descope Decision Points | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration
Critical
Number of critical activities
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | Previous Start | Previous Finish | Percent Complete | Previous Remaining Duration | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | IsLevelOfEffort | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | Global_Basis of Estimate | Global_Cobra Cost Class | Cobra PMT (EV Method)_Global | Global_Color of Money | Global_Control Account Manager | Global_Design Maturity | Global_Judgement Factor | Global_Milestone Levels | Global_Project Phase | Global_Funding Source | Global_EDIA Survey | Global_MS Type | Phase | NSF Milestones | Loading Curve | Sensor Vendor | LSST_CA | Summary Schedule | ICD for NSF Input | LSST Camera Critical Paths | CD2 Budget Changes | DOE Reviews | Critical Path (CD Reviews) | LSST WP Summary | Critical Path (Camera Delivery) | AWARD / NEED Sub-System | Final Design Key Links | CP - CAMM2100 | CP - CAMM2130 | CP - CAMM2160 | BNL Work Org | Last ETC Update | BNL WBS | LSST Story List | Sum Sch 01 (Camera) | Sum Sch 02 (IT w/Needs) | Sum Sch 03 (Sensors_RTM_IT) | LSST Raft Particulate Mitigation | LSST RTM
FALSE |  | CRYO70165 | Final Assy & Test - Cold System Verification Test | LSST Forecast - B57 - B1 | 40 | 5 | 2018-05-01 | 2019-06-07 | -18 | 2018-05-01 |  | 0 | 2019-06-03 | 2019-06-07 | 2019-05-07 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | TRUE | 2018-06-01 | 2018-07-27 |  |  |  |  | 0.8 | 0 | FALSE | TRUE | None |  | None |  | 2019-06-07 |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 266 |  | InProgress | 80% | 260 | 0 | 260 | 260 | LSST Forecast - B57 - B1.3.06.04.06.02 | Refrigeration System - IR2 | 208 | 260 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) | [6 empty] | Utility Trunk | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC31820 | ETU EO/BOT Testing | LSST Forecast - B57 - B1 | 10 | 5 | 2019-04-01 | 2019-06-07 | -18 | 2019-04-01 |  | 0 | 2019-06-03 | 2019-06-07 | 2019-05-07 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2019-05-01 | 2019-05-14 |  |  |  |  | 0.5 | 0 | FALSE | TRUE | None |  | None |  | 2019-06-07 |  |  |  |  | 2 | 0 | 1 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 44 |  | InProgress | 50% | 281 | 0 | 281 | 281 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 140.5 | 281 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | CRYO646240 | Test Individual Circuits - 4 Cryo (15 d) | LSST Forecast - B57 - B1 | 13 | 5 | 2019-05-12 | 2019-06-07 | -113 | 2019-05-12 |  | 0 | 2019-06-03 | 2019-06-07 | 2018-12-07 | 2018-12-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2019-06-03 | 2019-06-19 |  |  |  |  | 0.5 | 0 | FALSE | TRUE | None |  | None |  | 2019-06-07 |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 13 | 14 |  | InProgress | 50% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.04.03 | 4 Cryo Heat Ex | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | [24 empty] | CP #01 (Cryostat/Camera Integration)
FALSE |  | CRYO70185 | Analyze Data - Cold System Verification Test | LSST Forecast - B57 - B1 | 8 | 5 | 2019-05-20 | 2019-06-07 | -18 | 2019-05-20 |  | 0 | 2019-06-03 | 2019-06-07 | 2019-05-07 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-06-10 | 2019-06-19 |  |  |  |  | 0.5 | 0 | FALSE | TRUE | None |  | None |  | 2019-06-07 |  |  |  |  | 3 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 8 | 9 |  | InProgress | 50% | 40 | 0 | 40 | 40 | LSST Forecast - B57 - B1.3.06.04.06.02 | Refrigeration System - IR2 | 20 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) | [6 empty] | Utility Trunk
FALSE |  | CRYO02825 | COMP: Cryostat Chamber & I&T Refrigeration System Ready for Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-07 | 2019-06-07 | -113 |  |  | 0 | 2019-06-07 | 2019-06-07 | 2018-12-13 | 2018-12-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | TRUE | 2019-06-07 | 2019-06-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04 | Cryostat | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 3 Milestone | Management/Administration
FALSE |  | CRYO70205 | COMP: Cold System Verification Test | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-07 | 2019-06-07 | -18 |  |  | 0 | 2019-06-07 | 2019-06-07 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2019-06-07 | 2019-06-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.02 | Refrigeration System - IR2 | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% | Level 4 Milestone | Design/Engineering
FALSE |  | CRYO61685_1 | AVAIL: Cryostat Assembly with Refrigeration for Integration (4 Cryo) | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-07 | 2019-06-07 | -18 |  |  | 0 | 2019-06-07 | 2019-06-07 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2019-06-07 | 2019-06-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.02 | Refrigeration System - IR2 | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 5 Milestone | Fabrication/Assembly | [16 empty] | Cryostat
FALSE |  | ITC31835 | NEED: Completion of Run Single-Circuit Cryo/Cold System Tests (4 Cryo) | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-07 | 2019-06-07 | -18 |  |  | 0 | 2019-06-07 | 2019-06-07 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | TRUE | 2019-06-07 | 2019-06-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Fabrication and Assembly | [12 empty] | Integration and Test
FALSE |  | CRYO646250 | AVAIL: Cryostat Assembly with Refrigeration for Integration (4 Cryo) | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-07 | 2019-06-07 | -113 |  |  | 0 | 2019-06-07 | 2019-06-07 | 2018-12-13 | 2018-12-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | TRUE | 2019-06-07 | 2019-06-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.04.03 | 4 Cryo Heat Ex | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | [7 empty] | Level 5 Milestone
FALSE |  | ITC31820_1 | ETU De-integration | LSST Forecast - B57 - B1 | 12 | 12 | 2019-06-10 | 2019-06-25 | -18 |  |  | 0 | 2019-06-10 | 2019-06-25 | 2019-05-14 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2019-06-10 | 2019-06-25 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 12 | 0 |  | Planned | 0% | 238 | 0 | 238 | 238 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC00290 | START: Science Raft Tower Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-25 | 2019-06-25 | -18 |  |  | 0 | 2019-06-25 | 2019-06-25 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2019-06-25 | 2019-06-25 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration
FALSE |  | ITC31840 | START: Science Raft Tower Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-25 | 2019-06-25 | -18 |  |  | 0 | 2019-06-25 | 2019-06-25 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | TRUE | 2019-06-25 | 2019-06-25 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 10 | 0 | 10 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [11 empty] | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC31830 | AVAIL: Eng Raft Tower from I&T for ComCam | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-25 | 2019-06-25 | -18 |  |  | 0 | 2019-06-25 | 2019-06-25 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2019-06-25 | 2019-06-25 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Fabrication/Assembly |  |  |  | Engineering | [12 empty] | Integration and Test
FALSE |  | ITC31860 | Integrate Science Raft Tower #1 of 21 | LSST Forecast - B57 - B1 | 4 | 4 | 2019-06-26 | 2019-07-01 | -18 |  |  | 0 | 2019-06-26 | 2019-07-01 | 2019-05-31 | 2019-06-05 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-06-26 | 2019-07-01 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T
FALSE |  | ITC31860_R | Integrate Science Raft Tower #1 of 21 | LSST Forecast - B57 - B1 | 4 | 4 | 2019-06-26 | 2019-07-01 | -18 |  |  | 0 | 2019-06-26 | 2019-07-01 | 2019-05-31 | 2019-06-05 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-06-26 | 2019-07-01 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 4 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 103 | 0 | 103 | 103 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Commissioning and Testing | [5 empty] | Cryostat I&T (TEC) | [7 empty] | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC31880 | Integrate Science Raft Tower #2 of 21 | LSST Forecast - B57 - B1 | 4 | 4 | 2019-07-02 | 2019-07-08 | -18 |  |  | 0 | 2019-07-02 | 2019-07-08 | 2019-06-06 | 2019-06-11 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-07-02 | 2019-07-08 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 102 | 0 | 102 | 102 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC31920 | Integrate Science Raft Tower #3 of 21 | LSST Forecast - B57 - B1 | 4 | 4 | 2019-07-09 | 2019-07-12 | -18 |  |  | 0 | 2019-07-09 | 2019-07-12 | 2019-06-12 | 2019-06-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2019-07-09 | 2019-07-12 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 104 | 0 | 104 | 104 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC31940 | Integrate Science Raft Tower #4 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-07-15 | 2019-07-16 | -18 |  |  | 0 | 2019-07-15 | 2019-07-16 | 2019-06-18 | 2019-06-19 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-07-15 | 2019-07-16 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC31960 | Integrate Science Raft Tower #5 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-07-17 | 2019-07-18 | -18 |  |  | 0 | 2019-07-17 | 2019-07-18 | 2019-06-20 | 2019-06-21 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-07-17 | 2019-07-18 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC31980 | Integrate Science Raft Tower #6 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-07-19 | 2019-07-22 | -18 |  |  | 0 | 2019-07-19 | 2019-07-22 | 2019-06-24 | 2019-06-25 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2019-07-19 | 2019-07-22 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32225 | Integrate Corner Raft Tower #1 of 4 | LSST Forecast - B57 - B1 | 4 | 4 | 2019-07-23 | 2019-07-26 | -18 |  |  | 0 | 2019-07-23 | 2019-07-26 | 2019-06-26 | 2019-07-01 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-07-23 | 2019-07-26 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 119 | 0 | 119 | 119 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32230 | Integrate Corner Raft Tower #2 of 4 | LSST Forecast - B57 - B1 | 4 | 4 | 2019-07-29 | 2019-08-01 | -18 |  |  | 0 | 2019-07-29 | 2019-08-01 | 2019-07-02 | 2019-07-08 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-07-29 | 2019-08-01 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 119 | 0 | 119 | 119 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32290 | Integrate Corner Raft Tower #3 of 4 | LSST Forecast - B57 - B1 | 4 | 4 | 2019-08-02 | 2019-08-07 | -18 |  |  | 0 | 2019-08-02 | 2019-08-07 | 2019-07-09 | 2019-07-12 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-08-02 | 2019-08-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 118 | 0 | 118 | 118 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32410 | Integrate Corner Raft Tower #4 of 4 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-08-08 | 2019-08-09 | -18 |  |  | 0 | 2019-08-08 | 2019-08-09 | 2019-07-15 | 2019-07-16 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-08-08 | 2019-08-09 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 118 | 0 | 118 | 118 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32000 | Integrate Science Raft Tower #7 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-08-12 | 2019-08-13 | -18 |  |  | 0 | 2019-08-12 | 2019-08-13 | 2019-07-17 | 2019-07-18 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-08-12 | 2019-08-13 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32020 | Integrate Science Raft Tower #8 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-08-14 | 2019-08-15 | -18 |  |  | 0 | 2019-08-14 | 2019-08-15 | 2019-07-19 | 2019-07-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-08-14 | 2019-08-15 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32040 | Integrate Science Raft Tower #9 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-08-16 | 2019-08-19 | -18 |  |  | 0 | 2019-08-16 | 2019-08-19 | 2019-07-23 | 2019-07-24 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-08-16 | 2019-08-19 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32140 | BOT Testing with Raft Tower #1-9 | LSST Forecast - B57 - B1 | 38 | 38 | 2019-08-20 | 2019-10-11 | -18 |  |  | 0 | 2019-08-20 | 2019-10-11 | 2019-07-25 | 2019-09-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2019-08-20 | 2019-10-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 38 | 0 |  | Planned | 0% | 517 | 0 | 517 | 517 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | CAMM6190 | DECISION: Spares for L1, L2 | LSST Forecast - B57 - B1 | 0 | 0 | 2019-09-18 | 2019-09-18 | 252 |  |  | 0 | 2019-09-18 | 2019-09-18 | 2020-09-29 | 2020-09-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2019-09-18 | 2019-09-18 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 360 | 360 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.05 | Upscope/Descope Decision Points | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration
FALSE |  | ITC00300 | COMP: Integration of 9 SR into Cryostat | LSST Forecast - B57 - B1 | 0 | 0 | 2019-10-11 | 2019-10-11 | -18 |  |  | 0 | 2019-10-11 | 2019-10-11 | 2019-09-17 | 2019-09-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2019-10-11 | 2019-10-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration
FALSE |  | ITC32160 | COMP: Integration of 9 SR into Cryostat | LSST Forecast - B57 - B1 | 0 | 0 | 2019-10-11 | 2019-10-11 | -18 |  |  | 0 | 2019-10-11 | 2019-10-11 | 2019-09-17 | 2019-09-17 | 0 | 0 | 0 | 0 | 0 | 6 | FALSE | Finish Milestone | TRUE | 2019-10-11 | 2019-10-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Testing/Integration
FALSE |  | ITC32180 | Integrate Science Raft Tower #10 of 21 | LSST Forecast - B57 - B1 | 6 | 6 | 2019-10-14 | 2019-10-21 | -18 |  |  | 0 | 2019-10-14 | 2019-10-21 | 2019-09-18 | 2019-09-25 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-10-14 | 2019-10-21 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 6 | 0 |  | Planned | 0% | 147 | 0 | 147 | 147 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing | [5 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32200 | Integrate Science Raft Tower #11 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-10-22 | 2019-10-23 | -18 |  |  | 0 | 2019-10-22 | 2019-10-23 | 2019-09-26 | 2019-09-27 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-10-22 | 2019-10-23 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32220 | Integrate Science Raft Tower #12 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-10-24 | 2019-10-25 | -18 |  |  | 0 | 2019-10-24 | 2019-10-25 | 2019-09-30 | 2019-10-01 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-10-24 | 2019-10-25 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32240 | Integrate Science Raft Tower #13 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-10-28 | 2019-10-29 | -18 |  |  | 0 | 2019-10-28 | 2019-10-29 | 2019-10-02 | 2019-10-03 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-10-28 | 2019-10-29 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32260 | Integrate Science Raft Tower #14 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-10-30 | 2019-10-31 | -18 |  |  | 0 | 2019-10-30 | 2019-10-31 | 2019-10-04 | 2019-10-07 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-10-30 | 2019-10-31 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32280 | Integrate Science Raft Tower #15 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-11-01 | 2019-11-04 | -18 |  |  | 0 | 2019-11-01 | 2019-11-04 | 2019-10-08 | 2019-10-09 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-11-01 | 2019-11-04 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32300 | Integrate Science Raft Tower #16 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-11-05 | 2019-11-06 | -18 |  |  | 0 | 2019-11-05 | 2019-11-06 | 2019-10-10 | 2019-10-11 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-11-05 | 2019-11-06 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32320 | Integrate Science Raft Tower #17 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-11-07 | 2019-11-08 | -18 |  |  | 0 | 2019-11-07 | 2019-11-08 | 2019-10-14 | 2019-10-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-11-07 | 2019-11-08 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32340 | Integrate Science Raft Tower #18 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-11-11 | 2019-11-12 | -18 |  |  | 0 | 2019-11-11 | 2019-11-12 | 2019-10-16 | 2019-10-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-11-11 | 2019-11-12 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32360 | Integrate Science Raft Tower #19 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-11-13 | 2019-11-14 | -18 |  |  | 0 | 2019-11-13 | 2019-11-14 | 2019-10-18 | 2019-10-21 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-11-13 | 2019-11-14 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32380 | Integrate Science Raft Tower #20 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-11-15 | 2019-11-18 | -18 |  |  | 0 | 2019-11-15 | 2019-11-18 | 2019-10-22 | 2019-10-23 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-11-15 | 2019-11-18 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32400 | Integrate Science Raft Tower #21 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-11-19 | 2019-11-20 | -18 |  |  | 0 | 2019-11-19 | 2019-11-20 | 2019-10-24 | 2019-10-25 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-11-19 | 2019-11-20 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32420 | BOT Testing with Raft Tower #1-21+4CR | LSST Forecast - B57 - B1 | 38 | 38 | 2019-11-21 | 2020-01-30 | -18 |  |  | 0 | 2019-11-21 | 2020-01-30 | 2019-10-28 | 2019-12-20 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-11-21 | 2020-01-30 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 38 | 0 |  | Planned | 0% | 517 | 0 | 517 | 517 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC00330 | START: Integrated Cryostat Testing | LSST Forecast - B57 - B1 | 0 | 0 | 2019-11-21 | 2019-11-21 | -18 |  |  | 0 | 2019-11-21 | 2019-11-21 | 2019-10-25 | 2019-10-25 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | TRUE | 2019-11-21 | 2019-11-21 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration
FALSE |  | ITC32415 | START: Final Integrated Cryostat Testing | LSST Forecast - B57 - B1 | 0 | 0 | 2019-11-21 | 2019-11-21 | -18 |  |  | 0 | 2019-11-21 | 2019-11-21 | 2019-10-25 | 2019-10-25 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Start Milestone | TRUE | 2019-11-21 | 2019-11-21 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Management/Administration
FALSE |  | CAMM6220 | DECISION: Spares for filters (6) | LSST Forecast - B57 - B1 | 0 | 0 | 2019-12-13 | 2019-12-13 | 252 |  |  | 0 | 2019-12-13 | 2019-12-13 | 2021-01-07 | 2021-01-07 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2019-12-13 | 2019-12-13 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 300 | 300 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.05 | Upscope/Descope Decision Points | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration
FALSE |  | ITC00335 | COMP: I&T of Loaded Cryostat (21 SR+4 CR) | LSST Forecast - B57 - B1 | 0 | 0 | 2020-01-30 | 2020-01-30 | -18 |  |  | 0 | 2020-01-30 | 2020-01-30 | 2019-12-20 | 2019-12-20 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | TRUE | 2020-01-30 | 2020-01-30 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration
FALSE |  | ITC32460 | NEED: L3 Lens Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2020-01-30 | 2020-01-30 | -18 |  |  | 0 | 2020-01-30 | 2020-01-30 | 2019-12-20 | 2019-12-20 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | TRUE | 2020-01-30 | 2020-01-30 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Optics
FALSE |  | ITC32440 | COMP: I&T of Loaded Cryostat (21 SR+4 CR) | LSST Forecast - B57 - B1 | 0 | 0 | 2020-01-30 | 2020-01-30 | -18 |  |  | 0 | 2020-01-30 | 2020-01-30 | 2019-12-20 | 2019-12-20 | 0 | 0 | 0 | 0 | 0 | 6 | FALSE | Finish Milestone | TRUE | 2020-01-30 | 2020-01-30 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [6 empty] | Critical Path #1 (Sensor & Raft Tower Production) |  |  |  |  | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32480 | Mount L3 Lens Assembly | LSST Forecast - B57 - B1 | 8 | 8 | 2020-01-31 | 2020-02-11 | -18 |  |  | 0 | 2020-01-31 | 2020-02-11 | 2020-01-06 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-01-31 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 8 | 0 |  | Planned | 0% | 65 | 0 | 65 | 65 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32500 | NEED: Utility Trunk | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Cryostat
FALSE |  | ITC32520 | NEED: Camera purge unit | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Camera Body & Shutter
FALSE |  | ITC32540 | NEED: UT cooling system | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Utility Trunk
FALSE |  | ITC32580 | NEED: UT Aux Electronics | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 14 | 0 | 14 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Auxiliary Electronics
FALSE |  | ITC32565 | NEED: Diagnostic Cluster from CCS | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Auxiliary Electronics
FALSE |  | ITC32590 | NEED: Cryostat Lift Fixture for Cryostat I&T | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Cryostat
FALSE |  | ITC32510 | NEED: Vacuum Purge | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Cryostat
FALSE |  | ITC32530 | NEED: Cryostat Handling Equipment | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | ITC32570 | NEED: Controls for Utility Trunk | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | ITC32620 | Mount and Populate Utility Trunk | LSST Forecast - B57 - B1 | 40 | 40 | 2020-02-12 | 2020-04-08 | -18 |  |  | 0 | 2020-02-12 | 2020-04-08 | 2020-01-16 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-02-12 | 2020-04-08 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 13 | 0 | 13 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 0 |  | Planned | 0% | 767 | 0 | 767 | 767 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | CAMM6200 | DECISION: Spares for L3 | LSST Forecast - B57 - B1 | 0 | 0 | 2020-03-24 | 2020-03-24 | 252 |  |  | 0 | 2020-03-24 | 2020-03-24 | 2021-04-02 | 2021-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-03-24 | 2020-03-24 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 240 | 240 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.05 | Upscope/Descope Decision Points | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration
FALSE |  | ITC00340 | COMP: Cryostat and UT Assembled | LSST Forecast - B57 - B1 | 0 | 0 | 2020-04-08 | 2020-04-08 | -18 |  |  | 0 | 2020-04-08 | 2020-04-08 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-04-08 | 2020-04-08 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration |  |  |  |  | SR Rafts Installed and Cryostat Closed (min of 5 SR and 4 CR)
FALSE |  | ITC19850 | NEED: Loaded Cryostat | LSST Forecast - B57 - B1 | 0 | 0 | 2020-04-08 | 2020-04-08 | -18 |  |  | 0 | 2020-04-08 | 2020-04-08 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-04-08 | 2020-04-08 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Integration and Test
FALSE |  | ITC32660 | AVAIL: Loaded Cryostat Ready for Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2020-04-08 | 2020-04-08 | -18 |  |  | 0 | 2020-04-08 | 2020-04-08 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | TRUE | 2020-04-08 | 2020-04-08 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration | [16 empty] | Integration and Test
FALSE |  | ITC19852 | NEED: Camera Handling Equipment Ready for Camera I&T | LSST Forecast - B57 - B1 | 0 | 0 | 2020-04-08 | 2020-04-08 | -18 |  |  | 0 | 2020-04-08 | 2020-04-08 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-04-08 | 2020-04-08 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | ITC19900 | Camera / Cryostat Integration | LSST Forecast - B57 - B1 | 30 | 30 | 2020-04-09 | 2020-05-20 | -18 |  |  | 0 | 2020-04-09 | 2020-05-20 | 2020-03-16 | 2020-04-24 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2020-04-09 | 2020-05-20 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 7 | 0 | 7 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 0 |  | Planned | 0% | 518 | 0 | 518 | 518 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration | Stanford University | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Camera I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Camera I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC20000 | NEED: L1-L2 Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2020-05-20 | 2020-05-20 | -18 |  |  | 0 | 2020-05-20 | 2020-05-20 | 2020-04-24 | 2020-04-24 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-05-20 | 2020-05-20 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Optics
FALSE |  | ITC00450 | COMP: Cryostat Integrated Into Camera Body | LSST Forecast - B57 - B1 | 0 | 0 | 2020-05-20 | 2020-05-20 | -18 |  |  | 0 | 2020-05-20 | 2020-05-20 | 2020-04-24 | 2020-04-24 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-05-20 | 2020-05-20 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration
FALSE |  | ITC20025 | L1-L2 Integration | LSST Forecast - B57 - B1 | 25 | 25 | 2020-05-21 | 2020-06-25 | -18 |  |  | 0 | 2020-05-21 | 2020-06-25 | 2020-04-27 | 2020-06-01 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-05-21 | 2020-06-25 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 0 |  | Planned | 0% | 816 | 0 | 816 | 816 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration | Stanford University | Commissioning and Testing | [5 empty] | Camera I&T (TEC) | [5 empty] | Critical Path to CD-2 |  | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC20050 | Final Camera Assembly / Closeout | LSST Forecast - B57 - B1 | 15 | 15 | 2020-06-26 | 2020-07-17 | -18 |  |  | 0 | 2020-06-26 | 2020-07-17 | 2020-06-02 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-06-26 | 2020-07-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 0 |  | Planned | 0% | 270 | 0 | 270 | 270 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration | Stanford University | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Camera I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Camera I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC00475 | COMP: Camera Ready for Verification Testing | LSST Forecast - B57 - B1 | 0 | 0 | 2020-07-17 | 2020-07-17 | -18 |  |  | 0 | 2020-07-17 | 2020-07-17 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | TRUE | 2020-07-17 | 2020-07-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration
FALSE |  | ITC20070 | NEED: Filters (partial) | LSST Forecast - B57 - B1 | 0 | 0 | 2020-07-17 | 2020-07-17 | -18 |  |  | 0 | 2020-07-17 | 2020-07-17 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-07-17 | 2020-07-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration | [16 empty] | Optics
FALSE |  | ITC20060 | COMP: Camera Ready for Verification Testing | LSST Forecast - B57 - B1 | 0 | 0 | 2020-07-17 | 2020-07-17 | -18 |  |  | 0 | 2020-07-17 | 2020-07-17 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | TRUE | 2020-07-17 | 2020-07-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Testing/Integration | [10 empty] | Critical Path #1 (Sensor & Raft Tower Production)
FALSE |  | ITC20065 | NEED: OCS & CCS Ready for I&T Testing (CCS Suite #9) | LSST Forecast - B57 - B1 | 0 | 0 | 2020-07-17 | 2020-07-17 | -18 |  |  | 0 | 2020-07-17 | 2020-07-17 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-07-17 | 2020-07-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 11 | 0 | 11 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration | [16 empty] | Project Management
FALSE |  | ITC20076 | NEED: DAQ Production V5.0 | LSST Forecast - B57 - B1 | 0 | 0 | 2020-07-17 | 2020-07-17 | -18 |  |  | 0 | 2020-07-17 | 2020-07-17 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-07-17 | 2020-07-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 10 | 0 | 10 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | ITC20072 | NEED: Filter Loader | LSST Forecast - B57 - B1 | 0 | 0 | 2020-07-17 | 2020-07-17 | -18 |  |  | 0 | 2020-07-17 | 2020-07-17 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-07-17 | 2020-07-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | ITC20125 | Camera Functional Testing | LSST Forecast - B57 - B1 | 46 | 46 | 2020-07-20 | 2020-09-22 | -18 |  |  | 0 | 2020-07-20 | 2020-09-22 | 2020-06-23 | 2020-08-26 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2020-07-20 | 2020-09-22 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 46 | 0 |  | Planned | 0% | 1432 | 0 | 1432 | 1432 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration | Stanford University | Commissioning and Testing | [5 empty] | Camera I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Camera I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | CAMM6210 | DECISION: Spare filter blank | LSST Forecast - B57 - B1 | 0 | 0 | 2020-09-11 | 2020-09-11 | 252 |  |  | 0 | 2020-09-11 | 2020-09-11 | 2021-09-22 | 2021-09-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-09-11 | 2020-09-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 120 | 120 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.05 | Upscope/Descope Decision Points | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration
FALSE |  | CAMM6150 | DECISION: Postpone System-Level Verification Testing | LSST Forecast - B57 - B1 | 0 | 0 | 2020-09-22 | 2020-09-22 | -18 |  |  | 0 | 2020-09-22 | 2020-09-22 | 2020-08-26 | 2020-08-26 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-09-22 | 2020-09-22 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.05 | Upscope/Descope Decision Points | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration
FALSE |  | ITC20130 | NEED: CCOB Ready for Camera Verification Testing | LSST Forecast - B57 - B1 | 0 | 0 | 2020-09-22 | 2020-09-22 | -18 |  |  | 0 | 2020-09-22 | 2020-09-22 | 2020-08-26 | 2020-08-26 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-09-22 | 2020-09-22 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | ITC20150 | Camera Verification Testing | LSST Forecast - B57 - B1 | 45 | 45 | 2020-09-23 | 2020-11-24 | -18 |  |  | 0 | 2020-09-23 | 2020-11-24 | 2020-08-27 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | TRUE | 2020-09-23 | 2020-11-24 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 7 | 0 | 5 | 0 | 0 | 2 | 3 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 45 | 0 |  | Planned | 0% | 1468 | 0 | 1468 | 1468 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration | Stanford University | Commissioning and Testing | [5 empty] | Camera I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Camera I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | CAM112810 | CD-4/CRR Director's Team Pre Doc Review | LSST Forecast - B57 - B1 | 5 | 5 | 2020-11-06 | 2020-11-12 | 252 |  |  | 0 | 2020-11-06 | 2020-11-12 | 2021-11-17 | 2021-11-23 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-11-06 | 2020-11-12 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01.01.02 | Reviews & Collaboration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Vincent Riot | (1.10) Task/item is a modification of an existing design | 0% |  | Management/Administration |  | Project Management (cost estimating, scheduling, project controls, Risk assessment) | [10 empty] | CD-3b | Critical Path to CD-3b | Project Management
FALSE |  | CAM112820 | CD-4/CRR Directors Review | LSST Forecast - B57 - B1 | 3 | 3 | 2020-11-13 | 2020-11-17 | 252 |  |  | 0 | 2020-11-13 | 2020-11-17 | 2021-11-24 | 2021-11-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-11-13 | 2020-11-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 3 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01.01.02 | Reviews & Collaboration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Vincent Riot | (1.10) Task/item is a modification of an existing design | 0% |  | Management/Administration |  | Project Management (cost estimating, scheduling, project controls, Risk assessment) | [12 empty] | Project Management
FALSE |  | CAM112830 | CD-4/CRR Documentation Updates | LSST Forecast - B57 - B1 | 20 | 20 | 2020-11-18 | 2020-12-17 | 252 |  |  | 0 | 2020-11-18 | 2020-12-17 | 2021-12-01 | 2022-01-11 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-11-18 | 2020-12-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01.01.02 | Reviews & Collaboration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Vincent Riot | (1.10) Task/item is a modification of an existing design | 0% |  | Management/Administration | [14 empty] | Project Management
FALSE |  | ITC20160 | NEED: Filters Remaining | LSST Forecast - B57 - B1 | 0 | 0 | 2020-11-24 | 2020-11-24 | -18 |  |  | 0 | 2020-11-24 | 2020-11-24 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-11-24 | 2020-11-24 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration | [16 empty] | Optics
FALSE |  | ITC20170 | NEED: Cryostat Sieve (Getter Pumps) | LSST Forecast - B57 - B1 | 0 | 0 | 2020-11-24 | 2020-11-24 | -18 |  |  | 0 | 2020-11-24 | 2020-11-24 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-11-24 | 2020-11-24 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration | [16 empty] | Optics
FALSE |  | ITC20175 | NEED: Cryostat Evaporative Getter Pumps | LSST Forecast - B57 - B1 | 0 | 0 | 2020-11-24 | 2020-11-24 | -18 |  |  | 0 | 2020-11-24 | 2020-11-24 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-11-24 | 2020-11-24 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration | [16 empty] | Optics
FALSE |  | ITC20180 | Recover from tests, secure Camera for shipping | LSST Forecast - B57 - B1 | 7 | 7 | 2020-11-25 | 2020-12-07 | -18 |  |  | 0 | 2020-11-25 | 2020-12-07 | 2020-10-30 | 2020-11-09 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-11-25 | 2020-12-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 7 | 0 |  | Planned | 0% | 392 | 0 | 392 | 392 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration | Stanford University | Commissioning and Testing | [5 empty] | Camera I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Camera I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC00500 | COMP: Camera Ready - Integrated & Tested @ SLAC | LSST Forecast - B57 - B1 | 0 | 0 | 2020-12-07 | 2020-12-07 | -18 |  |  | 0 | 2020-12-07 | 2020-12-07 | 2020-11-09 | 2020-11-09 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-12-07 | 2020-12-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration
FALSE |  | ITC20200 | COMP: Camera Verification Tests Complete | LSST Forecast - B57 - B1 | 0 | 0 | 2020-12-07 | 2020-12-07 | -18 |  |  | 0 | 2020-12-07 | 2020-12-07 | 2020-11-09 | 2020-11-09 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | TRUE | 2020-12-07 | 2020-12-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Testing/Integration | [10 empty] | Critical Path #1 (Sensor & Raft Tower Production)
FALSE |  | ITC20349 | NEED: As-built documentation | LSST Forecast - B57 - B1 | 0 | 0 | 2020-12-07 | 2020-12-07 | -18 |  |  | 0 | 2020-12-07 | 2020-12-07 | 2020-11-09 | 2020-11-09 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | TRUE | 2020-12-07 | 2020-12-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration | [10 empty] | Critical Path #1 (Sensor & Raft Tower Production)
FALSE |  | ITC20350 | Prep for C_PSR/ORR--Camera | LSST Forecast - B57 - B1 | 6 | 6 | 2020-12-08 | 2020-12-15 | -18 |  |  | 0 | 2020-12-08 | 2020-12-15 | 2020-11-10 | 2020-11-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-12-08 | 2020-12-15 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 10 | 0 | 10 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 6 | 0 |  | Planned | 0% | 120 | 0 | 120 | 120 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration | Stanford University | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Camera I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Camera I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC20375 | Camera Pre-Ship/Operations Readiness Review | LSST Forecast - B57 - B1 | 2 | 2 | 2020-12-16 | 2020-12-17 | -18 |  |  | 0 | 2020-12-16 | 2020-12-17 | 2020-11-18 | 2020-11-19 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-12-16 | 2020-12-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 48 | 0 | 48 | 48 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration | Stanford University | Commissioning and Testing | [5 empty] | Camera I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 |  | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC00100 | COMP: Ready for CD-4 - I&T | LSST Forecast - B57 - B1 | 0 | 0 | 2020-12-17 | 2020-12-17 | 212 |  |  | 0 | 2020-12-17 | 2020-12-17 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-12-17 | 2020-12-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 31 | 0 | 31 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration
FALSE |  | ITC20400 | COMP: C_PSR/ORR--Camera Pre-Ship/Operations Readiness Review Complete | LSST Forecast - B57 - B1 | 0 | 0 | 2020-12-17 | 2020-12-17 | -18 |  |  | 0 | 2020-12-17 | 2020-12-17 | 2020-11-19 | 2020-11-19 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Finish Milestone | TRUE | 2020-12-17 | 2020-12-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration
FALSE |  | CAMC02750 | COMP: Ready for CD-4 Review - Camera | LSST Forecast - B57 - B1 | 0 | 0 | 2020-12-17 | 2020-12-17 | 212 |  |  | 0 | 2020-12-17 | 2020-12-17 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | TRUE | 2020-12-17 | 2020-12-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01 | Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 3 Milestone | Management/Administration
FALSE |  | CAM112800 | COMP: Project Ready for CD-4/CRR | LSST Forecast - B57 - B1 | 0 | 0 | 2020-12-17 | 2020-12-17 | 212 |  |  | 0 | 2020-12-17 | 2020-12-17 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-12-17 | 2020-12-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 13 | 0 | 13 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01.01.02 | Reviews & Collaboration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Vincent Riot | (1.10) Task/item is a modification of an existing design | 0% | Level 4 Milestone | Management/Administration | [12 empty] | CD-3b | Critical Path to CD-3b | Project Management
FALSE |  | CAM112840 | CD-4/CRR DOE/SC Team Pre Doc Review | LSST Forecast - B57 - B1 | 10 | 10 | 2020-12-18 | 2021-01-14 | 252 |  |  | 0 | 2020-12-18 | 2021-01-14 | 2022-01-12 | 2022-01-26 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-12-18 | 2021-01-14 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01.01.02 | Reviews & Collaboration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Vincent Riot | (1.10) Task/item is a modification of an existing design | 0% |  | Management/Administration | [14 empty] | Project Management
FALSE |  | CAM112850 | CD-4/CRR DOE/SC Review | LSST Forecast - B57 - B1 | 3 | 3 | 2021-01-15 | 2021-01-19 | 252 |  |  | 0 | 2021-01-15 | 2021-01-19 | 2022-01-27 | 2022-01-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2021-01-15 | 2021-01-19 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 3 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01.01.02 | Reviews & Collaboration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Vincent Riot | (1.10) Task/item is a modification of an existing design | 0% |  | Management/Administration | [14 empty] | Project Management
FALSE |  | CAMC02850 | COMP: CD-4 Review - Camera Readiness Review | LSST Forecast - B57 - B1 | 0 | 0 | 2021-01-19 | 2021-01-19 | 252 |  |  | 0 | 2021-01-19 | 2021-01-19 | 2022-01-31 | 2022-01-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2021-01-19 | 2021-01-19 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01 | Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 3 Milestone | Management/Administration |  |  |  |  | CD-4 Lehman Review - Readiness Review
FALSE |  | CAM112860 | COMP: Camera Ready for CD4 Approval | LSST Forecast - B57 - B1 | 0 | 0 | 2021-01-19 | 2021-01-19 | 252 |  |  | 0 | 2021-01-19 | 2021-01-19 | 2022-01-31 | 2022-01-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2021-01-19 | 2021-01-19 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01.01.02 | Reviews & Collaboration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Vincent Riot | (1.10) Task/item is a modification of an existing design | 0% | Level 4 Milestone | Management/Administration | [14 empty] | Project Management
FALSE |  | CAM112870 | CD-4 Approval Process | LSST Forecast - B57 - B1 | 40 | 40 | 2021-01-20 | 2021-03-17 | 252 |  |  | 0 | 2021-01-20 | 2021-03-17 | 2022-02-01 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2021-01-20 | 2021-03-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01.01.02 | Reviews & Collaboration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Vincent Riot | (1.10) Task/item is a modification of an existing design | 0% |  | Management/Administration | [14 empty] | Project Management
FALSE |  | CAMM1060 | COMP: CD-4, Approve Project Completion | LSST Forecast - B57 - B1 | 0 | 0 | 2021-03-17 | 2021-03-17 | 252 |  |  | 0 | 2021-03-17 | 2021-03-17 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 0 | FALSE | Finish Milestone | TRUE | 2021-03-17 | 2021-03-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | FinishOnOrBefore | 2022-03-31 | None | [6 empty] | 17 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  |  | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.01 | DOE Project Milestones | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 1 Milestone | Management/Administration
FALSE |  | CAMC02950 | COMP: CD-4, Approve Project Completion (Early) | LSST Forecast - B57 - B1 | 0 | 0 | 2021-03-17 | 2021-03-17 | 252 |  |  | 0 | 2021-03-17 | 2021-03-17 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2021-03-17 | 2021-03-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01 | Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 3 Milestone | Management/Administration
FALSE |  | CAMM6120 | DECISION: Reduce Effective Area of the Focal Plane (3) | LSST Forecast - B57 - B1 | 0 | 0 | 2021-03-17 | 2021-03-17 | 252 |  |  | 0 | 2021-03-17 | 2021-03-17 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 0 | FALSE | Finish Milestone | TRUE | 2021-03-17 | 2021-03-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.05 | Upscope/Descope Decision Points | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration
Negative Float
Number of activities with total finish float less than 0 working days.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | Previous Start | Previous Finish | Percent Complete | Previous Remaining Duration | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | IsLevelOfEffort | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | Global_Basis of Estimate | Global_Cobra Cost Class | Cobra PMT (EV Method)_Global | Global_Color of Money | Global_Control Account Manager | Global_Design Maturity | Global_Judgement Factor | Global_Milestone Levels | Global_Project Phase | Global_Funding Source | Global_EDIA Survey | Global_MS Type | Phase | NSF Milestones | Loading Curve | Sensor Vendor | LSST_CA | Summary Schedule | ICD for NSF Input | LSST Camera Critical Paths | CD2 Budget Changes | DOE Reviews | Critical Path (CD Reviews) | LSST WP Summary | Critical Path (Camera Delivery) | AWARD / NEED Sub-System | Final Design Key Links | CP - CAMM2100 | CP - CAMM2130 | CP - CAMM2160 | BNL Work Org | Last ETC Update | BNL WBS | LSST Story List | Sum Sch 01 (Camera) | Sum Sch 02 (IT w/Needs) | Sum Sch 03 (Sensors_RTM_IT) | LSST Raft Particulate Mitigation | LSST RTM
FALSE |  | CAMF669050 | Inspect Procured Parts - Carousel | LSST Forecast - B57 - B1 | 100 | 5 | 2018-02-01 | 2019-06-07 | -149 | 2018-02-01 |  | 0 | 2019-06-03 | 2019-06-07 | 2018-10-16 | 2018-10-22 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-03-01 | 2018-07-20 |  |  |  |  | 0.95 | 0 | FALSE | FALSE | None |  | None |  | 2019-06-07 |  |  |  |  | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 100 | 328 |  | InProgress | 95% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Fabrication/Assembly
FALSE |  | ITC92200 | Procurements - Com Cam | LSST Forecast - B57 - B1 | 59 | 10 | 2018-02-05 | 2019-06-14 | -10 | 2018-02-05 |  | 0 | 2019-06-03 | 2019-06-14 | 2019-05-17 | 2019-05-31 | 201650 | 201650 | 0 | 201650 | 201650 | 2 | FALSE | Normal | FALSE | 2018-04-11 | 2018-07-02 |  |  |  |  | 0.95 | 0 | FALSE | FALSE | None |  | None |  | 2019-06-14 |  |  |  |  | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 59 | 345 |  | InProgress | 95% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.06.01 | Commissioning Camera Hardware | 0 | 0 | 0 | 191567.5 | 201650 | 201650 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Kevin Reil | (1.00) Task/item is fully invoiced/completed | 0% |  | Engineering Test/Validation |  | R&D | [5 empty] | Commissioning Camera (TEC)
FALSE |  | CAMF669100 | Clean - Carousel | LSST Forecast - B57 - B1 | 105 | 10 | 2018-04-02 | 2019-06-14 | -149 | 2018-04-02 |  | 0 | 2019-06-03 | 2019-06-14 | 2018-10-16 | 2018-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-05-01 | 2018-09-27 |  |  |  |  | 0.9 | 0 | FALSE | FALSE | None |  | None |  | 2019-06-14 |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 105 | 287 |  | InProgress | 90% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Fabrication/Assembly
FALSE |  | ITC92240 | UT Assembly - Com Cam | LSST Forecast - B57 - B1 | 40 | 10 | 2018-04-09 | 2019-06-14 | -10 | 2018-04-09 |  | 0 | 2019-06-03 | 2019-06-14 | 2019-05-16 | 2019-05-31 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2018-07-03 | 2018-08-28 |  |  |  |  | 0.95 | 0 | FALSE | FALSE | None |  | None |  | 2019-06-14 |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 282 |  | InProgress | 95% | 336 | 0 | 336 | 336 | LSST Forecast - B57 - B1.3.08.06.01 | Commissioning Camera Hardware | 319.2 | 336 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Kevin Reil | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | R&D | [5 empty] | Commissioning Camera (TEC)
FALSE |  | CRYO70165 | Final Assy & Test - Cold System Verification Test | LSST Forecast - B57 - B1 | 40 | 5 | 2018-05-01 | 2019-06-07 | -18 | 2018-05-01 |  | 0 | 2019-06-03 | 2019-06-07 | 2019-05-07 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | TRUE | 2018-06-01 | 2018-07-27 |  |  |  |  | 0.8 | 0 | FALSE | TRUE | None |  | None |  | 2019-06-07 |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 266 |  | InProgress | 80% | 260 | 0 | 260 | 260 | LSST Forecast - B57 - B1.3.06.04.06.02 | Refrigeration System - IR2 | 208 | 260 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) | [6 empty] | Utility Trunk | CP #01 (Cryostat/Camera Integration)
FALSE |  | CCS117425 | Refactoring of FCS code to increase code quality/maintainability | LSST Forecast - B57 - B1 | 121 | 54 | 2018-06-01 | 2019-08-16 | -175 | 2018-06-01 |  | 0 | 2019-06-03 | 2019-08-16 | 2018-09-10 | 2018-11-26 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-07-02 | 2018-12-21 |  |  |  |  | 0.9 | 0 | FALSE | FALSE | None |  | None |  | 2019-08-16 |  |  |  |  | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 121 | 244 |  | InProgress | 90% | 200 | 0 | 200 | 200 | LSST Forecast - B57 - B1.3.07.01.03.05 | Filter/Carousel HCU | 180 | 200 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering | [7 empty] | CCS HCU (TEC)
FALSE |  | CAMF669235 | Integration and Test - Carousel | LSST Forecast - B57 - B1 | 75 | 55 | 2018-07-06 | 2019-08-19 | -176 | 2018-07-06 |  | 0 | 2019-06-03 | 2019-08-19 | 2018-09-07 | 2018-11-26 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-08-01 | 2018-11-14 |  |  |  |  | 0.8 | 0 | FALSE | FALSE | None |  | None |  | 2019-08-19 |  |  |  |  | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 75 | 220 |  | InProgress | 80% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Fabrication/Assembly | [15 empty] | CP #03 (Carousel/Camera Integration)
FALSE |  | CCS117430 | Develop final documentation for FCS software | LSST Forecast - B57 - B1 | 79 | 54 | 2018-08-01 | 2019-08-16 | -175 | 2018-08-01 |  | 0 | 2019-06-03 | 2019-08-16 | 2018-09-10 | 2018-11-26 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-09-04 | 2019-01-08 |  |  |  |  | 0.9 | 0 | FALSE | FALSE | None |  | None |  | 2019-08-16 |  |  |  |  | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 79 | 202 |  | InProgress | 90% | 200 | 0 | 200 | 200 | LSST Forecast - B57 - B1.3.07.01.03.05 | Filter/Carousel HCU | 180 | 200 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering | [7 empty] | CCS HCU (TEC)
FALSE |  | CCS117440 | Produce version of FCS software adapted for use with ComCom | LSST Forecast - B57 - B1 | 79 | 54 | 2018-08-01 | 2019-08-16 | -175 | 2018-08-01 |  | 0 | 2019-06-03 | 2019-08-16 | 2018-09-10 | 2018-11-26 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-09-04 | 2019-01-08 |  |  |  |  | 0.9 | 0 | FALSE | FALSE | None |  | None |  | 2019-08-16 |  |  |  |  | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 79 | 202 |  | InProgress | 90% | 200 | 0 | 200 | 200 | LSST Forecast - B57 - B1.3.07.01.03.05 | Filter/Carousel HCU | 180 | 200 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering | [7 empty] | CCS HCU (TEC)
FALSE |  | CCS117445 | Extended stress testing of software with final hardware | LSST Forecast - B57 - B1 | 79 | 54 | 2018-08-01 | 2019-08-16 | -175 | 2018-08-01 |  | 0 | 2019-06-03 | 2019-08-16 | 2018-09-10 | 2018-11-26 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-09-04 | 2019-01-08 |  |  |  |  | 0.75 | 0 | FALSE | FALSE | None |  | None |  | 2019-08-16 |  |  |  |  | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 79 | 202 |  | InProgress | 75% | 200 | 0 | 200 | 200 | LSST Forecast - B57 - B1.3.07.01.03.05 | Filter/Carousel HCU | 150 | 200 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering | [7 empty] | CCS HCU (TEC)
FALSE |  | OP541200 | L3 Assembly - Phase 4 (Lens Assy - Integration & Test) | LSST Forecast - B57 - B1 | 60 | 10 | 2019-03-11 | 2019-06-14 | -42 | 2019-03-11 |  | 0 | 2019-06-03 | 2019-06-14 | 2019-04-02 | 2019-04-16 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2019-04-01 | 2019-06-24 |  |  |  |  | 0.6 | 0 | FALSE | FALSE | None |  | None |  | 2019-06-14 |  |  |  |  | 2 | 0 | 2 | 0 | 0 | 0 | 3 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 59 |  | InProgress | 60% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor | [11 empty] | L1-L2 Opto-Mechanics
FALSE |  | OP541385 | Procurement Support - Phase 4 (Lens Assembly) | LSST Forecast - B57 - B1 | 69 | 20 | 2019-03-11 | 2019-06-28 | -42 | 2019-03-11 |  | 0 | 2019-06-03 | 2019-06-28 | 2019-04-02 | 2019-04-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-04-01 | 2019-07-08 |  |  |  |  | 0.6 | 0 | FALSE | FALSE | None |  | None |  | 2019-06-28 |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 69 | 59 |  | InProgress | 60% | 908 | 0 | 908 | 908 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 544.8 | 579.0145 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | L3 Assembly (TEC) | [6 empty] | L1-L2 Opto-Mechanics
FALSE |  | ITC31820 | ETU EO/BOT Testing | LSST Forecast - B57 - B1 | 10 | 5 | 2019-04-01 | 2019-06-07 | -18 | 2019-04-01 |  | 0 | 2019-06-03 | 2019-06-07 | 2019-05-07 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2019-05-01 | 2019-05-14 |  |  |  |  | 0.5 | 0 | FALSE | TRUE | None |  | None |  | 2019-06-07 |  |  |  |  | 2 | 0 | 1 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 44 |  | InProgress | 50% | 281 | 0 | 281 | 281 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 140.5 | 281 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | CRYO646240 | Test Individual Circuits - 4 Cryo (15 d) | LSST Forecast - B57 - B1 | 13 | 5 | 2019-05-12 | 2019-06-07 | -113 | 2019-05-12 |  | 0 | 2019-06-03 | 2019-06-07 | 2018-12-07 | 2018-12-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2019-06-03 | 2019-06-19 |  |  |  |  | 0.5 | 0 | FALSE | TRUE | None |  | None |  | 2019-06-07 |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 13 | 14 |  | InProgress | 50% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.04.03 | 4 Cryo Heat Ex | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | [24 empty] | CP #01 (Cryostat/Camera Integration)
FALSE |  | CRYO70185 | Analyze Data - Cold System Verification Test | LSST Forecast - B57 - B1 | 8 | 5 | 2019-05-20 | 2019-06-07 | -18 | 2019-05-20 |  | 0 | 2019-06-03 | 2019-06-07 | 2019-05-07 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-06-10 | 2019-06-19 |  |  |  |  | 0.5 | 0 | FALSE | TRUE | None |  | None |  | 2019-06-07 |  |  |  |  | 3 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 8 | 9 |  | InProgress | 50% | 40 | 0 | 40 | 40 | LSST Forecast - B57 - B1.3.06.04.06.02 | Refrigeration System - IR2 | 20 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) | [6 empty] | Utility Trunk
FALSE |  | OP541360 | L3 Assembly - Review & Validate Vacuum Optical Performance | LSST Forecast - B57 - B1 | 20 | 20 | 2019-06-03 | 2019-06-28 | -42 |  |  | 0 | 2019-06-03 | 2019-06-28 | 2019-04-02 | 2019-04-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-06-03 | 2019-06-28 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 392 | 0 | 392 | 392 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 14% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | L3 Assembly (TEC) |  |  |  | Scope that can be reduced |  |  | L3 Optics
FALSE |  | ITC31725 | NEED: Final Quad Box Assy from CCS | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-03 | 2019-06-03 | -14 |  |  | 0 | 2019-06-03 | 2019-06-03 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-06-03 | 2019-06-03 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Auxiliary Electronics
FALSE |  | ITC31726 | I&T Acceptance of Quad Box from CCS | LSST Forecast - B57 - B1 | 1 | 1 | 2019-06-03 | 2019-06-03 | -14 |  |  | 0 | 2019-06-03 | 2019-06-03 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-03 | 2019-06-03 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis |  | Percent Complete on Work Package |  | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Other (specify) |  | Fabrication and Assembly | [9 empty] | Critical Path to CD-2
FALSE |  | ITC31813_1 | START: Cryostat Vacuum Testing | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-03 | 2019-06-03 | -14 |  |  | 4 | 2019-06-03 | 2019-06-03 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-06-03 | 2019-06-03 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Testing/Integration
FALSE |  | CAMM2195 | COMP: Cryostat Chamber & I&T Refrigeration System Ready for Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-07 | 2019-06-07 | -113 |  |  | 378 | 2019-06-07 | 2019-06-07 | 2018-12-13 | 2018-12-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-06-07 | 2019-06-07 |  |  |  |  | 0 | 0 | FALSE | FALSE | FinishOnOrBefore | 2018-12-13 | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.01 | DOE Project Milestones | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 2 Milestone | Management/Administration
FALSE |  | CRYO02825 | COMP: Cryostat Chamber & I&T Refrigeration System Ready for Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-07 | 2019-06-07 | -113 |  |  | 0 | 2019-06-07 | 2019-06-07 | 2018-12-13 | 2018-12-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | TRUE | 2019-06-07 | 2019-06-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04 | Cryostat | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 3 Milestone | Management/Administration
FALSE |  | CRYO70205 | COMP: Cold System Verification Test | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-07 | 2019-06-07 | -18 |  |  | 0 | 2019-06-07 | 2019-06-07 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2019-06-07 | 2019-06-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.02 | Refrigeration System - IR2 | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% | Level 4 Milestone | Design/Engineering
FALSE |  | CRYO61685_1 | AVAIL: Cryostat Assembly with Refrigeration for Integration (4 Cryo) | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-07 | 2019-06-07 | -18 |  |  | 0 | 2019-06-07 | 2019-06-07 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2019-06-07 | 2019-06-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.02 | Refrigeration System - IR2 | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 5 Milestone | Fabrication/Assembly | [16 empty] | Cryostat
FALSE |  | ITC31835 | NEED: Completion of Run Single-Circuit Cryo/Cold System Tests (4 Cryo) | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-07 | 2019-06-07 | -18 |  |  | 0 | 2019-06-07 | 2019-06-07 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | TRUE | 2019-06-07 | 2019-06-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Fabrication and Assembly | [12 empty] | Integration and Test
FALSE |  | CRYO646250 | AVAIL: Cryostat Assembly with Refrigeration for Integration (4 Cryo) | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-07 | 2019-06-07 | -113 |  |  | 0 | 2019-06-07 | 2019-06-07 | 2018-12-13 | 2018-12-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | TRUE | 2019-06-07 | 2019-06-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.04.03 | 4 Cryo Heat Ex | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | [7 empty] | Level 5 Milestone
FALSE |  | CCS300035 | NEED: DAQ with support for 9 rafts in IR2 | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-10 | 2019-06-10 | -9 |  |  | 0 | 2019-06-10 | 2019-06-10 | 2019-05-24 | 2019-05-24 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-06-10 | 2019-06-10 |  |  |  |  | 0 | 0 | FALSE | FALSE | FinishOnOrAfter | 2019-06-10 | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.08.03 | CCOB HCU | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Tony Johnson |  |  | Level 5 Milestone | Design/Engineering | [15 empty] | CP #02 (CCS Focal Plane Software)
FALSE |  | CCS300040 | Second release of full focal plane software in IR2 with support for 9+ rafts | LSST Forecast - B57 - B1 | 41 | 41 | 2019-06-10 | 2019-08-06 | -9 |  |  | 0 | 2019-06-10 | 2019-08-06 | 2019-05-28 | 2019-07-24 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-06-10 | 2019-08-06 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 41 | 0 |  | Planned | 0% | 360 | 0 | 360 | 360 | LSST Forecast - B57 - B1.3.07.01.03.08.03 | CCOB HCU | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | CCS HCU (TEC) | [7 empty] | CP #02 (CCS Focal Plane Software)
FALSE |  | ITC31820_1 | ETU De-integration | LSST Forecast - B57 - B1 | 12 | 12 | 2019-06-10 | 2019-06-25 | -18 |  |  | 0 | 2019-06-10 | 2019-06-25 | 2019-05-14 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2019-06-10 | 2019-06-25 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 12 | 0 |  | Planned | 0% | 238 | 0 | 238 | 238 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | CAMM2230 | COMP: Commissioning Camera Ready to Ship for Testing | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-14 | 2019-06-14 | -10 |  |  | 373 | 2019-06-14 | 2019-06-14 | 2019-05-31 | 2019-05-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-06-14 | 2019-06-14 |  |  |  |  | 0 | 0 | FALSE | FALSE | FinishOnOrBefore | 2019-05-31 | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.01 | DOE Project Milestones | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 2 Milestone | Management/Administration
FALSE |  | ITC00550 | COMP: Commissioning Camera Shipped to Tucson | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-14 | 2019-06-14 | -10 |  |  | 0 | 2019-06-14 | 2019-06-14 | 2019-05-31 | 2019-05-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-06-14 | 2019-06-14 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration
FALSE |  | OP541220 | RCV: L3 Assembly - Phase 4 (Lens Assembly) | LSST Forecast - B57 - B1 | 10 | 10 | 2019-06-17 | 2019-06-28 | -42 |  |  | 0 | 2019-06-17 | 2019-06-28 | 2019-04-16 | 2019-04-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-06-17 | 2019-06-28 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | 0-100% Method | TEC Non-ARRA | Scott Winters | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 23% |  | Procurement |  | Other (specify) | [5 empty] | L3 Assembly (TEC)
FALSE |  | CAMF669245 | Combined Test Assembly (Carousel + Loader 1+ Auto Changer 1) | LSST Forecast - B57 - B1 | 4 | 4 | 2019-06-25 | 2019-06-28 | -159 |  |  | 0 | 2019-06-25 | 2019-06-28 | 2018-10-24 | 2018-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-25 | 2019-06-28 |  |  |  |  | 0 | 0 | FALSE | FALSE | StartOnOrAfter | 2019-06-25 | None | [6 empty] | 6 | 0 | 5 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Fabrication/Assembly
FALSE |  | ITC00290 | START: Science Raft Tower Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-25 | 2019-06-25 | -18 |  |  | 0 | 2019-06-25 | 2019-06-25 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2019-06-25 | 2019-06-25 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration
FALSE |  | ITC31840 | START: Science Raft Tower Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-25 | 2019-06-25 | -18 |  |  | 0 | 2019-06-25 | 2019-06-25 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | TRUE | 2019-06-25 | 2019-06-25 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 10 | 0 | 10 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [11 empty] | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC31830 | AVAIL: Eng Raft Tower from I&T for ComCam | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-25 | 2019-06-25 | -18 |  |  | 0 | 2019-06-25 | 2019-06-25 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2019-06-25 | 2019-06-25 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Fabrication/Assembly |  |  |  | Engineering | [12 empty] | Integration and Test
FALSE |  | ITC31860 | Integrate Science Raft Tower #1 of 21 | LSST Forecast - B57 - B1 | 4 | 4 | 2019-06-26 | 2019-07-01 | -18 |  |  | 0 | 2019-06-26 | 2019-07-01 | 2019-05-31 | 2019-06-05 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-06-26 | 2019-07-01 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T
FALSE |  | ITC31860_R | Integrate Science Raft Tower #1 of 21 | LSST Forecast - B57 - B1 | 4 | 4 | 2019-06-26 | 2019-07-01 | -18 |  |  | 0 | 2019-06-26 | 2019-07-01 | 2019-05-31 | 2019-06-05 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-06-26 | 2019-07-01 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 4 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 103 | 0 | 103 | 103 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Commissioning and Testing | [5 empty] | Cryostat I&T (TEC) | [7 empty] | CP #01 (Cryostat/Camera Integration)
FALSE |  | CAMM2200 | COMP: L3 Assembly Ready for Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-28 | 2019-06-28 | -42 |  |  | 363 | 2019-06-28 | 2019-06-28 | 2019-04-30 | 2019-04-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-06-28 | 2019-06-28 |  |  |  |  | 0 | 0 | FALSE | FALSE | FinishOnOrBefore | 2019-04-30 | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.01 | DOE Project Milestones | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 2 Milestone | Management/Administration
FALSE |  | OP00980 | COMP: Camera L3 Lenses Ready for I&T | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-28 | 2019-06-28 | -42 |  |  | 0 | 2019-06-28 | 2019-06-28 | 2019-04-30 | 2019-04-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2019-06-28 | 2019-06-28 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05 | Optics | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  | Level 3 Milestone | Management/Administration |  |  |  |  | Camera Lenses
FALSE |  | OP541380 | AVAIL: L3 Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-28 | 2019-06-28 | -42 |  |  | 0 | 2019-06-28 | 2019-06-28 | 2019-04-30 | 2019-04-30 | 0 | 0 | 0 | 0 | 0 | 6 | FALSE | Finish Milestone | FALSE | 2019-06-28 | 2019-06-28 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  | Level 5 Milestone | Procurement | [10 empty] | Critical Path #2 (L1_L2 Assembly) | [5 empty] | Optics
FALSE |  | CAMF669250 | Combined Functionality and Performance Tests (Carousel + Loader 1 + Auto Changer 1) | LSST Forecast - B57 - B1 | 18 | 18 | 2019-07-01 | 2019-07-25 | -159 |  |  | 0 | 2019-07-01 | 2019-07-25 | 2018-10-30 | 2018-11-26 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2019-07-01 | 2019-07-25 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 8 | 0 | 8 | 0 | 0 | 0 | 3 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 18 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Fabrication/Assembly
FALSE |  | CAMF650350 | START: Filter Exchange System Testing | LSST Forecast - B57 - B1 | 0 | 0 | 2019-07-01 | 2019-07-01 | -104 |  |  | 0 | 2019-07-01 | 2019-07-01 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 5 | FALSE | Finish Milestone | FALSE | 2019-07-01 | 2019-07-01 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 0 | 3 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03 | Exchange System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  | Level 3 Milestone | Management/Administration
FALSE |  | ITC31880 | Integrate Science Raft Tower #2 of 21 | LSST Forecast - B57 - B1 | 4 | 4 | 2019-07-02 | 2019-07-08 | -18 |  |  | 0 | 2019-07-02 | 2019-07-08 | 2019-06-06 | 2019-06-11 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-07-02 | 2019-07-08 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 102 | 0 | 102 | 102 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC31920 | Integrate Science Raft Tower #3 of 21 | LSST Forecast - B57 - B1 | 4 | 4 | 2019-07-09 | 2019-07-12 | -18 |  |  | 0 | 2019-07-09 | 2019-07-12 | 2019-06-12 | 2019-06-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2019-07-09 | 2019-07-12 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 104 | 0 | 104 | 104 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC31940 | Integrate Science Raft Tower #4 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-07-15 | 2019-07-16 | -18 |  |  | 0 | 2019-07-15 | 2019-07-16 | 2019-06-18 | 2019-06-19 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-07-15 | 2019-07-16 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC31960 | Integrate Science Raft Tower #5 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-07-17 | 2019-07-18 | -18 |  |  | 0 | 2019-07-17 | 2019-07-18 | 2019-06-20 | 2019-06-21 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-07-17 | 2019-07-18 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC31980 | Integrate Science Raft Tower #6 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-07-19 | 2019-07-22 | -18 |  |  | 0 | 2019-07-19 | 2019-07-22 | 2019-06-24 | 2019-06-25 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2019-07-19 | 2019-07-22 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32225 | Integrate Corner Raft Tower #1 of 4 | LSST Forecast - B57 - B1 | 4 | 4 | 2019-07-23 | 2019-07-26 | -18 |  |  | 0 | 2019-07-23 | 2019-07-26 | 2019-06-26 | 2019-07-01 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-07-23 | 2019-07-26 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 119 | 0 | 119 | 119 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32230 | Integrate Corner Raft Tower #2 of 4 | LSST Forecast - B57 - B1 | 4 | 4 | 2019-07-29 | 2019-08-01 | -18 |  |  | 0 | 2019-07-29 | 2019-08-01 | 2019-07-02 | 2019-07-08 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-07-29 | 2019-08-01 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 119 | 0 | 119 | 119 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32290 | Integrate Corner Raft Tower #3 of 4 | LSST Forecast - B57 - B1 | 4 | 4 | 2019-08-02 | 2019-08-07 | -18 |  |  | 0 | 2019-08-02 | 2019-08-07 | 2019-07-09 | 2019-07-12 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-08-02 | 2019-08-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 118 | 0 | 118 | 118 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | CCS300045 | AVAIL: Support for 9 rafts in full focal plane | LSST Forecast - B57 - B1 | 0 | 0 | 2019-08-06 | 2019-08-06 | -9 |  |  | 9 | 2019-08-06 | 2019-08-06 | 2019-07-24 | 2019-07-24 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-08-06 | 2019-08-06 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.08.03 | CCOB HCU | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  | Level 5 Milestone | Design/Engineering | [15 empty] | CP #02 (CCS Focal Plane Software)
FALSE |  | ITC32410 | Integrate Corner Raft Tower #4 of 4 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-08-08 | 2019-08-09 | -18 |  |  | 0 | 2019-08-08 | 2019-08-09 | 2019-07-15 | 2019-07-16 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-08-08 | 2019-08-09 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 118 | 0 | 118 | 118 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32000 | Integrate Science Raft Tower #7 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-08-12 | 2019-08-13 | -18 |  |  | 0 | 2019-08-12 | 2019-08-13 | 2019-07-17 | 2019-07-18 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-08-12 | 2019-08-13 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32020 | Integrate Science Raft Tower #8 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-08-14 | 2019-08-15 | -18 |  |  | 0 | 2019-08-14 | 2019-08-15 | 2019-07-19 | 2019-07-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-08-14 | 2019-08-15 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32040 | Integrate Science Raft Tower #9 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-08-16 | 2019-08-19 | -18 |  |  | 0 | 2019-08-16 | 2019-08-19 | 2019-07-23 | 2019-07-24 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-08-16 | 2019-08-19 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32140 | BOT Testing with Raft Tower #1-9 | LSST Forecast - B57 - B1 | 38 | 38 | 2019-08-20 | 2019-10-11 | -18 |  |  | 0 | 2019-08-20 | 2019-10-11 | 2019-07-25 | 2019-09-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2019-08-20 | 2019-10-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 38 | 0 |  | Planned | 0% | 517 | 0 | 517 | 517 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | CAMF669270 | Subsystem Packaging - Carousel | LSST Forecast - B57 - B1 | 4 | 4 | 2019-08-20 | 2019-08-23 | -176 |  |  | 0 | 2019-08-20 | 2019-08-23 | 2018-11-27 | 2018-11-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-08-20 | 2019-08-23 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 9 | 0 | 9 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Fabrication/Assembly | [15 empty] | CP #03 (Carousel/Camera Integration)
FALSE |  | CAMF669280 | Shipped to SLAC - Carousel | LSST Forecast - B57 - B1 | 24 | 24 | 2019-08-26 | 2019-09-27 | -176 |  |  | 0 | 2019-08-26 | 2019-09-27 | 2018-12-03 | 2019-01-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-08-26 | 2019-09-27 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 24 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment |  | TEC Non-ARRA | Kevin Reil | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Commissioning and Testing | [13 empty] | CP #03 (Carousel/Camera Integration)
FALSE |  | CAMF669290 | Processed through Customes - Carousel #1 | LSST Forecast - B57 - B1 | 9 | 9 | 2019-09-30 | 2019-10-10 | -176 |  |  | 0 | 2019-09-30 | 2019-10-10 | 2019-01-18 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2019-09-30 | 2019-10-10 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 9 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications |  |  |  | Kevin Reil | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Commissioning and Testing | [13 empty] | CP #03 (Carousel/Camera Integration)
FALSE |  | CAMF650900 | COMP: Exchange System Ready for Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2019-10-10 | 2019-10-10 | -176 |  |  | 0 | 2019-10-10 | 2019-10-10 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2019-10-10 | 2019-10-10 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03 | Exchange System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  | Level 3 Milestone | Management/Administration | [15 empty] | CP #03 (Carousel/Camera Integration)
FALSE |  | CAMF669300 | AVAIL: Ready for Integration - Carousel | LSST Forecast - B57 - B1 | 0 | 0 | 2019-10-10 | 2019-10-10 | -176 |  |  | 0 | 2019-10-10 | 2019-10-10 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 5 | FALSE | Finish Milestone | FALSE | 2019-10-10 | 2019-10-10 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  | Level 5 Milestone | Fabrication/Assembly | [16 empty] | Exchange System
FALSE |  | ITC19600 | NEED: Carousel (with back flange #1) | LSST Forecast - B57 - B1 | 0 | 0 | 2019-10-10 | 2019-10-10 | -8 |  |  | 0 | 2019-10-10 | 2019-10-10 | 2019-09-30 | 2019-09-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-10-10 | 2019-10-10 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Exchange System
FALSE |  | CAMM2210 | COMP: Filter Exchange System Ready for Integration (IN2P3) | LSST Forecast - B57 - B1 | 0 | 0 | 2019-10-10 | 2019-10-10 | -176 |  |  | 291 | 2019-10-10 | 2019-10-10 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-10-10 | 2019-10-10 |  |  |  |  | 0 | 0 | FALSE | FALSE | FinishOnOrBefore | 2019-01-31 | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.01 | DOE Project Milestones | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 2 Milestone | Management/Administration
FALSE |  | ITC19700 | Acceptance Testing of Back Flange with Carousel | LSST Forecast - B57 - B1 | 6 | 6 | 2019-10-11 | 2019-10-18 | -8 |  |  | 0 | 2019-10-11 | 2019-10-18 | 2019-10-01 | 2019-10-08 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-10-11 | 2019-10-18 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 6 | 0 |  | Planned | 0% | 124 | 0 | 124 | 124 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Commissioning and Testing | [5 empty] | Camera I&T (TEC) | [7 empty] | CP #03 (Carousel/Camera Integration)
FALSE |  | ITC00300 | COMP: Integration of 9 SR into Cryostat | LSST Forecast - B57 - B1 | 0 | 0 | 2019-10-11 | 2019-10-11 | -18 |  |  | 0 | 2019-10-11 | 2019-10-11 | 2019-09-17 | 2019-09-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2019-10-11 | 2019-10-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration
FALSE |  | ITC32160 | COMP: Integration of 9 SR into Cryostat | LSST Forecast - B57 - B1 | 0 | 0 | 2019-10-11 | 2019-10-11 | -18 |  |  | 0 | 2019-10-11 | 2019-10-11 | 2019-09-17 | 2019-09-17 | 0 | 0 | 0 | 0 | 0 | 6 | FALSE | Finish Milestone | TRUE | 2019-10-11 | 2019-10-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Testing/Integration
FALSE |  | ITC32180 | Integrate Science Raft Tower #10 of 21 | LSST Forecast - B57 - B1 | 6 | 6 | 2019-10-14 | 2019-10-21 | -18 |  |  | 0 | 2019-10-14 | 2019-10-21 | 2019-09-18 | 2019-09-25 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-10-14 | 2019-10-21 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 6 | 0 |  | Planned | 0% | 147 | 0 | 147 | 147 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing | [5 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC19715 | Mount and check camera housing to back flange | LSST Forecast - B57 - B1 | 11 | 11 | 2019-10-21 | 2019-11-04 | -8 |  |  | 0 | 2019-10-21 | 2019-11-04 | 2019-10-09 | 2019-10-23 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-10-21 | 2019-11-04 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 11 | 0 |  | Planned | 0% | 177 | 0 | 177 | 177 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Commissioning and Testing | [5 empty] | Camera I&T (TEC) | [7 empty] | CP #03 (Carousel/Camera Integration)
FALSE |  | ITC32200 | Integrate Science Raft Tower #11 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-10-22 | 2019-10-23 | -18 |  |  | 0 | 2019-10-22 | 2019-10-23 | 2019-09-26 | 2019-09-27 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-10-22 | 2019-10-23 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32220 | Integrate Science Raft Tower #12 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-10-24 | 2019-10-25 | -18 |  |  | 0 | 2019-10-24 | 2019-10-25 | 2019-09-30 | 2019-10-01 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-10-24 | 2019-10-25 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32240 | Integrate Science Raft Tower #13 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-10-28 | 2019-10-29 | -18 |  |  | 0 | 2019-10-28 | 2019-10-29 | 2019-10-02 | 2019-10-03 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-10-28 | 2019-10-29 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32260 | Integrate Science Raft Tower #14 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-10-30 | 2019-10-31 | -18 |  |  | 0 | 2019-10-30 | 2019-10-31 | 2019-10-04 | 2019-10-07 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-10-30 | 2019-10-31 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32280 | Integrate Science Raft Tower #15 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-11-01 | 2019-11-04 | -18 |  |  | 0 | 2019-11-01 | 2019-11-04 | 2019-10-08 | 2019-10-09 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-11-01 | 2019-11-04 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC19752 | NEED: Auto Changer | LSST Forecast - B57 - B1 | 0 | 0 | 2019-11-04 | 2019-11-04 | -8 |  |  | 0 | 2019-11-04 | 2019-11-04 | 2019-10-23 | 2019-10-23 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-11-04 | 2019-11-04 |  |  |  |  | 0 | 0 | FALSE | FALSE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | ITC19754 | Camera Assembly - Autochanger | LSST Forecast - B57 - B1 | 30 | 30 | 2019-11-05 | 2019-12-18 | -8 |  |  | 0 | 2019-11-05 | 2019-12-18 | 2019-10-24 | 2019-12-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-11-05 | 2019-12-18 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 0 |  | Planned | 0% | 783 | 0 | 783 | 783 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Camera I&T (TEC) | [6 empty] | Camera I&T | CP #03 (Carousel/Camera Integration)
FALSE |  | ITC32300 | Integrate Science Raft Tower #16 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-11-05 | 2019-11-06 | -18 |  |  | 0 | 2019-11-05 | 2019-11-06 | 2019-10-10 | 2019-10-11 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-11-05 | 2019-11-06 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32320 | Integrate Science Raft Tower #17 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-11-07 | 2019-11-08 | -18 |  |  | 0 | 2019-11-07 | 2019-11-08 | 2019-10-14 | 2019-10-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-11-07 | 2019-11-08 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32340 | Integrate Science Raft Tower #18 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-11-11 | 2019-11-12 | -18 |  |  | 0 | 2019-11-11 | 2019-11-12 | 2019-10-16 | 2019-10-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-11-11 | 2019-11-12 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32360 | Integrate Science Raft Tower #19 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-11-13 | 2019-11-14 | -18 |  |  | 0 | 2019-11-13 | 2019-11-14 | 2019-10-18 | 2019-10-21 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-11-13 | 2019-11-14 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32380 | Integrate Science Raft Tower #20 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-11-15 | 2019-11-18 | -18 |  |  | 0 | 2019-11-15 | 2019-11-18 | 2019-10-22 | 2019-10-23 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-11-15 | 2019-11-18 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32400 | Integrate Science Raft Tower #21 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-11-19 | 2019-11-20 | -18 |  |  | 0 | 2019-11-19 | 2019-11-20 | 2019-10-24 | 2019-10-25 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-11-19 | 2019-11-20 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32420 | BOT Testing with Raft Tower #1-21+4CR | LSST Forecast - B57 - B1 | 38 | 38 | 2019-11-21 | 2020-01-30 | -18 |  |  | 0 | 2019-11-21 | 2020-01-30 | 2019-10-28 | 2019-12-20 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-11-21 | 2020-01-30 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 38 | 0 |  | Planned | 0% | 517 | 0 | 517 | 517 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC00330 | START: Integrated Cryostat Testing | LSST Forecast - B57 - B1 | 0 | 0 | 2019-11-21 | 2019-11-21 | -18 |  |  | 0 | 2019-11-21 | 2019-11-21 | 2019-10-25 | 2019-10-25 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | TRUE | 2019-11-21 | 2019-11-21 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration
FALSE |  | ITC32415 | START: Final Integrated Cryostat Testing | LSST Forecast - B57 - B1 | 0 | 0 | 2019-11-21 | 2019-11-21 | -18 |  |  | 0 | 2019-11-21 | 2019-11-21 | 2019-10-25 | 2019-10-25 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Start Milestone | TRUE | 2019-11-21 | 2019-11-21 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Management/Administration
FALSE |  | ITC19756 | NEED: Shutter | LSST Forecast - B57 - B1 | 0 | 0 | 2019-12-18 | 2019-12-18 | -8 |  |  | 0 | 2019-12-18 | 2019-12-18 | 2019-12-06 | 2019-12-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-12-18 | 2019-12-18 |  |  |  |  | 0 | 0 | FALSE | FALSE | AsLateAsPossible |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Camera Body & Shutter
FALSE |  | ITC19758 | NEED: Shutter CCS Software & HCU | LSST Forecast - B57 - B1 | 0 | 0 | 2019-12-18 | 2019-12-18 | -8 |  |  | 0 | 2019-12-18 | 2019-12-18 | 2019-12-06 | 2019-12-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-12-18 | 2019-12-18 |  |  |  |  | 0 | 0 | FALSE | FALSE | AsLateAsPossible |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Camera Body & Shutter
FALSE |  | ITC19760 | Camera Assembly - Shutter | LSST Forecast - B57 - B1 | 27 | 27 | 2019-12-19 | 2020-02-10 | -8 |  |  | 0 | 2019-12-19 | 2020-02-10 | 2019-12-09 | 2020-01-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-12-19 | 2020-02-10 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 27 | 0 |  | Planned | 0% | 407 | 0 | 407 | 407 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Camera I&T (TEC) | [6 empty] | Camera I&T | CP #03 (Carousel/Camera Integration)
FALSE |  | ITC00335 | COMP: I&T of Loaded Cryostat (21 SR+4 CR) | LSST Forecast - B57 - B1 | 0 | 0 | 2020-01-30 | 2020-01-30 | -18 |  |  | 0 | 2020-01-30 | 2020-01-30 | 2019-12-20 | 2019-12-20 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | TRUE | 2020-01-30 | 2020-01-30 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration
FALSE |  | ITC32460 | NEED: L3 Lens Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2020-01-30 | 2020-01-30 | -18 |  |  | 0 | 2020-01-30 | 2020-01-30 | 2019-12-20 | 2019-12-20 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | TRUE | 2020-01-30 | 2020-01-30 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Optics
FALSE |  | ITC32440 | COMP: I&T of Loaded Cryostat (21 SR+4 CR) | LSST Forecast - B57 - B1 | 0 | 0 | 2020-01-30 | 2020-01-30 | -18 |  |  | 0 | 2020-01-30 | 2020-01-30 | 2019-12-20 | 2019-12-20 | 0 | 0 | 0 | 0 | 0 | 6 | FALSE | Finish Milestone | TRUE | 2020-01-30 | 2020-01-30 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [6 empty] | Critical Path #1 (Sensor & Raft Tower Production) |  |  |  |  | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32480 | Mount L3 Lens Assembly | LSST Forecast - B57 - B1 | 8 | 8 | 2020-01-31 | 2020-02-11 | -18 |  |  | 0 | 2020-01-31 | 2020-02-11 | 2020-01-06 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-01-31 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 8 | 0 |  | Planned | 0% | 65 | 0 | 65 | 65 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC00400 | COMP: Shutter Integrated Into Camera | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-10 | 2020-02-10 | -8 |  |  | 0 | 2020-02-10 | 2020-02-10 | 2020-01-29 | 2020-01-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2020-02-10 | 2020-02-10 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration | [15 empty] | CP #03 (Carousel/Camera Integration)
FALSE |  | ITC19772 | NEED: CCS Suite #8 (+HCU) (NEEDS LINK) | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-10 | 2020-02-10 | -8 |  |  | 0 | 2020-02-10 | 2020-02-10 | 2020-01-29 | 2020-01-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2020-02-10 | 2020-02-10 |  |  |  |  | 0 | 0 | FALSE | FALSE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | ITC19775 | Camera Assembly - Integrated Testing | LSST Forecast - B57 - B1 | 26 | 26 | 2020-02-11 | 2020-03-18 | -8 |  |  | 0 | 2020-02-11 | 2020-03-18 | 2020-01-30 | 2020-03-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2020-02-11 | 2020-03-18 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 26 | 0 |  | Planned | 0% | 555 | 0 | 555 | 555 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Commissioning and Testing | [5 empty] | Camera I&T (TEC) | [7 empty] | CP #03 (Carousel/Camera Integration)
FALSE |  | ITC32500 | NEED: Utility Trunk | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Cryostat
FALSE |  | ITC32520 | NEED: Camera purge unit | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Camera Body & Shutter
FALSE |  | ITC32540 | NEED: UT cooling system | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Utility Trunk
FALSE |  | ITC32580 | NEED: UT Aux Electronics | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 14 | 0 | 14 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Auxiliary Electronics
FALSE |  | ITC32565 | NEED: Diagnostic Cluster from CCS | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Auxiliary Electronics
FALSE |  | ITC32590 | NEED: Cryostat Lift Fixture for Cryostat I&T | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Cryostat
FALSE |  | ITC32510 | NEED: Vacuum Purge | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Cryostat
FALSE |  | ITC32530 | NEED: Cryostat Handling Equipment | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | ITC32570 | NEED: Controls for Utility Trunk | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | ITC32620 | Mount and Populate Utility Trunk | LSST Forecast - B57 - B1 | 40 | 40 | 2020-02-12 | 2020-04-08 | -18 |  |  | 0 | 2020-02-12 | 2020-04-08 | 2020-01-16 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-02-12 | 2020-04-08 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 13 | 0 | 13 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 0 |  | Planned | 0% | 767 | 0 | 767 | 767 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC00425 | COMP: Filter Systems Integrated Into Camera | LSST Forecast - B57 - B1 | 0 | 0 | 2020-03-18 | 2020-03-18 | -8 |  |  | 0 | 2020-03-18 | 2020-03-18 | 2020-03-06 | 2020-03-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2020-03-18 | 2020-03-18 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration | [15 empty] | CP #03 (Carousel/Camera Integration)
FALSE |  | ITC19800 | Camera Disassembly | LSST Forecast - B57 - B1 | 5 | 5 | 2020-03-19 | 2020-03-25 | -8 |  |  | 10 | 2020-03-19 | 2020-03-25 | 2020-03-09 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2020-03-19 | 2020-03-25 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 0 |  | Planned | 0% | 108 | 0 | 108 | 108 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Commissioning and Testing | [5 empty] | Camera I&T (TEC) | [7 empty] | CP #03 (Carousel/Camera Integration)
FALSE |  | ITC00340 | COMP: Cryostat and UT Assembled | LSST Forecast - B57 - B1 | 0 | 0 | 2020-04-08 | 2020-04-08 | -18 |  |  | 0 | 2020-04-08 | 2020-04-08 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-04-08 | 2020-04-08 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration |  |  |  |  | SR Rafts Installed and Cryostat Closed (min of 5 SR and 4 CR)
FALSE |  | ITC19850 | NEED: Loaded Cryostat | LSST Forecast - B57 - B1 | 0 | 0 | 2020-04-08 | 2020-04-08 | -18 |  |  | 0 | 2020-04-08 | 2020-04-08 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-04-08 | 2020-04-08 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Integration and Test
FALSE |  | ITC32660 | AVAIL: Loaded Cryostat Ready for Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2020-04-08 | 2020-04-08 | -18 |  |  | 0 | 2020-04-08 | 2020-04-08 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | TRUE | 2020-04-08 | 2020-04-08 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration | [16 empty] | Integration and Test
FALSE |  | ITC19852 | NEED: Camera Handling Equipment Ready for Camera I&T | LSST Forecast - B57 - B1 | 0 | 0 | 2020-04-08 | 2020-04-08 | -18 |  |  | 0 | 2020-04-08 | 2020-04-08 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-04-08 | 2020-04-08 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | ITC19900 | Camera / Cryostat Integration | LSST Forecast - B57 - B1 | 30 | 30 | 2020-04-09 | 2020-05-20 | -18 |  |  | 0 | 2020-04-09 | 2020-05-20 | 2020-03-16 | 2020-04-24 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2020-04-09 | 2020-05-20 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 7 | 0 | 7 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 0 |  | Planned | 0% | 518 | 0 | 518 | 518 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration | Stanford University | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Camera I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Camera I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC20000 | NEED: L1-L2 Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2020-05-20 | 2020-05-20 | -18 |  |  | 0 | 2020-05-20 | 2020-05-20 | 2020-04-24 | 2020-04-24 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-05-20 | 2020-05-20 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Optics
FALSE |  | ITC00450 | COMP: Cryostat Integrated Into Camera Body | LSST Forecast - B57 - B1 | 0 | 0 | 2020-05-20 | 2020-05-20 | -18 |  |  | 0 | 2020-05-20 | 2020-05-20 | 2020-04-24 | 2020-04-24 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-05-20 | 2020-05-20 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration
FALSE |  | ITC20025 | L1-L2 Integration | LSST Forecast - B57 - B1 | 25 | 25 | 2020-05-21 | 2020-06-25 | -18 |  |  | 0 | 2020-05-21 | 2020-06-25 | 2020-04-27 | 2020-06-01 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-05-21 | 2020-06-25 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 0 |  | Planned | 0% | 816 | 0 | 816 | 816 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration | Stanford University | Commissioning and Testing | [5 empty] | Camera I&T (TEC) | [5 empty] | Critical Path to CD-2 |  | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC20050 | Final Camera Assembly / Closeout | LSST Forecast - B57 - B1 | 15 | 15 | 2020-06-26 | 2020-07-17 | -18 |  |  | 0 | 2020-06-26 | 2020-07-17 | 2020-06-02 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-06-26 | 2020-07-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 0 |  | Planned | 0% | 270 | 0 | 270 | 270 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration | Stanford University | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Camera I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Camera I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC00475 | COMP: Camera Ready for Verification Testing | LSST Forecast - B57 - B1 | 0 | 0 | 2020-07-17 | 2020-07-17 | -18 |  |  | 0 | 2020-07-17 | 2020-07-17 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | TRUE | 2020-07-17 | 2020-07-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration
FALSE |  | ITC20070 | NEED: Filters (partial) | LSST Forecast - B57 - B1 | 0 | 0 | 2020-07-17 | 2020-07-17 | -18 |  |  | 0 | 2020-07-17 | 2020-07-17 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-07-17 | 2020-07-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration | [16 empty] | Optics
FALSE |  | ITC20060 | COMP: Camera Ready for Verification Testing | LSST Forecast - B57 - B1 | 0 | 0 | 2020-07-17 | 2020-07-17 | -18 |  |  | 0 | 2020-07-17 | 2020-07-17 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | TRUE | 2020-07-17 | 2020-07-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Testing/Integration | [10 empty] | Critical Path #1 (Sensor & Raft Tower Production)
FALSE |  | ITC20065 | NEED: OCS & CCS Ready for I&T Testing (CCS Suite #9) | LSST Forecast - B57 - B1 | 0 | 0 | 2020-07-17 | 2020-07-17 | -18 |  |  | 0 | 2020-07-17 | 2020-07-17 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-07-17 | 2020-07-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 11 | 0 | 11 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration | [16 empty] | Project Management
FALSE |  | ITC20076 | NEED: DAQ Production V5.0 | LSST Forecast - B57 - B1 | 0 | 0 | 2020-07-17 | 2020-07-17 | -18 |  |  | 0 | 2020-07-17 | 2020-07-17 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-07-17 | 2020-07-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 10 | 0 | 10 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | ITC20072 | NEED: Filter Loader | LSST Forecast - B57 - B1 | 0 | 0 | 2020-07-17 | 2020-07-17 | -18 |  |  | 0 | 2020-07-17 | 2020-07-17 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-07-17 | 2020-07-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | ITC20125 | Camera Functional Testing | LSST Forecast - B57 - B1 | 46 | 46 | 2020-07-20 | 2020-09-22 | -18 |  |  | 0 | 2020-07-20 | 2020-09-22 | 2020-06-23 | 2020-08-26 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2020-07-20 | 2020-09-22 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 46 | 0 |  | Planned | 0% | 1432 | 0 | 1432 | 1432 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration | Stanford University | Commissioning and Testing | [5 empty] | Camera I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Camera I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | CAMM6150 | DECISION: Postpone System-Level Verification Testing | LSST Forecast - B57 - B1 | 0 | 0 | 2020-09-22 | 2020-09-22 | -18 |  |  | 0 | 2020-09-22 | 2020-09-22 | 2020-08-26 | 2020-08-26 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-09-22 | 2020-09-22 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.05 | Upscope/Descope Decision Points | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration
FALSE |  | ITC20130 | NEED: CCOB Ready for Camera Verification Testing | LSST Forecast - B57 - B1 | 0 | 0 | 2020-09-22 | 2020-09-22 | -18 |  |  | 0 | 2020-09-22 | 2020-09-22 | 2020-08-26 | 2020-08-26 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-09-22 | 2020-09-22 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | ITC20150 | Camera Verification Testing | LSST Forecast - B57 - B1 | 45 | 45 | 2020-09-23 | 2020-11-24 | -18 |  |  | 0 | 2020-09-23 | 2020-11-24 | 2020-08-27 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | TRUE | 2020-09-23 | 2020-11-24 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 7 | 0 | 5 | 0 | 0 | 2 | 3 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 45 | 0 |  | Planned | 0% | 1468 | 0 | 1468 | 1468 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration | Stanford University | Commissioning and Testing | [5 empty] | Camera I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Camera I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC20160 | NEED: Filters Remaining | LSST Forecast - B57 - B1 | 0 | 0 | 2020-11-24 | 2020-11-24 | -18 |  |  | 0 | 2020-11-24 | 2020-11-24 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-11-24 | 2020-11-24 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration | [16 empty] | Optics
FALSE |  | ITC20170 | NEED: Cryostat Sieve (Getter Pumps) | LSST Forecast - B57 - B1 | 0 | 0 | 2020-11-24 | 2020-11-24 | -18 |  |  | 0 | 2020-11-24 | 2020-11-24 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-11-24 | 2020-11-24 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration | [16 empty] | Optics
FALSE |  | ITC20175 | NEED: Cryostat Evaporative Getter Pumps | LSST Forecast - B57 - B1 | 0 | 0 | 2020-11-24 | 2020-11-24 | -18 |  |  | 0 | 2020-11-24 | 2020-11-24 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-11-24 | 2020-11-24 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration | [16 empty] | Optics
FALSE |  | ITC20180 | Recover from tests, secure Camera for shipping | LSST Forecast - B57 - B1 | 7 | 7 | 2020-11-25 | 2020-12-07 | -18 |  |  | 0 | 2020-11-25 | 2020-12-07 | 2020-10-30 | 2020-11-09 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-11-25 | 2020-12-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 7 | 0 |  | Planned | 0% | 392 | 0 | 392 | 392 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration | Stanford University | Commissioning and Testing | [5 empty] | Camera I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Camera I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC00500 | COMP: Camera Ready - Integrated & Tested @ SLAC | LSST Forecast - B57 - B1 | 0 | 0 | 2020-12-07 | 2020-12-07 | -18 |  |  | 0 | 2020-12-07 | 2020-12-07 | 2020-11-09 | 2020-11-09 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-12-07 | 2020-12-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration
FALSE |  | ITC20200 | COMP: Camera Verification Tests Complete | LSST Forecast - B57 - B1 | 0 | 0 | 2020-12-07 | 2020-12-07 | -18 |  |  | 0 | 2020-12-07 | 2020-12-07 | 2020-11-09 | 2020-11-09 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | TRUE | 2020-12-07 | 2020-12-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Testing/Integration | [10 empty] | Critical Path #1 (Sensor & Raft Tower Production)
FALSE |  | ITC20349 | NEED: As-built documentation | LSST Forecast - B57 - B1 | 0 | 0 | 2020-12-07 | 2020-12-07 | -18 |  |  | 0 | 2020-12-07 | 2020-12-07 | 2020-11-09 | 2020-11-09 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | TRUE | 2020-12-07 | 2020-12-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration | [10 empty] | Critical Path #1 (Sensor & Raft Tower Production)
FALSE |  | ITC20350 | Prep for C_PSR/ORR--Camera | LSST Forecast - B57 - B1 | 6 | 6 | 2020-12-08 | 2020-12-15 | -18 |  |  | 0 | 2020-12-08 | 2020-12-15 | 2020-11-10 | 2020-11-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-12-08 | 2020-12-15 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 10 | 0 | 10 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 6 | 0 |  | Planned | 0% | 120 | 0 | 120 | 120 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration | Stanford University | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Camera I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Camera I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC20375 | Camera Pre-Ship/Operations Readiness Review | LSST Forecast - B57 - B1 | 2 | 2 | 2020-12-16 | 2020-12-17 | -18 |  |  | 0 | 2020-12-16 | 2020-12-17 | 2020-11-18 | 2020-11-19 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-12-16 | 2020-12-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 48 | 0 | 48 | 48 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration | Stanford University | Commissioning and Testing | [5 empty] | Camera I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 |  | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC00525 | COMP: C_PSR/ORR - Camera Pre-Ship/Operations Readiness Review Complete | LSST Forecast - B57 - B1 | 0 | 0 | 2020-12-17 | 2020-12-17 | -18 |  |  | 0 | 2020-12-17 | 2020-12-17 | 2020-11-19 | 2020-11-19 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2020-12-17 | 2020-12-17 |  |  |  |  | 0 | 0 | FALSE | FALSE | FinishOnOrBefore | 2020-11-19 | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration | [10 empty] | Critical Path #1 (Sensor & Raft Tower Production) |  |  |  |  | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC20400 | COMP: C_PSR/ORR--Camera Pre-Ship/Operations Readiness Review Complete | LSST Forecast - B57 - B1 | 0 | 0 | 2020-12-17 | 2020-12-17 | -18 |  |  | 0 | 2020-12-17 | 2020-12-17 | 2020-11-19 | 2020-11-19 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Finish Milestone | TRUE | 2020-12-17 | 2020-12-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration
Insufficient Detail™
Number of activities that have a duration longer than 10% of the total duration of the project. This number should not exceed 5%.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | Previous Start | Previous Finish | Percent Complete | Previous Remaining Duration | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | IsLevelOfEffort | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | Global_Basis of Estimate | Global_Cobra Cost Class | Cobra PMT (EV Method)_Global | Global_Color of Money | Global_Control Account Manager | Global_Design Maturity | Global_Judgement Factor | Global_Milestone Levels | Global_Project Phase | Global_Funding Source | Global_EDIA Survey | Global_MS Type | Phase | NSF Milestones | Loading Curve | Sensor Vendor | LSST_CA | Summary Schedule | ICD for NSF Input | LSST Camera Critical Paths | CD2 Budget Changes | DOE Reviews | Critical Path (CD Reviews) | LSST WP Summary | Critical Path (Camera Delivery) | AWARD / NEED Sub-System | Final Design Key Links | CP - CAMM2100 | CP - CAMM2130 | CP - CAMM2160 | BNL Work Org | Last ETC Update | BNL WBS | LSST Story List | Sum Sch 01 (Camera) | Sum Sch 02 (IT w/Needs) | Sum Sch 03 (Sensors_RTM_IT) | LSST Raft Particulate Mitigation | LSST RTM
FALSE |  | CAMF804360 | ETU Final Design, Document and Oversite - Auto Changer | LSST Forecast - B57 - B1 | 639 | 0 | 2011-05-23 | 2013-10-31 | 0 | 2011-05-23 | 2013-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2011-05-23 | 2013-10-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 639 | 638 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.01 | Auto Changer | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Engineering Test/Validation
FALSE |  | CAMF804460 | ETU Procurement Preps and Fabrication - Auto Changer | LSST Forecast - B57 - B1 | 1037 | 0 | 2011-05-23 | 2016-12-30 | 0 | 2011-05-23 | 2016-12-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2011-05-23 | 2015-05-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1037 | 1464 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.01 | Auto Changer | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Engineering Test/Validation
FALSE |  | CAMF804560 | ETU Test and Validate - Auto Changer | LSST Forecast - B57 - B1 | 1300 | 0 | 2011-05-23 | 2018-11-30 | 0 | 2011-05-23 | 2018-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2018-10-24 | 2018-10-24 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2011-05-23 | 2016-05-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1300 | 1964 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.01 | Auto Changer | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Engineering Test/Validation
FALSE |  | CAMF804860 | ETU Final Design, Document and Oversite - Filter Loader | LSST Forecast - B57 - B1 | 639 | 0 | 2011-05-23 | 2013-10-31 | 0 | 2011-05-23 | 2013-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2011-05-23 | 2013-10-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 639 | 638 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.02 | Filter Loader | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Engineering Test/Validation
FALSE |  | CAMF804960 | ETU Procurement Preps and Fabrication - Filter Loader | LSST Forecast - B57 - B1 | 1055 | 0 | 2011-05-23 | 2016-03-08 | 0 | 2011-05-23 | 2016-03-08 | 0 | 2019-06-01 | 2019-06-01 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2011-05-23 | 2015-06-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1055 | 1251 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.02 | Filter Loader | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Engineering Test/Validation
FALSE |  | CAMF805560 | ETU Test and Validate - Carousel | LSST Forecast - B57 - B1 | 1299 | 0 | 2011-05-23 | 2018-12-10 | 0 | 2011-05-23 | 2018-12-10 | 0 | 2019-06-01 | 2019-06-01 | 2018-10-24 | 2018-10-24 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2011-05-23 | 2016-05-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1299 | 1970 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Engineering Test/Validation
FALSE |  | x-1331023 | LSST SRS Management (SLAC) (buy-off) | LSST Forecast - B57 - B1 | 596 | 0 | 2011-08-15 | 2014-01-31 | 0 | 2011-08-15 | 2014-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2011-08-15 | 2014-01-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 596 | 594 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.01 | Science Sensors | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien |  |  | OPC Non-ARRA | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 0% |  | Development (includes R&D) |  | Construction Management | [12 empty] | Science Sensors | [8 empty] | Science Sensors
FALSE |  | OP10950 | Update Optics subsystem spec (After CD1) | LSST Forecast - B57 - B1 | 667 | 0 | 2011-11-30 | 2014-07-25 | 0 | 2011-11-30 | 2014-07-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2011-11-30 | 2014-07-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 667 | 666 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.01 | Optics Integration & Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | OPC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Optics System Management
FALSE |  | OP11000 | Update Optics subsystem ICD's (After CD1) | LSST Forecast - B57 - B1 | 667 | 0 | 2011-11-30 | 2014-07-25 | 0 | 2011-11-30 | 2014-07-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2011-11-30 | 2014-07-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 667 | 666 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.01 | Optics Integration & Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | OPC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Optics System Management
FALSE |  | SR331030 | Preliminary Design & Development - RSA Hardware (Thermal Strap, Make-Up Heater,RTD) | LSST Forecast - B57 - B1 | 427 | 0 | 2011-12-01 | 2013-08-12 | 0 | 2011-12-01 | 2013-08-12 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2011-12-01 | 2013-08-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 427 | 426 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.02 | Science Raft Sensor Assembly (SRSA) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | OPC Non-ARRA | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 0% |  | Development (includes R&D) |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Raft Sensor Assembly (RSA) | [8 empty] | Science Raft System
FALSE |  | CR210840 | Update CSS CD-2- Corner Raft | LSST Forecast - B57 - B1 | 540 | 0 | 2011-12-01 | 2014-02-28 | 0 | 2011-12-01 | 2014-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 6 | FALSE | Normal | FALSE | 2011-12-01 | 2014-02-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 540 | 539 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.01 | Corner Raft System Integration and Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | OPC Non-ARRA | Vincent Riot | (1.00) Task/item is fully invoiced/completed | 0% |  | Development (includes R&D) |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [6 empty] | Management | [5 empty] | Corner Raft System Integration and Management
FALSE |  | OP530080 | Update L1-L2 opto-mech spec, ICD, IDD | LSST Forecast - B57 - B1 | 419 | 0 | 2011-12-01 | 2013-07-31 | 0 | 2011-12-01 | 2013-07-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2011-12-01 | 2013-07-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 419 | 418 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | OPC Non-ARRA | Scott Winters | (1.00) Task/item is fully invoiced/completed | 0% |  | Development (includes R&D) |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | L1-L2 Opto-Mechanics
FALSE |  | x-1331013 | Sensor Design and Evaluation (Harvard) (buy-off) | LSST Forecast - B57 - B1 | 544 | 0 | 2011-12-01 | 2014-01-31 | 0 | 2011-12-01 | 2014-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2011-12-01 | 2014-01-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 544 | 543 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.01 | Science Sensors Prototype & Development | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien |  |  |  | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 0% |  | Design/Engineering |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [6 empty] | Prototype & Development | [14 empty] | Science Sensors
FALSE |  | x-19055 | Test Stands (buy-off) | LSST Forecast - B57 - B1 | 544 | 0 | 2011-12-01 | 2014-01-31 | 0 | 2011-12-01 | 2014-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2011-12-01 | 2014-01-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 544 | 543 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.01 | Science Sensors Prototype & Development | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien |  |  |  | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 0% |  | Design/Engineering |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [6 empty] | Prototype & Development | [14 empty] | Science Sensors
FALSE |  | x-19056 | Sensors (buy-off) | LSST Forecast - B57 - B1 | 544 | 0 | 2011-12-01 | 2014-01-31 | 0 | 2011-12-01 | 2014-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2011-12-01 | 2014-01-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 544 | 543 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.01 | Science Sensors Prototype & Development | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien |  |  |  | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 0% |  | Design/Engineering |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [6 empty] | Prototype & Development | [14 empty] | Science Sensors
FALSE |  | SR321110 | Procure material - RTM Material Dummy (combine with ETU) | LSST Forecast - B57 - B1 | 663 | 0 | 2011-12-12 | 2014-07-31 | 0 | 2011-12-12 | 2014-07-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2011-12-12 | 2014-07-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 663 | 662 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.01 | Science Raft Tower Module (SRTM) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | OPC Non-ARRA | Bill Wahl | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Development (includes R&D) |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | Subcontractor | [11 empty] | Raft Tower Module (RTM) | [8 empty] | Science Raft System
FALSE |  | CCS111900 | Generate CSS CD-2 -CCS | LSST Forecast - B57 - B1 | 635 | 0 | 2012-01-01 | 2014-07-31 | 0 | 2012-01-01 | 2014-07-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2012-01-03 | 2014-07-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 635 | 634 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.01 | CCS Integration & Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Tony Johnson | (1.00) Task/item is fully invoiced/completed | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [7 empty] | ICD's for Phase 2 |  |  |  |  | Camera Control System
FALSE |  | CAMF658950 | Preliminary Design - Auto Changer | LSST Forecast - B57 - B1 | 456 | 0 | 2012-01-02 | 2013-10-31 | 0 | 2012-01-02 | 2013-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2018-10-16 | 2018-10-16 | 0 | 0 | 0 | 0 | 0 | 5 | FALSE | Normal | FALSE | 2012-01-03 | 2013-10-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 456 | 455 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.01 | Auto Changer | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Design/Engineering
FALSE |  | ITC20500 | Generate CCOB test plans | LSST Forecast - B57 - B1 | 677 | 0 | 2012-01-03 | 2014-09-30 | 0 | 2012-01-03 | 2014-09-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2012-01-03 | 2014-09-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 677 | 676 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.03.02 | CCOB (France) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  | OPC Non-ARRA | Tim Bond |  |  |  | Design/Engineering |  |  |  | Development
FALSE |  | ITC30300 | Generate Preliminary Software Development test plans | LSST Forecast - B57 - B1 | 508 | 0 | 2012-01-03 | 2014-01-30 | 0 | 2012-01-03 | 2014-01-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2012-01-03 | 2014-01-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 508 | 507 |  | Complete | 100% | 0 | 8 | 0 | 8 | LSST Forecast - B57 - B1.3.08.02.04 | Verification Software Development | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  | OPC Non-ARRA | Tim Bond | (1.00) Task/item is fully invoiced/completed | 0% |  | Development (includes R&D) |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Verification Test Systems
FALSE |  | SR331020 | Preliminary Design & Development - RSA Base Plate | LSST Forecast - B57 - B1 | 390 | 0 | 2012-01-13 | 2013-07-31 | 0 | 2012-01-13 | 2013-07-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2012-01-13 | 2013-07-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 390 | 389 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.02 | Science Raft Sensor Assembly (SRSA) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | OPC Non-ARRA | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 0% |  | Development (includes R&D) |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Raft Sensor Assembly (RSA) | [8 empty] | Science Raft System
FALSE |  | SR332060 | Test Stand Initial Design and Layout | LSST Forecast - B57 - B1 | 467 | 0 | 2012-03-05 | 2014-01-31 | 0 | 2012-03-05 | 2014-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2012-03-05 | 2014-01-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 467 | 466 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.01 | Science Sensors Prototype & Development | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Bill Wahl |  |  |  | Design/Engineering | [8 empty] | Prototype & Development | [14 empty] | Science Sensors
FALSE |  | CRYO21300 | Interim Design - Grid Assembly | LSST Forecast - B57 - B1 | 445 | 0 | 2012-05-01 | 2014-02-28 | 0 | 2012-05-01 | 2014-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2012-05-01 | 2014-02-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 445 | 444 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.04 | Grid Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | OPC Non-ARRA | Brian J. Langton | (1.00) Task/item is fully invoiced/completed | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Grid Assembly
FALSE |  | CRYO21350 | Interim Analysis - Grid Assembly | LSST Forecast - B57 - B1 | 445 | 0 | 2012-05-01 | 2014-02-28 | 0 | 2012-05-01 | 2014-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2012-05-01 | 2014-02-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 445 | 444 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.04 | Grid Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | OPC Non-ARRA | Brian J. Langton | (1.00) Task/item is fully invoiced/completed | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Grid Assembly
FALSE |  | SR332065 | Test Stand Prototype Development | LSST Forecast - B57 - B1 | 422 | 0 | 2012-05-07 | 2014-01-31 | 0 | 2012-05-07 | 2014-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2012-05-07 | 2014-01-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 422 | 421 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.01 | Science Sensors Prototype & Development | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Bill Wahl |  |  |  | Design/Engineering | [8 empty] | Prototype & Development | [14 empty] | Science Sensors
FALSE |  | CRYO16300 | Interim Design - Cryo & Cold Plate | LSST Forecast - B57 - B1 | 402 | 0 | 2012-07-01 | 2014-02-28 | 0 | 2012-07-01 | 2014-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2012-07-02 | 2014-02-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 402 | 401 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.03 | Cryo and Cold Plates | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | OPC Non-ARRA | Brian J. Langton | (1.00) Task/item is fully invoiced/completed | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Cryo and Cold Plates
FALSE |  | CRYO16350 | Interim Analysis - Cryo & Cold Plate | LSST Forecast - B57 - B1 | 402 | 0 | 2012-07-01 | 2014-02-28 | 0 | 2012-07-01 | 2014-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2012-07-02 | 2014-02-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 402 | 401 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.03 | Cryo and Cold Plates | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | OPC Non-ARRA | Brian J. Langton | (1.00) Task/item is fully invoiced/completed | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Cryo and Cold Plates
FALSE |  | SR321090 | Design & Drawings - RTM Dummy ( delete & combine resource with ETU) | LSST Forecast - B57 - B1 | 522 | 0 | 2012-07-03 | 2014-07-31 | 0 | 2012-07-03 | 2014-07-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2012-07-03 | 2014-07-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 522 | 521 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.01 | Science Raft Tower Module (SRTM) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | OPC Non-ARRA | Bill Wahl | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Development (includes R&D) |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Raft Tower Module (RTM) | [8 empty] | Science Raft System
FALSE |  | CBM21300 | Update CSS CD-2- Camera Body | LSST Forecast - B57 - B1 | 406 | 0 | 2012-08-27 | 2014-04-30 | 0 | 2012-08-27 | 2014-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2018-09-07 | 2018-09-07 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2012-08-27 | 2014-04-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 406 | 405 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.01.02 | Camera Body Development | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | OPC Non-ARRA | Martin Nordby | (1.00) Task/item is fully invoiced/completed | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Cam Body/Purge Engin/Dsn
FALSE |  | OP540220 | Update L3 optics spec, ICD, IDD | LSST Forecast - B57 - B1 | 413 | 0 | 2012-12-03 | 2014-07-25 | 0 | 2012-12-03 | 2014-07-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2012-12-03 | 2014-07-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 413 | 412 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | OPC Non-ARRA | Scott Winters | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | L3 Optics
FALSE |  | CAMF805060 | ETU Test and Validate - Filter Loader | LSST Forecast - B57 - B1 | 777 | 0 | 2013-05-23 | 2018-08-21 | 0 | 2013-05-23 | 2018-08-21 | 0 | 2019-06-01 | 2019-06-01 | 2018-10-24 | 2018-10-24 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2013-05-23 | 2016-05-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 777 | 1368 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.02 | Filter Loader | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Engineering Test/Validation
FALSE |  | CCS401000 | Maintenance of existing refrigeration test stand - Refrigeration HCU | LSST Forecast - B57 - B1 | 485 | 0 | 2014-12-05 | 2016-11-15 | 0 | 2014-12-05 | 2016-11-15 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-12-05 | 2016-11-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 485 | 475 |  | Complete | 100% | 480 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.02 | Refrigeration HCU | 480 | 480 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Testing/Integration |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | CCS HCU (TEC) | [6 empty] | Camera I&T Hardware Control Unit
FALSE |  | OP531160 | Procurement Support - L1-L2 Assembly - Phase 4b | LSST Forecast - B57 - B1 | 558 | 0 | 2015-11-02 | 2019-03-29 | 0 | 2015-11-02 | 2019-03-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-05 | 2019-09-05 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-12-01 | 2018-02-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 558 | 853 |  | Complete | 100% | 800 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 800 | 800 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 0% |  | Procurement | [7 empty] | L1-L2 Assembly (TEC) | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly) |  |  |  | L1-L2 Opto-Mechanics
FALSE |  | OP522440 | Support Filter fabrication | LSST Forecast - B57 - B1 | 475 | 107 | 2016-08-10 | 2019-10-31 | 168 | 2016-08-10 |  | 0 | 2019-06-03 | 2019-10-31 | 2020-02-04 | 2020-07-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-09-02 | 2018-07-25 |  |  |  |  | 0.1 | 0 | FALSE | FALSE | None |  | None |  | 2019-10-31 |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 475 | 705 |  | InProgress | 77.47% | 400 | 0 | 400 | 400 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 309.8947 | 400 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Drtn | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 18% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Filters (TEC) | Production Filters Polish and integration | [5 empty] | Filter Optics
FALSE |  | DAQ103600 | FY17 - FY19 Sub-System Management | LSST Forecast - B57 - B1 | 728 | 84 | 2016-10-01 | 2019-09-30 | 604 | 2016-10-01 |  | 0 | 2019-06-03 | 2019-09-30 | 2021-11-12 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-11-01 | 2019-10-29 |  |  |  |  | 0.5192 | 0 | FALSE | FALSE | None |  | None |  | 2019-09-30 |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 728 | 644 |  | InProgress | 88.46% | 700 | 0 | 700 | 700 | LSST Forecast - B57 - B1.3.07.02.01 | DAQ Integration & Management | 619.2308 | 599.0385 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Drtn | Existing Lien | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Management/Administration |  | Construction Management | [5 empty] | DAQ Integration & Management (TEC) | [6 empty] | DAQ Management
FALSE |  | DAQ104200 | FY17 - FY19 Travel - Management | LSST Forecast - B57 - B1 | 728 | 84 | 2016-10-01 | 2019-09-30 | 604 | 2016-10-01 |  | 0 | 2019-06-03 | 2019-09-30 | 2021-11-12 | 2022-03-29 | 30000 | 30000 | 0 | 30000 | 30000 | 1 | FALSE | Normal | FALSE | 2016-11-01 | 2019-10-29 |  |  |  |  | 0.5192 | 0 | FALSE | FALSE | None |  | None |  | 2019-09-30 |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 728 | 644 |  | InProgress | 88.46% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.01 | DAQ Integration & Management | 0 | 0 | 0 | 26538.46 | 25673.08 | 30000 | PercentComplete | 6% | CP_Drtn | Catalog Listing or Industrial Construction Databases | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Management/Administration |  | Construction Management | [5 empty] | DAQ Integration & Management (TEC) | [6 empty] | DAQ Management
FALSE |  | DAQ104900 | FY17 - 19 Sub-System Maintenance | LSST Forecast - B57 - B1 | 728 | 84 | 2016-10-01 | 2019-09-30 | 604 | 2016-10-01 |  | 0 | 2019-06-03 | 2019-09-30 | 2021-11-12 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-11-01 | 2019-10-29 |  |  |  |  | 0.5192 | 0 | FALSE | FALSE | None |  | None |  | 2019-09-30 |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 728 | 644 |  | InProgress | 88.46% | 582.4 | 0 | 582.4 | 582.4 | LSST Forecast - B57 - B1.3.07.02.01 | DAQ Integration & Management | 515.2 | 498.4 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Drtn | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Management/Administration |  | Construction Management | [5 empty] | DAQ Integration & Management (TEC) | [6 empty] | DAQ Management
FALSE |  | OP522475 | Five Remaining Filters Complete and Ready to Ship (MS5) - Filter Fabrication | LSST Forecast - B57 - B1 | 444 | 92 | 2017-01-02 | 2019-10-10 | 163 | 2017-01-02 |  | 0 | 2019-06-03 | 2019-10-10 | 2020-01-28 | 2020-06-05 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-03-01 | 2018-11-30 |  |  |  |  | 0.73 | 0 | FALSE | FALSE | None |  | None |  | 2019-10-10 |  |  |  |  | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 444 | 607 |  | InProgress | 73% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  |  | Procurement
FALSE |  | ITC98005 | I&T Test Engineer - I&T | LSST Forecast - B57 - B1 | 641 | 132 | 2017-05-01 | 2019-12-09 | 556 | 2017-05-01 |  | 0 | 2019-06-03 | 2019-12-09 | 2021-09-07 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-06-01 | 2020-01-23 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None |  | 2019-12-09 |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 641 | 509 |  | InProgress | 79.41% | 1700 | 0 | 1700 | 1700 | LSST Forecast - B57 - B1.3.08.01 | I&T Integration & Management | 1349.922 | 1291.5757 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Drtn | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Construction Management |  | Engineering |  |  |  | Integration & Testing (TEC) | [6 empty] | Integration & Testing
FALSE |  | ITC92430 | Travel - Interface Meetings and Reviews | LSST Forecast - B57 - B1 | 413 | 0 | 2017-05-08 | 2019-01-22 | 0 | 2017-05-08 | 2019-01-22 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 30000 | 30000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-08-30 | 2019-05-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 413 | 412 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.06.01 | Commissioning Camera Hardware | 0 | 0 | 0 | 30000 | 30000 | 0 | PercentComplete | 4% | CP_Drtn | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Kevin Reil | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Construction Management | [5 empty] | Commissioning Camera (TEC)
FALSE |  | ITC98030 | I&T Sust Engineering - SR (Start of RTM Integration) | LSST Forecast - B57 - B1 | 406 | 15 | 2017-12-01 | 2019-06-21 | 673 | 2017-12-01 |  | 0 | 2019-06-03 | 2019-06-21 | 2022-03-09 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-01 | 2019-10-17 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None |  | 2019-06-21 |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 406 | 360 |  | InProgress | 96.31% | 660 | 0 | 660 | 660 | LSST Forecast - B57 - B1.3.08.01 | I&T Integration & Management | 635.6158 | 502.3153 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Drtn | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Construction Management |  | Engineering |  |  |  | Integration & Testing (TEC) | [6 empty] | Integration & Testing
FALSE |  | ITC98010 | I&T Sust Engineering - Cryostat (Start of Prepare cryostat for integ) | LSST Forecast - B57 - B1 | 426 | 77 | 2018-01-02 | 2019-09-19 | 611 | 2018-01-02 |  | 0 | 2019-06-03 | 2019-09-19 | 2021-11-23 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-08-23 | 2020-05-26 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None |  | 2019-09-19 |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 426 | 349 |  | InProgress | 81.92% | 1350 | 0 | 1350 | 1350 | LSST Forecast - B57 - B1.3.08.01 | I&T Integration & Management | 1105.9859 | 589.4366 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Drtn | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Construction Management |  | Engineering |  |  |  | Integration & Testing (TEC) | [6 empty] | Integration & Testing
FALSE |  | ITC98070 | I&T Sust Engineering - CCS | LSST Forecast - B57 - B1 | 476 | 328 | 2018-02-05 | 2020-09-29 | 360 | 2018-02-05 |  | 0 | 2019-06-03 | 2020-09-29 | 2020-11-13 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-12-17 | 2020-11-25 |  |  |  |  | 0.2419 | 0 | FALSE | FALSE | None |  | None |  | 2020-09-29 |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 476 | 326 |  | InProgress | 31.09% | 4200 | 0 | 4200 | 4200 | LSST Forecast - B57 - B1.3.08.01 | I&T Integration & Management | 1305.8824 | 944.1176 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Drtn | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Construction Management |  | Engineering |  |  |  | Integration & Testing (TEC) | [6 empty] | Integration & Testing
Number of Lags
Total number of activities that have lags in their predecessors. This number should not exceed 5%.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | Previous Start | Previous Finish | Percent Complete | Previous Remaining Duration | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | IsLevelOfEffort | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | Global_Basis of Estimate | Global_Cobra Cost Class | Cobra PMT (EV Method)_Global | Global_Color of Money | Global_Control Account Manager | Global_Design Maturity | Global_Judgement Factor | Global_Milestone Levels | Global_Project Phase | Global_Funding Source | Global_EDIA Survey | Global_MS Type | Phase | NSF Milestones | Loading Curve | Sensor Vendor | LSST_CA | Summary Schedule | ICD for NSF Input | LSST Camera Critical Paths | CD2 Budget Changes | DOE Reviews | Critical Path (CD Reviews) | LSST WP Summary | Critical Path (Camera Delivery) | AWARD / NEED Sub-System | Final Design Key Links | CP - CAMM2100 | CP - CAMM2130 | CP - CAMM2160 | BNL Work Org | Last ETC Update | BNL WBS | LSST Story List | Sum Sch 01 (Camera) | Sum Sch 02 (IT w/Needs) | Sum Sch 03 (Sensors_RTM_IT) | LSST Raft Particulate Mitigation | LSST RTM
FALSE |  | SR341060 | Bench Test - ASPIC 3 | LSST Forecast - B57 - B1 | 186 | 0 | 2013-11-01 | 2014-07-31 | 0 | 2013-11-01 | 2014-07-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2013-11-01 | 2014-07-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 186 | 185 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.01 | ASPIC | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | OPC Non-ARRA | Bill Wahl | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Engineering Test/Validation | [14 empty] | Science Raft Electronics | [8 empty] | Science Raft System
FALSE |  | SR521055 | TS1- Computer, Network and Storage system final design | LSST Forecast - B57 - B1 | 9 | 0 | 2014-02-18 | 2014-02-28 | 0 | 2014-02-18 | 2014-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2014-02-18 | 2014-02-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 9 | 8 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.01 | Sensor Receiving & Inspection (TS1) - eLog, eTraveler | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | TEC Non-ARRA | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Science Sensors Test Stands | [8 empty] | Science Sensors
FALSE |  | SR523380 | TS3 - Dewer Cryostat (includes int fitting and flange) - final design drawing package | LSST Forecast - B57 - B1 | 102 | 0 | 2014-03-10 | 2014-07-31 | 0 | 2014-03-10 | 2014-07-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-03-10 | 2014-07-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 102 | 101 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.03 | Sensor Electro-Optical (TS3) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [6 empty] | Test Stand Effort | [5 empty] | Science Sensors Test Stands | [8 empty] | Science Sensors
FALSE |  | SR523390 | TS3 - XED (X-Ray exposure device) FE55 actuator - final design drawing package | LSST Forecast - B57 - B1 | 102 | 0 | 2014-03-10 | 2014-07-31 | 0 | 2014-03-10 | 2014-07-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-03-10 | 2014-07-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 102 | 101 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.03 | Sensor Electro-Optical (TS3) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [6 empty] | Test Stand Effort | [5 empty] | Science Sensors Test Stands | [8 empty] | Science Sensors
FALSE |  | SR523410 | TS3 - MOTS (miniture optical test stand) system - final design drawing package | LSST Forecast - B57 - B1 | 102 | 0 | 2014-03-10 | 2014-07-31 | 0 | 2014-03-10 | 2014-07-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-03-10 | 2014-07-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 102 | 101 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.03 | Sensor Electro-Optical (TS3) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [6 empty] | Test Stand Effort | [5 empty] | Science Sensors Test Stands | [8 empty] | Science Sensors
FALSE |  | SR522440 | TS2 - MF03 (raft hold down fixture) - final design drawing package | LSST Forecast - B57 - B1 | 46 | 0 | 2014-05-28 | 2014-07-31 | 0 | 2014-05-28 | 2014-07-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-05-28 | 2014-07-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 46 | 45 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.02 | Sensor Dimensional Metrology (TS2) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Science Sensors Test Stands | [8 empty] | Science Sensors
FALSE |  | SR529880 | TS8 - Source optical train layout | LSST Forecast - B57 - B1 | 22 | 0 | 2014-07-01 | 2014-07-31 | 0 | 2014-07-01 | 2014-07-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-07-01 | 2014-07-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 22 | 21 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.05 | RTM Electro-Optical Testing (TS8) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment |  | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering | [14 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 8 - Design |  | Science Raft System
FALSE |  | SR529555 | TS9 - Generate Test Plan - PT2 | LSST Forecast - B57 - B1 | 9 | 0 | 2014-08-01 | 2014-08-13 | 0 | 2014-08-01 | 2014-08-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-08-01 | 2014-08-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 9 | 8 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.07 | Mechanical Test Stand (TS9) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [8 empty] | Science Raft System
FALSE |  | SR330110 | Sensors First Articles - V1 - Back-thin | LSST Forecast - B57 - B1 | 119 | 0 | 2014-08-01 | 2015-01-23 | 0 | 2014-08-01 | 2015-01-23 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2014-08-01 | 2015-01-23 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 119 | 118 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien |  |  |  | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 14% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor | [10 empty] | Sensor
FALSE |  | SR344045 | Procurement of Equipment and Service (Infrastructure items including TS1-TS8 and service contracts) | LSST Forecast - B57 - B1 | 171 | 0 | 2014-08-22 | 2016-04-29 | 0 | 2014-08-22 | 2016-04-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 5 | FALSE | Normal | FALSE | 2014-08-22 | 2015-04-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 5 | 0 | 1 | 4 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 20 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 171 | 422 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.07.01 | Cleanroom Development & Commissioning | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Procurement | [7 empty] | Assembly and Test Facility (TEC) | Test Stand Effort | [5 empty] | Science Raft - Assembly and Test Facility | [6 empty] | Clean Room - Set Up & Assembly |  | Science Raft System
FALSE |  | CRYO60605 | Fab and Assembly - Subscale Test Stand (Elevation Articulation) | LSST Forecast - B57 - B1 | 130 | 0 | 2014-08-23 | 2015-08-15 | 0 | 2014-08-23 | 2015-08-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2014-08-25 | 2015-03-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 15 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 130 | 238 |  | Complete | 100% | 708 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 708 | 708 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 16% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | SR525120 | TS5 - generate final test stand requirements document | LSST Forecast - B57 - B1 | 165 | 0 | 2014-08-29 | 2015-05-28 | 0 | 2014-08-29 | 2015-05-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 5 | FALSE | Normal | FALSE | 2014-08-29 | 2015-04-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 10 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 165 | 185 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.02 | RSA & RTM Warm-Cold Metrology (TS5) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering | [7 empty] | Science Raft - Test Stands (TEC) | Test Stand Effort | [5 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 5 - Design |  | Science Raft System
FALSE |  | CRYO60616 | Test - Subscale Test Stand (Elevation Articulation) | LSST Forecast - B57 - B1 | 129 | 0 | 2014-09-01 | 2015-11-25 | 0 | 2014-09-01 | 2015-11-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2014-09-02 | 2015-03-19 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 40 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 129 | 304 |  | Complete | 100% | 148 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 148 | 148 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 16% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | CRYO60590 | Procurement - Subscale Test Stand (Elevation Articulation) | LSST Forecast - B57 - B1 | 125 | 0 | 2014-09-01 | 2015-08-15 | 0 | 2014-09-01 | 2015-08-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 8000 | 8000 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2014-09-02 | 2015-03-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 15 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 125 | 233 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 8000 | 8000 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 16% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | SR344065 | Installation and Setup of Infrastructure Equipment and TS1-TS3 large equipment | LSST Forecast - B57 - B1 | 139 | 0 | 2014-09-22 | 2015-04-13 | 0 | 2014-09-22 | 2015-04-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2014-09-22 | 2015-04-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 139 | 139 |  | Complete | 100% | 100 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.07.01 | Cleanroom Development & Commissioning | 100 | 100 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Assembly and Test Facility (TEC) | Test Stand Effort | [5 empty] | Science Raft - Assembly and Test Facility | [8 empty] | Science Raft System
FALSE |  | SR345150 | Fab/Assy Raft Electronics Board (DREB2) | LSST Forecast - B57 - B1 | 25 | 0 | 2014-09-29 | 2014-10-31 | 0 | 2014-09-29 | 2014-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-09-29 | 2014-10-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 24 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.04 | Digital Readout Electronics Board (DREB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [8 empty] | Science Raft System
FALSE |  | SR524125 | TS4 - generate prototype measurement test scripts - PT2 | LSST Forecast - B57 - B1 | 58 | 0 | 2014-10-06 | 2014-12-30 | 0 | 2014-10-06 | 2014-12-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-10-06 | 2014-12-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 58 | 57 |  | Complete | 100% | 28 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.01 | RSA Assembly (TS4) | 28 | 28 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | OPC BCR Impact Assessment (LSST ONLY) | Percent Complete on Work Package | OPC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering | [7 empty] | Science Raft - Test Stands (OPC) | Test Stand Effort | [5 empty] | Science Raft - Test Stands | [8 empty] | Science Raft System
FALSE |  | SR552480 | Final Design Drawings - RTM Mechanical | LSST Forecast - B57 - B1 | 196 | 0 | 2014-10-06 | 2016-12-29 | 0 | 2014-10-06 | 2016-12-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2014-10-06 | 2015-07-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 4 | 0 | 1 | 3 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 196 | 559 |  | Complete | 100% | 480 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.01 | Science Raft Tower Module (SRTM) | 480 | 480 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Science Raft Tower Module (SRTM) (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Tower Module |  | Science Raft System
FALSE |  | SR343182 | Firmware for REB3 | LSST Forecast - B57 - B1 | 106 | 0 | 2014-10-13 | 2015-06-26 | 0 | 2014-10-13 | 2015-06-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-10-13 | 2015-03-18 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 106 | 176 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation | [7 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [6 empty] | Raft Electronics Board 3 |  | Science Raft System
FALSE |  | SR343183 | Software for REB3 | LSST Forecast - B57 - B1 | 156 | 0 | 2014-10-13 | 2015-09-22 | 0 | 2014-10-13 | 2015-09-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-10-13 | 2015-05-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 156 | 236 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation | [7 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [6 empty] | Raft Electronics Board 3 |  | Science Raft System
FALSE |  | SR330422 | RCV: First Articles Sensor - V2 - Manufacturing Readiness Review (MRR) | LSST Forecast - B57 - B1 | 1 | 0 | 2014-10-21 | 2014-10-21 | 0 | 2014-10-21 | 2014-10-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 438093 | 438093 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-10-21 | 2014-10-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 438093 | 438093 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 14% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC) | [5 empty] | Sensor | Science Sensors Procurement
FALSE |  | CR241660 | PROC: WGEB mech. model (PCB & components) | LSST Forecast - B57 - B1 | 9 | 0 | 2014-11-01 | 2014-11-13 | 0 | 2014-11-01 | 2014-11-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 1000 | 1000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-11-03 | 2014-11-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 9 | 8 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.02 | Guider Electronics Board (GEB) | 0 | 0 | 0 | 1000 | 1000 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Engineering Test/Validation | [7 empty] | Corner Raft Electronics (TEC) | GEB Prototype
FALSE |  | CR220320 | Design Prototype - corner raft test setup prototype (sidewall, cooling bars, support rods) | LSST Forecast - B57 - B1 | 42 | 0 | 2014-11-06 | 2015-01-10 | 0 | 2014-11-06 | 2015-01-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2014-11-06 | 2015-01-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 42 | 42 |  | Complete | 100% | 160 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 160 | 160 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Tower Module (CRTM) (TEC) | CRTM Prelim Design | [5 empty] | Corner Raft Tower Module (CRTM)
FALSE |  | OP520480 | Procurement Prep - Components for filter frame testing | LSST Forecast - B57 - B1 | 78 | 0 | 2014-12-03 | 2015-02-27 | 0 | 2014-12-03 | 2015-02-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2014-12-03 | 2015-03-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 78 | 57 |  | Complete | 100% | 20 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 20 | 20 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 18% |  | Design/Engineering |  | Commissioning and Testing | [5 empty] | Filters (TEC) | Prototype Filter Assemblies | [5 empty] | Filter Opto-Mechanics
FALSE |  | CRYO60790 | Procurement - Heat Ex Test Stand #2 | LSST Forecast - B57 - B1 | 68 | 0 | 2014-12-10 | 2015-10-01 | 0 | 2014-12-10 | 2015-10-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 52450 | 52450 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-12-10 | 2015-03-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 68 | 196 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 52450 | 52450 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 16% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | CR220420 | Update Camera System Specifications CD-3 - Corner raft tower | LSST Forecast - B57 - B1 | 69 | 0 | 2014-12-15 | 2015-04-15 | 0 | 2014-12-15 | 2015-04-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2014-12-15 | 2015-03-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 20 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 69 | 82 |  | Complete | 100% | 20 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 20 | 20 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Tower Module (CRTM) (TEC) | CRTM Final Design | [5 empty] | Corner Raft Tower Module (CRTM)
FALSE |  | CRYO60640 | Procurement - Subscale Test Stand (Second CRYO) | LSST Forecast - B57 - B1 | 80 | 0 | 2015-01-15 | 2015-09-22 | 0 | 2015-01-15 | 2015-09-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 81750 | 81750 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-01-15 | 2015-05-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 80 | 173 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 81750 | 81750 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 16% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | SR344060 | Assembly & Test Facility Personel Development | LSST Forecast - B57 - B1 | 106 | 0 | 2015-01-19 | 2015-07-15 | 0 | 2015-01-19 | 2015-07-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-01-20 | 2015-06-18 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 106 | 123 |  | Complete | 100% | 221 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.07.01 | Cleanroom Development & Commissioning | 221 | 221 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Assembly and Test Facility (TEC) | Test Stand Effort | [5 empty] | Science Raft - Assembly and Test Facility | [6 empty] | Clean Room - Set Up & Assembly |  | Science Raft System
FALSE |  | OP520360 | PROC: Procure parts for filter frame test units | LSST Forecast - B57 - B1 | 26 | 0 | 2015-02-06 | 2015-03-24 | 0 | 2015-02-06 | 2015-03-24 | 0 | 2019-06-01 | 2019-06-01 | 2018-10-30 | 2018-10-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-03-02 | 2015-04-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 26 | 31 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 22% |  | Design/Engineering |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Filters (TEC) | Prototype Filter Assemblies | [5 empty] | Filter Opto-Mechanics
FALSE |  | CR230260 | Final Design & Analysis - Corner raft sensor assembly (Mechanical Aspect) | LSST Forecast - B57 - B1 | 52 | 0 | 2015-02-13 | 2016-02-19 | 0 | 2015-02-13 | 2016-02-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2015-03-30 | 2015-06-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 52 | 247 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | SR414200 | NEED: CCS-DAQ (DAQ V0.0 GEN 1 Multi REB) | LSST Forecast - B57 - B1 | 0 | 0 | 2015-02-16 | 2015-02-16 | 0 | 2015-02-16 | 2015-02-16 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2015-05-01 | 2015-05-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.04 | Raft Optimization And Readout (ROAR) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% | Level 5 Milestone | Engineering Test/Validation | [23 empty] | Science Raft System
FALSE |  | CR230300 | Final Design & Analysis - Wavefront Sensor jig removal fixture | LSST Forecast - B57 - B1 | 60 | 0 | 2015-02-23 | 2015-08-14 | 0 | 2015-02-23 | 2015-08-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-03-30 | 2015-06-22 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 30 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 122 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CR230310 | Final Design & Analysis - Wavefront Sensor protective cover | LSST Forecast - B57 - B1 | 60 | 0 | 2015-02-23 | 2015-08-14 | 0 | 2015-02-23 | 2015-08-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-03-30 | 2015-06-22 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 30 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 122 |  | Complete | 100% | 15 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 15 | 15 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CCS111100 | Procurement Process - Parts - eTraveler test stand Hardware | LSST Forecast - B57 - B1 | 20 | 0 | 2015-03-01 | 2015-04-12 | 0 | 2015-03-01 | 2015-04-12 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-04-01 | 2015-04-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 10 | 10 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 30 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.10 | E Manufacturing | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  |  | Procurement
FALSE |  | CRYO60810 | Test - Heat Ex Test Stand #2 | LSST Forecast - B57 - B1 | 65 | 0 | 2015-03-12 | 2015-10-27 | 0 | 2015-03-12 | 2015-10-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-05-12 | 2015-08-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 65 | 160 |  | Complete | 100% | 213 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 213 | 213 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 16% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | SR330424 | RCV: First Articles Sensor - V2 - Test Readiness Review (TRR) | LSST Forecast - B57 - B1 | 1 | 0 | 2015-03-12 | 2015-03-12 | 0 | 2015-03-12 | 2015-03-12 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 438093 | 438093 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-03-12 | 2015-03-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 1 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 438093 | 438093 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 14% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC) | Sensor Delivery |  |  |  |  | Sensor | Science Sensors Procurement
FALSE |  | SR342220 | Design Review - CABAC 2 | LSST Forecast - B57 - B1 | 3 | 0 | 2015-03-16 | 2015-03-18 | 0 | 2015-03-16 | 2015-03-18 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-04-01 | 2015-04-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 3 | 2 |  | Complete | 100% | 32 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.02 | CABAC | 32 | 32 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation |  | Design Reviews | [5 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [8 empty] | Science Raft System
FALSE |  | CR220440 | Update Camera System Specifications CD-3 - Corner raft tower tooling (Cage Holding Struct, Board Insert Fix, Trans Cart) | LSST Forecast - B57 - B1 | 10 | 0 | 2015-03-16 | 2015-05-29 | 0 | 2015-03-16 | 2015-05-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-04-01 | 2015-04-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 53 |  | Complete | 100% | 36 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 36 | 36 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Tower Module (CRTM) (TEC) | CRTM Final Design | [5 empty] | Corner Raft Tower Module (CRTM)
FALSE |  | CR220460 | Update Camera System Specifications CD-3 - Shipping Container | LSST Forecast - B57 - B1 | 22 | 0 | 2015-03-16 | 2015-05-29 | 0 | 2015-03-16 | 2015-05-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-03-16 | 2015-04-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 22 | 53 |  | Complete | 100% | 32 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 32 | 32 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Tower Module (CRTM) (TEC) | CRTM Final Design | [5 empty] | Corner Raft Tower Module (CRTM)
FALSE |  | CR230290 | Final Design & Analysis - CRSA protective cover | LSST Forecast - B57 - B1 | 60 | 0 | 2015-03-23 | 2015-08-14 | 0 | 2015-03-23 | 2015-08-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-06-10 | 2015-09-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 90 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 102 |  | Complete | 100% | 15 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 15 | 15 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CR230320 | Final Design & Analysis - Wavefront Sensor insertion tool | LSST Forecast - B57 - B1 | 60 | 0 | 2015-03-23 | 2015-08-14 | 0 | 2015-03-23 | 2015-08-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-05-27 | 2015-08-19 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 45 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 102 |  | Complete | 100% | 20 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 20 | 20 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | OP520540 | Assemble test filter frame | LSST Forecast - B57 - B1 | 15 | 0 | 2015-03-30 | 2015-04-22 | 0 | 2015-03-30 | 2015-04-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-04-01 | 2015-04-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 17 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 18% |  | Design/Engineering |  | Commissioning and Testing | [5 empty] | Filters (TEC) | Prototype Filter Assemblies | [5 empty] | Filter Opto-Mechanics
FALSE |  | SR330140 | RCV: First Articles Sensor - V1 - Test Readiness Review (TRR) | LSST Forecast - B57 - B1 | 1 | 0 | 2015-03-30 | 2015-03-30 | 0 | 2015-03-30 | 2015-03-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 735000 | 735000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-03-30 | 2015-03-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 1 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 735000 | 735000 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 14% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC) | Sensor Delivery |  |  |  |  | Sensor | Science Sensors Procurement
FALSE |  | CCS111200 | Vendor Lead Time - Parts - eTraveler test stand Hardware | LSST Forecast - B57 - B1 | 21 | 0 | 2015-04-01 | 2015-04-29 | 0 | 2015-04-01 | 2015-04-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-05-01 | 2015-06-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 10 | 10 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 21 | 20 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.10 | E Manufacturing | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  |  | Procurement
FALSE |  | SR330200 | Prepare Award Documents - Production Lot 1 Sensors V1 (Option 1) | LSST Forecast - B57 - B1 | 10 | 0 | 2015-04-01 | 2015-04-16 | 0 | 2015-04-01 | 2015-04-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-04-01 | 2015-04-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 11 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien |  |  |  | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 14% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [8 empty] | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Sensor
FALSE |  | CR234230 | AWARD: Contract - First article 2Kx4K Wavefront Sensor w package (2+3 2kx4k sensors) | LSST Forecast - B57 - B1 | 1 | 0 | 2015-04-03 | 2015-04-03 | 0 | 2015-04-03 | 2015-04-03 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 1539764 | 1539764 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-05-01 | 2015-05-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.02 | Wavefront Sensor | 0 | 0 | 0 | 1539764 | 1539764 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | B1 Procurement Commitment (C5.1) |  | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 1% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | [6 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CR230330 | Final Design & Analysis - CRSA Warm-Cold Metrology - test stand | LSST Forecast - B57 - B1 | 60 | 0 | 2015-04-06 | 2015-08-14 | 0 | 2015-04-06 | 2015-08-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-04-06 | 2015-06-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 30 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 92 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | SE222210 | Final grid/cryostat - Check & Update IDD | LSST Forecast - B57 - B1 | 11 | 0 | 2015-04-08 | 2015-05-29 | 0 | 2015-04-08 | 2015-05-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 7 | FALSE | Normal | FALSE | 2015-05-01 | 2015-05-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 0 | 4 | 0 | 0 | 7 | 0 | 6 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 11 | 36 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.02 | Mechanical Integration | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | CCS111300 | RCV: Components - Parts - eTraveler test stand Hardware | LSST Forecast - B57 - B1 | 20 | 0 | 2015-04-15 | 2015-04-30 | 0 | 2015-04-15 | 2015-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 20000 | 20000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-05-15 | 2015-06-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 11 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.10 | E Manufacturing | 0 | 0 | 0 | 20000 | 20000 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Procurement | [7 empty] | CCS Core (TEC) | [6 empty] | Shutter Engin/Dsn
FALSE |  | SR530220 | COMP: TS7 part, assy dwg's complete | LSST Forecast - B57 - B1 | 0 | 0 | 2015-04-29 | 2015-04-29 | 0 | 2015-04-29 | 2015-04-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2015-05-12 | 2015-05-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.04 | RTM Cryostat Integration (TS7) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% | Level 4 Milestone | Design/Engineering | [14 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 7 - Design |  | Science Raft System
FALSE |  | CR230450 | RELEASE: RFP - First Article Corner Rafts Baseplate (1 unit) | LSST Forecast - B57 - B1 | 1 | 0 | 2015-05-04 | 2015-05-04 | 0 | 2015-05-04 | 2015-05-04 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-06-01 | 2015-06-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  |  | Procurement | [8 empty] | CRSA Prototype (Baseplate)
FALSE |  | CR211620 | Generate Wavefront sensors final performance allocation budgets - Corner Raft | LSST Forecast - B57 - B1 | 60 | 0 | 2015-05-14 | 2016-02-05 | 0 | 2015-05-14 | 2016-02-05 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-06-01 | 2015-08-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 175 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.01 | Corner Raft System Integration and Management | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft System Integration and Management (TEC) | Management | [5 empty] | Corner Raft System Integration and Management
FALSE |  | CR211640 | Generate guide sensors final performance allocation budgets - Corner Raft | LSST Forecast - B57 - B1 | 49 | 0 | 2015-05-14 | 2016-02-05 | 0 | 2015-05-14 | 2016-02-05 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-06-01 | 2015-08-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 49 | 175 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.01 | Corner Raft System Integration and Management | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft System Integration and Management (TEC) | Management | [5 empty] | Corner Raft System Integration and Management
FALSE |  | CR211660 | Generate Wavefront sensors chain final integrated test plan - Corner Raft | LSST Forecast - B57 - B1 | 60 | 0 | 2015-05-14 | 2016-02-05 | 0 | 2015-05-14 | 2016-02-05 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-06-01 | 2015-08-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 175 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.01 | Corner Raft System Integration and Management | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft System Integration and Management (TEC) | Management | [5 empty] | Corner Raft System Integration and Management
FALSE |  | SR330210 | AWARD: Production Lot 1 Sensors Procurement - Vendor 1 | LSST Forecast - B57 - B1 | 0 | 0 | 2015-05-21 | 2015-05-21 | 0 | 2015-05-21 | 2015-05-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 5400000 | 5400000 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2015-06-01 | 2015-06-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 5400000 | 5400000 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien | B1 Procurement Commitment (C5.1) |  | TEC Non-ARRA | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 14% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Sensor | Science Sensors Procurement |  |  |  |  | CP - CAMM2130 (Award of Sensor Lot #2) |  | Sensors Vendor 1
FALSE |  | CR241780 | Functional Testing - WGEB Protoype (Guider mode) | LSST Forecast - B57 - B1 | 20 | 0 | 2015-06-01 | 2015-06-19 | 0 | 2015-06-01 | 2015-06-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2015-08-13 | 2015-09-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 20 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 14 |  | Complete | 100% | 100 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.02 | Guider Electronics Board (GEB) | 100 | 100 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Engineering Test/Validation | [7 empty] | Corner Raft Electronics (TEC) | GEB Prototype
FALSE |  | CR230580 | Generate Final Drawings - CRSA Warm-Cold Metrology - test stand | LSST Forecast - B57 - B1 | 60 | 0 | 2015-06-01 | 2015-09-30 | 0 | 2015-06-01 | 2015-09-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-10-01 | 2016-01-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 85 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | SE222280 | Final Design - Analyze Interfaces & Impacts - SE | LSST Forecast - B57 - B1 | 5 | 0 | 2015-06-01 | 2015-06-10 | 0 | 2015-06-01 | 2015-06-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-13 | 2019-09-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-07-01 | 2015-07-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 7 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.02 | Mechanical Integration | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | CR240520 | Performance validation with single CCD - WGEB Prototype (WF mode) | LSST Forecast - B57 - B1 | 40 | 0 | 2015-06-08 | 2015-06-30 | 0 | 2015-06-08 | 2015-06-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-07-01 | 2015-08-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 27 | 27 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 16 |  | Complete | 100% | 340 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.01 | Wavefront Electronics Board (WEB) | 340 | 340 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering | [7 empty] | Corner Raft Electronics (TEC) | WEB Prototype
FALSE |  | CR230280 | Final Design & Analysis - Corner raft sensor assembly (Instrumental Aspect) | LSST Forecast - B57 - B1 | 86 | 0 | 2015-06-12 | 2015-09-30 | 0 | 2015-06-12 | 2015-09-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2015-07-01 | 2015-10-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 86 | 76 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CRYO60625 | Test - Subscale Depluggling Test | LSST Forecast - B57 - B1 | 60 | 0 | 2015-06-15 | 2015-08-25 | 0 | 2015-06-15 | 2015-08-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-06-15 | 2015-09-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 50 |  | Complete | 100% | 200 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 200 | 200 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 16% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | CRYO16900 | Check and Release Detail and Assembly Drawings - Cryo & Cold Plate | LSST Forecast - B57 - B1 | 60 | 0 | 2015-06-22 | 2015-10-29 | 0 | 2015-06-22 | 2015-10-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2015-07-17 | 2015-10-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 91 |  | Complete | 100% | 300 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.03 | Cryo and Cold Plates | 300 | 300 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryo and Cold Plates (TEC) | [6 empty] | Cryo and Cold Plates
FALSE |  | OP530600 | L2 Lens Substrate Arrives at AOS - L1-L2 Assembly - Phase 3 | LSST Forecast - B57 - B1 | 25 | 0 | 2015-06-26 | 2015-06-30 | 0 | 2015-06-26 | 2015-06-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-03 | 2019-09-03 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-07-01 | 2015-08-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 2 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Scott Winters | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor | [5 empty] | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly) |  |  |  | L1-L2 Opto-Mechanics
FALSE |  | CCS124820 | Vendor Lead Time - Parts - Shutter HCU | LSST Forecast - B57 - B1 | 30 | 0 | 2015-06-30 | 2015-09-04 | 0 | 2015-06-30 | 2015-09-04 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-06 | 2019-08-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-01-04 | 2016-02-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 10 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 47 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.06 | Shutter HCU | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  |  | Engineering Test/Validation
FALSE |  | CCS124830 | RCV: Components - Parts - Shutter HCU | LSST Forecast - B57 - B1 | 20 | 0 | 2015-08-01 | 2015-09-16 | 0 | 2015-08-01 | 2015-09-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-06 | 2019-08-06 | 4000 | 4000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-09-01 | 2015-09-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 31 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.06 | Shutter HCU | 0 | 0 | 0 | 4000 | 4000 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Engineering Test/Validation | [7 empty] | CCS HCU (TEC) | [6 empty] | Shutter Engin/Dsn
FALSE |  | CCS207500 | Generate XML files for OCS V3 release - CCS/OCS | LSST Forecast - B57 - B1 | 10 | 0 | 2015-08-01 | 2015-10-13 | 0 | 2015-08-01 | 2015-10-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-17 | 2019-10-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-09-01 | 2015-09-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 50 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.04 | CCS/OCS Bridge | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Testing/Integration | [7 empty] | CCS Core (TEC)
FALSE |  | CRYO60750 | Fab and Assembly - Subscale Test Stand (Final Details) | LSST Forecast - B57 - B1 | 50 | 0 | 2015-08-05 | 2016-02-19 | 0 | 2015-08-05 | 2016-02-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-02-02 | 2016-04-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 10 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 50 | 127 |  | Complete | 100% | 430 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 430 | 430 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 16% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | CR220700 | Design prototype - corner raft test setup EM revision (sidewall, cooling bars, support rods) | LSST Forecast - B57 - B1 | 15 | 0 | 2015-08-07 | 2015-10-05 | 0 | 2015-08-07 | 2015-10-05 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2015-08-06 | 2015-08-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 40 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Tower Module (CRTM) (TEC) | CRTM Prototype EM Revision | [5 empty] | Corner Raft Tower Module (CRTM)
FALSE |  | CR230540 | Generate Final Drawings - CRSA protective cover | LSST Forecast - B57 - B1 | 60 | 0 | 2015-08-17 | 2015-08-28 | 0 | 2015-08-17 | 2015-08-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-09-01 | 2015-11-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 9 |  | Complete | 100% | 60 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 60 | 60 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CR230550 | Generate Final Drawings - Wavefront Sensor jig removal fixture | LSST Forecast - B57 - B1 | 60 | 0 | 2015-08-17 | 2015-08-28 | 0 | 2015-08-17 | 2015-08-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-10-01 | 2016-01-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 9 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CR230560 | Generate Final Drawings - Wavefront Sensor protective cover | LSST Forecast - B57 - B1 | 10 | 0 | 2015-08-17 | 2015-08-28 | 0 | 2015-08-17 | 2015-08-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-08-17 | 2015-08-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 10 |  | Complete | 100% | 60 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 60 | 60 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CR230570 | Generate Final Drawings - Wavefront Sensor insertion tool | LSST Forecast - B57 - B1 | 60 | 0 | 2015-08-28 | 2015-09-30 | 0 | 2015-08-28 | 2015-09-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-08-28 | 2015-11-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 22 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CRYO60740 | Procurement - Subscale Test Stand (Final Details) | LSST Forecast - B57 - B1 | 40 | 0 | 2015-10-01 | 2015-11-08 | 0 | 2015-10-01 | 2015-11-08 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 21000 | 21000 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-11-02 | 2016-01-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 10 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 27 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 21000 | 21000 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 16% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | CRYO60745 | Procurement - Refrigerant (4 Recharges) | LSST Forecast - B57 - B1 | 40 | 0 | 2015-10-01 | 2015-10-26 | 0 | 2015-10-01 | 2015-10-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 14000 | 14000 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-10-01 | 2015-11-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 17 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 14000 | 14000 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 16% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | SR345830 | Firmware development for (RTB) | LSST Forecast - B57 - B1 | 42 | 0 | 2015-10-01 | 2016-03-25 | 0 | 2015-10-01 | 2016-03-25 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-10-01 | 2015-12-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 42 | 119 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.06 | Electronics Production Test | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering | [7 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [6 empty] | RTB - Design |  | Science Raft System
FALSE |  | CR240540 | WGEB prototype to WEB EM workshop | LSST Forecast - B57 - B1 | 6 | 0 | 2015-10-05 | 2016-04-22 | 0 | 2015-10-05 | 2016-04-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-11-10 | 2015-11-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 6 | 130 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.01 | Wavefront Electronics Board (WEB) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering | [7 empty] | Corner Raft Electronics (TEC) | WEB EM
FALSE |  | CRYO60850 | Fab and Assembly - Hose and Fitting Test Stand | LSST Forecast - B57 - B1 | 60 | 0 | 2015-10-12 | 2016-04-20 | 0 | 2015-10-12 | 2016-04-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2015-11-09 | 2016-02-18 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 123 |  | Complete | 100% | 352 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 352 | 352 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 16% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | CR230340 | Final requirements and operations documentation - CRSA Warm-Cold Metrology - test stand | LSST Forecast - B57 - B1 | 4 | 0 | 2015-10-12 | 2016-07-18 | 0 | 2015-10-12 | 2016-07-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-11-02 | 2015-11-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 184 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CR222530 | RCV: Procure Cold Single CCD test stand Commercial Components | LSST Forecast - B57 - B1 | 20 | 0 | 2015-10-15 | 2016-02-26 | 0 | 2015-10-15 | 2016-02-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 55000 | 55000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-10-29 | 2015-11-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 82 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 55000 | 55000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | [11 empty] | Corner Raft Tower Module (CRTM) (TEC)
FALSE |  | CR222520 | Procure Cold Single CCD test stand Commercial Components - Vendor Lead Time | LSST Forecast - B57 - B1 | 40 | 19 | 2015-10-15 | 2016-02-26 | 0 | 2015-10-15 | 2016-02-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-10-15 | 2015-12-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 20 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 82 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot
FALSE |  | CRYO60840 | Procurement - Hose and Fitting Test Stand | LSST Forecast - B57 - B1 | 40 | 0 | 2015-10-19 | 2016-03-30 | 0 | 2015-10-19 | 2016-03-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 27100 | 27100 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-10-19 | 2015-12-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 15 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 103 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 27100 | 27100 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 16% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | OP540610 | RCV: L3 Assembly - Phase 1 (Delta PDR) | LSST Forecast - B57 - B1 | 1 | 0 | 2015-10-22 | 2016-02-14 | 0 | 2015-10-22 | 2016-02-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-14 | 2019-05-14 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-11-18 | 2015-11-18 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 76 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% | Level 4 Milestone | Procurement | [7 empty] | L3 Assembly (TEC) |  |  | Critical Path #2 (L1_L2 Assembly) |  |  |  | L1-L2 Opto-Mechanics
FALSE |  | SR530470 | TS5 - generate preliminary measurement test scripts | LSST Forecast - B57 - B1 | 27 | 0 | 2015-11-02 | 2015-12-18 | 0 | 2015-11-02 | 2015-12-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-11-02 | 2015-12-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 27 | 32 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.02 | RSA & RTM Warm-Cold Metrology (TS5) | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 5 - Design |  | Science Raft System
FALSE |  | CR211680 | Generate guide sensors chain final integrated test plan - Corner Raft | LSST Forecast - B57 - B1 | 40 | 0 | 2015-11-09 | 2016-02-05 | 0 | 2015-11-09 | 2016-02-05 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-11-09 | 2016-01-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 51 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.01 | Corner Raft System Integration and Management | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft System Integration and Management (TEC) | Management | [5 empty] | Corner Raft System Integration and Management
FALSE |  | CR230350 | Measurement and analysis software - CRSA Warm-Cold Metrology - test stand | LSST Forecast - B57 - B1 | 44 | 0 | 2015-11-13 | 2018-01-19 | 0 | 2015-11-13 | 2018-01-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-12-01 | 2016-02-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 44 | 521 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CR235200 | Generate final acceptance, verification and test plan - Guide sensor | LSST Forecast - B57 - B1 | 20 | 0 | 2015-11-17 | 2016-07-18 | 0 | 2015-11-17 | 2016-07-18 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-01-04 | 2016-02-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 158 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.03 | Guide Sensors | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | Guide Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | SR341160 | Test - Prod ASPIC | LSST Forecast - B57 - B1 | 49 | 0 | 2015-11-27 | 2015-12-21 | 0 | 2015-11-27 | 2015-12-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 5 | FALSE | Normal | FALSE | 2015-12-15 | 2016-02-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 1 | 0 | 2 | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 140 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 49 | 15 |  | Complete | 100% | 400 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.01 | ASPIC | 400 | 400 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [6 empty] | ASPICS |  | Science Raft System
FALSE |  | CRYO60760 | Test - Subscale Test Stand (Final Details) | LSST Forecast - B57 - B1 | 26 | 0 | 2015-12-01 | 2016-07-30 | 0 | 2015-12-01 | 2016-07-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-01-04 | 2016-02-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 26 | 160 |  | Complete | 100% | 115 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 115 | 115 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 16% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | CR222550 | Procure EO testing support instrumentation - Vendor Lead Time | LSST Forecast - B57 - B1 | 40 | 0 | 2015-12-09 | 2016-09-30 | 0 | 2015-12-09 | 2016-09-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-01-04 | 2016-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 20 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 197 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Vincent Riot
FALSE |  | SR530050 | TS8 - fabrication/assy - X-Y-Z stage controller | LSST Forecast - B57 - B1 | 30 | 0 | 2015-12-14 | 2015-12-28 | 0 | 2015-12-14 | 2015-12-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-01-04 | 2016-02-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 8 |  | Complete | 100% | 60 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.05 | RTM Electro-Optical Testing (TS8) | 60 | 60 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 8 - Procurement & Fabrication |  | Science Raft System
FALSE |  | SR530090 | TS8 - Assembly technical support | LSST Forecast - B57 - B1 | 30 | 0 | 2015-12-21 | 2016-06-30 | 0 | 2015-12-21 | 2016-06-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-01-04 | 2016-02-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 132 |  | Complete | 100% | 128 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.05 | RTM Electro-Optical Testing (TS8) | 128 | 128 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 8 - Procurement & Fabrication |  | Science Raft System
FALSE |  | SR332505 | FA Testing - Sensors V1 (1 Set, 5 sensors, 1-5) | LSST Forecast - B57 - B1 | 32 | 0 | 2016-01-04 | 2016-11-25 | 0 | 2016-01-04 | 2016-11-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-02-02 | 2016-03-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 4 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 32 | 228 |  | Complete | 100% | 210 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 210 | 210 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Catalog Listing or Industrial Construction Databases | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [6 empty] | Science Sensors Acceptance | [6 empty] | Sensors Vendor 1 |  | Science Sensors
FALSE |  | SR530060 | TS8 - fabrication/assy - source optical train | LSST Forecast - B57 - B1 | 25 | 0 | 2016-01-04 | 2016-06-30 | 0 | 2016-01-04 | 2016-06-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-02-01 | 2016-03-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 10 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 125 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.05 | RTM Electro-Optical Testing (TS8) | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 8 - Procurement & Fabrication |  | Science Raft System
FALSE |  | SR530080 | TS8 - fabrication/assy - point projector/mask | LSST Forecast - B57 - B1 | 35 | 0 | 2016-01-04 | 2016-06-24 | 0 | 2016-01-04 | 2016-06-24 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-02-01 | 2016-03-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 35 | 121 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.05 | RTM Electro-Optical Testing (TS8) | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 8 - Procurement & Fabrication |  | Science Raft System
FALSE |  | CR220580 | Final Design & Analysis - Corner raft tower tooling (Cage Holding Struct, Board Insert Fix, Trans Cart) | LSST Forecast - B57 - B1 | 33 | 0 | 2016-01-11 | 2016-02-10 | 0 | 2016-01-11 | 2016-02-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-02-01 | 2016-03-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 33 | 21 |  | Complete | 100% | 90 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 90 | 90 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Tower Module (CRTM) (TEC) | CRTM Final Design | [5 empty] | Corner Raft Tower Module (CRTM)
FALSE |  | SE223180 | L3 sub-system FDR contamination compliance | LSST Forecast - B57 - B1 | 20 | 0 | 2016-01-18 | 2016-07-07 | 0 | 2016-01-18 | 2016-07-07 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-02-01 | 2016-02-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 119 |  | Complete | 100% | 44 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.03 | Thermal and contamination system analysis | 44 | 44 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | CRYO53090 | Vendor Lead Time - All Parts - System Flushing for SLAC System | LSST Forecast - B57 - B1 | 30 | 0 | 2016-01-20 | 2016-08-30 | 0 | 2016-01-20 | 2016-08-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-05-24 | 2016-07-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 40 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 156 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc)
FALSE |  | CRYO53100 | RCV: All Parts - System Flushing for SLAC System | LSST Forecast - B57 - B1 | 30 | 0 | 2016-01-25 | 2016-06-24 | 0 | 2016-01-25 | 2016-06-24 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 35000 | 35000 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-07-21 | 2016-08-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 107 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 35000 | 35000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% | Level 4 Milestone | Procurement | [7 empty] | Refrigeration System (TEC)
FALSE |  | DAQ360500 | COMP: Prototype - IMS/IMC | LSST Forecast - B57 - B1 | 0 | 0 | 2016-02-08 | 2016-02-08 | 0 | 2016-02-08 | 2016-02-08 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2016-04-05 | 2016-04-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.09.01 | Image Management/Server/Client Software | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer |  |  | Level 4 Milestone | Engineering Test/Validation
FALSE |  | CR222560 | RCV: Procure EO testing support instrumentation | LSST Forecast - B57 - B1 | 20 | 0 | 2016-02-08 | 2016-10-31 | 0 | 2016-02-08 | 2016-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 49000 | 49000 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2016-02-01 | 2016-02-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 186 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 49000 | 49000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | [11 empty] | Corner Raft Tower Module (CRTM) (TEC)
FALSE |  | CRYO11703 | Fabrication & Assembly - Station 1 Assy - Cryostat Assembly | LSST Forecast - B57 - B1 | 54 | 0 | 2016-03-01 | 2017-01-17 | 0 | 2016-03-01 | 2017-01-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-04-01 | 2016-06-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 54 | 230 |  | Complete | 100% | 48 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 48 | 48 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package |  | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 10% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Cryostat Housing & Assembly (TEC)
FALSE |  | CRYO11749 | Final Design & Engineering - Purge Box - Cryostat Assembly | LSST Forecast - B57 - B1 | 40 | 0 | 2016-03-05 | 2016-12-16 | 0 | 2016-03-05 | 2016-12-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-08-05 | 2016-09-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 199 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Housing & Assembly (TEC)
FALSE |  | CRYO11709 | Fabrication & Assembly - Station 2 Assy - Cryostat Assembly | LSST Forecast - B57 - B1 | 54 | 0 | 2016-03-06 | 2017-01-17 | 0 | 2016-03-06 | 2017-01-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-05-06 | 2016-07-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 40 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 54 | 226 |  | Complete | 100% | 48 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 48 | 48 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package |  | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 10% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Cryostat Housing & Assembly (TEC)
FALSE |  | CR222650 | Procure Cold Raft Electronics test stand Commercial Components - Vendor Lead Time | LSST Forecast - B57 - B1 | 40 | 0 | 2016-03-21 | 2016-09-30 | 0 | 2016-03-21 | 2016-09-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-04-25 | 2016-06-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 20 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 136 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Vincent Riot
FALSE |  | CR222660 | RCV: Procure Cold Raft Electronics test stand Commercial Components | LSST Forecast - B57 - B1 | 20 | 0 | 2016-03-21 | 2016-10-31 | 0 | 2016-03-21 | 2016-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 21000 | 21000 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-05-23 | 2016-06-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 157 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 21000 | 21000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | [11 empty] | Corner Raft Tower Module (CRTM) (TEC)
FALSE |  | OP520960 | PROC: Procure parts for filter mass simulator | LSST Forecast - B57 - B1 | 80 | 0 | 2016-03-25 | 2016-10-11 | 0 | 2016-03-25 | 2016-10-11 | 0 | 2019-06-01 | 2019-06-01 | 2018-10-30 | 2018-10-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-04-01 | 2016-07-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 80 | 139 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 26% |  | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Filters (TEC) | Prototype Filter Assemblies |  |  | Maybe |  |  | Filter Opto-Mechanics
FALSE |  | CRYO11721 | Fabrication & Assembly - Faro Arm Stand - Cryostat Assembly | LSST Forecast - B57 - B1 | 40 | 0 | 2016-04-02 | 2016-12-16 | 0 | 2016-04-02 | 2016-12-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-05-02 | 2016-06-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 10 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 184 |  | Complete | 100% | 32 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 32 | 32 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package |  | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 10% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Cryostat Housing & Assembly (TEC)
FALSE |  | CRYO11740 | Vendor Lead Time - All Parts - Test Fixtures - Cryostat Assembly | LSST Forecast - B57 - B1 | 30 | 0 | 2016-04-02 | 2017-03-28 | 0 | 2016-04-02 | 2017-03-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-05-02 | 2016-06-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 10 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 256 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 10% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor
FALSE |  | SR330270 | Production Lot 1 Sensors - V1 - Assembly & Test | LSST Forecast - B57 - B1 | 50 | 0 | 2016-04-04 | 2017-08-18 | 0 | 2016-04-04 | 2017-08-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 10 | FALSE | Normal | FALSE | 2017-03-01 | 2017-05-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 10 | 0 | 1 | 9 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 50 | 347 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien |  |  |  | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 14% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor | [10 empty] | Sensor | [7 empty] | Sensors Vendor 1 |  | Science Sensors
FALSE |  | CRYO11741 | RCV: All Parts - Test Fixtures - Cryostat Assembly | LSST Forecast - B57 - B1 | 20 | 0 | 2016-04-16 | 2017-02-28 | 0 | 2016-04-16 | 2017-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 10000 | 10000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-05-16 | 2016-06-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 226 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 10000 | 10000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 5% | Level 4 Milestone | Procurement | [7 empty] | Cryostat Housing & Assembly (TEC)
FALSE |  | CCS108900 | Vendor Lead Time - Components - Diagnostic Cluster for I&T | LSST Forecast - B57 - B1 | 45 | 0 | 2016-05-02 | 2016-08-27 | 0 | 2016-05-02 | 2016-08-27 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-05-02 | 2016-07-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 30 | 30 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 45 | 83 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.09 | CCS Diagnostic Cluster and Visualization | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  |  | Procurement
FALSE |  | CRYO60700 | Fab and Assembly - Subscale Test Stand (Add Cold System) | LSST Forecast - B57 - B1 | 50 | 0 | 2016-05-09 | 2016-08-09 | 0 | 2016-05-09 | 2016-08-09 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-06-01 | 2016-08-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 15 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 50 | 64 |  | Complete | 100% | 928 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 928 | 928 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 16% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | SR330165 | RCV: First Articles Sensor - V1 (1 Set, Batch 1b, 4 Sensors, 2-5) | LSST Forecast - B57 - B1 | 5 | 0 | 2016-05-10 | 2016-11-10 | 0 | 2016-05-10 | 2016-11-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 490000 | 490000 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-06-01 | 2016-06-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 129 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 490000 | 490000 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 20% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC) | [5 empty] | Sensor | [7 empty] | Sensors Vendor 1 |  | Science Sensors
FALSE |  | CCS207800 | Develop Simple Camera Command Simulator for Use by OCS - CCS/OCS | LSST Forecast - B57 - B1 | 15 | 0 | 2016-05-11 | 2016-05-29 | 0 | 2016-05-11 | 2016-05-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-17 | 2019-10-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-11-28 | 2016-12-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 13 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.04 | CCS/OCS Bridge | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Testing/Integration | [7 empty] | CCS Core (TEC)
FALSE |  | CR242100 | PROC: GEB EM (PCB & components) | LSST Forecast - B57 - B1 | 10 | 0 | 2016-06-01 | 2016-06-24 | 0 | 2016-06-01 | 2016-06-24 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 22000 | 22000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-07-01 | 2016-07-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 17 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.02 | Guider Electronics Board (GEB) | 0 | 0 | 0 | 22000 | 22000 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Procurement | [7 empty] | Corner Raft Electronics (TEC) | GEB EM
FALSE |  | SR332530 | FA Testing - Sensors V2 (Sensor #1) | LSST Forecast - B57 - B1 | 5 | 0 | 2016-06-10 | 2016-07-11 | 0 | 2016-06-10 | 2016-07-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-07-01 | 2016-07-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 20 |  | Complete | 100% | 42 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 42 | 42 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  | Percent Complete on Work Package |  | Bill Wahl | [5 empty] | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [13 empty] | Sensors Vendor 2 |  | Science Sensors
FALSE |  | CRYO60710 | Test - Subscale Test Stand (Add Cold System) | LSST Forecast - B57 - B1 | 50 | 0 | 2016-06-13 | 2016-12-16 | 0 | 2016-06-13 | 2016-12-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-07-01 | 2016-09-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 50 | 130 |  | Complete | 100% | 177 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 177 | 177 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 16% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | SR561000 | Prepare C/C Material (24 Rafts) | LSST Forecast - B57 - B1 | 1 | 0 | 2016-06-15 | 2016-06-16 | 0 | 2016-06-15 | 2016-06-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-07-18 | 2016-07-18 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 1 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.02 | Science Raft Sensor Assembly (SRSA) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Bill Wahl | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement | [21 empty] | Sensor Assembly |  | Science Raft System
FALSE |  | SR343743_1 | Prepare for REB5 MRR | LSST Forecast - B57 - B1 | 14 | 0 | 2016-06-15 | 2016-08-12 | 0 | 2016-06-15 | 2016-08-12 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-06-15 | 2016-07-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 14 | 41 |  | Complete | 100% | 32 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 32 | 32 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | [11 empty] | Science Raft Electronics (TEC) | [13 empty] | First Article REB-5 Build |  | Science Raft System
FALSE |  | CCS120730 | RCV: Components - Parts - Trending & Configuration Database | LSST Forecast - B57 - B1 | 22 | 0 | 2016-07-01 | 2016-08-13 | 0 | 2016-07-01 | 2016-08-13 | 0 | 2019-06-01 | 2019-06-01 | 2020-02-18 | 2020-02-18 | 13000 | 13000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-08-01 | 2016-08-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 22 | 30 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.06 | CCS Database | 0 | 0 | 0 | 13000 | 13000 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Procurement | [7 empty] | CCS Core (TEC) | [6 empty] | Shutter Engin/Dsn
FALSE |  | CCS109300 | Vendor Lead Time - Components - Visulization System for I&T | LSST Forecast - B57 - B1 | 30 | 0 | 2016-07-01 | 2016-07-12 | 0 | 2016-07-01 | 2016-07-12 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-08-01 | 2016-09-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 10 | 10 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 6 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.09 | CCS Diagnostic Cluster and Visualization | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  |  | Procurement
FALSE |  | CCS200160 | Vendor Lead Time - Parts - Single Bay HCU | LSST Forecast - B57 - B1 | 15 | 0 | 2016-07-01 | 2016-10-21 | 0 | 2016-07-01 | 2016-10-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-12-01 | 2017-01-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 10 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 78 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.08.01 | Single Bay HCU | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  |  | Procurement
FALSE |  | SR530110 | TS8 - exercise apparatus, scripting and analysis | LSST Forecast - B57 - B1 | 10 | 0 | 2016-07-01 | 2016-10-31 | 0 | 2016-07-01 | 2016-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-08-01 | 2016-08-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 84 |  | Complete | 100% | 480 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.05 | RTM Electro-Optical Testing (TS8) | 480 | 480 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 8 - Assembly & Commissioning |  | Science Raft System
FALSE |  | SR330705 | Sensors Production Lot 1 - V2- Backside Batch and Test (21-65) | LSST Forecast - B57 - B1 | 65 | 0 | 2016-07-01 | 2016-07-26 | 0 | 2016-07-01 | 2016-07-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 10 | FALSE | Normal | FALSE | 2016-08-01 | 2016-10-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 10 | 0 | 1 | 9 | 0 | 0 | 1 | 0 | 3 | 0 | 0 | 49 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 65 | 16 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien |  |  |  | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 14% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor | [10 empty] | Sensor | [7 empty] | Sensors Vendor 2
FALSE |  | CRYO11710 | Vendor Lead Time - All Parts - Station 2 Assy - Cryostat Assembly | LSST Forecast - B57 - B1 | 30 | 0 | 2016-07-01 | 2016-11-30 | 0 | 2016-07-01 | 2016-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-08-01 | 2016-09-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 108 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 10% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor
FALSE |  | CRYO11717 | RCV: All Parts - Off-Load Frame - Cryostat Assembly | LSST Forecast - B57 - B1 | 20 | 0 | 2016-07-01 | 2017-02-28 | 0 | 2016-07-01 | 2017-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 25000 | 25000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-08-15 | 2016-09-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 172 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 25000 | 25000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 5% | Level 4 Milestone | Procurement | [7 empty] | Cryostat Housing & Assembly (TEC)
FALSE |  | CRYO11716 | Vendor Lead Time - All Parts - Off-Load Frame - Cryostat Assembly | LSST Forecast - B57 - B1 | 30 | 0 | 2016-07-01 | 2017-02-28 | 0 | 2016-07-01 | 2017-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-08-01 | 2016-09-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 10 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 172 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 10% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor
FALSE |  | CCS109400 | RCV: Components - Visualization System for I&T | LSST Forecast - B57 - B1 | 20 | 0 | 2016-07-15 | 2016-07-30 | 0 | 2016-07-15 | 2016-07-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 22000 | 22000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-08-15 | 2016-09-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 11 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.09 | CCS Diagnostic Cluster and Visualization | 0 | 0 | 0 | 22000 | 22000 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 4% |  | Procurement | [7 empty] | CCS Core (TEC) | [6 empty] | Shutter Engin/Dsn
FALSE |  | SR341161 | AVAIL: ASPIC Production (REB Batch 1) | LSST Forecast - B57 - B1 | 0 | 0 | 2016-07-15 | 2016-07-15 | 0 | 2016-07-15 | 2016-07-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2016-08-15 | 2016-08-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.01 | ASPIC | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Bill Wahl |  |  | Level 5 Milestone | [22 empty] | ASPICS |  | Science Raft System
FALSE |  | CR222760 | Procure Cold Raft Electronics enhancement Commercial Components - Vendor Lead Time | LSST Forecast - B57 - B1 | 20 | 0 | 2016-07-18 | 2016-12-20 | 0 | 2016-07-18 | 2016-12-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-08-01 | 2016-08-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 107 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Vincent Riot |  |  |  | Procurement
FALSE |  | CR222770 | RCV: Procure Cold Raft Electronics enhancement Commercial Components | LSST Forecast - B57 - B1 | 20 | 0 | 2016-07-18 | 2016-12-20 | 0 | 2016-07-18 | 2016-12-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 54299 | 54299 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-08-08 | 2016-09-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 107 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 54299 | 54299 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot |  |  |  | Procurement | [7 empty] | Corner Raft Tower Module (CRTM) (TEC)
FALSE |  | CCS109600 | Vendor Lead Time - Wall Mounted Displays - Diagnostic Cluster for I&T | LSST Forecast - B57 - B1 | 30 | 0 | 2016-08-01 | 2016-08-13 | 0 | 2016-08-01 | 2016-08-13 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-09-01 | 2016-10-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 10 | 10 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 10 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.09 | CCS Diagnostic Cluster and Visualization | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  |  | Procurement
FALSE |  | CR222670 | Procure and fabricate Cold Raft Electronics test stand holding cart/table - Support | LSST Forecast - B57 - B1 | 10 | 0 | 2016-08-01 | 2016-08-19 | 0 | 2016-08-01 | 2016-08-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-09-01 | 2016-09-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 5 | 5 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 14 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | [11 empty] | Corner Raft Tower Module (CRTM) (TEC)
FALSE |  | OP521800 | RCV: Readiness for Coating Report (MS2) - Filter Development Report and Witness Sample | LSST Forecast - B57 - B1 | 145 | 0 | 2016-08-02 | 2017-04-28 | 0 | 2016-08-02 | 2017-04-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-12-12 | 2019-12-12 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2016-08-01 | 2017-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 145 | 185 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 7% |  | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Filters (TEC)
FALSE |  | CCS109000 | RCV: Components - Diagnostic Cluster for I&T | LSST Forecast - B57 - B1 | 20 | 0 | 2016-08-11 | 2016-08-30 | 0 | 2016-08-11 | 2016-08-30 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 80000 | 80000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-11-11 | 2016-12-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 13 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.09 | CCS Diagnostic Cluster and Visualization | 0 | 0 | 0 | 80000 | 80000 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 4% |  | Procurement | [7 empty] | CCS Core (TEC) | [6 empty] | Shutter Engin/Dsn
FALSE |  | SR341165 | AVAIL: ASPIC Production (REB Batch 5) | LSST Forecast - B57 - B1 | 0 | 0 | 2016-08-15 | 2016-08-15 | 0 | 2016-08-15 | 2016-08-15 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2016-09-01 | 2016-09-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.01 | ASPIC | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Bill Wahl |  |  | Level 5 Milestone | Testing/Integration | [21 empty] | ASPICS |  | Science Raft System
FALSE |  | SR341163 | AVAIL: ASPIC Production (REB Batch 3) | LSST Forecast - B57 - B1 | 0 | 0 | 2016-08-15 | 2016-08-15 | 0 | 2016-08-15 | 2016-08-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2016-09-01 | 2016-09-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.01 | ASPIC | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Bill Wahl |  |  | Level 5 Milestone | [22 empty] | ASPICS |  | Science Raft System
FALSE |  | SR343744_2 | Issue PO for fabrication of (15) First Article REB5 "Raw" boards | LSST Forecast - B57 - B1 | 1 | 0 | 2016-08-15 | 2016-08-15 | 0 | 2016-08-15 | 2016-08-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-09-06 | 2016-09-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | [11 empty] | Science Raft Electronics (TEC) | [13 empty] | First Article REB-5 Build |  | Science Raft System
FALSE |  | CCS109700 | RCV: Components - Wall Mounted Displays - Diagnostic Cluster for I&T | LSST Forecast - B57 - B1 | 20 | 0 | 2016-08-16 | 2016-08-30 | 0 | 2016-08-16 | 2016-08-30 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 5000 | 5000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-09-16 | 2016-10-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 10 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.09 | CCS Diagnostic Cluster and Visualization | 0 | 0 | 0 | 5000 | 5000 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 4% |  | Procurement | [7 empty] | CCS Core (TEC) | [6 empty] | Shutter Engin/Dsn
FALSE |  | SR332685 | Prod. Testing - Sensors V2 (Sensors #29-32) | LSST Forecast - B57 - B1 | 10 | 0 | 2016-08-18 | 2016-08-31 | 0 | 2016-08-18 | 2016-08-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-09-01 | 2016-09-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 30 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 30 | 30 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Catalog Listing or Industrial Construction Databases | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [6 empty] | Science Sensors Acceptance | [6 empty] | Sensors Vendor 2 |  | Science Sensors
FALSE |  | CR222680 | Procure and fabricate Cold Raft Electronics test stand holding cart/table - Vendor Lead Time | LSST Forecast - B57 - B1 | 15 | 0 | 2016-08-22 | 2016-10-21 | 0 | 2016-08-22 | 2016-10-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-09-09 | 2016-09-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 10 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 43 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Vincent Riot
FALSE |  | CRYO35068 | Glycol System Mechanical Design/Analysis (Routing-Balancing-Coldplates) | LSST Forecast - B57 - B1 | 40 | 0 | 2016-08-25 | 2016-09-30 | 0 | 2016-08-25 | 2016-09-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-10-25 | 2017-01-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 25 |  | Complete | 100% | 32 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.05.02 | Utility Trunk Thermo-Mechanical and Assembly | 32 | 32 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Utility Trunk Thermo-Mechanical and Assembly (TEC) | [6 empty] | Utility Trunk
FALSE |  | CRYO35069 | UT prelim structure & heat exchanger vacuum chamber integration | LSST Forecast - B57 - B1 | 40 | 0 | 2016-08-25 | 2016-09-30 | 0 | 2016-08-25 | 2016-09-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2016-10-25 | 2017-01-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 30 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 25 |  | Complete | 100% | 19.2 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.05.02 | Utility Trunk Thermo-Mechanical and Assembly | 19.2 | 19.2 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Utility Trunk Thermo-Mechanical and Assembly (TEC) |  | ICD's for Phase 2 |  |  |  |  | Utility Trunk
FALSE |  | SR330745 | RCV: Production Lot 1 Sensor - V2 - Sensors #35,36 | LSST Forecast - B57 - B1 | 3 | 0 | 2016-09-01 | 2016-09-06 | 0 | 2016-09-01 | 2016-09-06 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 6640 | 6640 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-10-03 | 2016-10-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 3 | 2 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 6640 | 6640 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 14% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC) | Sensor Delivery |  |  |  |  | Sensor | Science Sensors Procurement | [6 empty] | Sensors Vendor 2
FALSE |  | SR561110 | Batch1B_Perform Final Correction of V-Posts at vendor (6 Rafts) | LSST Forecast - B57 - B1 | 23 | 0 | 2016-09-01 | 2016-09-29 | 0 | 2016-09-01 | 2016-09-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-10-03 | 2016-11-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 23 | 19 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.02 | Science Raft Sensor Assembly (SRSA) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Bill Wahl | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement | [21 empty] | Sensor Assembly |  | Science Raft System
FALSE |  | SR330750 | RCV: Production Lot 1 Sensor - V2 - Sensors #37,38 | LSST Forecast - B57 - B1 | 3 | 0 | 2016-09-07 | 2016-09-09 | 0 | 2016-09-07 | 2016-09-09 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 6640 | 6640 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-10-06 | 2016-10-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 3 | 2 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 6640 | 6640 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 14% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC) | [5 empty] | Sensor | Science Sensors Procurement | [6 empty] | Sensors Vendor 2
FALSE |  | CR241240 | PROC: WEB (PCB & components) | LSST Forecast - B57 - B1 | 27 | 0 | 2016-09-12 | 2017-09-21 | 0 | 2016-09-12 | 2017-09-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 50000 | 50000 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-07-28 | 2017-09-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 27 | 250 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.01 | Wavefront Electronics Board (WEB) | 0 | 0 | 0 | 50000 | 50000 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Procurement | [7 empty] | Corner Raft Electronics (TEC) | WEB
FALSE |  | SR330755 | RCV: Production Lot 1 Sensor - V2 - Sensors #39,40 | LSST Forecast - B57 - B1 | 3 | 0 | 2016-09-12 | 2016-12-20 | 0 | 2016-09-12 | 2016-12-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 6640 | 6640 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-10-11 | 2016-10-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 3 | 69 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 6640 | 6640 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 14% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC) | [5 empty] | Sensor | Science Sensors Procurement | [6 empty] | Sensors Vendor 2 |  | Science Sensors
FALSE |  | CR222690 | RCV: Procure and fabricate Cold Raft Electronics test stand holding cart/table | LSST Forecast - B57 - B1 | 15 | 0 | 2016-09-12 | 2016-11-30 | 0 | 2016-09-12 | 2016-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 20000 | 20000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-10-03 | 2016-10-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 55 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 20000 | 20000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | [11 empty] | Corner Raft Tower Module (CRTM) (TEC)
FALSE |  | SR330880 | Release RFP - Sensor Production Lot 2 + Option 1 for Lot 3 | LSST Forecast - B57 - B1 | 0 | 0 | 2016-09-15 | 2016-09-15 | 0 | 2016-09-15 | 2016-09-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2016-10-03 | 2016-10-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien |  |  |  | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 14% | Level 4 Milestone | Procurement | [13 empty] | Sensor | [5 empty] | CP - CAMM2130 (Award of Sensor Lot #2) |  | Lot 2 Primary Vendor
FALSE |  | CRYO11729 | RCV: All Parts - Assembly Mandrel - Cryostat Assembly | LSST Forecast - B57 - B1 | 36 | 0 | 2016-09-17 | 2016-10-31 | 0 | 2016-09-17 | 2016-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 15000 | 15000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-10-17 | 2016-12-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 36 | 30 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 15000 | 15000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 5% | Level 4 Milestone | Procurement | [7 empty] | Cryostat Housing & Assembly (TEC)
FALSE |  | CRYO11728 | Vendor Lead Time - All Parts - Assembly Mandrel - Cryostat Assembly | LSST Forecast - B57 - B1 | 24 | 0 | 2016-09-17 | 2016-10-31 | 0 | 2016-09-17 | 2016-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-10-03 | 2016-11-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 10 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 24 | 30 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 10% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor
FALSE |  | SR553030 | RTM (1-3) - Materials Lead Time | LSST Forecast - B57 - B1 | 38 | 0 | 2016-09-20 | 2017-01-10 | 0 | 2016-09-20 | 2017-01-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-10-19 | 2016-12-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 38 | 67 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Existing Lien |  |  |  | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 14% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [8 empty] | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Sensor | [5 empty] | CP - CAMM2130 (Award of Sensor Lot #2) |  | RTM Materials |  | Science Raft System
FALSE |  | ITC25680 | Early (Long Lead) Procurement - Vendor Lead Time - BOT | LSST Forecast - B57 - B1 | 20 | 0 | 2016-09-26 | 2017-03-03 | 0 | 2016-09-26 | 2017-03-03 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-10-03 | 2016-10-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 99 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.02.01 | Bench For Optical Testing (BOT) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc)
FALSE |  | CCS200170 | RCV: Components - Parts - Single Bay HCU | LSST Forecast - B57 - B1 | 15 | 0 | 2016-10-15 | 2016-10-30 | 0 | 2016-10-15 | 2016-10-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 4000 | 4000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-11-15 | 2016-12-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 10 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.08.01 | Single Bay HCU | 0 | 0 | 0 | 4000 | 4000 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 4% |  | Procurement | [7 empty] | CCS HCU (TEC) | [6 empty] | Shutter Engin/Dsn
FALSE |  | CR222860 | RCV: Parts for TS-7 Cart Assembly | LSST Forecast - B57 - B1 | 5 | 0 | 2016-10-17 | 2016-10-17 | 0 | 2016-10-17 | 2016-10-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 3000 | 3000 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-11-22 | 2016-11-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 3000 | 3000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Procurement | [7 empty] | Corner Raft Tower Module (CRTM) (TEC)
FALSE |  | CR223120 | RCV: bench top 48V supplies for REB power supply cards (x3) | LSST Forecast - B57 - B1 | 20 | 0 | 2016-10-28 | 2016-10-28 | 0 | 2016-10-28 | 2016-10-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 1500 | 1500 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-11-15 | 2016-12-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 1500 | 1500 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Procurement | [7 empty] | Corner Raft Tower Module (CRTM) (TEC)
FALSE |  | CR223090 | RCV: OTM power supplies (x3) | LSST Forecast - B57 - B1 | 20 | 0 | 2016-10-31 | 2016-10-31 | 0 | 2016-10-31 | 2016-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 1500 | 1500 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-11-01 | 2016-11-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 1500 | 1500 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Procurement | [7 empty] | Corner Raft Tower Module (CRTM) (TEC)
FALSE |  | CRYO35071 | UT Prelim to TMA Interface Design/Eng | LSST Forecast - B57 - B1 | 64 | 0 | 2016-11-01 | 2017-07-18 | 0 | 2016-11-01 | 2017-07-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-12-01 | 2017-03-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 64 | 168 |  | Complete | 100% | 224 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.05.02 | Utility Trunk Thermo-Mechanical and Assembly | 224 | 224 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Utility Trunk Thermo-Mechanical and Assembly (TEC) | [6 empty] | Utility Trunk
FALSE |  | CRYO53160 | Vendor Lead Time - All Parts - Refrigerant Tank Heater and Feed Back Control System | LSST Forecast - B57 - B1 | 60 | 0 | 2016-11-05 | 2016-11-15 | 0 | 2016-11-05 | 2016-11-15 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-12-15 | 2017-03-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 30 | 30 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 6 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc)
FALSE |  | CRYO53290 | Procurement Process - Flow Rate Test | LSST Forecast - B57 - B1 | 40 | 0 | 2016-11-10 | 2016-11-15 | 0 | 2016-11-10 | 2016-11-15 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-01-30 | 2017-03-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 20 | 20 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 3 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  |  | Procurement
FALSE |  | CRYO53170 | RCV: All Parts - Refrigerant Tank Heater and Feed Back Control System | LSST Forecast - B57 - B1 | 30 | 0 | 2016-11-15 | 2016-11-15 | 0 | 2016-11-15 | 2016-11-15 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 25000 | 25000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-02-13 | 2017-03-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 25000 | 25000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% | Level 4 Milestone | Procurement | [7 empty] | Refrigeration System (TEC)
FALSE |  | CRYO53300 | Vendor Lead Time - All Parts - Flow Rate Test | LSST Forecast - B57 - B1 | 30 | 0 | 2016-11-15 | 2016-11-25 | 0 | 2016-11-15 | 2016-11-25 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-02-28 | 2017-04-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 10 | 10 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 7 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc)
FALSE |  | CRYO53310 | RCV: All Parts - Flow Rate Test | LSST Forecast - B57 - B1 | 30 | 0 | 2016-11-25 | 2016-11-25 | 0 | 2016-11-25 | 2016-11-25 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 30000 | 30000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-03-14 | 2017-04-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 30000 | 30000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% | Level 4 Milestone | Procurement | [7 empty] | Refrigeration System (TEC)
FALSE |  | CRYO31050 | RCV: Feedthru Flange Subcomponents - Cryostat Back End | LSST Forecast - B57 - B1 | 20 | 0 | 2016-11-30 | 2016-11-30 | 0 | 2016-11-30 | 2016-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 55050 | 55050 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-02-13 | 2017-03-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.01 | Cryostat Back End | 0 | 0 | 0 | 55050 | 55050 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Procurement | [7 empty] | Cryostat Backend & Vacuum Systems (TEC) | [6 empty] | Cryostat Back End
FALSE |  | SR530130 | TS8 - practice test on engineering grade RTM | LSST Forecast - B57 - B1 | 20 | 0 | 2016-12-01 | 2016-12-30 | 0 | 2016-12-01 | 2016-12-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-01-03 | 2017-01-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 19 |  | Complete | 100% | 240 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.05 | RTM Electro-Optical Testing (TS8) | 240 | 240 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 8 - Assembly & Commissioning |  | Science Raft System
FALSE |  | CRYO11723 | RCV: All Parts - Faro Arm Stand - Cryostat Assembly | LSST Forecast - B57 - B1 | 16 | 0 | 2016-12-01 | 2016-12-16 | 0 | 2016-12-01 | 2016-12-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 5000 | 5000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-01-16 | 2017-02-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 16 | 11 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 5000 | 5000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 5% | Level 4 Milestone | Procurement | [7 empty] | Cryostat Housing & Assembly (TEC)
FALSE |  | CRYO11722 | Vendor Lead Time - All Parts - Faro Arm Stand - Cryostat Assembly | LSST Forecast - B57 - B1 | 24 | 0 | 2016-12-01 | 2016-12-16 | 0 | 2016-12-01 | 2016-12-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-01-02 | 2017-02-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 10 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 24 | 11 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 10% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor
FALSE |  | ITC17715 | COTS Procurement - Vendor Lead Time - SBMS | LSST Forecast - B57 - B1 | 20 | 0 | 2016-12-01 | 2016-12-30 | 0 | 2016-12-01 | 2016-12-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-01-03 | 2017-01-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 10 | 10 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 12 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.01.01 | Single Bay Metrology Tests | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc)
FALSE |  | CR222960 | RCV: Parts for Dark Box | LSST Forecast - B57 - B1 | 12 | 0 | 2016-12-05 | 2017-03-24 | 0 | 2016-12-05 | 2017-03-24 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 10000 | 10000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-01-03 | 2017-01-19 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 12 | 66 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 10000 | 10000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Procurement | [7 empty] | Corner Raft Tower Module (CRTM) (TEC)
FALSE |  | ITC17720 | RCV: COTS Procurement - SBMS | LSST Forecast - B57 - B1 | 10 | 0 | 2016-12-10 | 2017-03-07 | 0 | 2016-12-10 | 2017-03-07 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 73000 | 73000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-01-18 | 2017-01-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 4 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 48 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.01.01 | Single Bay Metrology Tests | 0 | 0 | 0 | 73000 | 73000 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC)
FALSE |  | ITC17730 | Outside Fabrication - Vendor Lead Time - SBMS | LSST Forecast - B57 - B1 | 30 | 0 | 2016-12-10 | 2016-12-16 | 0 | 2016-12-10 | 2016-12-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-01-03 | 2017-02-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 10 | 10 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 4 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.01.01 | Single Bay Metrology Tests | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc)
FALSE |  | ITC17735 | RCV: Outside Fabrication Procurement - SBMS | LSST Forecast - B57 - B1 | 20 | 0 | 2016-12-10 | 2016-12-16 | 0 | 2016-12-10 | 2016-12-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 10000 | 10000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-01-18 | 2017-02-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 4 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 4 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.01.01 | Single Bay Metrology Tests | 0 | 0 | 0 | 10000 | 10000 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC)
FALSE |  | SR551730 | Fabrication - SRTM Shipping Container (Prototype) | LSST Forecast - B57 - B1 | 10 | 0 | 2016-12-15 | 2016-12-30 | 0 | 2016-12-15 | 2016-12-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-01-10 | 2017-01-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.03 | Science Raft Shipping Container | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Raft Tower Module (SRTM) (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Science Raft Shipping Container |  | Science Raft System
FALSE |  | SR550330 | RTM #2 (1st Article) - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2016-12-27 | 2017-03-16 | 0 | 2016-12-27 | 2017-03-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-02-08 | 2017-03-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 54 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #2 |  | Science Raft System
FALSE |  | CRYO11758 | Vendor Lead Time - All Parts - Purge Box - Cryostat Assembly | LSST Forecast - B57 - B1 | 47 | 0 | 2017-01-02 | 2017-02-18 | 0 | 2017-01-02 | 2017-02-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-03-01 | 2017-05-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 47 | 35 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 10% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor
FALSE |  | SR343860 | Package/Ship (between BNL/Vendor/SLAC) | LSST Forecast - B57 - B1 | 103 | 0 | 2017-01-03 | 2017-08-29 | 0 | 2017-01-03 | 2017-08-29 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-02-01 | 2017-06-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 103 | 166 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [6 empty] | Prodcution REB-5 Build |  | Science Raft System
FALSE |  | CRYO23400 | Vendor Lead Time - Other items - Grid Assembly | LSST Forecast - B57 - B1 | 19 | 0 | 2017-01-09 | 2017-03-31 | 0 | 2017-01-09 | 2017-03-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-04-03 | 2017-04-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 19 | 57 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.04 | Grid Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [12 empty] | Grid Assembly
FALSE |  | CRYO11747 | RCV: All Parts - Other Lift Devices/Equipment - Cryostat Assembly | LSST Forecast - B57 - B1 | 12 | 0 | 2017-01-16 | 2017-01-31 | 0 | 2017-01-16 | 2017-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 20000 | 20000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-03-03 | 2017-03-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 12 | 11 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 20000 | 20000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 5% | Level 4 Milestone | Procurement | [7 empty] | Cryostat Housing & Assembly (TEC)
FALSE |  | CRYO11734 | Vendor Lead Time - All Parts - Grid Handling Fixture - Cryostat Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2017-02-01 | 2017-02-17 | 0 | 2017-02-01 | 2017-02-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-03-01 | 2017-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 0 | 12 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 10% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor
FALSE |  | SR343920 | Assemble at Vendor, Clean & Test REB5 Batch 2 at vendor (10 units - RTM 4-6) | LSST Forecast - B57 - B1 | 28 | 0 | 2017-02-01 | 2017-03-07 | 0 | 2017-02-01 | 2017-03-07 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2017-02-01 | 2017-03-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 28 | 23 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation | [7 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [6 empty] | Prodcution REB-5 Build |  | Science Raft System
FALSE |  | SR550274 | RTM1_RTM Construction at TS6 | LSST Forecast - B57 - B1 | 19 | 0 | 2017-02-02 | 2017-03-06 | 0 | 2017-02-02 | 2017-03-06 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-03-07 | 2017-03-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 3 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 19 | 21 |  | Complete | 100% | 64 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 64 | 64 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #1 (First Article) |  | Science Raft System
FALSE |  | SR551760 | Design Update - Incorporate FDR changes | LSST Forecast - B57 - B1 | 10 | 0 | 2017-02-14 | 2017-02-28 | 0 | 2017-02-14 | 2017-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-02-14 | 2017-02-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 10 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.03 | Science Raft Shipping Container | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Science Raft Tower Module (SRTM) (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Science Raft Shipping Container |  | Science Raft System
FALSE |  | SR344120 | Assemble, Clean & Test REB5 Batch 4 at vendor (25 units RTM 10-17) | LSST Forecast - B57 - B1 | 35 | 0 | 2017-02-15 | 2017-04-21 | 0 | 2017-02-15 | 2017-04-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-23 | 2019-07-23 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2017-02-15 | 2017-04-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 10 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 35 | 46 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation | [7 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [6 empty] | Prodcution REB-5 Build |  | Science Raft System
FALSE |  | SR344220 | Assemble at Vendor, Clean & Test REB5 Batch 5 at vendor (25 units RTM 18-24) | LSST Forecast - B57 - B1 | 41 | 0 | 2017-02-22 | 2017-05-30 | 0 | 2017-02-22 | 2017-05-30 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-02-22 | 2017-04-19 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 41 | 68 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation | [7 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [6 empty] | Prodcution REB-5 Build |  | Science Raft System
FALSE |  | SR550450 | RTM #4 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2017-03-21 | 2017-05-16 | 0 | 2017-03-21 | 2017-05-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-06-01 | 2017-07-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 3 | 2 | 0 | 1 | 2 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 40 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #4 |  | Science Raft System
FALSE |  | SR550570 | RTM #6 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2017-03-21 | 2017-08-15 | 0 | 2017-03-21 | 2017-08-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2017-05-22 | 2017-06-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 1 | 0 | 2 | 3 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 103 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #6 |  | Science Raft System
FALSE |  | SR550630 | RTM #7 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2017-03-21 | 2017-08-11 | 0 | 2017-03-21 | 2017-08-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-07-10 | 2017-08-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 0 | 1 | 0 | 3 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 101 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #7 |  | Science Raft System
FALSE |  | SR550690 | RTM #8 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2017-03-21 | 2017-09-11 | 0 | 2017-03-21 | 2017-09-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-06-20 | 2017-07-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 0 | 1 | 0 | 3 | 2 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 121 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #8 |  | Science Raft System
FALSE |  | SR550750 | RTM #9 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2017-03-21 | 2017-10-13 | 0 | 2017-03-21 | 2017-10-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-09-13 | 2017-10-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 1 | 0 | 2 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 145 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #9 |  | Science Raft System
FALSE |  | SR550810 | RTM #10 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 7 | 2017-03-21 | 2017-10-31 | 0 | 2017-03-21 | 2017-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-23 | 2019-07-23 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-10-04 | 2017-11-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 157 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #10 |  | Science Raft System
FALSE |  | SR550870 | RTM #11 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2017-03-21 | 2017-11-30 | 0 | 2017-03-21 | 2017-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-23 | 2019-07-23 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-10-25 | 2017-11-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 1 | 0 | 2 | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 177 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #11 |  | Science Raft System
FALSE |  | SR550930 | RTM #12 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2017-03-21 | 2018-01-23 | 0 | 2017-03-21 | 2018-01-23 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-23 | 2019-07-23 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-12-15 | 2018-01-23 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 1 | 0 | 2 | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 212 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #12 |  | Science Raft System
FALSE |  | SR550990 | RTM #13 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2017-03-21 | 2018-02-13 | 0 | 2017-03-21 | 2018-02-13 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-12-13 | 2018-01-19 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 1 | 0 | 2 | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 227 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #13 |  | Science Raft System
FALSE |  | SR551170 | RTM #16 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2017-03-21 | 2018-05-31 | 0 | 2017-03-21 | 2018-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-04-06 | 2018-05-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 302 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #16 |  | Science Raft System
FALSE |  | SR551410 | RTM #20 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2017-03-21 | 2018-09-10 | 0 | 2017-03-21 | 2018-09-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-06-19 | 2018-07-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 372 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #20 |  | Science Raft System
FALSE |  | SR550080 | SHIPPING: Ship RTM ETU #1 to SLAC | LSST Forecast - B57 - B1 | 6 | 0 | 2017-03-24 | 2017-03-31 | 0 | 2017-03-24 | 2017-03-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-04-26 | 2017-05-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 0 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 6 | 5 |  | Complete | 100% | 8 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 8 | 8 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration |  | Other (specify) | [5 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM ETU #1 |  | Science Raft System
FALSE |  | CRYO61220 | C_FDR - Final Design Review - Refrigeration System - IR2 | LSST Forecast - B57 - B1 | 2 | 0 | 2017-05-22 | 2017-05-22 | 0 | 2017-05-22 | 2017-05-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2017-06-01 | 2017-06-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.01 | Refrigeration System - Pre IR2 (System Design & Integration) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Design Reviews | [5 empty] | Refrigeration System (TEC) | [6 empty] | Refrigeration System
FALSE |  | SR344132 | Perform Mech. Assy/Tcycling/burnin-Test/Vac-Prep/RGA/ Prep for Ship at SLAC (25) REB5 boards | LSST Forecast - B57 - B1 | 48 | 0 | 2017-05-23 | 2017-09-11 | 0 | 2017-05-23 | 2017-09-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-23 | 2019-07-23 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-06-01 | 2017-08-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 48 | 76 |  | Complete | 100% | 100 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 100 | 100 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | [11 empty] | Science Raft Electronics (TEC) | [13 empty] | Prodcution REB-5 Build |  | Science Raft System
FALSE |  | SR343950 | Test REB5 Batch 2 Shipment at BNL (10 Units - RTM 4-6) | LSST Forecast - B57 - B1 | 25 | 0 | 2017-05-27 | 2017-07-18 | 0 | 2017-05-27 | 2017-07-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-05-30 | 2017-07-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 34 |  | Complete | 100% | 20 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 20 | 20 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation | [7 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [6 empty] | Prodcution REB-5 Build |  | Science Raft System
FALSE |  | CRYO60395 | Procurement Process - Compressors Oil Reservoirs - Cryo - IR2 (6 Units) | LSST Forecast - B57 - B1 | 30 | 0 | 2017-06-01 | 2017-06-07 | 0 | 2017-06-01 | 2017-06-07 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-07-03 | 2017-08-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 4 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.02 | Refrigeration System - Pre IR2 (Compressor Cabinet) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Alice Callen |  |  |  | Procurement
FALSE |  | ITC33340 | Procurement - Vendor Lead Time - Test Raft | LSST Forecast - B57 - B1 | 42 | 0 | 2017-06-05 | 2017-09-15 | 0 | 2017-06-05 | 2017-09-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-07-03 | 2017-08-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 42 | 72 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.02.02 | Pathfinder / Test Raft Program | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc)
FALSE |  | SR339400 | AWARD: Sensor Production Lot 2 V1, Long Lead Option 1 | LSST Forecast - B57 - B1 | 1 | 0 | 2017-06-06 | 2017-06-06 | 0 | 2017-06-06 | 2017-06-06 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 1362723 | 1362723 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-09-01 | 2017-09-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 1362723 | 1362723 | 0 | PercentComplete | 4% | CP_Phys |  | B1 Procurement Commitment (C5.1) |  | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR340255 | Backside Processing (Batch 3) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 15 | 0 | 2017-06-26 | 2017-07-24 | 0 | 2017-06-26 | 2017-07-24 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-07-03 | 2017-07-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 19 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR550150 | SHIPPING: Ship RTM ETU #2 to SLAC | LSST Forecast - B57 - B1 | 4 | 0 | 2017-07-03 | 2017-07-07 | 0 | 2017-07-03 | 2017-07-07 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-08-01 | 2017-08-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 3 |  | Complete | 100% | 8 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 8 | 8 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration |  | Other (specify) | [5 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM ETU #2 |  | Science Raft System
FALSE |  | ITC30580 | Perform Engineering RTM Receiving Test #2 | LSST Forecast - B57 - B1 | 25 | 0 | 2017-07-10 | 2017-09-15 | 0 | 2017-07-10 | 2017-09-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-08-07 | 2017-09-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 4 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 48 |  | Complete | 100% | 330 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.03 | Raft Acceptance Testing | 330 | 330 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [6 empty] | Cryostat I&T
FALSE |  | CR242520 | PROC: GEB (PCB & components) | LSST Forecast - B57 - B1 | 30 | 0 | 2017-07-10 | 2017-09-22 | 0 | 2017-07-10 | 2017-09-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 80000 | 80000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-08-15 | 2017-09-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 53 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.02 | Guider Electronics Board (GEB) | 0 | 0 | 0 | 80000 | 80000 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Procurement | [7 empty] | Corner Raft Electronics (TEC) | GEB
FALSE |  | ITC92090 | Early Procurements - Com Cam | LSST Forecast - B57 - B1 | 59 | 0 | 2017-07-10 | 2018-04-02 | 0 | 2017-07-10 | 2018-04-02 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-31 | 2019-05-31 | 170000 | 170000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-08-01 | 2017-10-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 59 | 190 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.06.01 | Commissioning Camera Hardware | 0 | 0 | 0 | 170000 | 170000 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Kevin Reil | (1.00) Task/item is fully invoiced/completed | 0% |  | Engineering Test/Validation |  | R&D | [5 empty] | Commissioning Camera (TEC)
FALSE |  | ITC17770 | Final Documentation - SBMS | LSST Forecast - B57 - B1 | 10 | 0 | 2017-07-11 | 2017-09-15 | 0 | 2017-07-11 | 2017-09-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-08-01 | 2017-08-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 47 |  | Complete | 100% | 168 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.01.01 | Single Bay Metrology Tests | 168 | 168 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC)
FALSE |  | CRYO61305 | Procurement - Condensing Unit & HW - IR2 | LSST Forecast - B57 - B1 | 36 | 0 | 2017-07-17 | 2018-04-04 | 0 | 2017-07-17 | 2018-04-04 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 24000 | 24000 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-08-01 | 2017-09-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 36 | 171 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.02 | Refrigeration System - Pre IR2 (Compressor Cabinet) | 0 | 0 | 0 | 24000 | 24000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | SR343990 | Receive REB5 Batch 3 Shipment at BNL (10 Units - RTM 7-9) | LSST Forecast - B57 - B1 | 10 | 0 | 2017-08-01 | 2017-08-14 | 0 | 2017-08-01 | 2017-08-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-09-01 | 2017-09-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment |  | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation | [7 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [6 empty] | Prodcution REB-5 Build |  | Science Raft System
FALSE |  | SR340295 | Backside Processing (Batch 5) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 19 | 0 | 2017-08-01 | 2017-08-28 | 0 | 2017-08-01 | 2017-08-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-09-01 | 2017-09-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 19 | 19 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR340315 | Backside Processing (Batch 6) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 14 | 0 | 2017-08-01 | 2017-08-28 | 0 | 2017-08-01 | 2017-08-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-09-11 | 2017-09-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 14 | 19 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR340355 | Backside Processing (Batch 8) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 6 | 0 | 2017-08-01 | 2017-08-30 | 0 | 2017-08-01 | 2017-08-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-09-01 | 2017-09-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 4 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 6 | 21 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR340335 | Backside Processing (Batch 7) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 2 | 0 | 2017-08-01 | 2017-08-28 | 0 | 2017-08-01 | 2017-08-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-08-01 | 2017-08-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 19 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | CCS208400 | OCS-DM-CCS complete visit test - CCS/OCS | LSST Forecast - B57 - B1 | 86 | 0 | 2017-08-21 | 2017-10-13 | 0 | 2017-08-21 | 2017-10-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-17 | 2019-10-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2018-02-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 86 | 38 |  | Complete | 100% | 240 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.04 | CCS/OCS Bridge | 240 | 240 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Testing/Integration | [7 empty] | CCS Core (TEC)
FALSE |  | ITC94000 | START: ComCam Baseline Planning | LSST Forecast - B57 - B1 | 0 | 0 | 2017-08-28 | 2017-08-28 | 0 | 2017-08-28 | 2017-08-28 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 5 | FALSE | Finish Milestone | FALSE | 2017-09-01 | 2017-09-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.06.06 | Commissioning Baseline Planning | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment |  | TEC Non-ARRA | Kevin Reil | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% | Level 4 Milestone | Testing/Integration
FALSE |  | CRYO61000 | Detail Piece Parts & Assemblies - Valve & Filters/Desiccators - Refrigeration (Compressor Chassis HW Outside) | LSST Forecast - B57 - B1 | 9 | 0 | 2017-09-01 | 2017-12-22 | 0 | 2017-09-01 | 2017-12-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2017-10-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 9 | 73 |  | Complete | 100% | 88 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.02 | Refrigeration System - Pre IR2 (Compressor Cabinet) | 88 | 88 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) | [6 empty] | Refrigeration System
FALSE |  | CRYO61340 | Requisition - Heat Exchanger Can Vac Sys - Cryostat | LSST Forecast - B57 - B1 | 10 | 0 | 2017-09-01 | 2017-09-15 | 0 | 2017-09-01 | 2017-09-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2017-10-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.04 | Refrigeration System - Pre IR2 (HX) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  |  | Procurement
FALSE |  | SR340375 | Backside Processing (Batch 9) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 20 | 0 | 2017-09-01 | 2017-09-15 | 0 | 2017-09-01 | 2017-09-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-10-02 | 2017-10-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 4 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 9 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR340395 | Backside Processing (Batch 10) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 25 | 0 | 2017-09-01 | 2017-09-15 | 0 | 2017-09-01 | 2017-09-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-10-02 | 2017-11-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 9 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR340415 | Backside Processing (Batch 11) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 27 | 0 | 2017-09-01 | 2017-09-15 | 0 | 2017-09-01 | 2017-09-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-10-05 | 2017-11-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 27 | 9 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR340435 | Backside Processing (Batch 12) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 27 | 0 | 2017-09-01 | 2017-09-15 | 0 | 2017-09-01 | 2017-09-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-10-12 | 2017-11-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 27 | 9 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | CRYO61255 | B750 Move-out - Refrigeration System | LSST Forecast - B57 - B1 | 20 | 0 | 2017-09-01 | 2018-01-31 | 0 | 2017-09-01 | 2018-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2017-10-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 93 |  | Complete | 100% | 240 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.01 | Refrigeration System - Pre IR2 (System Design & Integration) | 240 | 240 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC)
FALSE |  | ITC93350 | DAQ Pathfinder - Travel (1-5) | LSST Forecast - B57 - B1 | 200 | 0 | 2017-09-01 | 2018-09-05 | 0 | 2017-09-01 | 2018-09-05 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 15000 | 15000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2018-07-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 200 | 244 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.06.05 | DAQ Pathfinder | 0 | 0 | 0 | 15000 | 15000 | 0 | PercentComplete | 4% | CP_Drtn | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Kevin Reil | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Construction Management | [5 empty] | Commissioning Camera (TEC)
FALSE |  | ITC93000 | CCS Pathfinder 1 | LSST Forecast - B57 - B1 | 40 | 0 | 2017-09-01 | 2017-10-02 | 0 | 2017-09-01 | 2017-10-02 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2017-11-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 20 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.06.04 | CCS Pathfinder | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Kevin Reil | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | R&D | [5 empty] | Commissioning Camera (TEC)
FALSE |  | ITC93050 | CCS Pathfinder - Travel (1-5) | LSST Forecast - B57 - B1 | 200 | 0 | 2017-09-01 | 2018-08-02 | 0 | 2017-09-01 | 2018-08-02 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 15000 | 15000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2018-07-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 200 | 221 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.06.04 | CCS Pathfinder | 0 | 0 | 0 | 15000 | 15000 | 0 | PercentComplete | 4% | CP_Drtn | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Kevin Reil | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Construction Management | [5 empty] | Commissioning Camera (TEC)
FALSE |  | ITC33310 | Procurement - Vendor Lead Time - Cryostat Mockup | LSST Forecast - B57 - B1 | 19 | 0 | 2017-09-02 | 2017-09-28 | 0 | 2017-09-02 | 2017-09-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2017-10-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 19 | 17 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.02.02 | Pathfinder / Test Raft Program | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc)
FALSE |  | CAMF660600 | Requisition - Other Items - Auto Changer | LSST Forecast - B57 - B1 | 5 | 0 | 2017-09-05 | 2018-07-02 | 0 | 2017-09-05 | 2018-07-02 | 0 | 2019-06-01 | 2019-06-01 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2017-10-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 198 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.01 | Auto Changer | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Procurement
FALSE |  | CAMF664400 | Requisition - Parts - Filter Loader | LSST Forecast - B57 - B1 | 5 | 0 | 2017-09-05 | 2018-01-08 | 0 | 2017-09-05 | 2018-01-08 | 0 | 2019-06-01 | 2019-06-01 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2017-10-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 76 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.02 | Filter Loader | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Procurement
FALSE |  | CRYO32300 | Prep for Prelim Design Review - Cryostat Vacuum Purge | LSST Forecast - B57 - B1 | 5 | 0 | 2017-09-05 | 2017-09-11 | 0 | 2017-09-05 | 2017-09-11 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2017-10-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 4 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.03 | Vacuum Processing and Ground Support | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Cryostat Utillities
FALSE |  | CRYO61345 | Detail Drawings - Solenoid Valve Assy - Cryo - IR2 | LSST Forecast - B57 - B1 | 16 | 0 | 2017-09-05 | 2017-09-26 | 0 | 2017-09-05 | 2017-09-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2017-10-23 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 16 | 15 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.02 | Refrigeration System - Pre IR2 (Compressor Cabinet) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | CRYO70260 | Procurement - SS Tubes (Long Lines, Liquid) - IR2 | LSST Forecast - B57 - B1 | 20 | 0 | 2017-09-05 | 2017-09-28 | 0 | 2017-09-05 | 2017-09-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 5500 | 5500 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2017-10-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 17 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.03 | Refrigeration System - Pre IR2 (Long Lines) | 0 | 0 | 0 | 5500 | 5500 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | ITC33530 | Outside Fabrication - Vendor Lead Time - Gantry | LSST Forecast - B57 - B1 | 28 | 0 | 2017-09-08 | 2018-03-16 | 0 | 2017-09-08 | 2018-03-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2017-11-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 10 | 10 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 28 | 120 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.01 | Integration Gantry | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment |  | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc)
FALSE |  | SR340455 | Backside Processing (Batch 13) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 21 | 0 | 2017-09-18 | 2017-10-30 | 0 | 2017-09-18 | 2017-10-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-10-30 | 2017-12-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 21 | 30 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | OP521810_1 | RCV: 2nd-band Sub-scale Sample Metrology and Coating Report/Samples (MS3.1) - Filter Coating | LSST Forecast - B57 - B1 | 1 | 0 | 2017-09-22 | 2017-09-22 | 0 | 2017-09-22 | 2017-09-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-12-12 | 2019-12-12 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2017-10-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | 0-100% Method | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 7% |  | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Filters (TEC)
FALSE |  | CRYO73025 | Procurement of Servicing Equipment and Materials | LSST Forecast - B57 - B1 | 36 | 0 | 2017-09-23 | 2017-11-28 | 0 | 2017-09-23 | 2017-11-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 50400 | 50400 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2017-11-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 36 | 44 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.05 | Refrigeration System - Pre IR2 (Equipment & Refrigeration) | 0 | 0 | 0 | 50400 | 50400 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | CRYO70240 | Procurement - Long Line Hoses (Cold & Cryo) - IR2 | LSST Forecast - B57 - B1 | 20 | 0 | 2017-09-25 | 2017-10-02 | 0 | 2017-09-25 | 2017-10-02 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 12000 | 12000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2017-10-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 5 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.03 | Refrigeration System - Pre IR2 (Long Lines) | 0 | 0 | 0 | 12000 | 12000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | CCS208200 | NEED: OCS Release V4 - CCS/OCS | LSST Forecast - B57 - B1 | 0 | 0 | 2017-09-29 | 2017-09-29 | 0 | 2017-09-29 | 2017-09-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-17 | 2019-10-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-07-02 | 2018-07-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.04 | CCS/OCS Bridge | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | CRYO61510 | Requisition - Compressor Module Control Boxes - IR2 Install | LSST Forecast - B57 - B1 | 10 | 0 | 2017-10-02 | 2017-10-13 | 0 | 2017-10-02 | 2017-10-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-11-01 | 2017-11-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.02 | Refrigeration System - Pre IR2 (Compressor Cabinet) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  |  | Procurement
FALSE |  | CCS402920 | Develop Control System for IR2 Refrigeration - Cryostat HCU | LSST Forecast - B57 - B1 | 30 | 0 | 2017-10-02 | 2017-12-12 | 0 | 2017-10-02 | 2017-12-12 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-07 | 2019-05-07 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-11-01 | 2017-12-14 |  |  |  |  | 1 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 49 |  | Complete | 100% | 240 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.03 | Cryostat HCU | 240 | 240 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | CCS HCU (TEC) | [6 empty] | Camera I&T Hardware Control Unit
FALSE |  | AE214170 | Design Production Protection PLC System | LSST Forecast - B57 - B1 | 60 | 0 | 2017-10-02 | 2017-10-14 | 0 | 2017-10-02 | 2017-10-14 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-11-01 | 2018-02-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 10 |  | Complete | 100% | 220 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.02.14 | Protection PLC System | 220 | 220 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Gunther Haller | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Aux Elec Components (TEC) | [6 empty] | Power Control Monitoring
FALSE |  | AE215170 | Design Production Protection HCU System | LSST Forecast - B57 - B1 | 120 | 0 | 2017-10-02 | 2017-10-06 | 0 | 2017-10-02 | 2017-10-06 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-11-01 | 2018-05-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 120 | 4 |  | Complete | 100% | 20 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.02.15 | Protection HCU System | 20 | 20 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Gunther Haller | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Aux Elec Components (TEC) | [6 empty] | Power Control Monitoring
FALSE |  | CAMF702400 | Requisition - Production Parts - Filter Blocks | LSST Forecast - B57 - B1 | 5 | 0 | 2017-10-02 | 2017-10-06 | 0 | 2017-10-02 | 2017-10-06 | 0 | 2019-06-01 | 2019-06-01 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-11-01 | 2017-11-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 4 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.02 | Filter Loader | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Procurement
FALSE |  | SR340475 | Backside Processing (Batch 14) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 21 | 0 | 2017-10-02 | 2017-10-30 | 0 | 2017-10-02 | 2017-10-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-11-01 | 2017-12-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 21 | 20 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR339470 | E2v "Letters of Credit" for SLIN 0001 & 0002 | LSST Forecast - B57 - B1 | 15 | 0 | 2017-10-02 | 2017-10-20 | 0 | 2017-10-02 | 2017-10-20 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 34509 | 34509 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-11-01 | 2017-11-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 14 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 34509 | 34509 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC)
FALSE |  | SR340495 | Backside Processing (Batch 15) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 25 | 0 | 2017-10-03 | 2017-10-20 | 0 | 2017-10-03 | 2017-10-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-11-01 | 2017-12-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 13 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR340535 | Backside Processing (Batch 17) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 25 | 0 | 2017-10-04 | 2017-11-17 | 0 | 2017-10-04 | 2017-11-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-11-01 | 2017-12-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 32 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR340515 | Backside Processing (Batch 16) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 25 | 0 | 2017-10-10 | 2017-10-20 | 0 | 2017-10-10 | 2017-10-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-11-01 | 2017-12-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 8 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | DAQ341700 | Update Documentation - Production - RDS/RDC | LSST Forecast - B57 - B1 | 40 | 0 | 2017-10-23 | 2017-10-31 | 0 | 2017-10-23 | 2017-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-12 | 2018-05-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 6 |  | Complete | 100% | 20 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.09.02 | Raft Data Server/Client Software (RDS/RDC) | 20 | 20 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Testing/Integration |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | DAQ Readout Systems (TEC) |  | ICD's for Phase 3 |  |  |  |  | DAQ Readout Systems
FALSE |  | DAQ361400 | Update Documentation - Production - IMS/IMC | LSST Forecast - B57 - B1 | 40 | 0 | 2017-10-23 | 2017-10-31 | 0 | 2017-10-23 | 2017-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-12 | 2018-05-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 6 |  | Complete | 100% | 20 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.09.01 | Image Management/Server/Client Software | 20 | 20 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Testing/Integration |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | DAQ Readout Systems (TEC)
FALSE |  | SR339475 | AWARD: Sensor Production Lot 3 V1, Option 2 | LSST Forecast - B57 - B1 | 1 | 0 | 2017-10-24 | 2017-10-24 | 0 | 2017-10-24 | 2017-10-24 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 2077489 | 2077489 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-11-01 | 2017-11-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 2077489 | 2077489 | 0 | PercentComplete | 4% | CP_Phys |  | B1 Procurement Commitment (C5.1) |  | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC)
FALSE |  | CBM25551 | RCV: Intermediate Material Payment - Back Flange | LSST Forecast - B57 - B1 | 1 | 0 | 2017-10-31 | 2017-10-31 | 0 | 2017-10-31 | 2017-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2018-09-07 | 2018-09-07 | 15000 | 15000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-12-04 | 2017-12-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.01.02 | Camera Body Development | 0 | 0 | 0 | 15000 | 15000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | 0-100% Method | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% | Level 4 Milestone | Procurement | [7 empty] | Camera Body Development (TEC)
FALSE |  | CRYO61420 | Make Electrical Connections to Hex Vac Sys - Cryostat | LSST Forecast - B57 - B1 | 4 | 0 | 2017-11-01 | 2017-11-30 | 0 | 2017-11-01 | 2017-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-05-21 | 2018-05-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 19 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.04 | Refrigeration System - Pre IR2 (HX) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Fabrication/Assembly |  | Other (specify) | [5 empty] | Refrigeration System (TEC) | [6 empty] | Refrigeration System
FALSE |  | CRYO25550 | Finalize Design - Sieve | LSST Forecast - B57 - B1 | 80 | 0 | 2017-11-01 | 2017-11-17 | 0 | 2017-11-01 | 2017-11-17 | 0 | 2019-06-01 | 2019-06-01 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2018-04-02 | 2018-07-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 80 | 12 |  | Complete | 100% | 58 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.02 | Getter Pumps | 58 | 58 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Backend & Vacuum Systems (TEC) | [6 empty] | Cryostat Getter Pumps
FALSE |  | CRYO25560 | Finalize Analysis - Sieve | LSST Forecast - B57 - B1 | 80 | 0 | 2017-11-01 | 2017-11-17 | 0 | 2017-11-01 | 2017-11-17 | 0 | 2019-06-01 | 2019-06-01 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2018-04-02 | 2018-07-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 80 | 12 |  | Complete | 100% | 52 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.02 | Getter Pumps | 52 | 52 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Backend & Vacuum Systems (TEC) | [6 empty] | Cryostat Getter Pumps
FALSE |  | CCS250035 | Develop scripting interface for BOT - BOT HCU | LSST Forecast - B57 - B1 | 23 | 0 | 2017-11-01 | 2018-03-15 | 0 | 2017-11-01 | 2018-03-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-12-01 | 2018-01-18 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 23 | 81 |  | Complete | 100% | 200 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.08.02 | BOT HCU | 200 | 200 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Expert Opinion (Engineering Allowance) | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 6% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | CCS HCU (TEC) | [6 empty] | Camera I&T Hardware Control Unit
FALSE |  | ITC25865 | NEED: CCOB Wide Beam Ready | LSST Forecast - B57 - B1 | 0 | 0 | 2017-11-01 | 2017-11-01 | 0 | 2017-11-01 | 2017-11-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-12-01 | 2017-12-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.02.01 | Bench For Optical Testing (BOT) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | CCS310700 | NEED: Integration Gantry Hardware from I&T | LSST Forecast - B57 - B1 | 0 | 0 | 2017-11-01 | 2017-11-01 | 0 | 2017-11-01 | 2017-11-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-12-01 | 2017-12-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.08.04 | Gantry HCU | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Tony Johnson |  |  | Level 5 Milestone | Design/Engineering
FALSE |  | SR340555 | Backside Processing (Batch 18) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 25 | 0 | 2017-11-01 | 2017-11-17 | 0 | 2017-11-01 | 2017-11-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-12-01 | 2018-01-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 12 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | CRYO60986 | RCV: Compressor Module - IR2 | LSST Forecast - B57 - B1 | 22 | 0 | 2017-11-01 | 2017-11-30 | 0 | 2017-11-01 | 2017-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-01-31 | 2018-03-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 22 | 19 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.02 | Refrigeration System - Pre IR2 (Compressor Cabinet) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 20% |  | Procurement | [7 empty] | Refrigeration System (TEC)
FALSE |  | CRYO61635 | Beta Test Software for 8 Systems - Cold/Cryo | LSST Forecast - B57 - B1 | 15 | 0 | 2017-11-01 | 2017-11-30 | 0 | 2017-11-01 | 2017-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-06-15 | 2018-07-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 19 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.02 | Refrigeration System - IR2 | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | CRYO56400 | Assemble - Hx and Capillaries - Cryo - IR2 | LSST Forecast - B57 - B1 | 50 | 0 | 2017-11-01 | 2017-11-30 | 0 | 2017-11-01 | 2017-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-02-09 | 2018-04-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 50 | 19 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.04 | Refrigeration System - Pre IR2 (HX) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | CRYO56200 | Procurement - Hx & HW - Cold - IR2 | LSST Forecast - B57 - B1 | 1 | 0 | 2017-11-01 | 2017-11-30 | 0 | 2017-11-01 | 2017-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-11-30 | 2017-11-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 20 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.04 | Refrigeration System - Pre IR2 (HX) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | SR310640 | Sub-system Scientist | LSST Forecast - B57 - B1 | 240 | 0 | 2017-11-01 | 2018-10-15 | 0 | 2017-11-01 | 2018-10-15 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-12-01 | 2018-11-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 240 | 239 |  | Complete | 100% | 880 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.01 | Science Raft System Integration & Management | 880 | 880 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Drtn |  | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 0% |  | Management/Administration |  | Construction Management | [5 empty] | Science Raft System (TEC) | [13 empty] | Management - LOE |  | Science Raft System
FALSE |  | SR310650 | Sub-system Deputy PM | LSST Forecast - B57 - B1 | 240 | 0 | 2017-11-01 | 2018-10-15 | 0 | 2017-11-01 | 2018-10-15 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-12-01 | 2018-11-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 240 | 239 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.01 | Science Raft System Integration & Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Drtn |  | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 0% |  | Management/Administration |  | Construction Management | [5 empty] | Science Raft System (TEC) | [13 empty] | Management - LOE |  | Science Raft System
FALSE |  | DAQ313310 | Switch Selection - COB Production Candidate | LSST Forecast - B57 - B1 | 10 | 0 | 2017-11-01 | 2017-11-14 | 0 | 2017-11-01 | 2017-11-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-31 | 2019-10-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-12-01 | 2017-12-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.02 | DAQ COB (Main ATCA DAQ Module) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | DAQ Readout Systems (TEC)
FALSE |  | CBM27800 | Vendor Efforts - Fixtures/Equip - Camera Body | LSST Forecast - B57 - B1 | 45 | 0 | 2017-11-06 | 2018-01-31 | 0 | 2017-11-06 | 2018-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-26 | 2019-08-26 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-12-01 | 2018-02-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 45 | 48 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.01.02 | Camera Body Development | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Martin Nordby |  |  |  | Procurement
FALSE |  | CRYO61182 | Prep for C_IRR - Integration Readiness Review - IR2 Configuration | LSST Forecast - B57 - B1 | 23 | 0 | 2017-11-13 | 2017-12-15 | 0 | 2017-11-13 | 2017-12-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-12-01 | 2018-01-18 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 23 | 22 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.02 | Refrigeration System - IR2 | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC)
FALSE |  | SR340875 | Backside Processing (Batch 20) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 31 | 0 | 2017-11-14 | 2017-11-27 | 0 | 2017-11-14 | 2017-11-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-12-01 | 2018-02-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 31 | 4 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR340895 | Backside Processing (Batch 21) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 31 | 0 | 2017-11-14 | 2017-11-27 | 0 | 2017-11-14 | 2017-11-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-12-01 | 2018-02-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 31 | 4 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | CCS121600 | Implement - Pre-Production - Configuration Database | LSST Forecast - B57 - B1 | 58 | 0 | 2017-11-15 | 2018-03-30 | 0 | 2017-11-15 | 2018-03-30 | 0 | 2019-06-01 | 2019-06-01 | 2020-02-18 | 2020-02-18 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-12-01 | 2018-03-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 58 | 82 |  | Complete | 100% | 420 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.06 | CCS Database | 420 | 420 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering | [7 empty] | CCS Core (TEC)
FALSE |  | CCS250015 | NEED: CCOB Narrow Beam light source (being delivered from France-- May 2016) | LSST Forecast - B57 - B1 | 0 | 0 | 2017-11-15 | 2017-11-15 | 0 | 2017-11-15 | 2017-11-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-12-15 | 2017-12-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.08.02 | BOT HCU | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  | Level 5 Milestone | Design/Engineering
FALSE |  | CRYO56190 | AWARD: P.O. - Heat Exchanger Cryo/Cold - Cryostat | LSST Forecast - B57 - B1 | 1 | 0 | 2017-11-17 | 2017-11-17 | 0 | 2017-11-17 | 2017-11-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 216504 | 216504 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-11-22 | 2017-11-22 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.04 | Refrigeration System - Pre IR2 (HX) | 0 | 0 | 0 | 216504 | 216504 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | B1 Procurement Commitment (C5.1) |  | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 20% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Refrigeration System (TEC)
FALSE |  | SR339325 | RCV: SLIN 3 Option 2 to Purchase 5 additional fall-out sensors from E2V for I&T | LSST Forecast - B57 - B1 | 10 | 0 | 2017-11-20 | 2017-11-30 | 0 | 2017-11-20 | 2017-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-14 | 2019-05-14 | 20000 | 20000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-12-01 | 2017-12-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 6 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 20000 | 20000 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC)
FALSE |  | CRYO25630 | Generate Manufacturing Docs - Sieve | LSST Forecast - B57 - B1 | 20 | 0 | 2017-11-22 | 2017-11-22 | 0 | 2017-11-22 | 2017-11-22 | 0 | 2019-06-01 | 2019-06-01 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-08-29 | 2018-09-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.02 | Getter Pumps | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  |  | Design/Engineering
FALSE |  | SR340915 | Backside Processing (Batch 22) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 30 | 0 | 2017-11-28 | 2017-12-15 | 0 | 2017-11-28 | 2017-12-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-12-01 | 2018-02-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 13 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | CRYO23850 | AVAIL: Ready for Integration - Grid Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2017-12-01 | 2017-12-01 | 0 | 2017-12-01 | 2017-12-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Finish Milestone | FALSE | 2018-01-12 | 2018-01-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.04 | Grid Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 5 Milestone | Fabrication/Assembly | [24 empty] | Clean Room at SLAC
FALSE |  | CRYO41250 | Check and Release Detail and Assembly Drawings Cryostat Vacuum Purge | LSST Forecast - B57 - B1 | 28 | 0 | 2017-12-01 | 2017-12-11 | 0 | 2017-12-01 | 2017-12-11 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-02-09 | 2018-03-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 28 | 6 |  | Complete | 100% | 76 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.03 | Vacuum Processing and Ground Support | 76 | 76 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Backend & Vacuum Systems (TEC) | [6 empty] | Vacuum Purge System
FALSE |  | CRYO41300 | Generate Manufacturing Docs | LSST Forecast - B57 - B1 | 21 | 0 | 2017-12-01 | 2017-12-11 | 0 | 2017-12-01 | 2017-12-11 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-05-16 | 2018-06-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 21 | 6 |  | Complete | 100% | 16 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.03 | Vacuum Processing and Ground Support | 16 | 16 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Backend & Vacuum Systems (TEC) | [6 empty] | Vacuum Purge System
FALSE |  | CRYO24900 | Finalize Analysis - Evaporable Getter Pumps | LSST Forecast - B57 - B1 | 80 | 0 | 2017-12-01 | 2018-01-31 | 0 | 2017-12-01 | 2018-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2018-01-02 | 2018-04-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 80 | 31 |  | Complete | 100% | 52 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.02 | Getter Pumps | 52 | 52 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Backend & Vacuum Systems (TEC) | [6 empty] | Cryostat Getter Pumps
FALSE |  | CRYO26700 | ETU Final Design, Document and Oversite - Sieve | LSST Forecast - B57 - B1 | 30 | 0 | 2017-12-01 | 2017-12-08 | 0 | 2017-12-01 | 2017-12-08 | 0 | 2019-06-01 | 2019-06-01 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-05-07 | 2018-06-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 5 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.02 | Getter Pumps | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Backend & Vacuum Systems (TEC) | [6 empty] | Cryostat Getter Pumps
FALSE |  | CRYO70140 | Procurement - Isolation Valve Assembly HW & Fixturing (IR2) - Cold and Cryo | LSST Forecast - B57 - B1 | 26 | 0 | 2017-12-01 | 2017-12-11 | 0 | 2017-12-01 | 2017-12-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 32000 | 32000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-01-02 | 2018-02-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 26 | 6 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.03 | Refrigeration System - Pre IR2 (Long Lines) | 0 | 0 | 0 | 32000 | 32000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | CRYO72020 | Detail Piece Parts & Assemblies - Valve & Filters/Desiccators - (Cmpr Cabinet Plumbing) - Chile System | LSST Forecast - B57 - B1 | 15 | 0 | 2017-12-01 | 2017-12-22 | 0 | 2017-12-01 | 2017-12-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-31 | 2019-10-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-01-02 | 2018-01-23 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 11 |  | Complete | 100% | 16 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.02 | Refrigeration System - Chile System (Compressor Cabinet) | 16 | 16 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC)
FALSE |  | ITC27030 | Installation - MF06 for Rafts | LSST Forecast - B57 - B1 | 16 | 0 | 2017-12-01 | 2017-12-22 | 0 | 2017-12-01 | 2017-12-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-01-02 | 2018-01-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 16 | 11 |  | Complete | 100% | 50 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.01.02 | Single Bay EO Tests | 50 | 50 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Verification Test Systems (TEC)
FALSE |  | SR344420 | Order electronics parts for populating - Replacement REB5 Boards | LSST Forecast - B57 - B1 | 20 | 0 | 2017-12-01 | 2017-12-25 | 0 | 2017-12-01 | 2017-12-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-01-02 | 2018-01-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 16 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly | [23 empty] | Science Raft System
FALSE |  | DAQ900535 | Kitting and Testing of DAQ System to support 2 rafts | LSST Forecast - B57 - B1 | 20 | 0 | 2017-12-01 | 2017-12-22 | 0 | 2017-12-01 | 2017-12-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-01-02 | 2018-01-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 11 |  | Complete | 100% | 8 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.13.03 | DAQ Version 2.0 | 8 | 8 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Testing/Integration | [7 empty] | DAQ Readout Systems (TEC)
FALSE |  | CRYO11195 | FY18 - Cryostat Lead Engineer - Cryostat | LSST Forecast - B57 - B1 | 200 | 0 | 2017-12-01 | 2018-09-28 | 0 | 2017-12-01 | 2018-09-28 | 0 | 2019-06-01 | 2019-06-01 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-01-02 | 2018-10-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 200 | 199 |  | Complete | 100% | 628 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.01 | Cryostat Integration & Management | 628 | 628 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Drtn |  | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Management/Administration |  | Construction Management | [5 empty] | Cryostat Integration & Management (TEC)
FALSE |  | CCS106500 | Sustaining engineering - CCS/OCS | LSST Forecast - B57 - B1 | 60 | 0 | 2017-12-01 | 2018-09-28 | 0 | 2017-12-01 | 2018-09-28 | 0 | 2019-06-01 | 2019-06-01 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-01-11 | 2018-04-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 199 |  | Complete | 100% | 452 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.04 | CCS/OCS Bridge | 452 | 452 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration | [7 empty] | CCS Core (TEC)
FALSE |  | CRYO70220 | Assemble & Test and Braze Hose Fittings - Cold and Cryo - IR2 | LSST Forecast - B57 - B1 | 38 | 0 | 2017-12-01 | 2018-01-26 | 0 | 2017-12-01 | 2018-01-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-12-01 | 2018-02-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 17 | 17 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 38 | 28 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.03 | Refrigeration System - Pre IR2 (Long Lines) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | SR340935 | Backside Processing (Batch 23) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 25 | 0 | 2017-12-04 | 2017-12-15 | 0 | 2017-12-04 | 2017-12-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-01-10 | 2018-02-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 9 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR340955 | Backside Processing (Batch 24) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 21 | 0 | 2017-12-04 | 2017-12-15 | 0 | 2017-12-04 | 2017-12-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-01-18 | 2018-02-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 21 | 9 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | CRYO26750 | ETU Procurement Preps and Fabrification - Sieve | LSST Forecast - B57 - B1 | 90 | 0 | 2017-12-11 | 2017-12-15 | 0 | 2017-12-11 | 2017-12-15 | 0 | 2019-06-01 | 2019-06-01 | 2020-10-29 | 2020-10-29 | 30950 | 30950 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-05-07 | 2018-09-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 90 | 4 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.02 | Getter Pumps | 0 | 0 | 0 | 30950 | 30950 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Engineering Test/Validation |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Cryostat Backend & Vacuum Systems (TEC) | [6 empty] | Cryostat Getter Pumps
FALSE |  | CRYO70105 | Design - Cold System Verification Test | LSST Forecast - B57 - B1 | 40 | 0 | 2017-12-11 | 2018-01-08 | 0 | 2017-12-11 | 2018-01-08 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-07 | 2019-05-07 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-01-02 | 2018-02-28 |  |  |  |  | 1 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 10 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 9 |  | Complete | 100% | 220 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.02 | Refrigeration System - IR2 | 220 | 220 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) | [6 empty] | Utility Trunk
FALSE |  | CRYO26800 | ETU Test and Validate - Sieve | LSST Forecast - B57 - B1 | 90 | 0 | 2017-12-18 | 2017-12-20 | 0 | 2017-12-18 | 2017-12-20 | 0 | 2019-06-01 | 2019-06-01 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-05-07 | 2018-09-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 90 | 2 |  | Complete | 100% | 396 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.02 | Getter Pumps | 396 | 396 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Engineering Test/Validation |  | Commissioning and Testing | [5 empty] | Cryostat Backend & Vacuum Systems (TEC) | [6 empty] | Cryostat Getter Pumps
FALSE |  | SR333320 | Fallout Sensors (ITL Phase A) | LSST Forecast - B57 - B1 | 20 | 0 | 2017-12-20 | 2017-12-30 | 0 | 2017-12-20 | 2017-12-30 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-01-02 | 2018-01-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 7 |  | Complete | 100% | 26 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 26 | 26 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Catalog Listing or Industrial Construction Databases | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [6 empty] | Science Sensors Acceptance | [6 empty] | Lot 3 Primary Vendor |  | Science Sensors
FALSE |  | ITC22250 | I&T Vacuum Qualification Test | LSST Forecast - B57 - B1 | 69 | 0 | 2018-01-02 | 2018-02-02 | 0 | 2018-01-02 | 2018-02-02 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-02-01 | 2018-05-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 6 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 69 | 22 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.01.03 | Vacuum Qualification Tests | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC)
FALSE |  | OP531235 | Shipping Container Design Update - L1-L2 | LSST Forecast - B57 - B1 | 60 | 0 | 2018-01-02 | 2018-02-28 | 0 | 2018-01-02 | 2018-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-05 | 2019-09-05 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-02-01 | 2018-04-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 39 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | L1-L2 Assembly (TEC)
FALSE |  | CRYO24850 | Finalize Design - Evaporable Getter Pumps | LSST Forecast - B57 - B1 | 21 | 0 | 2018-01-02 | 2018-01-31 | 0 | 2018-01-02 | 2018-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2018-01-02 | 2018-01-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 21 | 20 |  | Complete | 100% | 58 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.02 | Getter Pumps | 58 | 58 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Backend & Vacuum Systems (TEC) | [6 empty] | Cryostat Getter Pumps
FALSE |  | SR340975 | Backside Processing (Batch 25) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 20 | 0 | 2018-01-08 | 2018-01-19 | 0 | 2018-01-08 | 2018-01-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-02-01 | 2018-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 8 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | DAQ910010 | Design & Architecture - GDS | LSST Forecast - B57 - B1 | 40 | 0 | 2018-01-08 | 2018-01-26 | 0 | 2018-01-08 | 2018-01-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-12-09 | 2019-12-09 | 0 | 0 | 0 | 0 | 0 | 5 | FALSE | Normal | FALSE | 2018-02-01 | 2018-03-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 13 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.15 | Guiding Data System (GDS) | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | DAQ Readout Systems (TEC)
FALSE |  | CRYO70125 | Procurement Prep - Cold System Verification Test | LSST Forecast - B57 - B1 | 10 | 0 | 2018-01-09 | 2018-01-23 | 0 | 2018-01-09 | 2018-01-23 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-07 | 2019-05-07 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-02-01 | 2018-02-14 |  |  |  |  | 1 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.02 | Refrigeration System - IR2 | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  | Percent Complete on Work Package |  | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc)
FALSE |  | CRYO15250 | Clean Cryostat Housing | LSST Forecast - B57 - B1 | 22 | 0 | 2018-01-10 | 2018-01-29 | 0 | 2018-01-10 | 2018-01-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-02-01 | 2018-03-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 22 | 12 |  | Complete | 100% | 64 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.01 | Cryostat Housing | 64 | 64 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Fabrication/Assembly |  | Other (specify) | [5 empty] | Cryostat Housing & Assembly (TEC) | [6 empty] | Cryostat Housing
FALSE |  | CRYO70300 | Assemble IR2 Hoses with Fittings - Cold and Cryo | LSST Forecast - B57 - B1 | 31 | 0 | 2018-01-10 | 2018-01-26 | 0 | 2018-01-10 | 2018-01-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-02-01 | 2018-03-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 10 | 10 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 31 | 11 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.03 | Refrigeration System - Pre IR2 (Long Lines) | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | CRYO70320 | Pre-Clean IR2 Hoses (linked to RQD Hose Fitting Installed) | LSST Forecast - B57 - B1 | 12 | 0 | 2018-01-10 | 2018-01-26 | 0 | 2018-01-10 | 2018-01-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-01-10 | 2018-01-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 12 | 12 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.03 | Refrigeration System - Pre IR2 (Long Lines) | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | CCS300005 | Plan for deployment of full focal plane software | LSST Forecast - B57 - B1 | 50 | 0 | 2018-01-11 | 2018-03-23 | 0 | 2018-01-11 | 2018-03-23 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-02-01 | 2018-04-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 50 | 49 |  | Complete | 100% | 360 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.08.03 | CCOB HCU | 360 | 360 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | CCS HCU (TEC)
FALSE |  | CCS120205 | Plan configuration database & telemetry support for ComCam/Full Camera | LSST Forecast - B57 - B1 | 40 | 0 | 2018-01-11 | 2018-06-29 | 0 | 2018-01-11 | 2018-06-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-31 | 2019-05-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-02-01 | 2018-03-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 118 |  | Complete | 100% | 220 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.02.07 | CCS Core 6.0 Release (Comcam Ship) | 220 | 220 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering | [7 empty] | CCS Core (TEC)
FALSE |  | SR340995 | Backside Processing (Batch 26) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 20 | 0 | 2018-01-16 | 2018-01-26 | 0 | 2018-01-16 | 2018-01-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-02-01 | 2018-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 8 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | CRYO72260 | Procurement of Compressor - Chile System | LSST Forecast - B57 - B1 | 60 | 0 | 2018-01-16 | 2018-04-27 | 0 | 2018-01-16 | 2018-04-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-31 | 2019-10-31 | 3300 | 3300 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-02-01 | 2018-04-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 72 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.02 | Refrigeration System - Chile System (Compressor Cabinet) | 0 | 0 | 0 | 3300 | 3300 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | OP521810_2 | RCV: 3rd-band Sub-scale Sample Metrology and Coating Report/Samples (MS3.2) - Filter Coating | LSST Forecast - B57 - B1 | 1 | 0 | 2018-01-26 | 2018-01-26 | 0 | 2018-01-26 | 2018-01-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-12-12 | 2019-12-12 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-02-01 | 2018-02-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | 0-100% Method | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 7% |  | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Filters (TEC)
FALSE |  | SR341015 | Backside Processing (Batch 27) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 20 | 0 | 2018-01-29 | 2018-02-20 | 0 | 2018-01-29 | 2018-02-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-02-01 | 2018-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 15 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | CRYO60976 | Procurement - Pressure Transducers | LSST Forecast - B57 - B1 | 10 | 0 | 2018-02-01 | 2018-02-14 | 0 | 2018-02-01 | 2018-02-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 2300 | 2300 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-01 | 2018-03-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.02 | Refrigeration System - Pre IR2 (Compressor Cabinet) | 0 | 0 | 0 | 2300 | 2300 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | CRYO73045 | Procurement - Refrigerant - IR2 | LSST Forecast - B57 - B1 | 25 | 0 | 2018-02-01 | 2018-10-01 | 0 | 2018-02-01 | 2018-10-01 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-02 | 2020-06-02 | 84000 | 84000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-01 | 2018-04-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 168 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.05 | Refrigeration System - Pre IR2 (Equipment & Refrigeration) | 0 | 0 | 0 | 84000 | 84000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | CRYO71200 | Detail Piece Parts & Assemblies - Cryo/UT Integration - Chile System | LSST Forecast - B57 - B1 | 15 | 0 | 2018-02-01 | 2018-02-26 | 0 | 2018-02-01 | 2018-02-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-31 | 2019-10-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-14 | 2018-04-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 16 |  | Complete | 100% | 114 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.01 | Refrigeration System - Chile System (System Design & Integration) | 114 | 114 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC)
FALSE |  | CAMF2450 | Outstanding Performance Annual Bonus FY18 | LSST Forecast - B57 - B1 | 19 | 0 | 2018-02-01 | 2018-02-28 | 0 | 2018-02-01 | 2018-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-01 | 2018-03-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 19 | 18 |  | Complete | 100% | 308 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01.01.01 | Project Office | 308 | 308 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Drtn | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 0% |  | Management/Administration |  | Project Management (cost estimating, scheduling, project controls, Risk assessment) | [5 empty] | Project Management (TEC)
FALSE |  | ITC93310 | DAQ Pathfinder 2 | LSST Forecast - B57 - B1 | 10 | 0 | 2018-02-01 | 2018-02-09 | 0 | 2018-02-01 | 2018-02-09 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-01 | 2018-03-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 6 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.06.05 | DAQ Pathfinder | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Kevin Reil | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | R&D | [5 empty] | Commissioning Camera (TEC)
FALSE |  | SR341035 | Backside Processing (Batch 28) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 20 | 0 | 2018-02-05 | 2018-02-27 | 0 | 2018-02-05 | 2018-02-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-03-01 | 2018-03-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 15 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | CRYO73160 | Detailed Drawings Hx - Chile System Configuration - Cryo | LSST Forecast - B57 - B1 | 9 | 0 | 2018-02-05 | 2018-03-20 | 0 | 2018-02-05 | 2018-03-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-17 | 2019-06-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-01 | 2018-03-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 9 | 30 |  | Complete | 100% | 30 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.04 | Refrigeration System - Chile System (HX) | 30 | 30 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | CRYO70345 | Procure refrigerant fixtures and Hardware for IR2 | LSST Forecast - B57 - B1 | 11 | 0 | 2018-02-08 | 2018-02-23 | 0 | 2018-02-08 | 2018-02-23 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 4000 | 4000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-01 | 2018-03-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 11 | 10 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.03 | Refrigeration System - Pre IR2 (Long Lines) | 0 | 0 | 0 | 4000 | 4000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | AE210330 | Design Support - UT AC/DC components | LSST Forecast - B57 - B1 | 40 | 0 | 2018-02-12 | 2018-04-30 | 0 | 2018-02-12 | 2018-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2018-03-01 | 2018-04-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 54 |  | Complete | 100% | 176 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.02.01 | AC and DC Power Distribution | 176 | 176 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Gunther Haller | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Aux Elec Components (TEC)
FALSE |  | AE212330 | Design Support - Production Heater Ex, UT Cooling HCU Components | LSST Forecast - B57 - B1 | 40 | 0 | 2018-02-12 | 2018-04-30 | 0 | 2018-02-12 | 2018-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-03-01 | 2018-04-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 54 |  | Complete | 100% | 176 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.02.12 | Heater Ex, UT Cooling HCU | 176 | 176 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Gunther Haller | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Aux Elec Components (TEC)
FALSE |  | AE213170 | Design Support - Production Cables/Networking | LSST Forecast - B57 - B1 | 40 | 0 | 2018-02-12 | 2018-04-30 | 0 | 2018-02-12 | 2018-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-03-01 | 2018-04-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 54 |  | Complete | 100% | 176 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.02.13 | Cables/Networking | 176 | 176 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Gunther Haller | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Aux Elec Components (TEC)
FALSE |  | AE214240 | Design Support - Production Protection PLC System | LSST Forecast - B57 - B1 | 40 | 0 | 2018-02-12 | 2018-04-30 | 0 | 2018-02-12 | 2018-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-03-01 | 2018-04-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 54 |  | Complete | 100% | 176 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.02.14 | Protection PLC System | 176 | 176 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Gunther Haller | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Aux Elec Components (TEC)
FALSE |  | AE211270 | Ion Pump Main Control Board Design, Fabricate and Test | LSST Forecast - B57 - B1 | 40 | 0 | 2018-02-12 | 2018-04-25 | 0 | 2018-02-12 | 2018-04-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 3100 | 3100 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-01 | 2018-04-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 51 |  | Complete | 100% | 148 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.02.11 | Cryostat HCU | 148 | 148 | 0 | 3100 | 3100 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Gunther Haller | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Aux Elec Components (TEC)
FALSE |  | AE211280 | Front-end Control Board Design, Fabricate and Test | LSST Forecast - B57 - B1 | 40 | 0 | 2018-02-12 | 2018-04-25 | 0 | 2018-02-12 | 2018-04-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 4000 | 4000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-01 | 2018-04-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 51 |  | Complete | 100% | 108 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.02.11 | Cryostat HCU | 108 | 108 | 0 | 4000 | 4000 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Gunther Haller | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Aux Elec Components (TEC)
FALSE |  | CRYO72060 | Procurement - Filter Dryer & Hardware Parts - Chile System | LSST Forecast - B57 - B1 | 40 | 0 | 2018-02-13 | 2018-04-10 | 0 | 2018-02-13 | 2018-04-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-31 | 2019-10-31 | 26000 | 26000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-01 | 2018-04-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 39 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.02 | Refrigeration System - Chile System (Compressor Cabinet) | 0 | 0 | 0 | 26000 | 26000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | CRYO26300 | ETU Preliminary Design Analysis and Documentation - Evaporable Getter Pumps | LSST Forecast - B57 - B1 | 14 | 0 | 2018-02-15 | 2018-02-26 | 0 | 2018-02-15 | 2018-02-26 | 0 | 2019-06-01 | 2019-06-01 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2018-03-01 | 2018-03-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 14 | 7 |  | Complete | 100% | 16 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.02 | Getter Pumps | 16 | 16 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Backend & Vacuum Systems (TEC) | [6 empty] | Cryostat Getter Pumps
FALSE |  | CRYO73420 | Requisition - Hx Can Vac Sys Cryostat - Chile System | LSST Forecast - B57 - B1 | 5 | 0 | 2018-02-22 | 2018-02-28 | 0 | 2018-02-22 | 2018-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-15 | 2019-10-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-01 | 2018-03-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 4 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.04 | Refrigeration System - Chile System (HX) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Alice Callen |  |  |  | Procurement
FALSE |  | SR341055 | Backside Processing (Batch 29) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 26 | 0 | 2018-02-28 | 2018-03-15 | 0 | 2018-02-28 | 2018-03-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-03-01 | 2018-04-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 26 | 11 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | CCS125920 | Vendor Lead Time - Parts - Camera Body HCU | LSST Forecast - B57 - B1 | 20 | 0 | 2018-03-01 | 2018-03-28 | 0 | 2018-03-01 | 2018-03-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-19 | 2019-07-19 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-04-02 | 2018-04-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 10 | 10 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 19 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.07 | Camera Body HCU | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  |  | Engineering Test/Validation
FALSE |  | ITC33540 | RCV: Outside Fabrication Procurement - Gantry | LSST Forecast - B57 - B1 | 12 | 0 | 2018-03-01 | 2018-03-16 | 0 | 2018-03-01 | 2018-03-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 32500 | 32500 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-04-02 | 2018-04-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 4 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 12 | 11 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.01 | Integration Gantry | 0 | 0 | 0 | 32500 | 32500 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat I&T (TEC)
FALSE |  | SR341075 | Backside Processing (Batch 30) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 25 | 0 | 2018-03-01 | 2018-03-23 | 0 | 2018-03-01 | 2018-03-23 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-04-02 | 2018-05-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 16 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR341095 | Backside Processing (Batch 31) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 25 | 0 | 2018-03-01 | 2018-03-23 | 0 | 2018-03-01 | 2018-03-23 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-04-09 | 2018-05-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 16 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR341115 | Backside Processing (Batch 32) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 35 | 0 | 2018-03-01 | 2018-03-23 | 0 | 2018-03-01 | 2018-03-23 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-04-16 | 2018-06-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 35 | 16 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | ITC25895 | Augmented Risk Reduction Testing - BOT | LSST Forecast - B57 - B1 | 49 | 0 | 2018-03-01 | 2018-05-08 | 0 | 2018-03-01 | 2018-05-08 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-04-02 | 2018-06-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 5 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 49 | 48 |  | Complete | 100% | 240 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.02.01 | Bench For Optical Testing (BOT) | 240 | 240 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC)
FALSE |  | CRYO91290 | Aux Elec mechanical layout and hardware design | LSST Forecast - B57 - B1 | 20 | 0 | 2018-03-01 | 2018-08-24 | 0 | 2018-03-01 | 2018-08-24 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-04-02 | 2018-04-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 124 |  | Complete | 100% | 160 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.05.02 | Utility Trunk Thermo-Mechanical and Assembly | 160 | 160 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Utility Trunk Thermo-Mechanical and Assembly (TEC)
FALSE |  | ITC92520 | Commissioning Camera - CCS Filter Changer | LSST Forecast - B57 - B1 | 80 | 0 | 2018-03-05 | 2019-03-29 | 0 | 2018-03-05 | 2019-03-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-31 | 2019-05-31 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-04-02 | 2018-07-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 80 | 262 |  | Complete | 100% | 320 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.06.02 | CCS Commissioning Camera Tucson Hardware | 320 | 320 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Kevin Reil | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | R&D | [5 empty] | Commissioning Camera (TEC)
FALSE |  | CRYO73042 | Prep for Manufacturing Readiness Review - Hx Chile | LSST Forecast - B57 - B1 | 20 | 0 | 2018-03-12 | 2018-04-25 | 0 | 2018-03-12 | 2018-04-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-17 | 2019-06-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-04-11 | 2018-05-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 32 |  | Complete | 100% | 236 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.04 | Refrigeration System - Chile System (HX) | 236 | 236 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  | Percent Complete on Work Package |  | Brian J. Langton |  |  |  | Design/Engineering | [7 empty] | Refrigeration System (TEC)
FALSE |  | CCS125930 | RCV: Components - Parts - Camera Body HCU | LSST Forecast - B57 - B1 | 10 | 0 | 2018-03-15 | 2018-03-28 | 0 | 2018-03-15 | 2018-03-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-19 | 2019-07-19 | 4000 | 4000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-04-16 | 2018-04-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.07 | Camera Body HCU | 0 | 0 | 0 | 4000 | 4000 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Engineering Test/Validation | [7 empty] | CCS HCU (TEC) | [6 empty] | Shutter Engin/Dsn
FALSE |  | ITC33595 | Augmented Risk Reduction Testing - Gantry | LSST Forecast - B57 - B1 | 11 | 0 | 2018-03-19 | 2018-04-25 | 0 | 2018-03-19 | 2018-04-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-04-02 | 2018-04-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 5 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 11 | 27 |  | Complete | 100% | 280 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.01 | Integration Gantry | 280 | 280 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat I&T (TEC)
FALSE |  | ITC33375 | Refurbishment of 3 REB boards - ETU#1 REB Upgrade | LSST Forecast - B57 - B1 | 5 | 0 | 2018-03-19 | 2018-03-23 | 0 | 2018-03-19 | 2018-03-23 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-04-02 | 2018-04-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 4 |  | Complete | 100% | 72 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.02.02 | Pathfinder / Test Raft Program | 72 | 72 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration | [7 empty] | Verification Test Systems (TEC)
FALSE |  | SR341135 | Backside Processing (Batch 33) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 35 | 0 | 2018-03-23 | 2018-04-30 | 0 | 2018-03-23 | 2018-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-04-23 | 2018-06-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 35 | 26 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR341155 | Backside Processing (Batch 34) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 35 | 0 | 2018-04-02 | 2018-04-30 | 0 | 2018-04-02 | 2018-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-05-01 | 2018-06-19 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 35 | 20 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR341195 | Backside Processing (Batch 36) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 35 | 0 | 2018-04-02 | 2018-04-30 | 0 | 2018-04-02 | 2018-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-05-01 | 2018-06-19 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 35 | 20 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | CRYO71240 | Detail Piece Parts & Assemblies - Observatory Op Integration (TMA) - Chile System | LSST Forecast - B57 - B1 | 30 | 0 | 2018-04-02 | 2018-05-11 | 0 | 2018-04-02 | 2018-05-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-31 | 2019-10-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-05-01 | 2018-06-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 29 |  | Complete | 100% | 168 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.01 | Refrigeration System - Chile System (System Design & Integration) | 168 | 168 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC)
FALSE |  | CRYO71280 | Detail Piece Parts & Assemblies - Chile Systems | LSST Forecast - B57 - B1 | 30 | 0 | 2018-04-02 | 2018-05-11 | 0 | 2018-04-02 | 2018-05-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-31 | 2019-10-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-05-01 | 2018-06-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 29 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.01 | Refrigeration System - Chile System (System Design & Integration) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC)
FALSE |  | ITC14020 | Procurement Prep - IR2 Services Upgrades | LSST Forecast - B57 - B1 | 10 | 0 | 2018-04-02 | 2018-04-13 | 0 | 2018-04-02 | 2018-04-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-14 | 2019-05-14 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2018-05-01 | 2018-05-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 4 | 0 | 1 | 3 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.03 | IR2 Facility and Operations | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor
FALSE |  | SR341175 | Backside Processing (Batch 35) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 35 | 0 | 2018-04-09 | 2018-04-30 | 0 | 2018-04-09 | 2018-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-05-08 | 2018-06-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 35 | 15 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | CR231060 | CRSA#1 Guide Sensor #1 - pin locating fixture installation | LSST Forecast - B57 - B1 | 0 | 0 | 2018-04-13 | 2018-04-13 | 0 | 2018-04-13 | 2018-04-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-04-13 | 2018-04-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 8 | 0 | 8 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 0 | 1 |  | Complete | 100% | 4 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 4 | 4 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.45) Task/item is a conceptual design and/or advances the state of the art | 0% |  | Testing/Integration |  | Other (specify) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Integration (Guide/Wavefront Sensors) | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | OP541700 | Support L3 Coating | LSST Forecast - B57 - B1 | 104 | 0 | 2018-04-18 | 2018-09-28 | 0 | 2018-04-18 | 2018-09-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-05-01 | 2018-09-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 104 | 114 |  | Complete | 100% | 320 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 320 | 320 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Drtn | Engineering Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Scott Winters | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 15% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | L3 Assembly (TEC) | L1_L2 Summary | [5 empty] | L1-L2 Optics
FALSE |  | OP521810_3 | RCV: 4th-band Sub-scale Sample Metrology and Coating Report/Samples (MS3.3) - Filter Coating | LSST Forecast - B57 - B1 | 1 | 0 | 2018-04-27 | 2018-04-27 | 0 | 2018-04-27 | 2018-04-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-12-12 | 2019-12-12 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-05-21 | 2018-05-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | 0-100% Method | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 7% |  | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Filters (TEC)
FALSE |  | CCS106800 | Test/Validate Lock Manager Release 1 with Core and Console - Lock Manager | LSST Forecast - B57 - B1 | 30 | 0 | 2018-05-01 | 2019-02-28 | 0 | 2018-05-01 | 2019-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2020-03-30 | 2020-03-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-06-01 | 2018-07-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 200 |  | Complete | 100% | 400 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.05 | CCS Lock Manager | 400 | 400 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering | [7 empty] | CCS Core (TEC)
FALSE |  | ITC19885 | Early (Long Lead) Procurement - Vendor Lead Time - Handling Equipment | LSST Forecast - B57 - B1 | 30 | 0 | 2018-05-01 | 2018-05-31 | 0 | 2018-05-01 | 2018-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-07-26 | 2018-09-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 10 | 10 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 21 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.02 | Camera Handling Equipment | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc)
FALSE |  | ITC19895 | RCV: Early (Long Lead) Procurement - Handling Equipment | LSST Forecast - B57 - B1 | 20 | 0 | 2018-05-01 | 2018-05-31 | 0 | 2018-05-01 | 2018-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-08-09 | 2018-09-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 4 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 21 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.02 | Camera Handling Equipment | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Camera I&T (TEC)
FALSE |  | ITC19995 | COTS Procurement - Vendor Lead Time - Handling Equipment | LSST Forecast - B57 - B1 | 30 | 0 | 2018-05-01 | 2018-05-31 | 0 | 2018-05-01 | 2018-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-10-15 | 2018-11-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 10 | 10 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 21 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.02 | Camera Handling Equipment | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc)
FALSE |  | ITC20005 | RCV: COTS Procurement - Handling Equipment | LSST Forecast - B57 - B1 | 20 | 0 | 2018-05-01 | 2018-05-31 | 0 | 2018-05-01 | 2018-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-10-29 | 2018-11-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 4 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 21 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.02 | Camera Handling Equipment | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Camera I&T (TEC)
FALSE |  | ITC20026 | Outside Fabrication - Vendor Lead Time - Handling Equipment | LSST Forecast - B57 - B1 | 30 | 0 | 2018-05-01 | 2018-05-31 | 0 | 2018-05-01 | 2018-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-10-15 | 2018-11-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 10 | 10 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 21 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.02 | Camera Handling Equipment | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc)
FALSE |  | ITC20035 | RCV: Outside Fabrication Procurement - Handling Equipment | LSST Forecast - B57 - B1 | 20 | 0 | 2018-05-01 | 2018-05-31 | 0 | 2018-05-01 | 2018-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-10-29 | 2018-11-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 4 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 21 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.02 | Camera Handling Equipment | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Camera I&T (TEC)
FALSE |  | ITC94060 | Document Update - Commissioning Phase | LSST Forecast - B57 - B1 | 54 | 0 | 2018-05-01 | 2018-08-01 | 0 | 2018-05-01 | 2018-08-01 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-06-01 | 2018-08-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 54 | 64 |  | Complete | 100% | 50 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.06.06 | Commissioning Baseline Planning | 50 | 50 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Kevin Reil | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Project Management (cost estimating, scheduling, project controls, Risk assessment) | [5 empty] | Commissioning Camera (TEC)
FALSE |  | ITC22450 | Procurement Prep - TS7 HW | LSST Forecast - B57 - B1 | 10 | 0 | 2018-05-01 | 2018-05-04 | 0 | 2018-05-01 | 2018-05-04 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-06-01 | 2018-06-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 3 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.01.03 | Vacuum Qualification Tests | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor
FALSE |  | ITC32670 | Procurement Prep - IR2 Facility and Operations | LSST Forecast - B57 - B1 | 10 | 0 | 2018-05-01 | 2018-05-14 | 0 | 2018-05-01 | 2018-05-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-06-01 | 2018-06-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment |  | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor
FALSE |  | AE210340 | Installation Support - Auxiliary Electronics Power Distribution | LSST Forecast - B57 - B1 | 22 | 0 | 2018-05-01 | 2018-09-28 | 0 | 2018-05-01 | 2018-09-28 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-06-01 | 2018-07-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 22 | 105 |  | Complete | 100% | 176 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.02.01 | AC and DC Power Distribution | 176 | 176 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Gunther Haller | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Fabrication/Assembly |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Aux Elec Components (TEC)
FALSE |  | AE212340 | Installation Support - Auxiliary Electronics Heater Exchange and UT Cooling | LSST Forecast - B57 - B1 | 22 | 0 | 2018-05-01 | 2018-09-21 | 0 | 2018-05-01 | 2018-09-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-12-12 | 2019-12-12 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-06-01 | 2018-07-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 22 | 100 |  | Complete | 100% | 176 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.02.12 | Heater Ex, UT Cooling HCU | 176 | 176 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Gunther Haller | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Fabrication/Assembly |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Aux Elec Components (TEC)
FALSE |  | AE213180 | Installation Support - Auxiliary Electronics Cabling | LSST Forecast - B57 - B1 | 22 | 0 | 2018-05-01 | 2018-09-28 | 0 | 2018-05-01 | 2018-09-28 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-06-01 | 2018-07-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 22 | 105 |  | Complete | 100% | 176 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.02.13 | Cables/Networking | 176 | 176 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Gunther Haller | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Fabrication/Assembly |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Aux Elec Components (TEC)
FALSE |  | AE214250 | Programming Installation Support - Auxiliary Electronics Protection PLC System | LSST Forecast - B57 - B1 | 22 | 0 | 2018-05-01 | 2018-09-28 | 0 | 2018-05-01 | 2018-09-28 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-06-01 | 2018-07-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 22 | 105 |  | Complete | 100% | 176 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.02.14 | Protection PLC System | 176 | 176 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Gunther Haller | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Fabrication/Assembly |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Aux Elec Components (TEC)
FALSE |  | SR333535 | Batch Sensor Testing (RTM #16) | LSST Forecast - B57 - B1 | 15 | 0 | 2018-05-19 | 2018-05-31 | 0 | 2018-05-19 | 2018-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-06-21 | 2018-07-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 10 | 0 | 9 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 3 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 7 |  | Complete | 100% | 83 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 83 | 83 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | OP531240 | Procure L1 Coating | LSST Forecast - B57 - B1 | 40 | 0 | 2018-05-21 | 2018-11-21 | 0 | 2018-05-21 | 2018-11-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-03 | 2019-09-03 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-07-17 | 2018-09-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 5 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 129 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment |  | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 0% |  | Procurement | [7 empty] | L1-L2 Assembly (TEC) | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly) |  |  |  | L1-L2 Optics
FALSE |  | SR551171 | RTM16_RSA Construction at TS4 | LSST Forecast - B57 - B1 | 8 | 0 | 2018-06-01 | 2018-06-12 | 0 | 2018-06-01 | 2018-06-12 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-07-02 | 2018-07-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 8 | 7 |  | Complete | 100% | 44 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 44 | 44 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #16 |  | Science Raft System
FALSE |  | CRYO73055 | AWARD: P.O. - Heat Exchanger Cryo/Cold - Cryostat | LSST Forecast - B57 - B1 | 1 | 0 | 2018-06-01 | 2018-06-01 | 0 | 2018-06-01 | 2018-06-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-17 | 2019-06-17 | 188357 | 188357 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-07-02 | 2018-07-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.04 | Refrigeration System - Chile System (HX) | 0 | 0 | 0 | 188357 | 188357 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | B1 Procurement Commitment (C5.1) |  | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 20% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Refrigeration System (TEC)
FALSE |  | CRYO25250 | Generate Manufacturing Docs - Evaporable Getter Pump | LSST Forecast - B57 - B1 | 20 | 0 | 2018-06-04 | 2018-06-08 | 0 | 2018-06-04 | 2018-06-08 | 0 | 2019-06-01 | 2019-06-01 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-09-27 | 2018-10-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 4 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.02 | Getter Pumps | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  |  | Design/Engineering
FALSE |  | OP521810_4 | RCV: 5th-band Sub-scale Sample Metrology and Coating Report/Samples (MS3.4) - Filter Coating | LSST Forecast - B57 - B1 | 1 | 0 | 2018-06-14 | 2018-06-14 | 0 | 2018-06-14 | 2018-06-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-12-12 | 2019-12-12 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-07-09 | 2018-07-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | 0-100% Method | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 7% |  | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Filters (TEC)
FALSE |  | SR333545 | Batch Sensor Testing (RTM #17) | LSST Forecast - B57 - B1 | 10 | 0 | 2018-06-20 | 2018-07-06 | 0 | 2018-06-20 | 2018-07-06 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-07-03 | 2018-07-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 10 | 0 | 3 | 6 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 11 |  | Complete | 100% | 83 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 83 | 83 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | CRYO61405 | NEED: Cryostat Assembly Ready for Hx Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2018-06-28 | 2018-06-28 | 0 | 2018-06-28 | 2018-06-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-07-11 | 2018-07-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.04 | Refrigeration System - Pre IR2 (HX) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 5 Milestone | Fabrication/Assembly | [16 empty] | Cryostat
FALSE |  | CRYO61610 | Requisition - Compressor Module Control Boxes - Chile Hardware | LSST Forecast - B57 - B1 | 19 | 0 | 2018-07-02 | 2018-07-06 | 0 | 2018-07-02 | 2018-07-06 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-03 | 2019-10-03 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-08-01 | 2018-08-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 3 | 3 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 19 | 3 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.02 | Refrigeration System - Chile System (Compressor Cabinet) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  |  | Procurement
FALSE |  | ITC14090 | Procurement Prep - Raft Storage HW | LSST Forecast - B57 - B1 | 12 | 0 | 2018-07-02 | 2018-07-18 | 0 | 2018-07-02 | 2018-07-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-09 | 2019-09-09 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-08-01 | 2018-08-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 12 | 11 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.03 | IR2 Facility and Operations | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor
FALSE |  | CRYO61620 | Procurement Process - Compressor Module Control Boxes - Chile Hardware | LSST Forecast - B57 - B1 | 20 | 0 | 2018-07-06 | 2018-07-16 | 0 | 2018-07-06 | 2018-07-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-03 | 2019-10-03 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-08-06 | 2018-08-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 6 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.02 | Refrigeration System - Chile System (Compressor Cabinet) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  |  | Procurement
FALSE |  | SR333565 | Batch Sensor Testing (RTM #19) | LSST Forecast - B57 - B1 | 10 | 0 | 2018-07-12 | 2018-07-25 | 0 | 2018-07-12 | 2018-07-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-08-10 | 2018-08-23 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 103 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 103 | 103 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | CBM48900 | Engineering and Design Support for Fab/Assy/Test - Shutter | LSST Forecast - B57 - B1 | 195 | 15 | 2018-08-01 | 2019-06-21 | 116 | 2018-08-01 |  | 0 | 2019-06-03 | 2019-06-21 | 2019-11-14 | 2019-12-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-09-04 | 2019-06-24 |  |  |  |  | 0.65 | 0 | FALSE | FALSE | None |  | None |  | 2019-05-21 |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 195 | 202 |  | InProgress | 65% | 612 | 0 | 612 | 612 | LSST Forecast - B57 - B1.3.06.02.02 | Shutter Development | 397.8 | 561.7846 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 5% |  | Fabrication/Assembly |  | Construction Management | [5 empty] | Shutter Development (TEC) | [6 empty] | Shutter Prod Sprt
FALSE |  | SE221645 | Model Validation & I&T Test Support (LOE) | LSST Forecast - B57 - B1 | 340 | 84 | 2018-08-01 | 2019-09-30 | 273 | 2018-08-01 |  | 0 | 2019-06-03 | 2019-09-30 | 2020-07-14 | 2020-11-09 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-09-04 | 2020-02-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None |  | 2019-09-30 |  |  |  |  | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 340 | 202 |  | InProgress | 75.29% | 486 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.01 | Structural System Analysis | 365.9294 | 255.8647 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Drtn | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | ITC19805 | Update Defining Documentation - Handling Equipment | LSST Forecast - B57 - B1 | 24 | 0 | 2018-08-01 | 2018-08-10 | 0 | 2018-08-01 | 2018-08-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-16 | 2019-09-16 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-09-04 | 2018-10-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 24 | 7 |  | Complete | 100% | 9 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.02 | Camera Handling Equipment | 9 | 9 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Camera I&T (TEC)
FALSE |  | ITC98090 | I&T Physicist Support - IR2 Clean Room | LSST Forecast - B57 - B1 | 118 | 0 | 2018-08-01 | 2019-01-31 | 0 | 2018-08-01 | 2019-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-09-04 | 2019-03-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 118 | 117 |  | Complete | 100% | 1040 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.01 | I&T Integration & Management | 1040 | 1040 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Drtn | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Construction Management | [5 empty] | Integration & Testing (TEC)
FALSE |  | CRYO31505 | Procurement Prep - Material - Power Feedthrough | LSST Forecast - B57 - B1 | 10 | 0 | 2018-08-01 | 2018-08-14 | 0 | 2018-08-01 | 2018-08-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-09-04 | 2018-09-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.01 | Cryostat Back End | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Procurement
FALSE |  | CRYO31515 | Procurement Prep - Assy/Test Equipment - Power Feedthrough | LSST Forecast - B57 - B1 | 10 | 0 | 2018-08-01 | 2018-08-14 | 0 | 2018-08-01 | 2018-08-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-09-04 | 2018-09-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.01 | Cryostat Back End | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Procurement
FALSE |  | CAMM6390 | AVAIL: Camera Software for Auxiliary Telescope | LSST Forecast - B57 - B1 | 0 | 0 | 2018-08-01 | 2018-08-01 | 0 | 2018-08-01 | 2018-08-01 | 0 | 2019-06-01 | 2019-06-01 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-08-01 | 2018-08-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | FinishOnOrBefore | 2018-09-28 | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.03 | NSF Interface Milestone (NSF Needs) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration
FALSE |  | CAMF661550 | In-House Assembly - Auto Changer | LSST Forecast - B57 - B1 | 56 | 0 | 2018-08-02 | 2019-01-07 | 0 | 2018-08-02 | 2019-01-07 | 0 | 2019-06-01 | 2019-06-01 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-09-04 | 2018-11-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 56 | 99 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.01 | Auto Changer | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Fabrication/Assembly
FALSE |  | DAQ334600 | Procurement Process - Production Parts - ATCA Shelves | LSST Forecast - B57 - B1 | 10 | 0 | 2018-08-20 | 2018-08-27 | 0 | 2018-08-20 | 2018-08-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-24 | 2019-05-24 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-09-04 | 2018-09-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 5 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.06 | ATCA Shelves | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [7 empty] | ICD's for Phase 3 |  |  |  |  | DAQ Readout Systems
FALSE |  | DAQ920000 | START: Design and R & D (Firmware) | LSST Forecast - B57 - B1 | 0 | 0 | 2018-08-20 | 2018-08-20 | 0 | 2018-08-20 | 2018-08-20 | 0 | 2019-06-01 | 2019-06-01 | 2020-08-26 | 2020-08-26 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-09-18 | 2018-09-18 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.16 | Remote FPGA Reprogramming | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% | Level 5 Milestone | Design/Engineering
FALSE |  | DAQ313400 | START: (V2) of the New COB | LSST Forecast - B57 - B1 | 0 | 0 | 2018-08-28 | 2018-08-28 | 0 | 2018-08-28 | 2018-08-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-24 | 2019-05-24 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2018-09-04 | 2018-09-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.02 | DAQ COB (Main ATCA DAQ Module) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Michael Huffer |  |  | Level 5 Milestone
FALSE |  | ITC22320 | Develop Camera Shipping Plan | LSST Forecast - B57 - B1 | 20 | 0 | 2018-09-03 | 2018-09-21 | 0 | 2018-09-03 | 2018-09-21 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-10-01 | 2018-10-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 13 |  | Complete | 100% | 50 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.05 | Transportation & Storage Equipment | 50 | 50 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Kevin Reil | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Transportation & Storage Equipment (TEC)
FALSE |  | DAQ920030 | START: Design and R & D (Software) | LSST Forecast - B57 - B1 | 0 | 0 | 2018-09-04 | 2018-09-04 | 0 | 2018-09-04 | 2018-09-04 | 0 | 2019-06-01 | 2019-06-01 | 2020-07-16 | 2020-07-16 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-10-15 | 2018-10-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.16 | Remote FPGA Reprogramming | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment |  | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% | Level 5 Milestone | Design/Engineering
FALSE |  | CRYO31700 | Write Test and Verification Reports Cryostat Backend | LSST Forecast - B57 - B1 | 6 | 0 | 2018-09-17 | 2018-10-08 | 0 | 2018-09-17 | 2018-10-08 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2018-10-01 | 2018-10-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 6 | 15 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.01 | Cryostat Back End | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Brian J. Langton |  |  |  | Fabrication/Assembly
FALSE |  | ITC34090 | RCV: COTS Procurement - Cryo-Equip | LSST Forecast - B57 - B1 | 29 | 0 | 2018-09-21 | 2018-09-25 | 0 | 2018-09-21 | 2018-09-25 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 8000 | 8000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-10-15 | 2018-11-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 4 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 29 | 2 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.02 | Cryostat Handling Equipment | 0 | 0 | 0 | 8000 | 8000 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat I&T (TEC)
FALSE |  | CR231930 | CRSA#4 in cryostat cool down | LSST Forecast - B57 - B1 | 1 | 0 | 2018-09-24 | 2018-09-24 | 0 | 2018-09-24 | 2018-09-24 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-05 | 2019-06-05 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-09-24 | 2018-09-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 1 |  | Complete | 100% | 8 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 8 | 8 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Testing/Integration |  | Other (specify) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Integration (Guide/Wavefront Sensors) | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CRYO61040 | Detail Piece Parts & Assemblies - Evacuate, Purge & Charge HW - Chile System | LSST Forecast - B57 - B1 | 15 | 1 | 2018-10-01 | 2019-06-03 | 245 | 2018-10-01 |  | 0 | 2019-06-03 | 2019-06-03 | 2020-06-02 | 2020-06-03 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-11-01 | 2018-11-21 |  |  |  |  | 0.1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 160 |  | InProgress | 10% | 106 | 0 | 106 | 106 | LSST Forecast - B57 - B1.3.06.04.06.03.05 | Refrigeration System - Chile System (Equipment & Refrigeration) | 10.6 | 106 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) | [6 empty] | Refrigeration System
FALSE |  | CRYO72200 | Fab and Assembly - Compressors Oil Reservoirs - Cryo - Chile System (6 Unts) | LSST Forecast - B57 - B1 | 25 | 0 | 2018-10-01 | 2019-01-31 | 0 | 2018-10-01 | 2019-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-31 | 2019-10-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-11-01 | 2018-12-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 75 |  | Complete | 100% | 84 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.02 | Refrigeration System - Chile System (Compressor Cabinet) | 84 | 84 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.00) Task/item is fully invoiced/completed | 0% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC)
FALSE |  | DAQ900342 | Procure COB - FPGAs | LSST Forecast - B57 - B1 | 10 | 0 | 2018-10-01 | 2018-12-31 | 0 | 2018-10-01 | 2018-12-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 128000 | 128000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-02-01 | 2019-02-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 5 | 5 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 58 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.02 | DAQ COB (Main ATCA DAQ Module) | 0 | 0 | 0 | 128000 | 128000 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Fabrication/Assembly | [7 empty] | DAQ Readout Systems (TEC)
FALSE |  | CRYO61335 | Replace Condensing Unit - IR2 | LSST Forecast - B57 - B1 | 5 | 0 | 2018-10-08 | 2018-10-12 | 0 | 2018-10-08 | 2018-10-12 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-11-01 | 2018-11-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 4 |  | Complete | 100% | 16 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.02 | Refrigeration System - Pre IR2 (Compressor Cabinet) | 16 | 16 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | OP521810_5 | RCV: 6th-band Sub-scale Sample Metrology and Coating Report/Samples (MS3.5) - Filter Coating | LSST Forecast - B57 - B1 | 1 | 0 | 2018-10-29 | 2018-10-29 | 0 | 2018-10-29 | 2018-10-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-12-12 | 2019-12-12 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-11-01 | 2018-11-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | 0-100% Method | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 7% |  | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Filters (TEC)
FALSE |  | OP522105 | RCV: Filter First Article TWF testing data received (MS2) | LSST Forecast - B57 - B1 | 1 | 0 | 2018-10-31 | 2018-10-31 | 0 | 2018-10-31 | 2018-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-25 | 2019-07-25 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-11-12 | 2018-11-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | 0-100% Method | TEC Non-ARRA | Scott Winters |  |  | Level 4 Milestone | Procurement | [7 empty] | Filters (TEC)
FALSE |  | SE221370 | Prep camera FEA model for export to Obs; deliver and run verification checks | LSST Forecast - B57 - B1 | 40 | 0 | 2018-11-01 | 2018-11-30 | 0 | 2018-11-01 | 2018-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-13 | 2019-06-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-12-03 | 2019-02-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 19 |  | Complete | 100% | 20 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.01 | Structural System Analysis | 20 | 20 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | ITC31727 | NEED: All DAQ OTM's | LSST Forecast - B57 - B1 | 0 | 0 | 2018-11-02 | 2018-11-02 | 0 | 2018-11-02 | 2018-11-02 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-12-03 | 2018-12-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Auxiliary Electronics
FALSE |  | CRYO72340 | RCV: Compressor Module - Chile System | LSST Forecast - B57 - B1 | 40 | 0 | 2018-11-05 | 2019-01-18 | 0 | 2018-11-05 | 2019-01-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-31 | 2019-10-31 | 203981 | 203981 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-01-29 | 2019-03-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 42 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.02 | Refrigeration System - Chile System (Compressor Cabinet) | 0 | 0 | 0 | 203981 | 203981 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 20% |  | Procurement | [7 empty] | Refrigeration System (TEC)
FALSE |  | CBM50200 | Vendor Lead Time - Components - Shutter | LSST Forecast - B57 - B1 | 35 | 0 | 2018-12-03 | 2019-04-30 | 0 | 2018-12-03 | 2019-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-21 | 2019-08-21 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-01-07 | 2019-02-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 35 | 94 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.02.02 | Shutter Development | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Martin Nordby |  |  |  | Procurement
FALSE |  | OP541640 | Procure L3 Lens Coating | LSST Forecast - B57 - B1 | 59 | 0 | 2018-12-03 | 2019-02-22 | 0 | 2018-12-03 | 2019-02-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-01-02 | 2019-03-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 59 | 54 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement | [8 empty] | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly) |  |  |  | L1-L2 Optics
FALSE |  | ITC31775 | CCOB Analysis Software | LSST Forecast - B57 - B1 | 80 | 0 | 2019-01-07 | 2019-02-21 | 0 | 2019-01-07 | 2019-02-21 | 0 | 2019-06-01 | 2019-06-01 | 2020-05-05 | 2020-05-05 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-02-07 | 2019-05-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 80 | 31 |  | Complete | 100% | 335 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.04 | Verification Software Development | 335 | 335 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Other (specify) | [5 empty] | Verification Test Systems (TEC)
FALSE |  | SR571110 | Modify REC Walls (Design Update & Batch A1) | LSST Forecast - B57 - B1 | 20 | 0 | 2019-01-07 | 2019-01-31 | 0 | 2019-01-07 | 2019-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-02-01 | 2019-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 17 |  | Complete | 100% | 32 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 32 | 32 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Science Raft Production Assembly and Test (TEC) | [15 empty] | Science Raft System
FALSE |  | SR571140 | Modify A-Frames (Design Update & Batch A1) | LSST Forecast - B57 - B1 | 20 | 0 | 2019-01-07 | 2019-01-31 | 0 | 2019-01-07 | 2019-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-02-01 | 2019-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 17 |  | Complete | 100% | 17 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 17 | 17 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Science Raft Production Assembly and Test (TEC) | [15 empty] | Science Raft System
FALSE |  | SR571170 | Modify MF08 (Design Update & Batch A1) | LSST Forecast - B57 - B1 | 20 | 0 | 2019-01-07 | 2019-01-31 | 0 | 2019-01-07 | 2019-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-02-01 | 2019-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 17 |  | Complete | 100% | 29 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 29 | 29 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Science Raft Production Assembly and Test (TEC) | [15 empty] | Science Raft System
FALSE |  | ITC36080 | Develop RSA Cleaning Process | LSST Forecast - B57 - B1 | 20 | 0 | 2019-01-07 | 2019-02-28 | 0 | 2019-01-07 | 2019-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 10000 | 10000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-02-01 | 2019-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 36 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.03 | Raft Acceptance Testing | 40 | 40 | 0 | 10000 | 10000 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC)
FALSE |  | ITC36090 | RTM Tools, Storage Rack, Aliveness Bench | LSST Forecast - B57 - B1 | 20 | 0 | 2019-01-07 | 2019-02-28 | 0 | 2019-01-07 | 2019-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 16000 | 16000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-02-01 | 2019-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 36 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.03 | Raft Acceptance Testing | 0 | 0 | 0 | 16000 | 16000 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC)
FALSE |  | ITC36100 | I&T eTraveler Development | LSST Forecast - B57 - B1 | 20 | 0 | 2019-01-07 | 2019-02-28 | 0 | 2019-01-07 | 2019-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-02-01 | 2019-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 36 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.03 | Raft Acceptance Testing | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC)
FALSE |  | DAQ900350 | Assemble Production COBs | LSST Forecast - B57 - B1 | 24 | 0 | 2019-01-07 | 2019-04-15 | 0 | 2019-01-07 | 2019-04-15 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-01-07 | 2019-02-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 4 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 24 | 68 |  | Complete | 100% | 180 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.02 | DAQ COB (Main ATCA DAQ Module) | 180 | 180 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | [11 empty] | DAQ Readout Systems (TEC)
FALSE |  | SR310635 | Sub-system manager FY19 (Project Extension) | LSST Forecast - B57 - B1 | 124 | 54 | 2019-01-08 | 2019-08-15 | 683 | 2019-01-08 |  | 0 | 2019-06-03 | 2019-08-15 | 2022-01-13 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2019-02-01 | 2019-07-24 |  |  |  |  | 0.33 | 0 | FALSE | FALSE | None |  | None |  | 2019-08-15 |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 124 | 104 |  | InProgress | 56.45% | 264 | 0 | 264 | 264 | LSST Forecast - B57 - B1.3.04.01.01 | Science Raft System Integration & Management | 149.0323 | 183.0968 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Drtn |  | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 0% |  | Management/Administration |  | Construction Management | [5 empty] | Science Raft System (TEC) | [13 empty] | Management - LOE |  | Science Raft System
FALSE |  | SR570870 | RTM19_Disassemble REC | LSST Forecast - B57 - B1 | 4 | 0 | 2019-01-25 | 2019-01-31 | 0 | 2019-01-25 | 2019-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-13 | 2019-06-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-02-14 | 2019-02-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 4 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [13 empty] | RTM #19 |  | Science Raft System
FALSE |  | CRYO61493 | AWARD: P.O. - Gas to calibrate chromatograph - Chile System | LSST Forecast - B57 - B1 | 1 | 0 | 2019-01-31 | 2019-01-31 | 0 | 2019-01-31 | 2019-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-02 | 2020-06-02 | 28000 | 28000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-02-01 | 2019-02-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.05 | Refrigeration System - Chile System (Equipment & Refrigeration) | 0 | 0 | 0 | 28000 | 28000 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | B1 Procurement Commitment (C5.1) |  | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 20% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Refrigeration System (TEC)
FALSE |  | CRYO74040 | Procurement Process - Servicing Equipment & Materials - Chile System (240V, 50Hz) | LSST Forecast - B57 - B1 | 40 | 0 | 2019-01-31 | 2019-01-31 | 0 | 2019-01-31 | 2019-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-02 | 2020-06-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-02-01 | 2019-03-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.05 | Refrigeration System - Chile System (Equipment & Refrigeration) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Alice Callen |  |  |  | Procurement
FALSE |  | CBM50000 | RCV: Phase 2 Requirements - Shutter Blades | LSST Forecast - B57 - B1 | 1 | 0 | 2019-02-01 | 2019-02-01 | 0 | 2019-02-01 | 2019-02-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-22 | 2019-08-22 | 147369 | 147369 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-03-01 | 2019-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.02.02 | Shutter Development | 0 | 0 | 0 | 147369 | 147369 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | 0-100% Method | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 5% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Shutter Development (TEC) | [6 empty] | Shutter Prod Sprt
FALSE |  | CAMF2460 | Outstanding Performance Annual Bonus FY19 | LSST Forecast - B57 - B1 | 19 | 0 | 2019-02-01 | 2019-02-28 | 0 | 2019-02-01 | 2019-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-03-01 | 2019-03-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 19 | 18 |  | Complete | 100% | 295 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01.01.01 | Project Office | 295 | 295 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 0% |  | Management/Administration |  | Project Management (cost estimating, scheduling, project controls, Risk assessment) | [5 empty] | Project Management (TEC)
FALSE |  | ITC10892 | IT&C Travel--FY19 (UC Davis Support) | LSST Forecast - B57 - B1 | 160 | 76 | 2019-02-01 | 2019-09-18 | 612 | 2019-02-01 |  | 0 | 2019-06-03 | 2019-09-18 | 2021-11-24 | 2022-03-29 | 30000 | 30000 | 0 | 30000 | 30000 | 1 | FALSE | Normal | FALSE | 2019-03-01 | 2019-10-15 |  |  |  |  | 0.125 | 0 | FALSE | FALSE | None |  | None |  | 2019-09-18 |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 160 | 84 |  | InProgress | 52.5% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.01 | I&T Integration & Management | 0 | 0 | 0 | 15750 | 12187.5 | 30000 | PercentComplete | 4% | CP_Drtn | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Management/Administration |  | Construction Management | [5 empty] | Integration & Testing (TEC)
FALSE |  | OP521820 | RCV: r-band repeatability and Phase 1 deliverables (MS4) - Filter Coating | LSST Forecast - B57 - B1 | 2 | 0 | 2019-02-25 | 2019-02-26 | 0 | 2019-02-25 | 2019-02-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-12-12 | 2019-12-12 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-02-25 | 2019-02-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 2 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | 0-100% Method | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 23% |  | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Filters (TEC) | Witness Sample | [5 empty] | Filter Optics
FALSE |  | ITC31820 | ETU EO/BOT Testing | LSST Forecast - B57 - B1 | 10 | 5 | 2019-04-01 | 2019-06-07 | -18 | 2019-04-01 |  | 0 | 2019-06-03 | 2019-06-07 | 2019-05-07 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2019-05-01 | 2019-05-14 |  |  |  |  | 0.5 | 0 | FALSE | TRUE | None |  | None |  | 2019-06-07 |  |  |  |  | 2 | 0 | 1 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 44 |  | InProgress | 50% | 281 | 0 | 281 | 281 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 140.5 | 281 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | SR570280 | RTM06_Inspect, Clean & Test RSA | LSST Forecast - B57 - B1 | 6 | 0 | 2019-04-01 | 2019-04-08 | 0 | 2019-04-01 | 2019-04-08 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-20 | 2019-06-20 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-05-01 | 2019-05-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 6 | 5 |  | Complete | 100% | 70 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 70 | 70 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [13 empty] | RTM #6 |  | Science Raft System
FALSE |  | ITC36020 | Modify A-Frames (Batch B1) | LSST Forecast - B57 - B1 | 20 | 0 | 2019-04-01 | 2019-04-29 | 0 | 2019-04-01 | 2019-04-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-25 | 2019-10-25 | 600 | 600 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-05-01 | 2019-05-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 20 |  | Complete | 100% | 6 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.03 | Raft Acceptance Testing | 6 | 6 | 0 | 600 | 600 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC)
FALSE |  | ITC36050 | Modify MF08 (Batch B1) | LSST Forecast - B57 - B1 | 20 | 0 | 2019-04-01 | 2019-04-29 | 0 | 2019-04-01 | 2019-04-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-30 | 2019-08-30 | 1000 | 1000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-05-01 | 2019-05-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 20 |  | Complete | 100% | 12 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.03 | Raft Acceptance Testing | 12 | 12 | 0 | 1000 | 1000 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC)
FALSE |  | CRYO73090 | Eden Change Orders (Line Item 2,3,4) - Hx & HW - Chile System | LSST Forecast - B57 - B1 | 20 | 0 | 2019-04-01 | 2019-04-30 | 0 | 2019-04-01 | 2019-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 38684 | 38684 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-05-03 | 2019-05-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 21 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.04 | Refrigeration System - Chile System (HX) | 0 | 0 | 0 | 38684 | 38684 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | ITC36150 | RTM1 r1_Disassemble REC | LSST Forecast - B57 - B1 | 5 | 0 | 2019-04-01 | 2019-04-05 | 0 | 2019-04-01 | 2019-04-05 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-21 | 2019-08-21 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-05-01 | 2019-05-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 4 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.03 | Raft Acceptance Testing | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC)
FALSE |  | OP522490 | RCV: 2 of 6 Filter Complete and Ready to Ship (MS5) - Filter Fabrication | LSST Forecast - B57 - B1 | 1 | 0 | 2019-04-17 | 2019-04-17 | 0 | 2019-04-17 | 2019-04-17 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-06-03 | 2019-06-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | 0-100% Method | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Filters (TEC)
FALSE |  | OP522485 | COMP: 1st Production Filter Complete and Ready to Ship - Filter Fabrication | LSST Forecast - B57 - B1 | 0 | 0 | 2019-04-17 | 2019-04-17 | 0 | 2019-04-17 | 2019-04-17 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-06-03 | 2019-06-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters | (1.10) Task/item is a modification of an existing design | 7% | Level 4 Milestone | Procurement |  |  | Subcontractor
FALSE |  | SR570470 | RTM09_RTM Qualification at TS5 | LSST Forecast - B57 - B1 | 5 | 0 | 2019-04-17 | 2019-04-30 | 0 | 2019-04-17 | 2019-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-20 | 2019-06-20 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-05-02 | 2019-05-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 9 |  | Complete | 100% | 45 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 45 | 45 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [13 empty] | RTM #9 |  | Science Raft System
FALSE |  | CBM29000 | Perform Verification Testing - Purge Cabinets | LSST Forecast - B57 - B1 | 15 | 15 | 2019-04-21 | 2019-06-21 | 49 | 2019-04-21 |  | 0 | 2019-06-03 | 2019-06-21 | 2019-08-12 | 2019-08-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-05-01 | 2019-05-21 |  |  |  |  | 0.5 | 0 | FALSE | FALSE | None |  | None |  | 2019-06-21 |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 29 |  | InProgress | 50% | 168 | 0 | 168 | 168 | LSST Forecast - B57 - B1.3.06.01.02 | Camera Body Development | 84 | 168 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 15% |  | Testing/Integration |  | Other (specify) | [5 empty] | Camera Body Development (TEC) | [6 empty] | Camera Body and Purge Production
FALSE |  | CCS120310 | Procurement Process - Parts - CCS Computing Equipments for the Summit & Base | LSST Forecast - B57 - B1 | 20 | 10 | 2019-04-21 | 2019-06-14 | 26 | 2019-04-21 |  | 0 | 2019-06-03 | 2019-06-14 | 2019-07-10 | 2019-07-24 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-05-01 | 2019-05-29 |  |  |  |  | 0.8 | 0 | FALSE | FALSE | None |  | None |  | 2019-06-14 |  |  |  |  | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 29 |  | InProgress | 80% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.02.07 | CCS Core 6.0 Release (Comcam Ship) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment |  | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering
FALSE |  | CCS320100 | Modify OCS + CCS Bridge for Use with Camera Rotator - HCU | LSST Forecast - B57 - B1 | 20 | 14 | 2019-04-22 | 2019-06-20 | 8 | 2019-04-22 |  | 0 | 2019-06-03 | 2019-06-20 | 2019-06-13 | 2019-07-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-05-01 | 2019-05-29 |  |  |  |  | 0.5 | 0 | FALSE | FALSE | None |  | None |  | 2019-06-20 |  |  |  |  | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 29 |  | InProgress | 50% | 120 | 0 | 120 | 120 | LSST Forecast - B57 - B1.3.07.01.03.08.05 | Camera Rotator HCU | 60 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | CCS HCU (TEC)
FALSE |  | ITC36210 | RTM11 r1_Disassemble REC | LSST Forecast - B57 - B1 | 5 | 0 | 2019-05-01 | 2019-05-07 | 0 | 2019-05-01 | 2019-05-07 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-18 | 2019-06-18 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-03 | 2019-06-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 4 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.03 | Raft Acceptance Testing | 40 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration
FALSE |  | SR570230 | RTM05_Inspect, Clean & Test RSA | LSST Forecast - B57 - B1 | 4 | 0 | 2019-05-03 | 2019-05-06 | 0 | 2019-05-03 | 2019-05-06 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-30 | 2019-07-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-06-03 | 2019-06-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 1 |  | Complete | 100% | 70 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 70 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [13 empty] | RTM #5 |  | Science Raft System
FALSE |  | SR570130 | RTM03_Inspect, Clean & Test RSA | LSST Forecast - B57 - B1 | 3 | 0 | 2019-05-08 | 2019-05-10 | 0 | 2019-05-08 | 2019-05-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-10 | 2019-07-10 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-06-03 | 2019-06-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 3 | 2 |  | Complete | 100% | 70 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 70 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [13 empty] | RTM #3 |  | Science Raft System
FALSE |  | CCS126400 | Stress test and validate camera body HCU Purge Unit - Camera Body HCU | LSST Forecast - B57 - B1 | 5 | 0 | 2019-05-13 | 2019-05-31 | 0 | 2019-05-13 | 2019-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-19 | 2019-07-19 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-03 | 2019-06-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 13 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.07 | Camera Body HCU | 40 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | CCS HCU (TEC) | [6 empty] | Camera I&T Hardware Control Unit
FALSE |  | SR570360 | RTM07_Inspect, Clean & Test RSA | LSST Forecast - B57 - B1 | 3 | 0 | 2019-05-17 | 2019-05-21 | 0 | 2019-05-17 | 2019-05-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-30 | 2019-07-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-06-03 | 2019-06-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 3 | 2 |  | Complete | 100% | 70 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 70 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [13 empty] | RTM #7 |  | Science Raft System
FALSE |  | SR570650 | RTM12_Inspect, Clean & Test RSA | LSST Forecast - B57 - B1 | 2 | 0 | 2019-05-24 | 2019-05-28 | 0 | 2019-05-24 | 2019-05-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-07 | 2019-08-07 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-06-17 | 2019-06-18 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 1 |  | Complete | 100% | 70 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 70 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [13 empty] | RTM #12 |  | Science Raft System
FALSE |  | CRYO62080 | Requisition - Refrigerant - Chile Hardware | LSST Forecast - B57 - B1 | 20 | 20 | 2019-06-03 | 2019-06-28 | 103 |  |  | 0 | 2019-06-03 | 2019-06-28 | 2019-10-28 | 2019-11-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-03 | 2019-06-28 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.05 | Refrigeration System - Chile System (Equipment & Refrigeration) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  |  | Procurement
FALSE |  | ITC31780 | Camera Verification Analysis Software | LSST Forecast - B57 - B1 | 80 | 80 | 2019-06-03 | 2019-09-24 | 225 |  |  | 243 | 2019-06-03 | 2019-09-24 | 2020-05-05 | 2020-08-26 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-03 | 2019-09-24 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 80 | 0 |  | Planned | 0% | 1005 | 0 | 1005 | 1005 | LSST Forecast - B57 - B1.3.08.02.04 | Verification Software Development | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Other (specify) | [5 empty] | Verification Test Systems (TEC)
FALSE |  | ITC33890 | COTS Procurement - Vendor Lead Time - Cryo-Equip | LSST Forecast - B57 - B1 | 36 | 36 | 2019-06-03 | 2019-07-23 | 36 |  |  | 0 | 2019-06-03 | 2019-07-23 | 2019-07-24 | 2019-09-12 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-03 | 2019-07-23 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None |  | 2019-07-23 |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 36 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.02 | Cryostat Handling Equipment | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [13 empty] | CP #12 (Cryo Equip)
FALSE |  | ITC33920 | Outside Fabrication - Vendor Lead Time - Cryo-Equip | LSST Forecast - B57 - B1 | 36 | 36 | 2019-06-03 | 2019-07-23 | 36 |  |  | 0 | 2019-06-03 | 2019-07-23 | 2019-07-24 | 2019-09-12 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-03 | 2019-07-23 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None |  | 2019-07-23 |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 36 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.02 | Cryostat Handling Equipment | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [13 empty] | CP #12 (Cryo Equip)
FALSE |  | DAQ920050 | Server-Side Implementation & Test (Software) | LSST Forecast - B57 - B1 | 30 | 30 | 2019-06-03 | 2019-07-15 | 275 |  |  | 0 | 2019-06-03 | 2019-07-15 | 2020-07-16 | 2020-08-26 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-03 | 2019-07-15 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 0 |  | Planned | 0% | 40 | 0 | 40 | 40 | LSST Forecast - B57 - B1.3.07.02.02.16 | Remote FPGA Reprogramming | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Testing/Integration |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | DAQ Readout Systems (TEC)
FALSE |  | SR570700 | RTM13_Inspect, Clean & Test RSA | LSST Forecast - B57 - B1 | 1 | 1 | 2019-06-03 | 2019-06-03 | 51 |  |  | 0 | 2019-06-03 | 2019-06-03 | 2019-08-14 | 2019-08-14 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-06-03 | 2019-06-03 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None |  | 2019-05-28 |  |  |  |  | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Planned | 0% | 70 | 0 | 70 | 70 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [13 empty] | RTM #13 |  | Science Raft System
FALSE |  | ITC36110 | TS7-2 Modifiaction & Qualification | LSST Forecast - B57 - B1 | 22 | 22 | 2019-06-03 | 2019-07-02 | 573 |  |  | 361 | 2019-06-03 | 2019-07-02 | 2021-09-30 | 2021-10-29 | 6000 | 6000 | 0 | 6000 | 6000 | 1 | FALSE | Normal | FALSE | 2019-06-03 | 2019-07-02 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 22 | 0 |  | Planned | 0% | 40 | 0 | 40 | 40 | LSST Forecast - B57 - B1.3.08.03.03 | Raft Acceptance Testing | 0 | 0 | 0 | 0 | 0 | 6000 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC)
FALSE |  | ITC36120 | REB Re-Testing effort | LSST Forecast - B57 - B1 | 64 | 64 | 2019-06-03 | 2019-08-30 | 531 |  |  | 319 | 2019-06-03 | 2019-08-30 | 2021-08-02 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-03 | 2019-08-30 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 64 | 0 |  | Planned | 0% | 96 | 0 | 96 | 96 | LSST Forecast - B57 - B1.3.08.03.03 | Raft Acceptance Testing | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC)
FALSE |  | OP541386 | RCV: L3 Assembly - Phase 4 (L3 Clean Room Testing) | LSST Forecast - B57 - B1 | 20 | 20 | 2019-06-03 | 2019-06-28 | 121 |  |  | 146 | 2019-06-03 | 2019-06-28 | 2019-11-21 | 2019-12-20 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-03 | 2019-06-28 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement | [7 empty] | L3 Assembly (TEC)
FALSE |  | CCS300110 | Re Program CCS with Holding Pump Logic | LSST Forecast - B57 - B1 | 2 | 2 | 2019-06-06 | 2019-06-07 | 27 |  |  | 0 | 2019-06-06 | 2019-06-07 | 2019-07-16 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-06 | 2019-06-07 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.08.03 | CCOB HCU | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Martin Nordby
FALSE |  | CCS300040 | Second release of full focal plane software in IR2 with support for 9+ rafts | LSST Forecast - B57 - B1 | 41 | 41 | 2019-06-10 | 2019-08-06 | -9 |  |  | 0 | 2019-06-10 | 2019-08-06 | 2019-05-28 | 2019-07-24 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-06-10 | 2019-08-06 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 41 | 0 |  | Planned | 0% | 360 | 0 | 360 | 360 | LSST Forecast - B57 - B1.3.07.01.03.08.03 | CCOB HCU | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | CCS HCU (TEC) | [7 empty] | CP #02 (CCS Focal Plane Software)
FALSE |  | OP522490_1 | RCV: 3 of 6 Filter Complete and Ready to Ship (MS5) - Filter Fabrication | LSST Forecast - B57 - B1 | 1 | 1 | 2019-06-14 | 2019-06-14 | 245 |  |  | 82 | 2019-06-14 | 2019-06-14 | 2020-06-05 | 2020-06-05 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-14 | 2019-06-14 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | 0-100% Method | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Filters (TEC)
FALSE |  | CAMF669245 | Combined Test Assembly (Carousel + Loader 1+ Auto Changer 1) | LSST Forecast - B57 - B1 | 4 | 4 | 2019-06-25 | 2019-06-28 | -159 |  |  | 0 | 2019-06-25 | 2019-06-28 | 2018-10-24 | 2018-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-25 | 2019-06-28 |  |  |  |  | 0 | 0 | FALSE | FALSE | StartOnOrAfter | 2019-06-25 | None | [6 empty] | 6 | 0 | 5 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Fabrication/Assembly
FALSE |  | CCS300050 | M/S - CCOB HCU | LSST Forecast - B57 - B1 | 20 | 20 | 2019-07-10 | 2019-08-06 | 69 |  |  | 0 | 2019-07-10 | 2019-08-06 | 2019-10-16 | 2019-11-13 | 4000 | 4000 | 0 | 4000 | 4000 | 1 | FALSE | Normal | FALSE | 2019-07-10 | 2019-08-06 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.08.03 | CCOB HCU | 0 | 0 | 0 | 0 | 0 | 4000 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 4% |  | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | CCS HCU (TEC) | [6 empty] | Camera I&T Hardware Control Unit
FALSE |  | OP522490_2 | RCV: 4 of 6 Filter Complete and Ready to Ship (MS5) - Filter Fabrication | LSST Forecast - B57 - B1 | 1 | 1 | 2019-07-23 | 2019-07-23 | 219 |  |  | 56 | 2019-07-23 | 2019-07-23 | 2020-06-05 | 2020-06-05 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-07-23 | 2019-07-23 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | 0-100% Method | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Filters (TEC)
FALSE |  | CCS107000 | Implement Release 2 - Lock Manager | LSST Forecast - B57 - B1 | 30 | 30 | 2019-07-30 | 2019-09-10 | 159 |  |  | 0 | 2019-07-30 | 2019-09-10 | 2020-03-30 | 2020-05-08 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-07-30 | 2019-09-10 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 0 |  | Planned | 0% | 400 | 0 | 400 | 400 | LSST Forecast - B57 - B1.3.07.01.02.05 | CCS Lock Manager | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering | [7 empty] | CCS Core (TEC)
FALSE |  | CRYO73280 | Assemble - Hx and Capillaries - Cryo - Chile System | LSST Forecast - B57 - B1 | 20 | 20 | 2019-08-05 | 2019-08-30 | 10 |  |  | 0 | 2019-08-05 | 2019-08-30 | 2019-08-19 | 2019-09-16 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-08-05 | 2019-08-30 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 16 | 0 | 16 | 16 | LSST Forecast - B57 - B1.3.06.04.06.03.04 | Refrigeration System - Chile System (HX) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC) | [7 empty] | CP #09 (Cryo Chile System for Ready for UT)
FALSE |  | CCS120360 | RCV: Parts - CCS Computing Equipments for the Summit & Base (Other) | LSST Forecast - B57 - B1 | 20 | 20 | 2019-08-19 | 2019-09-16 | 594 |  |  | 0 | 2019-08-19 | 2019-09-16 | 2022-02-01 | 2022-03-01 | 154000 | 154000 | 0 | 154000 | 154000 | 1 | FALSE | Normal | FALSE | 2019-08-19 | 2019-09-16 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.02.07 | CCS Core 6.0 Release (Comcam Ship) | 0 | 0 | 0 | 0 | 0 | 154000 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering | [7 empty] | CCS Core (TEC)
FALSE |  | DAQ338700 | Design Prototype (blocks, interfaces, coding, review prep) - Crosstalk Correction Firmware | LSST Forecast - B57 - B1 | 20 | 20 | 2019-09-03 | 2019-09-30 | 4 |  |  | 0 | 2019-09-03 | 2019-09-30 | 2019-09-09 | 2019-10-04 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-09-03 | 2019-09-30 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 160 | 0 | 160 | 160 | LSST Forecast - B57 - B1.3.07.02.02.08 | Crosstalk Correction Firmware | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | DAQ Readout Systems (TEC) |  | ICD's for Phase 3 |  |  |  |  | DAQ Readout Systems | CP #07 (DAQ Crosstalk Correction)
FALSE |  | OP522490_3 | RCV: 5 of 6 Filter Complete and Ready to Ship (MS5) - Filter Fabrication | LSST Forecast - B57 - B1 | 1 | 1 | 2019-09-09 | 2019-09-09 | 186 |  |  | 23 | 2019-09-09 | 2019-09-09 | 2020-06-05 | 2020-06-05 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-09-09 | 2019-09-09 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | 0-100% Method | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Filters (TEC)
FALSE |  | CR222420 | CRTM#5 - Test - CRTM Performance test and optimization | LSST Forecast - B57 - B1 | 10 | 10 | 2019-09-18 | 2019-10-01 | 510 |  |  | 0 | 2019-09-18 | 2019-10-01 | 2021-10-18 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-09-18 | 2019-10-01 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 0 |  | Planned | 0% | 120 | 0 | 120 | 120 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Testing/Integration |  | Other (specify) | [5 empty] | Corner Raft Tower Module (CRTM) (TEC) | CRTM Assy CRT | [5 empty] | Corner Raft Tower Module (CRTM)
FALSE |  | OP522490_4 | RCV: 6 of 6 Filter Complete and Ready to Ship (MS5) - Filter Fabrication | LSST Forecast - B57 - B1 | 1 | 1 | 2019-10-10 | 2019-10-10 | 163 |  |  | 0 | 2019-10-10 | 2019-10-10 | 2020-06-05 | 2020-06-05 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-10-10 | 2019-10-10 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | 0-100% Method | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Filters (TEC)
FALSE |  | OP522800 | Mount filters in frame - Remaining filter | LSST Forecast - B57 - B1 | 60 | 60 | 2020-01-08 | 2020-04-02 | 107 |  |  | 0 | 2020-01-08 | 2020-04-02 | 2020-06-10 | 2020-09-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2020-01-08 | 2020-04-02 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 0 |  | Planned | 0% | 346 | 0 | 346 | 346 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 18% |  | Testing/Integration |  | Other (specify) | [5 empty] | Filters (TEC) | Production Filters Polish and integration | [5 empty] | Filter Opto-Mechanics
FALSE |  | CAMF2470 | Outstanding Performance Annual Bonus FY20 | LSST Forecast - B57 - B1 | 19 | 19 | 2020-02-03 | 2020-02-28 | 509 |  |  | 205 | 2020-02-03 | 2020-02-28 | 2022-03-03 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2020-02-03 | 2020-02-28 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 19 | 0 |  | Planned | 0% | 287 | 0 | 287 | 287 | LSST Forecast - B57 - B1.3.01.01.01 | Project Office | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 0% |  | Management/Administration |  | Project Management (cost estimating, scheduling, project controls, Risk assessment) | [5 empty] | Project Management (TEC)
FALSE |  | ITC98080 | I&T Sust Engineering - Project Extension | LSST Forecast - B57 - B1 | 86 | 86 | 2020-03-02 | 2020-06-30 | 423 |  |  | 119 | 2020-03-02 | 2020-06-30 | 2021-11-10 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2020-03-02 | 2020-06-30 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 86 | 0 |  | Planned | 0% | 242 | 0 | 242 | 242 | LSST Forecast - B57 - B1.3.08.01 | I&T Integration & Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Drtn | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Construction Management | [5 empty] | Integration & Testing (TEC)
FALSE |  | CAMM1060 | COMP: CD-4, Approve Project Completion | LSST Forecast - B57 - B1 | 0 | 0 | 2021-03-17 | 2021-03-17 | 252 |  |  | 0 | 2021-03-17 | 2021-03-17 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 0 | FALSE | Finish Milestone | TRUE | 2021-03-17 | 2021-03-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | FinishOnOrBefore | 2022-03-31 | None | [6 empty] | 17 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  |  | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.01 | DOE Project Milestones | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 1 Milestone | Management/Administration
Merge Hotspot
The total number of activities with a high number of predecessor links.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | Previous Start | Previous Finish | Percent Complete | Previous Remaining Duration | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | IsLevelOfEffort | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | Global_Basis of Estimate | Global_Cobra Cost Class | Cobra PMT (EV Method)_Global | Global_Color of Money | Global_Control Account Manager | Global_Design Maturity | Global_Judgement Factor | Global_Milestone Levels | Global_Project Phase | Global_Funding Source | Global_EDIA Survey | Global_MS Type | Phase | NSF Milestones | Loading Curve | Sensor Vendor | LSST_CA | Summary Schedule | ICD for NSF Input | LSST Camera Critical Paths | CD2 Budget Changes | DOE Reviews | Critical Path (CD Reviews) | LSST WP Summary | Critical Path (Camera Delivery) | AWARD / NEED Sub-System | Final Design Key Links | CP - CAMM2100 | CP - CAMM2130 | CP - CAMM2160 | BNL Work Org | Last ETC Update | BNL WBS | LSST Story List | Sum Sch 01 (Camera) | Sum Sch 02 (IT w/Needs) | Sum Sch 03 (Sensors_RTM_IT) | LSST Raft Particulate Mitigation | LSST RTM
FALSE |  | SE222025 | Prep for C_CDR - Mechanical Integration | LSST Forecast - B57 - B1 | 286 | 0 | 2010-10-01 | 2011-12-01 | 0 | 2010-10-01 | 2011-12-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2010-10-01 | 2011-12-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 286 | 285 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.02 | Mechanical Integration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  |  | Development (includes R&D)
FALSE |  | CBM41000 | Prep for Comp. Conceptual Design Review | LSST Forecast - B57 - B1 | 10 | 0 | 2011-03-11 | 2011-03-24 | 0 | 2011-03-11 | 2011-03-24 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2011-03-11 | 2011-03-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.02.02 | Shutter Development | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Martin Nordby |  |  |  | Development (includes R&D)
FALSE |  | CAMF658550 | COMP: C_CDR - Auto Changer | LSST Forecast - B57 - B1 | 0 | 0 | 2011-03-25 | 2011-03-25 | 0 | 2011-03-25 | 2011-03-25 | 0 | 2019-06-01 | 2019-06-01 | 2018-10-16 | 2018-10-16 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | FALSE | 2011-03-25 | 2011-03-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.01 | Auto Changer | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  | Level 4 Milestone | Development (includes R&D)
FALSE |  | CBM21200 | COMP: C_CDR - Camera Body | LSST Forecast - B57 - B1 | 0 | 0 | 2011-03-25 | 2011-03-25 | 0 | 2011-03-25 | 2011-03-25 | 0 | 2019-06-01 | 2019-06-01 | 2018-09-07 | 2018-09-07 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Finish Milestone | FALSE | 2011-03-25 | 2011-03-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.01.02 | Camera Body Development | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Martin Nordby |  |  | Level 4 Milestone | Development (includes R&D)
FALSE |  | CAMF662250 | Prep for Comp. Conceptual Design Review - Filter Loader | LSST Forecast - B57 - B1 | 10 | 0 | 2011-04-08 | 2011-04-21 | 0 | 2011-04-08 | 2011-04-21 | 0 | 2019-06-01 | 2019-06-01 | 2018-10-16 | 2018-10-16 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2011-04-08 | 2011-04-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.02 | Filter Loader | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Development (includes R&D)
FALSE |  | CRYO00100 | COMP: Ready for NSF FDR - Cryostat | LSST Forecast - B57 - B1 | 0 | 0 | 2011-08-11 | 2011-08-11 | 0 | 2011-08-11 | 2011-08-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2011-08-11 | 2011-08-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 11 | 0 | 11 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04 | Cryostat | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 3 Milestone | Management/Administration
FALSE |  | CAMF650050 | COMP: Ready for CD-1 - Exchange System | LSST Forecast - B57 - B1 | 0 | 0 | 2011-08-18 | 2011-08-18 | 0 | 2011-08-18 | 2011-08-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2011-08-18 | 2011-08-18 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03 | Exchange System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  | Level 3 Milestone | Management/Administration
FALSE |  | CRYO00150 | COMP: Ready for CD-1 - Cryostat | LSST Forecast - B57 - B1 | 0 | 0 | 2011-08-18 | 2011-08-18 | 0 | 2011-08-18 | 2011-08-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2011-08-18 | 2011-08-18 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 14 | 0 | 14 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04 | Cryostat | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 3 Milestone | Management/Administration
FALSE |  | OP00100 | COMP: Ready for CD-1 - Optics | LSST Forecast - B57 - B1 | 0 | 0 | 2011-08-18 | 2011-08-18 | 0 | 2011-08-18 | 2011-08-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2011-08-18 | 2011-08-18 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05 | Optics | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  | Level 3 Milestone | Management/Administration
FALSE |  | OP10925 | C_CDR - Optics | LSST Forecast - B57 - B1 | 1 | 0 | 2011-08-18 | 2011-08-18 | 0 | 2011-08-18 | 2011-08-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2011-08-18 | 2011-08-18 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.01 | Optics Integration & Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  |  | Development (includes R&D)
FALSE |  | CAMF5100 | QA Technical Support FY12 | LSST Forecast - B57 - B1 | 242 | 0 | 2011-10-01 | 2012-09-28 | 0 | 2011-10-01 | 2012-09-28 | 0 | 2019-06-01 | 2019-06-01 | 2021-11-12 | 2021-11-12 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2011-10-03 | 2012-09-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 242 | 241 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01.03.02 | Quality Assurance | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Drtn |  |  |  | OPC Non-ARRA | Vincent Riot | (1.00) Task/item is fully invoiced/completed | 0% |  | Management/Administration |  | QA Inspection/Testing/Acceptance | [12 empty] | Performance Safety & Assurance
FALSE |  | CR010140 | COMP: Ready for CD-1 - Corner Raft | LSST Forecast - B57 - B1 | 0 | 0 | 2011-11-30 | 2011-11-30 | 0 | 2011-11-30 | 2011-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2011-11-30 | 2011-11-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02 | Corner Raft System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 3 Milestone | Management/Administration
FALSE |  | CAMC01000 | COMP: Ready for CD-1 Lehman Review - Camera | LSST Forecast - B57 - B1 | 0 | 0 | 2011-11-30 | 2011-11-30 | 0 | 2011-11-30 | 2011-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | FALSE | 2011-11-30 | 2011-11-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 7 | 0 | 0 | 0 | 3 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01 | Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 3 Milestone | Management/Administration
FALSE |  | CRYO52100 | COMP: Phase 3b ETU Refrigeration System | LSST Forecast - B57 - B1 | 0 | 0 | 2012-10-01 | 2012-10-01 | 0 | 2012-10-01 | 2012-10-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | FALSE | 2012-10-01 | 2012-10-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Engineering Test/Validation
FALSE |  | CRYO51520 | Phase 3 ETU Review Heat Exchanger & Stand | LSST Forecast - B57 - B1 | 5 | 0 | 2013-01-15 | 2013-01-21 | 0 | 2013-01-15 | 2013-01-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2013-01-15 | 2013-01-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 4 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | OPC Non-ARRA | Brian J. Langton | (1.00) Task/item is fully invoiced/completed | 0% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Refrigeration System
FALSE |  | SR343070 | Bench Test Raft Electronics Board 1 | LSST Forecast - B57 - B1 | 209 | 0 | 2013-03-04 | 2013-12-30 | 0 | 2013-03-04 | 2013-12-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2013-03-04 | 2013-12-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 209 | 208 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | OPC Non-ARRA | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 0% |  | Development (includes R&D) | [14 empty] | Science Raft Electronics | [6 empty] | Raft Electronics Board 1 |  | Science Raft System
FALSE |  | SE223020 | Thermal Analysis of Loaded Cryostat - SE | LSST Forecast - B57 - B1 | 106 | 0 | 2013-04-01 | 2013-08-28 | 0 | 2013-04-01 | 2013-08-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2013-04-01 | 2013-08-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 106 | 105 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.03 | Thermal and contamination system analysis | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot | (1.00) Task/item is fully invoiced/completed | 0% |  | Development (includes R&D) |  | Design Management | [12 empty] | System Analysis
FALSE |  | SE223040 | Assess impact of Cryo, Exch, Shtr prelim design and power budget changes/ heat loads on camera thermal design - SE | LSST Forecast - B57 - B1 | 22 | 0 | 2013-04-01 | 2013-04-30 | 0 | 2013-04-01 | 2013-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2013-04-01 | 2013-04-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 5 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 22 | 21 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.03 | Thermal and contamination system analysis | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot | (1.00) Task/item is fully invoiced/completed | 0% |  | Development (includes R&D) |  | Design Management
FALSE |  | SE222070 | Preliminary Science Raft - Mechanical Integration | LSST Forecast - B57 - B1 | 38 | 0 | 2013-07-01 | 2013-08-22 | 0 | 2013-07-01 | 2013-08-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2013-07-01 | 2013-08-22 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 38 | 37 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.02 | Mechanical Integration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  |  | Development (includes R&D)
FALSE |  | SR342110 | Design - CABAC 1 | LSST Forecast - B57 - B1 | 202 | 0 | 2013-07-08 | 2014-04-25 | 0 | 2013-07-08 | 2014-04-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2013-07-08 | 2014-04-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 202 | 201 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.02 | CABAC | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | OPC Non-ARRA | Bill Wahl | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Engineering Test/Validation | [14 empty] | Science Raft Electronics | [8 empty] | Science Raft System
FALSE |  | SR331035 | Prep for C_PDR - RSA | LSST Forecast - B57 - B1 | 39 | 0 | 2013-07-15 | 2013-09-06 | 0 | 2013-07-15 | 2013-09-06 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2013-07-15 | 2013-09-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 0 | 3 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 39 | 38 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.02 | Science Raft Sensor Assembly (SRSA) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | OPC Non-ARRA | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 0% |  | Development (includes R&D) |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Raft Sensor Assembly (RSA) | [8 empty] | Science Raft System
FALSE |  | SR000020 | COMP: Ready for CD-2 - Science Raft System | LSST Forecast - B57 - B1 | 0 | 0 | 2013-09-10 | 2013-09-10 | 0 | 2013-09-10 | 2013-09-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2013-09-10 | 2013-09-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01 | Science Raft System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Bill Wahl |  |  | Level 3 Milestone | Management/Administration | [23 empty] | Science Raft System
FALSE |  | SR343120 | Design - Raft Electronics Board 2 (REB2) | LSST Forecast - B57 - B1 | 100 | 0 | 2013-10-01 | 2014-02-26 | 0 | 2013-10-01 | 2014-02-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2013-10-01 | 2014-02-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 100 | 99 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | OPC Non-ARRA | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 0% |  | Engineering Test/Validation | [14 empty] | Science Raft Electronics | [6 empty] | Raft Electronics Board 2 |  | Science Raft System
FALSE |  | CAMF659050 | Prep for Prelim Design Review - Auto Changer | LSST Forecast - B57 - B1 | 2 | 0 | 2013-11-02 | 2013-11-03 | 0 | 2013-11-02 | 2013-11-03 | 0 | 2019-06-01 | 2019-06-01 | 2018-10-16 | 2018-10-16 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2013-11-04 | 2013-11-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.01 | Auto Changer | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Design/Engineering
FALSE |  | CAMF662850 | Prep for Prelim Design Review - Filter Loader | LSST Forecast - B57 - B1 | 2 | 0 | 2013-11-02 | 2013-11-03 | 0 | 2013-11-02 | 2013-11-03 | 0 | 2019-06-01 | 2019-06-01 | 2018-10-16 | 2018-10-16 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2013-11-04 | 2013-11-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.02 | Filter Loader | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Design/Engineering
FALSE |  | CAMF666650 | Prep for Prelim Design Review - Carousel | LSST Forecast - B57 - B1 | 2 | 0 | 2013-11-02 | 2013-11-03 | 0 | 2013-11-02 | 2013-11-03 | 0 | 2019-06-01 | 2019-06-01 | 2018-10-16 | 2018-10-16 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2013-11-04 | 2013-11-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Design/Engineering
FALSE |  | CAMF659150 | COMP: C_PDR - Auto Changer | LSST Forecast - B57 - B1 | 0 | 0 | 2013-11-05 | 2013-11-05 | 0 | 2013-11-05 | 2013-11-05 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 6 | FALSE | Finish Milestone | FALSE | 2013-11-05 | 2013-11-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.01 | Auto Changer | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  | Level 4 Milestone | Design/Engineering
FALSE |  | SE222075 | Preliminary Filter/Exchange System - Mechanical Integration | LSST Forecast - B57 - B1 | 81 | 0 | 2014-01-03 | 2014-04-30 | 0 | 2014-01-03 | 2014-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2018-10-16 | 2018-10-16 | 0 | 0 | 0 | 0 | 0 | 5 | FALSE | Normal | FALSE | 2014-01-06 | 2014-04-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 81 | 80 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.02 | Mechanical Integration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  |  | Development (includes R&D)
FALSE |  | CRYO11260 | Preliminary Eng & Analysis A - Cryostat Assembly | LSST Forecast - B57 - B1 | 107 | 0 | 2014-03-01 | 2014-07-31 | 0 | 2014-03-01 | 2014-07-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2014-03-03 | 2014-07-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 107 | 106 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | TEC Non-ARRA | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Cryostat Assembly
FALSE |  | SR522475 | TS2 - MF05a (sensor removal fixture) - generate prototype analysis report | LSST Forecast - B57 - B1 | 78 | 0 | 2014-03-24 | 2014-07-11 | 0 | 2014-03-24 | 2014-07-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2014-03-24 | 2014-07-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 2 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 78 | 77 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.02 | Sensor Dimensional Metrology (TS2) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [6 empty] | Test Stand Effort | [5 empty] | Science Sensors Test Stands | [8 empty] | Science Sensors
FALSE |  | CBM22500 | Prep for Prelim Design Review - Camera Body | LSST Forecast - B57 - B1 | 29 | 0 | 2014-04-15 | 2014-05-23 | 0 | 2014-04-15 | 2014-05-23 | 0 | 2019-06-01 | 2019-06-01 | 2018-09-07 | 2018-09-07 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-04-15 | 2014-05-23 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 29 | 28 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.01.02 | Camera Body Development | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | TEC Non-ARRA | Martin Nordby | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Cam Body/Purge Engin/Dsn
FALSE |  | CBM42400 | Prep for Prelim Design Review - Shutter | LSST Forecast - B57 - B1 | 31 | 0 | 2014-04-15 | 2014-05-28 | 0 | 2014-04-15 | 2014-05-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-04-15 | 2014-05-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 31 | 30 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.02.02 | Shutter Development | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | TEC Non-ARRA | Martin Nordby | (1.00) Task/item is fully invoiced/completed | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Shutter Engin/Dsn
FALSE |  | OP520200 | Prep for C_PDR - Filter Assembly | LSST Forecast - B57 - B1 | 48 | 0 | 2014-05-17 | 2014-07-25 | 0 | 2014-05-17 | 2014-07-25 | 0 | 2019-06-01 | 2019-06-01 | 2018-10-30 | 2018-10-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-05-19 | 2014-07-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 2 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 48 | 47 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | OPC Non-ARRA | Scott Winters | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [6 empty] | Filter Design | [5 empty] | Filter Opto-Mechanics
FALSE |  | CAMF650100 | COMP: Ready for PDR - Exchange System | LSST Forecast - B57 - B1 | 0 | 0 | 2014-05-23 | 2014-05-23 | 0 | 2014-05-23 | 2014-05-23 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2014-05-23 | 2014-05-23 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03 | Exchange System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  | Level 3 Milestone | Management/Administration
FALSE |  | OP11050 | Support Prep for C_PDR--Optics - Management (need links to all PDRs) | LSST Forecast - B57 - B1 | 41 | 0 | 2014-05-29 | 2014-07-25 | 0 | 2014-05-29 | 2014-07-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2014-05-29 | 2014-07-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 41 | 40 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.01 | Optics Integration & Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | OPC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Optics System Management
FALSE |  | SR552220 | Documentation - Update Camera Design Manuel (Sensors and RTM chapters) | LSST Forecast - B57 - B1 | 43 | 0 | 2014-06-02 | 2014-07-31 | 0 | 2014-06-02 | 2014-07-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-06-02 | 2014-07-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 43 | 42 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.01 | Science Raft Tower Module (SRTM) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment |  | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering | [14 empty] | Science Raft - Test Stands | [8 empty] | Science Raft System
FALSE |  | SR529900 | Procurement - prototype components | LSST Forecast - B57 - B1 | 22 | 0 | 2014-07-01 | 2014-07-31 | 0 | 2014-07-01 | 2014-07-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-07-01 | 2014-07-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 0 | 4 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 22 | 21 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.05 | RTM Electro-Optical Testing (TS8) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment |  | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering | [14 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 8 - Design |  | Science Raft System
FALSE |  | SR522480 | COMP: TS2 - MF05a (sensor removal fixture) prototype | LSST Forecast - B57 - B1 | 0 | 0 | 2014-07-11 | 2014-07-11 | 0 | 2014-07-11 | 2014-07-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2014-07-11 | 2014-07-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.02 | Sensor Dimensional Metrology (TS2) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Bill Wahl |  |  | Level 4 Milestone | Engineering Test/Validation | [8 empty] | Test Stand Effort | [14 empty] | Science Sensors
FALSE |  | SR343170 | Performance bench test of REB2 | LSST Forecast - B57 - B1 | 14 | 0 | 2014-07-14 | 2014-07-31 | 0 | 2014-07-14 | 2014-07-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-11-19 | 2020-11-19 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-07-14 | 2014-07-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 2 | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 14 | 13 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | TEC Non-ARRA | Bill Wahl | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Engineering Test/Validation | [14 empty] | Science Raft Electronics | [6 empty] | Raft Electronics Board 2 |  | Science Raft System
FALSE |  | OP540180 | C_PDR--L3 Opto-Mechanics | LSST Forecast - B57 - B1 | 2 | 0 | 2014-07-28 | 2014-07-29 | 0 | 2014-07-28 | 2014-07-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-07-28 | 2014-07-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 1 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  |  | Design/Engineering
FALSE |  | CAMF650150 | COMP: Ready for CD-2 - Exchange System | LSST Forecast - B57 - B1 | 0 | 0 | 2014-08-01 | 2014-08-01 | 0 | 2014-08-01 | 2014-08-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2014-08-01 | 2014-08-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03 | Exchange System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  | Level 3 Milestone | Management/Administration
FALSE |  | SR552180 | Documentation - Finalize requirments | LSST Forecast - B57 - B1 | 124 | 0 | 2014-08-01 | 2015-01-30 | 0 | 2014-08-01 | 2015-01-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2014-08-01 | 2015-01-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 4 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 124 | 123 |  | Complete | 100% | 320 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.01 | Science Raft Tower Module (SRTM) | 320 | 320 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Science Raft Tower Module (SRTM) (TEC) | [6 empty] | Science Raft - Test Stands | [8 empty] | Science Raft System
FALSE |  | SR551850 | Prepare RSA Test Plan | LSST Forecast - B57 - B1 | 16 | 0 | 2014-08-01 | 2014-08-22 | 0 | 2014-08-01 | 2014-08-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-08-01 | 2014-08-22 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 16 | 0 | 16 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 16 | 15 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.02 | Science Raft Sensor Assembly (SRSA) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation |  | Construction Management | [5 empty] | Science Raft Tower Module (SRTM) (TEC) | [6 empty] | Science Raft - Test Stands | [8 empty] | Science Raft System
FALSE |  | SR344040 | Final Design and Layout | LSST Forecast - B57 - B1 | 165 | 0 | 2014-08-01 | 2015-03-31 | 0 | 2014-08-01 | 2015-03-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2014-08-01 | 2015-03-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 15 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 165 | 164 |  | Complete | 100% | 160 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.07.01 | Cleanroom Development & Commissioning | 160 | 160 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Assembly and Test Facility (TEC) | [15 empty] | Science Raft System
FALSE |  | CR211120 | Final Update for CD CD-2 - Corner Raft ICD's | LSST Forecast - B57 - B1 | 54 | 0 | 2014-08-01 | 2014-10-16 | 0 | 2014-08-01 | 2014-10-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-08-01 | 2014-10-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 54 | 53 |  | Complete | 100% | 30 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.01 | Corner Raft System Integration and Management | 30 | 30 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft System Integration and Management (TEC) | Management | [5 empty] | Corner Raft System Integration and Management
FALSE |  | CRYO60550 | Prep for Prelim Design Review - Refrigeration System | LSST Forecast - B57 - B1 | 15 | 0 | 2014-08-02 | 2014-08-22 | 0 | 2014-08-02 | 2014-08-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-08-04 | 2014-08-22 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 7 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 14 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | TEC Non-ARRA | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Refrigeration System
FALSE |  | SR530170 | TS7 - generate final test stand requirements document | LSST Forecast - B57 - B1 | 82 | 0 | 2014-08-02 | 2014-11-28 | 0 | 2014-08-02 | 2014-11-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2014-08-04 | 2014-11-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 82 | 82 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.04 | RTM Cryostat Integration (TS7) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 7 - Design |  | Science Raft System
FALSE |  | CRYO11300 | Prep for Preliminary Review - Cryostat Assembly | LSST Forecast - B57 - B1 | 15 | 0 | 2014-08-10 | 2014-08-31 | 0 | 2014-08-10 | 2014-08-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-08-11 | 2014-08-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 15 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Cryostat Assembly
FALSE |  | CRYO21450 | C_PDR - Prelim Design Review - Grid Assembly | LSST Forecast - B57 - B1 | 1 | 0 | 2014-08-24 | 2014-08-24 | 0 | 2014-08-24 | 2014-08-24 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-08-25 | 2014-08-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.04 | Grid Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Brian J. Langton | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Grid Assembly
FALSE |  | SE223060 | Sub-system PDR camera thermal integrated analysis - camera internal & purge | LSST Forecast - B57 - B1 | 137 | 0 | 2014-08-27 | 2015-02-06 | 0 | 2014-08-27 | 2015-02-06 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2014-08-27 | 2015-03-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 137 | 103 |  | Complete | 100% | 200 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.03 | Thermal and contamination system analysis | 200 | 200 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | CR211360 | Prep for C_PDR - Corner Raft | LSST Forecast - B57 - B1 | 20 | 0 | 2014-08-29 | 2014-09-26 | 0 | 2014-08-29 | 2014-09-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-08-29 | 2014-09-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 12 | 0 | 3 | 0 | 0 | 9 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 19 |  | Complete | 100% | 48 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.01 | Corner Raft System Integration and Management | 48 | 48 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft System Integration and Management (TEC) | Management | [5 empty] | Corner Raft System Integration and Management
FALSE |  | OP531670 | RCV: Anti-Reflection Coating Study (Vendor 1) | LSST Forecast - B57 - B1 | 1 | 0 | 2014-08-29 | 2014-08-29 | 0 | 2014-08-29 | 2014-08-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 34686 | 34686 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-08-29 | 2014-08-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 34686 | 34686 | 0 | PercentComplete | 6% | CP_Phys | Existing Lien | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Engineering Test/Validation | [7 empty] | L1-L2 Assembly (TEC)
FALSE |  | ITC24250 | Prep for C_CDR--BOT | LSST Forecast - B57 - B1 | 21 | 0 | 2014-09-01 | 2014-09-30 | 0 | 2014-09-01 | 2014-09-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2014-09-02 | 2014-09-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 2 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 21 | 20 |  | Complete | 100% | 16 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.02.01 | Bench For Optical Testing (BOT) | 16 | 16 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 13% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC) | [6 empty] | Verification Test Systems
FALSE |  | SR552370 | Fabrication - RTM Qualificaiton Unit | LSST Forecast - B57 - B1 | 9 | 0 | 2014-09-05 | 2014-09-17 | 0 | 2014-09-05 | 2014-09-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2014-09-05 | 2014-09-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 13 | 0 | 13 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 9 | 9 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.01 | Science Raft Tower Module (SRTM) | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation |  | R&D | [5 empty] | Science Raft Tower Module (SRTM) (TEC) | [6 empty] | Science Raft - Test Stands | [8 empty] | Science Raft System
FALSE |  | CRYO13325 | COMP: Preliminary Design/Analysis - Cryostat Housing | LSST Forecast - B57 - B1 | 0 | 0 | 2014-09-15 | 2014-09-15 | 0 | 2014-09-15 | 2014-09-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2014-09-15 | 2014-09-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.01 | Cryostat Housing | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Design/Engineering
FALSE |  | ITC22080 | Prep for C_CDR--MTF | LSST Forecast - B57 - B1 | 11 | 0 | 2014-09-16 | 2014-09-30 | 0 | 2014-09-16 | 2014-09-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2014-09-16 | 2014-09-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 11 | 10 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.01.03 | Vacuum Qualification Tests | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC) | [6 empty] | Verification Test Systems
FALSE |  | CR240200 | Prep for Prelim Design Review - WEB | LSST Forecast - B57 - B1 | 5 | 0 | 2014-09-22 | 2014-09-26 | 0 | 2014-09-22 | 2014-09-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-09-22 | 2014-09-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 4 |  | Complete | 100% | 48 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.01 | Wavefront Electronics Board (WEB) | 48 | 48 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Design Reviews | [5 empty] | Corner Raft Electronics (TEC) | WEB Prototype | [5 empty] | Corner Raft Electronics
FALSE |  | CR241580 | Prep for Prelim Design Review - GEB | LSST Forecast - B57 - B1 | 5 | 0 | 2014-09-22 | 2014-09-26 | 0 | 2014-09-22 | 2014-09-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-09-22 | 2014-09-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 4 |  | Complete | 100% | 48 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.02 | Guider Electronics Board (GEB) | 48 | 48 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Design Reviews | [5 empty] | Corner Raft Electronics (TEC) | GEB Prototype | [5 empty] | Corner Raft Electronics
FALSE |  | CR234130 | Prep for C_PDR - Wavefront Sensor | LSST Forecast - B57 - B1 | 5 | 0 | 2014-09-22 | 2014-09-26 | 0 | 2014-09-22 | 2014-09-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-09-22 | 2014-09-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 3 | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 4 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.02 | Wavefront Sensor | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | WFS Mech Design |  | Critical Path #3 |  |  |  | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CR235115 | Prep for Prelim Design Review - Guide Sensor | LSST Forecast - B57 - B1 | 5 | 0 | 2014-09-22 | 2014-09-26 | 0 | 2014-09-22 | 2014-09-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-09-22 | 2014-09-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 4 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 4 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.03 | Guide Sensors | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Design Reviews | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | Guide Prelim Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CR230210 | Prep for C_PDR - Corner raft sensor assembly | LSST Forecast - B57 - B1 | 5 | 0 | 2014-09-22 | 2014-09-26 | 0 | 2014-09-22 | 2014-09-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-09-22 | 2014-09-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 13 | 0 | 2 | 0 | 0 | 11 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 4 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Prelim Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CR220260 | Prep for C_PDR - Corner raft tower | LSST Forecast - B57 - B1 | 5 | 0 | 2014-09-22 | 2014-09-26 | 0 | 2014-09-22 | 2014-09-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-09-22 | 2014-09-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 1 | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 4 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Tower Module (CRTM) (TEC) | CRTM Prelim Design | [5 empty] | Corner Raft Tower Module (CRTM)
FALSE |  | CRYO00200 | COMP: Ready for CD-2 - Cryostat | LSST Forecast - B57 - B1 | 0 | 0 | 2014-09-29 | 2014-09-29 | 0 | 2014-09-29 | 2014-09-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 13 | FALSE | Finish Milestone | FALSE | 2014-09-29 | 2014-09-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 9 | 0 | 9 | 0 | 0 | 0 | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04 | Cryostat | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 3 Milestone | Management/Administration
FALSE |  | CR211400 | COMP: C_PDR - Corner Raft | LSST Forecast - B57 - B1 | 0 | 0 | 2014-10-01 | 2014-10-01 | 0 | 2014-10-01 | 2014-10-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 6 | FALSE | Finish Milestone | FALSE | 2014-10-01 | 2014-10-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 0 | 0 | 0 | 5 | 6 | 0 | 5 | 0 | 0 | 1 | 0 | 0 | 4 | 0 | 0 | 140 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.01 | Corner Raft System Integration and Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 4 Milestone | Design/Engineering | [8 empty] | Management
FALSE |  | SE222090 | Prelim Design - Analyze Interfaces & Impacts - SE | LSST Forecast - B57 - B1 | 3 | 0 | 2014-10-01 | 2014-10-03 | 0 | 2014-10-01 | 2014-10-03 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-10-01 | 2014-10-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 3 | 2 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.02 | Mechanical Integration | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Design Management | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | SR523460 | Prep for C_FDR--TS3 | LSST Forecast - B57 - B1 | 22 | 0 | 2014-10-01 | 2014-10-30 | 0 | 2014-10-01 | 2014-10-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-10-01 | 2014-10-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 13 | 0 | 12 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 22 | 21 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.03 | Sensor Electro-Optical (TS3) | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Design Reviews | [5 empty] | Science Sensors Test Stands (TEC) | Test Stand Effort | [5 empty] | Science Sensors Test Stands | [8 empty] | Science Sensors
FALSE |  | ITC10150 | C_PDR - I&T | LSST Forecast - B57 - B1 | 2 | 0 | 2014-10-15 | 2014-10-16 | 0 | 2014-10-15 | 2014-10-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-10-15 | 2014-10-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 1 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.01 | I&T Integration & Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  |  | Management/Administration |  |  |  | Engineering
FALSE |  | CAM112475 | COMP: Design Ready for CD-2 | LSST Forecast - B57 - B1 | 0 | 0 | 2014-10-16 | 2014-10-16 | 0 | 2014-10-16 | 2014-10-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2014-10-16 | 2014-10-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 12 | 0 | 12 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01.01.02 | Reviews & Collaboration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Vincent Riot | (1.10) Task/item is a modification of an existing design | 0% | Level 4 Milestone | Management/Administration | [12 empty] | CD-3a | Critical Path to CD-2 | Project Management
FALSE |  | CRYO11450 | Finalize Design Phase 1 - Cryostat Assembly | LSST Forecast - B57 - B1 | 122 | 0 | 2014-10-17 | 2015-05-08 | 0 | 2014-10-17 | 2015-05-08 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2014-10-17 | 2015-04-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 122 | 131 |  | Complete | 100% | 128 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 128 | 128 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Housing & Assembly (TEC) |  | ICD's for Phase 3 |  |  |  |  | Cryostat Assembly |  |  | Final Design Link
FALSE |  | CRYO16550 | Finalize Design - Cryo Plate & Cold Plate | LSST Forecast - B57 - B1 | 110 | 0 | 2014-10-17 | 2015-06-07 | 0 | 2014-10-17 | 2015-06-07 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 5 | FALSE | Normal | FALSE | 2014-10-17 | 2015-04-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 5 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 20 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 110 | 151 |  | Complete | 100% | 634 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.03 | Cryo and Cold Plates | 634 | 634 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryo and Cold Plates (TEC) | [6 empty] | Cryo and Cold Plates
FALSE |  | CAM112480 | COMP: CD-2 DOE/SC Review - Doc Sumbitted | LSST Forecast - B57 - B1 | 0 | 0 | 2014-10-17 | 2014-10-17 | 0 | 2014-10-17 | 2014-10-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2014-10-17 | 2014-10-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 9 | 0 | 9 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01.01.02 | Reviews & Collaboration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Vincent Riot | (1.10) Task/item is a modification of an existing design | 0% | Level 4 Milestone | Management/Administration | [12 empty] | CD-3a | Critical Path to CD-3a | Project Management
FALSE |  | CRYO21600 | Finalize Analysis - Grid Assembly | LSST Forecast - B57 - B1 | 144 | 0 | 2014-10-19 | 2015-06-07 | 0 | 2014-10-19 | 2015-06-07 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 5 | FALSE | Normal | FALSE | 2014-10-20 | 2015-05-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 5 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 144 | 150 |  | Complete | 100% | 224 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.04 | Grid Assembly | 224 | 224 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Grid Assembly (TEC) | [6 empty] | Grid Assembly
FALSE |  | SR530330 | Procurement - Prototype material | LSST Forecast - B57 - B1 | 127 | 0 | 2014-10-27 | 2015-05-27 | 0 | 2014-10-27 | 2015-05-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-10-27 | 2015-04-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 3 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 127 | 144 |  | Complete | 100% | 8 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.03 | RTM Assembly (TS6) | 8 | 8 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 6 - Procurement & Fabrication |  | Science Raft System
FALSE |  | SR522695 | COMP: TS2 - MF02 (Platen Baseplate for OGP) | LSST Forecast - B57 - B1 | 0 | 0 | 2014-10-30 | 2014-10-30 | 0 | 2014-10-30 | 2014-10-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2014-10-30 | 2014-10-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.02 | Sensor Dimensional Metrology (TS2) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl |  |  | Level 4 Milestone | Fabrication/Assembly | [8 empty] | Test Stand Effort | [14 empty] | Science Sensors
FALSE |  | SR522430 | COMP: TS2 - MF03 (raft hold down fixture) prototype | LSST Forecast - B57 - B1 | 0 | 0 | 2014-10-31 | 2014-10-31 | 0 | 2014-10-31 | 2014-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2014-10-31 | 2014-10-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.02 | Sensor Dimensional Metrology (TS2) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl |  |  | Level 4 Milestone | Engineering Test/Validation | [8 empty] | Test Stand Effort | [14 empty] | Science Sensors
FALSE |  | SR523590 | RCV: Test Stand TS3 fabrication (dewar+xray arm+MOTS)(2 units) | LSST Forecast - B57 - B1 | 0 | 0 | 2014-10-31 | 2014-10-31 | 0 | 2014-10-31 | 2014-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2014-10-31 | 2014-10-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.03 | Sensor Electro-Optical (TS3) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl |  |  | Level 4 Milestone | Fabrication/Assembly | [8 empty] | Test Stand Effort | [14 empty] | Science Sensors
FALSE |  | ITC24210 | Develop BOT prototype plans and design | LSST Forecast - B57 - B1 | 19 | 0 | 2014-11-01 | 2014-12-01 | 0 | 2014-11-01 | 2014-12-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-11-03 | 2014-12-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 19 | 18 |  | Complete | 100% | 85 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.02.01 | Bench For Optical Testing (BOT) | 85 | 85 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 13% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC) | [6 empty] | Verification Test Systems
FALSE |  | CAM112500 | CD-2 DOE/SC Review | LSST Forecast - B57 - B1 | 3 | 0 | 2014-11-04 | 2014-11-06 | 0 | 2014-11-04 | 2014-11-06 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2014-11-04 | 2014-11-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 3 | 2 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01.01.02 | Reviews & Collaboration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Vincent Riot | (1.10) Task/item is a modification of an existing design | 0% |  | Management/Administration | [12 empty] | CD-3a | Critical Path to CD-3a | Project Management
FALSE |  | CCS104400 | Update console for new command structure (LSSTCCS-156) - Core 1.6 | LSST Forecast - B57 - B1 | 22 | 0 | 2014-11-11 | 2014-12-14 | 0 | 2014-11-11 | 2014-12-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-11-11 | 2014-12-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 22 | 22 |  | Complete | 100% | 140 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.02.02 | CCS Core 1.6 Release | 140 | 140 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering | [7 empty] | CCS Core (TEC)
FALSE |  | SR521130 | Prep for C_FDR--TS1 | LSST Forecast - B57 - B1 | 100 | 0 | 2014-11-17 | 2015-05-14 | 0 | 2014-11-17 | 2015-05-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-11-17 | 2015-04-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 100 | 121 |  | Complete | 100% | 8 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.01 | Sensor Receiving & Inspection (TS1) - eLog, eTraveler | 8 | 8 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Design Reviews | [5 empty] | Science Sensors Test Stands (TEC) | [6 empty] | Science Sensors Test Stands | [6 empty] | Test Stand 1 - Reviews |  | Science Sensors
FALSE |  | SR522570 | Prep for C_FDR--TS2 | LSST Forecast - B57 - B1 | 112 | 0 | 2014-11-17 | 2015-05-22 | 0 | 2014-11-17 | 2015-05-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-11-17 | 2015-04-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 15 | 0 | 12 | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 112 | 127 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.02 | Sensor Dimensional Metrology (TS2) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Design Reviews | [5 empty] | Science Sensors Test Stands (TEC) | [6 empty] | Science Sensors Test Stands | [6 empty] | Test Stand 2 - Reviews | Baseline | Science Sensors
FALSE |  | CCS115600 | COMP: TS3 Prototype Test-Stand Delivered | LSST Forecast - B57 - B1 | 0 | 0 | 2014-11-26 | 2014-11-26 | 0 | 2014-11-26 | 2014-11-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2014-11-26 | 2014-11-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.01.03 | Test Stand 3 (Reflex/Archon Controller Based) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  | Level 4 Milestone | Design/Engineering
FALSE |  | CRYO13500 | Finalize Design - Cryostat Housing | LSST Forecast - B57 - B1 | 93 | 0 | 2014-12-01 | 2015-05-05 | 0 | 2014-12-01 | 2015-05-05 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 5 | FALSE | Normal | FALSE | 2014-12-01 | 2015-04-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 5 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 93 | 99 |  | Complete | 100% | 522 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.01 | Cryostat Housing | 522 | 522 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Housing & Assembly (TEC) | [6 empty] | Cryostat Housing
FALSE |  | CRYO21550 | Finalize Design - Grid Assembly | LSST Forecast - B57 - B1 | 112 | 0 | 2014-12-05 | 2015-06-07 | 0 | 2014-12-05 | 2015-06-07 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 7 | FALSE | Normal | FALSE | 2014-12-05 | 2015-05-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 7 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 20 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 112 | 118 |  | Complete | 100% | 194 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.04 | Grid Assembly | 194 | 194 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Grid Assembly (TEC) | [6 empty] | Grid Assembly
FALSE |  | CCS104700 | COMP: CCS Core 1.6.0 | LSST Forecast - B57 - B1 | 0 | 0 | 2014-12-15 | 2014-12-15 | 0 | 2014-12-15 | 2014-12-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2014-12-15 | 2014-12-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.02.02 | CCS Core 1.6 Release | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  | Level 4 Milestone | Design/Engineering
FALSE |  | SR551910 | RSA base plate thermal characterization | LSST Forecast - B57 - B1 | 83 | 0 | 2014-12-15 | 2015-05-08 | 0 | 2014-12-15 | 2015-05-08 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2014-12-15 | 2015-04-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 83 | 99 |  | Complete | 100% | 160 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.02 | Science Raft Sensor Assembly (SRSA) | 160 | 160 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation |  | R&D | [5 empty] | Science Raft Tower Module (SRTM) (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Sensor Assembly |  | Science Raft System
FALSE |  | SE223145 | System engineering contamination final design inputs for optics throughput | LSST Forecast - B57 - B1 | 62 | 0 | 2014-12-15 | 2015-06-26 | 0 | 2014-12-15 | 2015-06-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2014-12-15 | 2015-03-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 62 | 126 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.03 | Thermal and contamination system analysis | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | SE223140 | Sub-system FDR camera subsystem definition of contamination and material requirements | LSST Forecast - B57 - B1 | 62 | 0 | 2014-12-15 | 2015-10-16 | 0 | 2014-12-15 | 2015-10-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 7 | FALSE | Normal | FALSE | 2014-12-15 | 2015-03-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 7 | 0 | 4 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 62 | 204 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.03 | Thermal and contamination system analysis | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | CCS116500 | Build TS8 Distribution - Prototype | LSST Forecast - B57 - B1 | 53 | 0 | 2015-01-02 | 2015-05-19 | 0 | 2015-01-02 | 2015-05-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-01-05 | 2015-03-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 53 | 94 |  | Complete | 100% | 96 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.01.04 | Test Stand 8 (REB Based) | 96 | 96 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 11% |  | Design/Engineering | [7 empty] | CCS HCU (TEC)
FALSE |  | SR522505 | TS2 - MF05b (sensor removal fixture) - fabricate and assemble prototype fixture | LSST Forecast - B57 - B1 | 61 | 0 | 2015-01-02 | 2015-03-31 | 0 | 2015-01-02 | 2015-03-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-01-02 | 2015-03-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 61 | 61 |  | Complete | 100% | 20 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.02 | Sensor Dimensional Metrology (TS2) | 20 | 20 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Science Sensors Test Stands (TEC) | Test Stand Effort | [5 empty] | Science Sensors Test Stands | [7 empty] | Baseline | Science Sensors
FALSE |  | CCS114515 | Integrate REB1 Driver with full raft readout using DREB1 | LSST Forecast - B57 - B1 | 7 | 0 | 2015-01-05 | 2015-01-13 | 0 | 2015-01-05 | 2015-01-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-01-05 | 2015-01-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 7 | 6 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.01.02 | Rafts Subsystem | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering | [7 empty] | CCS HCU (TEC)
FALSE |  | SR332345 | COMP: Science Sensors Prototype & Development | LSST Forecast - B57 - B1 | 0 | 0 | 2015-01-30 | 2015-01-30 | 0 | 2015-01-30 | 2015-01-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2015-01-30 | 2015-01-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 14 | 0 | 14 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.01 | Science Sensors Prototype & Development | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Bill Wahl |  |  | Level 4 Milestone | Design/Engineering | [6 empty] | e2v |  | Prototype & Development | [14 empty] | Science Sensors
FALSE |  | ITC22205 | Finalize MTF equipment design | LSST Forecast - B57 - B1 | 20 | 0 | 2015-02-02 | 2015-02-27 | 0 | 2015-02-02 | 2015-02-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-03-30 | 2015-04-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 2 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 18 |  | Complete | 100% | 160 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.01.03 | Vacuum Qualification Tests | 160 | 160 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC) | [6 empty] | Verification Test Systems
FALSE |  | OP530410 | AWARD: L1-L2 Assembly - Phase 2 | LSST Forecast - B57 - B1 | 1 | 0 | 2015-02-12 | 2015-02-12 | 0 | 2015-02-12 | 2015-02-12 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-13 | 2019-06-13 | 1868008 | 1868008 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2015-03-16 | 2015-03-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 1868008 | 1868008 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | B1 Procurement Commitment (C5.1) | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 0% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | L1-L2 Assembly (TEC) | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly) |  |  |  | L1-L2 Opto-Mechanics
FALSE |  | CCS114513 | Integrate CCS with WREB | LSST Forecast - B57 - B1 | 15 | 0 | 2015-02-15 | 2015-04-15 | 0 | 2015-02-15 | 2015-04-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-03-02 | 2015-03-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 41 |  | Complete | 100% | 70 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.01.02 | Rafts Subsystem | 70 | 70 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering | [7 empty] | CCS HCU (TEC)
FALSE |  | SR530570 | Fabrication - TS5 Cryostat custom components (TS7) | LSST Forecast - B57 - B1 | 20 | 0 | 2015-02-16 | 2015-07-29 | 0 | 2015-02-16 | 2015-07-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-06-25 | 2015-07-23 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 114 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.02 | RSA & RTM Warm-Cold Metrology (TS5) | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 5 - Procurement & Fabrication |  | Science Raft System
FALSE |  | SR552450 | Conduct RSA thermal cycling tests | LSST Forecast - B57 - B1 | 53 | 0 | 2015-02-16 | 2015-05-28 | 0 | 2015-02-16 | 2015-05-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-02-17 | 2015-04-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 2 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 53 | 71 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.01 | Science Raft Tower Module (SRTM) | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation |  | R&D | [5 empty] | Science Raft Tower Module (SRTM) (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Tower Module |  | Science Raft System
FALSE |  | SR414200 | NEED: CCS-DAQ (DAQ V0.0 GEN 1 Multi REB) | LSST Forecast - B57 - B1 | 0 | 0 | 2015-02-16 | 2015-02-16 | 0 | 2015-02-16 | 2015-02-16 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2015-05-01 | 2015-05-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.04 | Raft Optimization And Readout (ROAR) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% | Level 5 Milestone | Engineering Test/Validation | [23 empty] | Science Raft System
FALSE |  | SR523530 | TS3 -Work Flow | LSST Forecast - B57 - B1 | 65 | 0 | 2015-02-16 | 2015-06-25 | 0 | 2015-02-16 | 2015-06-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-03-02 | 2015-06-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 65 | 91 |  | Complete | 100% | 240 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.03 | Sensor Electro-Optical (TS3) | 240 | 240 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Science Sensors Test Stands (TEC) | Test Stand Effort | [5 empty] | Science Sensors Test Stands | [6 empty] | Test Stand 3 - Design |  | Science Sensors
FALSE |  | CR240460 | Functional Testing - WGEB Protoype (WF mode) | LSST Forecast - B57 - B1 | 40 | 0 | 2015-02-17 | 2015-03-27 | 0 | 2015-02-17 | 2015-03-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2015-04-20 | 2015-06-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 20 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 28 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.01 | Wavefront Electronics Board (WEB) | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering | [7 empty] | Corner Raft Electronics (TEC) | WEB Prototype
FALSE |  | CR241825 | Layout DCBS prototype variant A | LSST Forecast - B57 - B1 | 10 | 0 | 2015-02-18 | 2015-02-25 | 0 | 2015-02-18 | 2015-02-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-03-16 | 2015-03-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 5 |  | Complete | 100% | 60 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.02 | Guider Electronics Board (GEB) | 60 | 60 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Engineering Test/Validation | [7 empty] | Corner Raft Electronics (TEC)
FALSE |  | CCS114530 | NEED: REB2 Driver | LSST Forecast - B57 - B1 | 0 | 0 | 2015-03-02 | 2015-03-02 | 0 | 2015-03-02 | 2015-03-02 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2015-04-01 | 2015-04-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.01.02 | Rafts Subsystem | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Tony Johnson |  |  | Level 5 Milestone | Design/Engineering | [14 empty] | CCS Infrastructure
FALSE |  | SE210071 | Prep for SI FDR | LSST Forecast - B57 - B1 | 10 | 0 | 2015-03-02 | 2015-06-10 | 0 | 2015-03-02 | 2015-06-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-06-01 | 2015-06-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 2 | 2 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 71 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.01 | Systems Engineering | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 0% |  | Management/Administration |  | Design Reviews | [5 empty] | Systems Engineering (TEC) | [6 empty] | Systems Engineering
FALSE |  | SE224040 | LCA-17 final allocation | LSST Forecast - B57 - B1 | 40 | 0 | 2015-03-02 | 2016-07-07 | 0 | 2015-03-02 | 2016-07-07 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-17 | 2020-06-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-11-02 | 2016-01-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 334 |  | Complete | 100% | 220 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.04 | Optics system analysis | 220 | 220 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | CRYO18301 | ETU Test and Validate - Cryogenic Feedthrough Test Parts - Cryo & Cold Plate | LSST Forecast - B57 - B1 | 100 | 0 | 2015-03-11 | 2015-09-14 | 0 | 2015-03-11 | 2015-09-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-05-11 | 2015-09-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 2 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 4 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 100 | 130 |  | Complete | 100% | 344 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.03 | Cryo and Cold Plates | 344 | 344 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation |  | Commissioning and Testing | [5 empty] | Cryo and Cold Plates (TEC) | [6 empty] | Cryo and Cold Plates
FALSE |  | SE223200 | Filter exchange sub-system FDR contamination compliance | LSST Forecast - B57 - B1 | 20 | 0 | 2015-03-16 | 2015-10-21 | 0 | 2015-03-16 | 2015-10-21 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-04-28 | 2015-05-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 154 |  | Complete | 100% | 44 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.03 | Thermal and contamination system analysis | 44 | 44 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | CR220480 | Review Camera System Specifications CD-3 - Corner raft tower and tooling | LSST Forecast - B57 - B1 | 22 | 0 | 2015-03-16 | 2015-04-15 | 0 | 2015-03-16 | 2015-04-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-03-16 | 2015-04-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 22 | 22 |  | Complete | 100% | 16 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 16 | 16 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Tower Module (CRTM) (TEC) | CRTM Final Design | [5 empty] | Corner Raft Tower Module (CRTM)
FALSE |  | CCS119700 | COMP: CCS Core 2.0 Release | LSST Forecast - B57 - B1 | 0 | 0 | 2015-03-20 | 2015-03-20 | 0 | 2015-03-20 | 2015-03-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Finish Milestone | FALSE | 2015-04-20 | 2015-04-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.02.03 | CCS Core 2.0 Release | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  | Level 4 Milestone | Design/Engineering
FALSE |  | SR552500 | Prep for Final Design Review - RTM Mechanic | LSST Forecast - B57 - B1 | 16 | 0 | 2015-03-23 | 2015-05-15 | 0 | 2015-03-23 | 2015-05-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-04-20 | 2015-05-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 4 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 16 | 39 |  | Complete | 100% | 240 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.01 | Science Raft Tower Module (SRTM) | 240 | 240 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Design Reviews | [5 empty] | Science Raft Tower Module (SRTM) (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Tower Module |  | Science Raft System
FALSE |  | CR240420 | NEED: corner raft test setup (prototype) | LSST Forecast - B57 - B1 | 0 | 0 | 2015-03-25 | 2015-03-25 | 0 | 2015-03-25 | 2015-03-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2015-04-23 | 2015-04-23 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.01 | Wavefront Electronics Board (WEB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 5 Milestone | Engineering Test/Validation | [8 empty] | WEB Prototype
FALSE |  | SR551970 | Prep for C_FDR - RSA | LSST Forecast - B57 - B1 | 18 | 0 | 2015-03-27 | 2015-05-15 | 0 | 2015-03-27 | 2015-05-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-04-16 | 2015-05-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 2 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 18 | 35 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.02 | Science Raft Sensor Assembly (SRSA) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Design Reviews | [5 empty] | Science Raft Tower Module (SRTM) (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Sensor Assembly |  | Science Raft System
FALSE |  | CR240480 | AVAIL: WGEB prototype | LSST Forecast - B57 - B1 | 0 | 0 | 2015-03-27 | 2015-03-27 | 0 | 2015-03-27 | 2015-03-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Finish Milestone | FALSE | 2015-06-22 | 2015-06-22 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 50 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.01 | Wavefront Electronics Board (WEB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 5 Milestone | Engineering Test/Validation | [8 empty] | WEB Prototype
FALSE |  | OP520540 | Assemble test filter frame | LSST Forecast - B57 - B1 | 15 | 0 | 2015-03-30 | 2015-04-22 | 0 | 2015-03-30 | 2015-04-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-04-01 | 2015-04-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 17 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 18% |  | Design/Engineering |  | Commissioning and Testing | [5 empty] | Filters (TEC) | Prototype Filter Assemblies | [5 empty] | Filter Opto-Mechanics
FALSE |  | CAMF663500 | Prep for C_FDR - Filter Loader | LSST Forecast - B57 - B1 | 10 | 0 | 2015-04-01 | 2015-04-20 | 0 | 2015-04-01 | 2015-04-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-05-18 | 2015-06-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 13 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.02 | Filter Loader | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Design/Engineering
FALSE |  | CAMF667300 | Prep for C_FDR - Carousel | LSST Forecast - B57 - B1 | 10 | 0 | 2015-04-01 | 2015-04-21 | 0 | 2015-04-01 | 2015-04-21 | 0 | 2019-06-01 | 2019-06-01 | 2018-10-16 | 2018-10-16 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-05-18 | 2015-06-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 14 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Design/Engineering
FALSE |  | CRYO29750 | Finalize Design - Cryostat Back End | LSST Forecast - B57 - B1 | 22 | 0 | 2015-04-01 | 2015-06-07 | 0 | 2015-04-01 | 2015-06-07 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 7 | FALSE | Normal | FALSE | 2015-05-01 | 2015-06-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 7 | 0 | 2 | 4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 22 | 47 |  | Complete | 100% | 154 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.01 | Cryostat Back End | 154 | 154 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Backend & Vacuum Systems (TEC) | [6 empty] | Cryostat Back End
FALSE |  | SE223090 | Cryostat Sub-system FDR cryostat thermal analysis integrated material | LSST Forecast - B57 - B1 | 14 | 0 | 2015-04-01 | 2015-05-29 | 0 | 2015-04-01 | 2015-05-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-05-13 | 2015-06-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 3 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 14 | 41 |  | Complete | 100% | 60 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.03 | Thermal and contamination system analysis | 60 | 60 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | SR522900 | COMP: TS2 - MF07a (CCD Cover & Handling fixture) | LSST Forecast - B57 - B1 | 0 | 0 | 2015-04-01 | 2015-04-01 | 0 | 2015-04-01 | 2015-04-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2015-04-01 | 2015-04-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.02 | Sensor Dimensional Metrology (TS2) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl |  |  | Level 4 Milestone | Fabrication/Assembly | [8 empty] | Test Stand Effort | [14 empty] | Science Sensors
FALSE |  | CR234230 | AWARD: Contract - First article 2Kx4K Wavefront Sensor w package (2+3 2kx4k sensors) | LSST Forecast - B57 - B1 | 1 | 0 | 2015-04-03 | 2015-04-03 | 0 | 2015-04-03 | 2015-04-03 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 1539764 | 1539764 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-05-01 | 2015-05-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.02 | Wavefront Sensor | 0 | 0 | 0 | 1539764 | 1539764 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | B1 Procurement Commitment (C5.1) |  | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 1% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | [6 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CAMF659700 | Prep for C_FDR - Auto Changer | LSST Forecast - B57 - B1 | 10 | 0 | 2015-04-07 | 2015-04-20 | 0 | 2015-04-07 | 2015-04-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-05-07 | 2015-05-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.01 | Auto Changer | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Design/Engineering
FALSE |  | SE222210 | Final grid/cryostat - Check & Update IDD | LSST Forecast - B57 - B1 | 11 | 0 | 2015-04-08 | 2015-05-29 | 0 | 2015-04-08 | 2015-05-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 7 | FALSE | Normal | FALSE | 2015-05-01 | 2015-05-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 0 | 4 | 0 | 0 | 7 | 0 | 6 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 11 | 36 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.02 | Mechanical Integration | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | OP520680 | Prep for C_FDR - Filter Assembly | LSST Forecast - B57 - B1 | 28 | 0 | 2015-04-13 | 2015-06-02 | 0 | 2015-04-13 | 2015-06-02 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-05-18 | 2015-06-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 28 | 35 |  | Complete | 100% | 300 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 300 | 300 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 18% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Filters (TEC) | Filter Design | [5 empty] | Filter Opto-Mechanics
FALSE |  | SR523650 | TS3 - Commissioning | LSST Forecast - B57 - B1 | 40 | 0 | 2015-04-20 | 2015-06-29 | 0 | 2015-04-20 | 2015-06-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-06-15 | 2015-08-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 4 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 49 |  | Complete | 100% | 360 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.03 | Sensor Electro-Optical (TS3) | 360 | 360 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Testing/Integration |  | Commissioning and Testing | [5 empty] | Science Sensors Test Stands (TEC) | Test Stand Effort | [5 empty] | Science Sensors Test Stands | [6 empty] | Test Stand 3 - Assembly & Commissioning |  | Science Sensors
FALSE |  | SR330595 | Sensors First Articles - V2- Backside Batch and Test | LSST Forecast - B57 - B1 | 100 | 0 | 2015-04-20 | 2015-04-30 | 0 | 2015-04-20 | 2015-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-05-01 | 2015-09-22 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 4 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 100 | 8 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien |  |  |  | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 14% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor | [10 empty] | Sensor
FALSE |  | CRYO24700 | Prep for Prelim Design Review - Evaporable Getter Pumps | LSST Forecast - B57 - B1 | 4 | 0 | 2015-04-25 | 2015-04-28 | 0 | 2015-04-25 | 2015-04-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-05-04 | 2015-05-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 1 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.02 | Getter Pumps | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Cryostat Getter Pumps
FALSE |  | SR530220 | COMP: TS7 part, assy dwg's complete | LSST Forecast - B57 - B1 | 0 | 0 | 2015-04-29 | 2015-04-29 | 0 | 2015-04-29 | 2015-04-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2015-05-12 | 2015-05-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.04 | RTM Cryostat Integration (TS7) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% | Level 4 Milestone | Design/Engineering | [14 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 7 - Design |  | Science Raft System
FALSE |  | SE222250 | Final Filter/Exchange System - Mechanical Integration | LSST Forecast - B57 - B1 | 4 | 0 | 2015-05-01 | 2015-05-29 | 0 | 2015-05-01 | 2015-05-29 | 0 | 2019-06-01 | 2019-06-01 | 2018-10-16 | 2018-10-16 | 0 | 0 | 0 | 0 | 0 | 6 | FALSE | Normal | FALSE | 2015-06-10 | 2015-06-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 3 | 0 | 0 | 6 | 0 | 5 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 19 |  | Complete | 100% | 96 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.02 | Mechanical Integration | 96 | 96 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | SE223150 | Cryostat sub-system FDR contamination compliance | LSST Forecast - B57 - B1 | 8 | 0 | 2015-05-01 | 2015-05-29 | 0 | 2015-05-01 | 2015-05-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 8 | FALSE | Normal | FALSE | 2015-06-04 | 2015-06-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 2 | 5 | 0 | 0 | 8 | 0 | 7 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 8 | 19 |  | Complete | 100% | 44 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.03 | Thermal and contamination system analysis | 44 | 44 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | SE223160 | Science Raft sub-system FDR contamination compliance | LSST Forecast - B57 - B1 | 14 | 0 | 2015-05-01 | 2015-05-19 | 0 | 2015-05-01 | 2015-05-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-06-19 | 2015-07-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 14 | 12 |  | Complete | 100% | 44 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.03 | Thermal and contamination system analysis | 44 | 44 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | CRYO13600 | Prep for C_FDR - Cryostat Housing | LSST Forecast - B57 - B1 | 17 | 0 | 2015-05-06 | 2015-06-08 | 0 | 2015-05-06 | 2015-06-08 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-06-04 | 2015-06-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 17 | 22 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.01 | Cryostat Housing | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment |  | TEC Non-ARRA | Brian J. Langton | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Cryostat Housing
FALSE |  | CRYO29850 | Prep for C_FDR - Cryostat Back End | LSST Forecast - B57 - B1 | 1 | 0 | 2015-05-08 | 2015-06-08 | 0 | 2015-05-08 | 2015-06-08 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-07-02 | 2015-07-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 2 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 20 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.01 | Cryostat Back End | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Cryostat Back End
FALSE |  | CRYO11550 | Prep for Final Review - Cryostat Assembly | LSST Forecast - B57 - B1 | 1 | 0 | 2015-05-11 | 2015-06-08 | 0 | 2015-05-11 | 2015-06-08 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-06-09 | 2015-06-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 2 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 19 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Cryostat Assembly
FALSE |  | CRYO16650 | Prep for C_FDR - Cryo & Cold Plate | LSST Forecast - B57 - B1 | 1 | 0 | 2015-05-11 | 2015-06-08 | 0 | 2015-05-11 | 2015-06-08 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-06-16 | 2015-06-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 2 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 19 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.03 | Cryo and Cold Plates | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Brian J. Langton | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Cryo and Cold Plates
FALSE |  | DAQ105400 | Prep for C_FDR | LSST Forecast - B57 - B1 | 15 | 0 | 2015-05-15 | 2015-05-30 | 0 | 2015-05-15 | 2015-05-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-06-01 | 2015-06-19 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 10 |  | Complete | 100% | 16 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.01 | DAQ Integration & Management | 16 | 16 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Design/Engineering | [7 empty] | DAQ Integration & Management (TEC)
FALSE |  | CRYO09120 | Prep for Final Design Review - Cryostat | LSST Forecast - B57 - B1 | 10 | 0 | 2015-05-18 | 2015-06-08 | 0 | 2015-05-18 | 2015-06-08 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-06-04 | 2015-06-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 14 |  | Complete | 100% | 200 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.01 | Cryostat Integration & Management | 200 | 200 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Management/Administration |  | Design Reviews | [5 empty] | Cryostat Integration & Management (TEC) | [6 empty] | Utility Trunk
FALSE |  | CRYO13800 | Generate Detail and Assembly Drawings Cryostat Housing | LSST Forecast - B57 - B1 | 56 | 0 | 2015-05-18 | 2015-12-28 | 0 | 2015-05-18 | 2015-12-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-06-11 | 2015-08-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 56 | 150 |  | Complete | 100% | 252 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.01 | Cryostat Housing | 252 | 252 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Housing & Assembly (TEC) | [6 empty] | Cryostat Housing
FALSE |  | CRYO21650 | Prep for C_FDR - Grid Assembly | LSST Forecast - B57 - B1 | 10 | 0 | 2015-05-18 | 2015-06-08 | 0 | 2015-05-18 | 2015-06-08 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-06-16 | 2015-06-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 3 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 14 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.04 | Grid Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Brian J. Langton | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Grid Assembly
FALSE |  | SR330600 | RCV: First Articles Sensor - V2 - Sensor #1 | LSST Forecast - B57 - B1 | 5 | 0 | 2015-05-18 | 2016-05-31 | 0 | 2015-05-18 | 2016-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 73016 | 73016 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-06-01 | 2015-06-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 8 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 260 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 73016 | 73016 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 14% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC) | Sensor Delivery |  |  |  |  | Sensor | Science Sensors Procurement |  |  |  |  | CP - CAMM2130 (Award of Sensor Lot #2) |  | Sensors Vendor 2
FALSE |  | SE221255 | Generate structural report & slides for SI FDR | LSST Forecast - B57 - B1 | 5 | 0 | 2015-05-26 | 2015-05-29 | 0 | 2015-05-26 | 2015-05-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-06-01 | 2015-06-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 3 |  | Complete | 100% | 20 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.01 | Structural System Analysis | 20 | 20 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | CRYO11750 | Generate Detail and Assembly Drawings - Cryostat Assembly | LSST Forecast - B57 - B1 | 40 | 0 | 2015-06-01 | 2015-10-30 | 0 | 2015-06-01 | 2015-10-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-08-12 | 2015-10-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 107 |  | Complete | 100% | 140 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 140 | 140 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Housing & Assembly (TEC) | [6 empty] | Cryostat Assembly
FALSE |  | CRYO30050 | Generate Detail and Assembly Drawings Cryostat Back End | LSST Forecast - B57 - B1 | 45 | 0 | 2015-06-01 | 2016-04-27 | 0 | 2015-06-01 | 2016-04-27 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-11-30 | 2016-02-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 45 | 221 |  | Complete | 100% | 244 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.01 | Cryostat Back End | 244 | 244 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Backend & Vacuum Systems (TEC) | [6 empty] | Cryostat Back End
FALSE |  | CR241780 | Functional Testing - WGEB Protoype (Guider mode) | LSST Forecast - B57 - B1 | 20 | 0 | 2015-06-01 | 2015-06-19 | 0 | 2015-06-01 | 2015-06-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2015-08-13 | 2015-09-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 20 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 14 |  | Complete | 100% | 100 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.02 | Guider Electronics Board (GEB) | 100 | 100 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Engineering Test/Validation | [7 empty] | Corner Raft Electronics (TEC) | GEB Prototype
FALSE |  | SE222290 | Revise layout dwg's for camera-level FDR | LSST Forecast - B57 - B1 | 10 | 0 | 2015-06-01 | 2015-06-10 | 0 | 2015-06-01 | 2015-06-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-13 | 2019-09-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-07-01 | 2015-07-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 7 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.02 | Mechanical Integration | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | OP520700 | C_FDR - Filter Assembly | LSST Forecast - B57 - B1 | 2 | 0 | 2015-06-03 | 2015-06-04 | 0 | 2015-06-03 | 2015-06-04 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-07-06 | 2015-07-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 1 |  | Complete | 100% | 32 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 32 | 32 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 18% |  | Design/Engineering | [7 empty] | Filters (TEC) | Filter Design
FALSE |  | DAQ100125 | COMP: Ready for CD-3 - DAQ | LSST Forecast - B57 - B1 | 0 | 0 | 2015-06-03 | 2015-06-03 | 0 | 2015-06-03 | 2015-06-03 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2015-06-03 | 2015-06-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02 | Data Acquisition System (DAQ) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer |  |  | Level 3 Milestone | Management/Administration
FALSE |  | OP540600 | L3 Assembly - Phase 1 (Engineering & Requirements Defined) | LSST Forecast - B57 - B1 | 167 | 0 | 2015-06-09 | 2016-07-29 | 0 | 2015-06-09 | 2016-07-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-07-02 | 2016-03-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 0 | 0 | 1 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 95 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 167 | 287 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor | [7 empty] | Critical Path #2 (L1_L2 Assembly) |  |  |  | L1-L2 Opto-Mechanics
FALSE |  | CRYO21800 | COMP: C_FDR - Grid Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2015-06-10 | 2015-06-10 | 0 | 2015-06-10 | 2015-06-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2015-07-16 | 2015-07-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.04 | Grid Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Design/Engineering
FALSE |  | CRYO30000 | COMP: C_FDR - Cryostat Back End | LSST Forecast - B57 - B1 | 0 | 0 | 2015-06-10 | 2015-06-10 | 0 | 2015-06-10 | 2015-06-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2015-07-17 | 2015-07-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.01 | Cryostat Back End | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Design/Engineering
FALSE |  | CAM112685 | COMP: Design Ready for CD-3 | LSST Forecast - B57 - B1 | 0 | 0 | 2015-06-12 | 2015-06-12 | 0 | 2015-06-12 | 2015-06-12 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2015-07-01 | 2015-07-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 11 | 0 | 11 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01.01.02 | Reviews & Collaboration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Vincent Riot | (1.10) Task/item is a modification of an existing design | 0% | Level 4 Milestone | Management/Administration | [12 empty] | CD-3b | Critical Path to CD-3b | Project Management
FALSE |  | CAMF650200 | COMP: Ready for CD-3 - Exchange System | LSST Forecast - B57 - B1 | 0 | 0 | 2015-06-15 | 2015-06-15 | 0 | 2015-06-15 | 2015-06-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2015-07-16 | 2015-07-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 8 | 0 | 8 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03 | Exchange System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  | Level 3 Milestone | Management/Administration
FALSE |  | SR530520 | Finalize part, assy dwg's for TS5 | LSST Forecast - B57 - B1 | 10 | 0 | 2015-06-15 | 2015-12-28 | 0 | 2015-06-15 | 2015-12-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-07-01 | 2015-07-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 1 | 0 | 0 | 3 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 134 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.02 | RSA & RTM Warm-Cold Metrology (TS5) | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 5 - Design |  | Science Raft System
FALSE |  | CRYO09180 | Prep for CD3 Review - Cryostat | LSST Forecast - B57 - B1 | 1 | 0 | 2015-06-18 | 2015-07-15 | 0 | 2015-06-18 | 2015-07-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-07-01 | 2015-07-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 18 |  | Complete | 100% | 200 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.01 | Cryostat Integration & Management | 200 | 200 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Management/Administration |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Integration & Management (TEC) | [6 empty] | Utility Trunk
FALSE |  | OP520740 | COMP: C_FDR - Filter Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2015-06-19 | 2015-06-19 | 0 | 2015-06-19 | 2015-06-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 5 | FALSE | Finish Milestone | FALSE | 2015-07-15 | 2015-07-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  | Level 4 Milestone | Design/Engineering | [8 empty] | Filter Design
FALSE |  | SR530850 | TS5 - Optical flat stand - fabricate and assemble fixture | LSST Forecast - B57 - B1 | 10 | 0 | 2015-06-22 | 2015-11-20 | 0 | 2015-06-22 | 2015-11-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-09-16 | 2015-09-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 108 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.02 | RSA & RTM Warm-Cold Metrology (TS5) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 5 - Procurement & Fabrication |  | Science Raft System
FALSE |  | OP521500 | Update Plan Procurement (Post FDR) - Filter Coating (all phases) | LSST Forecast - B57 - B1 | 30 | 0 | 2015-06-22 | 2015-09-30 | 0 | 2015-06-22 | 2015-09-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-12-12 | 2019-12-12 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-07-01 | 2015-08-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 70 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 18% |  | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Filters (TEC) | Witness & First Article RFP | [5 empty] | Filter Optics
FALSE |  | SR343185 | Fab/Assy Raft Electronics Board (REB3) - PT2 | LSST Forecast - B57 - B1 | 16 | 0 | 2015-06-29 | 2015-09-22 | 0 | 2015-06-29 | 2015-09-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-07-21 | 2015-08-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 16 | 59 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [6 empty] | Raft Electronics Board 3 |  | Science Raft System
FALSE |  | SR523710 | AVAIL: Test Stand 3 - Ready for Production | LSST Forecast - B57 - B1 | 0 | 0 | 2015-06-30 | 2015-06-30 | 0 | 2015-06-30 | 2015-06-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2015-07-31 | 2015-07-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.03 | Sensor Electro-Optical (TS3) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl |  |  | Level 5 Milestone | Testing/Integration | [8 empty] | Test Stand Effort | [12 empty] | Test Stand 3 - Assembly & Commissioning |  | Science Sensors
FALSE |  | CRYO22353 | ETU - Design and Analysis - Grid Flexure Tests | LSST Forecast - B57 - B1 | 30 | 0 | 2015-07-01 | 2015-10-30 | 0 | 2015-07-01 | 2015-10-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-10-01 | 2015-11-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 85 |  | Complete | 100% | 50 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.04 | Grid Assembly | 50 | 50 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 11% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Grid Assembly (TEC) | [6 empty] | Grid Assembly
FALSE |  | ITC24400 | Complete BOT prototype design | LSST Forecast - B57 - B1 | 30 | 0 | 2015-07-01 | 2015-09-14 | 0 | 2015-07-01 | 2015-09-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-08-03 | 2015-09-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 51 |  | Complete | 100% | 60 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.02.01 | Bench For Optical Testing (BOT) | 60 | 60 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 13% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC) | [6 empty] | Verification Test Systems
FALSE |  | CR306240 | Procurement Prep - PCRTS Cryostat Mech Comp/Cabling - Corner raft test station | LSST Forecast - B57 - B1 | 10 | 0 | 2015-07-01 | 2015-08-28 | 0 | 2015-07-01 | 2015-08-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-08-31 | 2015-09-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 41 |  | Complete | 100% | 10 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.05 | Corner Raft Assembly and Test Station | 10 | 10 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Assembly and Test Station (TEC) | CR Assy/Test Station Prelim Design | [5 empty] | Corner Raft Assembly and Test Station
FALSE |  | OP530620 | COMP: L1-L2 Assembly Phase 3 | LSST Forecast - B57 - B1 | 0 | 0 | 2015-07-01 | 2015-07-01 | 0 | 2015-07-01 | 2015-07-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-03 | 2019-09-03 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | FALSE | 2015-09-01 | 2015-09-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  | Level 4 Milestone | Procurement | [8 empty] | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly)
FALSE |  | CRYO18230 | ETU Design & Analysis - Cryoplate Flexure Test Article - Cryo & Cold Plate | LSST Forecast - B57 - B1 | 40 | 0 | 2015-07-04 | 2015-10-30 | 0 | 2015-07-04 | 2015-10-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-11-04 | 2016-01-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 83 |  | Complete | 100% | 360 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.03 | Cryo and Cold Plates | 360 | 360 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryo and Cold Plates (TEC) | [6 empty] | Cryo and Cold Plates
FALSE |  | SE224050 | LCA-18 final allocation | LSST Forecast - B57 - B1 | 39 | 0 | 2015-07-06 | 2016-07-29 | 0 | 2015-07-06 | 2016-07-29 | 0 | 2019-06-01 | 2019-06-01 | 2020-07-16 | 2020-07-16 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-03-17 | 2017-05-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 39 | 262 |  | Complete | 100% | 100 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.04 | Optics system analysis | 100 | 100 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | CAM112690 | COMP: CD-3 DOE/SC Review - Doc Sumbitted | LSST Forecast - B57 - B1 | 0 | 0 | 2015-07-17 | 2015-07-17 | 0 | 2015-07-17 | 2015-07-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2015-08-03 | 2015-08-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 10 | 0 | 10 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01.01.02 | Reviews & Collaboration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Vincent Riot | (1.10) Task/item is a modification of an existing design | 0% | Level 4 Milestone | Management/Administration | [12 empty] | CD-3a | Critical Path to CD-3a | Project Management
FALSE |  | SR552590 | Prep for Sensor MRR (TS1-TS3) | LSST Forecast - B57 - B1 | 10 | 0 | 2015-07-20 | 2015-08-21 | 0 | 2015-07-20 | 2015-08-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-08-17 | 2015-08-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 24 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.07.01 | Cleanroom Development & Commissioning | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Assembly and Test Facility (TEC) | Test Stand Effort | [5 empty] | Science Raft - Assembly and Test Facility | [6 empty] | Test Stand - Reviews |  | Science Raft System
FALSE |  | CRYO21950 | Generate Manufacturing Docs - Grid Assembly | LSST Forecast - B57 - B1 | 8 | 0 | 2015-07-24 | 2016-04-27 | 0 | 2015-07-24 | 2016-04-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-02-24 | 2016-03-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 8 | 183 |  | Complete | 100% | 32 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.04 | Grid Assembly | 32 | 32 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Grid Assembly (TEC) | [6 empty] | Grid Assembly
FALSE |  | OP530490 | RCV: Critical Design Review - L1-L2 Assembly - Phase 2 (MS10) | LSST Forecast - B57 - B1 | 1 | 0 | 2015-07-27 | 2015-09-11 | 0 | 2015-07-27 | 2015-09-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-13 | 2019-06-13 | 0 | 0 | 0 | 0 | 0 | 5 | FALSE | Normal | FALSE | 2015-09-11 | 2015-09-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 5 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 33 |  | Complete | 100% | 56 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 56 | 56 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 0% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | L1-L2 Assembly (TEC) | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly) |  |  |  | L1-L2 Opto-Mechanics |  |  |  | CP - CAMM2100 (L1-L2 Assembly Phase 2 FDR)
FALSE |  | CAMF663700 | Final Check & Approve Detail Dwgs - Filter Loader | LSST Forecast - B57 - B1 | 24 | 0 | 2015-08-01 | 2015-08-30 | 0 | 2015-08-01 | 2015-08-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-09-01 | 2015-10-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 24 | 20 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.02 | Filter Loader | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Design/Engineering
FALSE |  | CCS127200 | COMP: Sensor 1st Article & Management Reports - eTraveler | LSST Forecast - B57 - B1 | 0 | 0 | 2015-08-01 | 2015-08-01 | 0 | 2015-08-01 | 2015-08-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2015-09-14 | 2015-09-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.10 | E Manufacturing | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Tony Johnson |  |  | Level 4 Milestone | Design/Engineering | [14 empty] | CCS Infrastructure
FALSE |  | CR230360 | Generate Final ICD - Corner raft sensor assembly to wavefront sensor | LSST Forecast - B57 - B1 | 10 | 0 | 2015-08-03 | 2015-08-14 | 0 | 2015-08-03 | 2015-08-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-10-20 | 2015-11-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 0 | 0 | 0 | 6 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 16 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 16 | 16 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | SR530600 | TS5 - Cryo Supt. Fixture Fab and Assembly | LSST Forecast - B57 - B1 | 10 | 0 | 2015-08-03 | 2015-10-30 | 0 | 2015-08-03 | 2015-10-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-09-01 | 2015-09-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 63 |  | Complete | 100% | 160 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.02 | RSA & RTM Warm-Cold Metrology (TS5) | 160 | 160 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 5 - Procurement & Fabrication |  | Science Raft System
FALSE |  | CR230370 | Generate Final ICD - Corner raft sensor assembly to Guide Sensor | LSST Forecast - B57 - B1 | 10 | 0 | 2015-08-03 | 2015-08-14 | 0 | 2015-08-03 | 2015-08-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-08-03 | 2015-08-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 10 |  | Complete | 100% | 16 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 16 | 16 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CR220700 | Design prototype - corner raft test setup EM revision (sidewall, cooling bars, support rods) | LSST Forecast - B57 - B1 | 15 | 0 | 2015-08-07 | 2015-10-05 | 0 | 2015-08-07 | 2015-10-05 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2015-08-06 | 2015-08-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 40 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Tower Module (CRTM) (TEC) | CRTM Prototype EM Revision | [5 empty] | Corner Raft Tower Module (CRTM)
FALSE |  | CCS105200 | Test/Validate Release 1 - CCS MCM | LSST Forecast - B57 - B1 | 13 | 0 | 2015-08-17 | 2015-08-23 | 0 | 2015-08-17 | 2015-08-23 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-10-07 | 2015-10-23 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 13 | 5 |  | Complete | 100% | 208 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.03 | CCS Master Control Module | 208 | 208 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering | [7 empty] | CCS Core (TEC)
FALSE |  | SR343220 | Perform vendor qualification & Extended VST | LSST Forecast - B57 - B1 | 19 | 0 | 2015-08-17 | 2015-10-30 | 0 | 2015-08-17 | 2015-10-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2015-11-02 | 2015-11-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 3 | 0 | 0 | 2 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 19 | 54 |  | Complete | 100% | 174 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 174 | 174 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation | [7 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [6 empty] | History Activity - Cannot Change |  | Science Raft System
FALSE |  | CRYO60880 | Final Design & Analysis - Sys Architecture and Functional Layout - Refrigeration | LSST Forecast - B57 - B1 | 60 | 0 | 2015-09-01 | 2016-04-30 | 0 | 2015-09-01 | 2016-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2015-10-01 | 2016-01-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 159 |  | Complete | 100% | 220 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 220 | 220 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | CRYO60890 | Final Design & Analysis - Compressor Chassis - Refrigeration | LSST Forecast - B57 - B1 | 60 | 0 | 2015-09-01 | 2016-04-30 | 0 | 2015-09-01 | 2016-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-10-01 | 2016-01-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 159 |  | Complete | 100% | 108 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 108 | 108 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | CRYO60900 | Final Design & Analysis - Valve & Filters/Desiccators - Refrigeration | LSST Forecast - B57 - B1 | 60 | 0 | 2015-09-01 | 2016-04-30 | 0 | 2015-09-01 | 2016-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-10-01 | 2016-01-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 159 |  | Complete | 100% | 108 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 108 | 108 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | CRYO60910 | Final Design & Analysis - Control Chassis and Instrumentation - Refrigeration | LSST Forecast - B57 - B1 | 60 | 0 | 2015-09-01 | 2016-04-30 | 0 | 2015-09-01 | 2016-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-10-01 | 2016-01-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 159 |  | Complete | 100% | 128 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 128 | 128 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | CRYO60920 | Final Design & Analysis - OP Evacuate, Purge & Charge HW - Refrigeration | LSST Forecast - B57 - B1 | 60 | 0 | 2015-09-01 | 2016-04-30 | 0 | 2015-09-01 | 2016-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-10-01 | 2016-01-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 159 |  | Complete | 100% | 264 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 264 | 264 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | CRYO11552 | Finalize Design Phase 2 - Cryostat Assembly | LSST Forecast - B57 - B1 | 50 | 0 | 2015-09-01 | 2015-10-31 | 0 | 2015-09-01 | 2015-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-10-01 | 2015-12-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 50 | 43 |  | Complete | 100% | 105 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 105 | 105 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Housing & Assembly (TEC) |  | ICD's for Phase 3 |  |  |  |  | Cryostat Assembly |  |  | Final Design Link
FALSE |  | CRYO11554 | Finalize Analysis - Phase 2 - Cryostat Assembly | LSST Forecast - B57 - B1 | 47 | 0 | 2015-09-05 | 2015-10-31 | 0 | 2015-09-05 | 2015-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-10-05 | 2015-12-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 47 | 39 |  | Complete | 100% | 88 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 88 | 88 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Housing & Assembly (TEC) | [6 empty] | Cryostat Assembly
FALSE |  | CRYO18302 | COMP: Cryogenic Feedthrough Test Parts - Cryo & Cold Plate | LSST Forecast - B57 - B1 | 0 | 0 | 2015-09-14 | 2015-09-14 | 0 | 2015-09-14 | 2015-09-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2015-12-14 | 2015-12-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.03 | Cryo and Cold Plates | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Engineering Test/Validation
FALSE |  | OP530500 | Critical Design Review Actions Complete - L1-L2 Assembly - Phase 2 | LSST Forecast - B57 - B1 | 20 | 0 | 2015-09-14 | 2015-10-30 | 0 | 2015-09-14 | 2015-10-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-03 | 2019-09-03 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-10-01 | 2015-10-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 2 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 34 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Scott Winters | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor | [5 empty] | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly) |  |  |  | L1-L2 Opto-Mechanics |  |  |  | CP - CAMM2100 (L1-L2 Assembly Phase 2 FDR)
FALSE |  | SR522605 | COMP: Test Stand 2 assy dwg's complete | LSST Forecast - B57 - B1 | 0 | 0 | 2015-09-18 | 2015-09-18 | 0 | 2015-09-18 | 2015-09-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2015-10-29 | 2015-10-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.02 | Sensor Dimensional Metrology (TS2) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl |  |  | Level 4 Milestone | Design/Engineering | [8 empty] | Test Stand Effort | [12 empty] | Test Stand 2 - Design |  | Science Sensors
FALSE |  | SR522935 | AVAIL: Test Stand 2 - Ready for Production | LSST Forecast - B57 - B1 | 0 | 0 | 2015-09-18 | 2015-09-18 | 0 | 2015-09-18 | 2015-09-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2015-10-29 | 2015-10-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 11 | 0 | 11 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.02 | Sensor Dimensional Metrology (TS2) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl |  |  | Level 5 Milestone | Fabrication/Assembly | [8 empty] | Test Stand Effort | [12 empty] | Test Stand 2 - Assembly & Commissioning |  | Science Sensors
FALSE |  | CRYO18228 | COMP: Flow/Thermal Design Prototype - Cryo & Cold Plate | LSST Forecast - B57 - B1 | 0 | 0 | 2015-09-25 | 2015-09-25 | 0 | 2015-09-25 | 2015-09-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2015-11-02 | 2015-11-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 2 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.03 | Cryo and Cold Plates | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Engineering Test/Validation
FALSE |  | CAMF806080 | NEED: CCS Pre-Production - Auto Changer | LSST Forecast - B57 - B1 | 0 | 0 | 2015-09-29 | 2015-09-29 | 0 | 2015-09-29 | 2015-09-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-06-19 | 2017-06-19 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.01 | Auto Changer | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  | Level 5 Milestone | Engineering Test/Validation
FALSE |  | OP531730 | AVAIL: Anti-Reflection Coating witness sample | LSST Forecast - B57 - B1 | 0 | 0 | 2015-09-30 | 2015-09-30 | 0 | 2015-09-30 | 2015-09-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2015-10-29 | 2015-10-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  | Level 5 Milestone | Engineering Test/Validation
FALSE |  | CCS119850 | COMP: Core 2.1 Release | LSST Forecast - B57 - B1 | 0 | 0 | 2015-10-01 | 2015-10-01 | 0 | 2015-10-01 | 2015-10-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-31 | 2019-05-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2015-12-01 | 2015-12-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.02.04 | CCS Core 3.0 Release (Support MCM) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  | Level 4 Milestone | Design/Engineering
FALSE |  | CCS100600 | Management FY16 - CCS | LSST Forecast - B57 - B1 | 245 | 0 | 2015-10-01 | 2016-09-30 | 0 | 2015-10-01 | 2016-09-30 | 0 | 2019-06-01 | 2019-06-01 | 2021-11-15 | 2021-11-15 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2015-10-01 | 2016-09-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 3 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 245 | 244 |  | Complete | 100% | 580 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.01 | CCS Integration & Management | 580 | 580 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Management/Administration |  | Construction Management | [5 empty] | CCS Integration & Management (TEC) | [6 empty] | Camera Control System
FALSE |  | SR345850 | Procurement of RTB (Fab and Assembly) | LSST Forecast - B57 - B1 | 7 | 0 | 2015-10-01 | 2015-10-09 | 0 | 2015-10-01 | 2015-10-09 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-10-01 | 2015-10-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 7 | 7 |  | Complete | 100% | 4 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.06 | Electronics Production Test | 4 | 4 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering | [7 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [6 empty] | RTB - Procurement & Fabrication |  | Science Raft System
FALSE |  | SR552650 | Install & Commission Test Stand 4 | LSST Forecast - B57 - B1 | 15 | 0 | 2015-10-01 | 2016-02-15 | 0 | 2015-10-01 | 2016-02-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-10-01 | 2015-10-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 91 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.07.01 | Cleanroom Development & Commissioning | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Assembly and Test Facility (TEC) | Test Stand Effort | [5 empty] | Science Raft - Assembly and Test Facility | [6 empty] | Test Stand 4 - Assembly & Commissioning |  | Science Raft System
FALSE |  | CCS108800 | Procurement Process - Components - Diagnostic Cluster for I&T | LSST Forecast - B57 - B1 | 20 | 0 | 2015-10-02 | 2016-06-15 | 0 | 2015-10-02 | 2016-06-15 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-11-02 | 2015-12-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 10 | 10 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 168 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.09 | CCS Diagnostic Cluster and Visualization | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  |  | Procurement
FALSE |  | ITC24600 | Assemble and test BOT prototype | LSST Forecast - B57 - B1 | 20 | 0 | 2015-10-02 | 2016-06-30 | 0 | 2015-10-02 | 2016-06-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-10-02 | 2015-10-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 179 |  | Complete | 100% | 160 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.02.01 | Bench For Optical Testing (BOT) | 160 | 160 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 13% |  | Engineering Test/Validation |  | Commissioning and Testing | [5 empty] | Verification Test Systems (TEC) | [6 empty] | Verification Test Systems
FALSE |  | CR220800 | Assemble & Test prototype - corner raft test setup EM revision (sidewall, cooling bars, support rods) | LSST Forecast - B57 - B1 | 15 | 0 | 2015-10-07 | 2016-02-25 | 0 | 2015-10-07 | 2016-02-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-12-21 | 2016-01-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 3 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 94 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Tower Module (CRTM) (TEC) | CRTM Prototype EM Revision | [5 empty] | Corner Raft Tower Module (CRTM)
FALSE |  | SR552540 | Prep for SRTM MRR | LSST Forecast - B57 - B1 | 2 | 0 | 2015-10-19 | 2016-09-12 | 0 | 2015-10-19 | 2016-09-12 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-12-07 | 2015-12-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 225 |  | Complete | 100% | 160 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.01 | Science Raft Tower Module (SRTM) | 160 | 160 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Construction Management | [5 empty] | Science Raft Tower Module (SRTM) (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Tower Module |  | Science Raft System
FALSE |  | CRYO60820 | COMP: Heat Ex Test Stand #2 | LSST Forecast - B57 - B1 | 0 | 0 | 2015-10-27 | 2015-10-27 | 0 | 2015-10-27 | 2015-10-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2016-01-21 | 2016-01-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Engineering Test/Validation
FALSE |  | OP530650 | AWARD: L1-L2 Assembly - Phase 4a | LSST Forecast - B57 - B1 | 1 | 0 | 2015-10-29 | 2015-10-29 | 0 | 2015-10-29 | 2015-10-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-03 | 2019-09-03 | 2052000 | 2052000 | 0 | 0 | 0 | 5 | FALSE | Normal | FALSE | 2015-11-16 | 2015-11-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 2052000 | 2052000 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | B1 Procurement Commitment (C5.1) | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 2% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | L1-L2 Assembly (TEC) | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly) |  |  |  | L1-L2 Opto-Mechanics
FALSE |  | OP530880 | AWARD: L1-L2 Assembly - Phase 4b | LSST Forecast - B57 - B1 | 1 | 0 | 2015-10-29 | 2015-10-29 | 0 | 2015-10-29 | 2015-10-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-03 | 2019-09-03 | 2921762 | 2921762 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2015-12-02 | 2015-12-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 2921762 | 2921762 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | B1 Procurement Commitment (C5.1) | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 2% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | L1-L2 Assembly (TEC) | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly) |  |  |  | L1-L2 Opto-Mechanics
FALSE |  | SR530650 | TS4 - generate Work-Flow | LSST Forecast - B57 - B1 | 20 | 0 | 2015-11-02 | 2016-01-29 | 0 | 2015-11-02 | 2016-01-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-11-02 | 2015-12-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 59 |  | Complete | 100% | 160 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.01 | RSA Assembly (TS4) | 160 | 160 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 4 - Design |  | Science Raft System
FALSE |  | SE223170 | Corner Raft sub-system FDR contamination compliance | LSST Forecast - B57 - B1 | 19 | 0 | 2015-11-09 | 2016-04-29 | 0 | 2015-11-09 | 2016-04-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-12-01 | 2016-01-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 19 | 110 |  | Complete | 100% | 44 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.03 | Thermal and contamination system analysis | 44 | 44 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | DAQ340800 | AVAIL: Prototype - RDS/RDC | LSST Forecast - B57 - B1 | 0 | 0 | 2015-11-15 | 2015-11-15 | 0 | 2015-11-15 | 2015-11-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | FALSE | 2016-02-17 | 2016-02-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.09.02 | Raft Data Server/Client Software (RDS/RDC) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer |  |  | Level 5 Milestone | Engineering Test/Validation | [9 empty] | ICD's for Phase 3
FALSE |  | CR240680 | Prep for C_FDR - WEB | LSST Forecast - B57 - B1 | 9 | 0 | 2015-11-17 | 2016-02-26 | 0 | 2015-11-17 | 2016-02-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-01-13 | 2016-01-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 8 | 0 | 5 | 0 | 0 | 3 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 9 | 59 |  | Complete | 100% | 48 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.01 | Wavefront Electronics Board (WEB) | 48 | 48 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Electronics (TEC) | WEB EM | [5 empty] | Corner Raft Electronics
FALSE |  | CR241980 | Prep for C_FDR - GEB | LSST Forecast - B57 - B1 | 10 | 0 | 2015-11-17 | 2016-02-26 | 0 | 2015-11-17 | 2016-02-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-02-10 | 2016-02-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 1 | 5 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 59 |  | Complete | 100% | 48 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.02 | Guider Electronics Board (GEB) | 48 | 48 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Electronics (TEC) | GEB EM | [5 empty] | Corner Raft Electronics
FALSE |  | SR530870 | TS5 - Verification testing and commissioning | LSST Forecast - B57 - B1 | 10 | 0 | 2015-11-23 | 2016-11-30 | 0 | 2015-11-23 | 2016-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-12-18 | 2016-01-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 2 | 0 | 0 | 2 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 255 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.02 | RSA & RTM Warm-Cold Metrology (TS5) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 5 - Assembly & Commissioning |  | Science Raft System
FALSE |  | CRYO60620 | COMP: Subscale Test Stand (Elevation Articulation) | LSST Forecast - B57 - B1 | 0 | 0 | 2015-11-25 | 2015-11-25 | 0 | 2015-11-25 | 2015-11-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Finish Milestone | FALSE | 2016-01-25 | 2016-01-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 0 | 0 | 1 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Engineering Test/Validation
FALSE |  | SR341160 | Test - Prod ASPIC | LSST Forecast - B57 - B1 | 49 | 0 | 2015-11-27 | 2015-12-21 | 0 | 2015-11-27 | 2015-12-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 5 | FALSE | Normal | FALSE | 2015-12-15 | 2016-02-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 1 | 0 | 2 | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 140 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 49 | 15 |  | Complete | 100% | 400 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.01 | ASPIC | 400 | 400 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [6 empty] | ASPICS |  | Science Raft System
FALSE |  | CAMF667500 | Final Check & Approve Detail Dwgs - Carousel | LSST Forecast - B57 - B1 | 20 | 0 | 2015-12-01 | 2017-01-27 | 0 | 2015-12-01 | 2017-01-27 | 0 | 2019-06-01 | 2019-06-01 | 2018-10-16 | 2018-10-16 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-01-20 | 2016-02-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 274 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Design/Engineering
FALSE |  | CRYO18244 | COMP: Cryoplate Flexure Test Article - Cryo & Cold Plate | LSST Forecast - B57 - B1 | 0 | 0 | 2015-12-01 | 2015-12-01 | 0 | 2015-12-01 | 2015-12-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2016-01-04 | 2016-01-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.03 | Cryo and Cold Plates | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Engineering Test/Validation
FALSE |  | CCS116680 | Build TS8 - Production | LSST Forecast - B57 - B1 | 25 | 0 | 2015-12-01 | 2016-03-31 | 0 | 2015-12-01 | 2016-03-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-02-09 | 2016-03-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 75 |  | Complete | 100% | 96 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.01.04 | Test Stand 8 (REB Based) | 96 | 96 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 11% |  | Fabrication/Assembly | [7 empty] | CCS HCU (TEC)
FALSE |  | CR222590 | Assemble Cold Single CCD test stand | LSST Forecast - B57 - B1 | 4 | 0 | 2015-12-07 | 2016-02-19 | 0 | 2015-12-07 | 2016-02-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-03-01 | 2016-03-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 1 | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 42 |  | Complete | 100% | 16 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 16 | 16 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | [11 empty] | Corner Raft Tower Module (CRTM) (TEC)
FALSE |  | CRYO17000 | Generate Manufacturing Docs - Cryo & Cold Plate | LSST Forecast - B57 - B1 | 30 | 0 | 2015-12-09 | 2017-04-28 | 0 | 2015-12-09 | 2017-04-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-04-06 | 2016-05-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 332 |  | Complete | 100% | 64 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.03 | Cryo and Cold Plates | 64 | 64 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryo and Cold Plates (TEC) | [6 empty] | Cryo and Cold Plates
FALSE |  | SR530090 | TS8 - Assembly technical support | LSST Forecast - B57 - B1 | 30 | 0 | 2015-12-21 | 2016-06-30 | 0 | 2015-12-21 | 2016-06-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-01-04 | 2016-02-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 132 |  | Complete | 100% | 128 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.05 | RTM Electro-Optical Testing (TS8) | 128 | 128 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 8 - Procurement & Fabrication |  | Science Raft System
FALSE |  | SR530430 | PREP for TS6 MRR | LSST Forecast - B57 - B1 | 8 | 0 | 2015-12-30 | 2015-12-31 | 0 | 2015-12-30 | 2015-12-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-12-30 | 2016-01-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 1 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 8 | 1 |  | Complete | 100% | 30 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.03 | RTM Assembly (TS6) | 30 | 30 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 6 - Reviews |  | Science Raft System
FALSE |  | SR530770 | Prep for C_MRR-TS4 | LSST Forecast - B57 - B1 | 20 | 0 | 2016-01-01 | 2016-01-30 | 0 | 2016-01-01 | 2016-01-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-02-01 | 2016-02-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 4 | 1 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 19 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.01 | RSA Assembly (TS4) | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 4 - Reviews |  | Science Raft System
FALSE |  | SR332505 | FA Testing - Sensors V1 (1 Set, 5 sensors, 1-5) | LSST Forecast - B57 - B1 | 32 | 0 | 2016-01-04 | 2016-11-25 | 0 | 2016-01-04 | 2016-11-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-02-02 | 2016-03-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 4 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 32 | 228 |  | Complete | 100% | 210 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 210 | 210 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Catalog Listing or Industrial Construction Databases | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [6 empty] | Science Sensors Acceptance | [6 empty] | Sensors Vendor 1 |  | Science Sensors
FALSE |  | SR344320 | Integrate emulator w/JK software (BNL & UPenn) | LSST Forecast - B57 - B1 | 20 | 0 | 2016-01-16 | 2016-04-29 | 0 | 2016-01-16 | 2016-04-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-02-16 | 2016-03-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 1 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 72 |  | Complete | 100% | 200 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 200 | 200 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation | [7 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [6 empty] | REB4 Test Stand Development (TS-REB) |  | Science Raft System
FALSE |  | CCS119950 | Bug fixes from 2.5 release - Core 3.0 Release | LSST Forecast - B57 - B1 | 20 | 0 | 2016-01-25 | 2016-03-13 | 0 | 2016-01-25 | 2016-03-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-31 | 2019-05-31 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-04-01 | 2016-04-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 34 |  | Complete | 100% | 125 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.02.04 | CCS Core 3.0 Release (Support MCM) | 125 | 125 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering | [7 empty] | CCS Core (TEC)
FALSE |  | SR529740 | TS8a - Construct test platform using TS8 dewar | LSST Forecast - B57 - B1 | 7 | 0 | 2016-02-01 | 2016-02-28 | 0 | 2016-02-01 | 2016-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-04-21 | 2016-04-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 7 | 19 |  | Complete | 100% | 48 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.06 | RTM Electro-Optical Testing (TS8a) For SLAC | 48 | 48 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 8a - Testing |  | Science Raft System
FALSE |  | OP540660 | Prep for C_FDR/MRR--Optics - L3 Assembly | LSST Forecast - B57 - B1 | 19 | 0 | 2016-02-01 | 2016-07-07 | 0 | 2016-02-01 | 2016-07-07 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2016-06-10 | 2016-07-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 19 | 110 |  | Complete | 100% | 604 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 604 | 604 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 14% |  | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | L3 Assembly (TEC) | [6 empty] | L1-L2 Opto-Mechanics
FALSE |  | ITC17605 | Update Defining Documentation - SBMS | LSST Forecast - B57 - B1 | 10 | 0 | 2016-02-01 | 2016-05-27 | 0 | 2016-02-01 | 2016-05-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-04-12 | 2016-04-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 83 |  | Complete | 100% | 36 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.01.01 | Single Bay Metrology Tests | 36 | 36 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC)
FALSE |  | SR531100 | TS7 - acceptance test of fabrication/assy hardware | LSST Forecast - B57 - B1 | 10 | 0 | 2016-02-01 | 2016-02-15 | 0 | 2016-02-01 | 2016-02-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-02-01 | 2016-02-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 10 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.04 | RTM Cryostat Integration (TS7) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 7 - Procurement & Fabrication |  | Science Raft System
FALSE |  | SR529940 | TS8 - generate final measurement test script and software requirements | LSST Forecast - B57 - B1 | 23 | 0 | 2016-02-01 | 2016-11-30 | 0 | 2016-02-01 | 2016-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-02-01 | 2016-03-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 23 | 211 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.05 | RTM Electro-Optical Testing (TS8) | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 8 - Design |  | Science Raft System
FALSE |  | CR211700 | Prep for C_FDR - Corner Raft | LSST Forecast - B57 - B1 | 10 | 0 | 2016-02-08 | 2016-02-26 | 0 | 2016-02-08 | 2016-02-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-02-12 | 2016-02-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 4 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 13 |  | Complete | 100% | 48 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.01 | Corner Raft System Integration and Management | 48 | 48 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft System Integration and Management (TEC) | Management | [5 empty] | Corner Raft System Integration and Management
FALSE |  | CR230400 | Prep for C_FDR - Corner raft sensor assembly | LSST Forecast - B57 - B1 | 10 | 0 | 2016-02-08 | 2016-02-26 | 0 | 2016-02-08 | 2016-02-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-02-12 | 2016-02-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 13 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | DAQ360500 | COMP: Prototype - IMS/IMC | LSST Forecast - B57 - B1 | 0 | 0 | 2016-02-08 | 2016-02-08 | 0 | 2016-02-08 | 2016-02-08 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2016-04-05 | 2016-04-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.09.01 | Image Management/Server/Client Software | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer |  |  | Level 4 Milestone | Engineering Test/Validation
FALSE |  | ITC33306 | Update Defining Documentation - Gantry | LSST Forecast - B57 - B1 | 10 | 0 | 2016-02-08 | 2016-06-30 | 0 | 2016-02-08 | 2016-06-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2016-03-01 | 2016-03-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 101 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.01 | Integration Gantry | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat I&T (TEC)
FALSE |  | ITC33700 | Update Defining Documentation - Cryo-Equip | LSST Forecast - B57 - B1 | 5 | 0 | 2016-02-08 | 2016-10-18 | 0 | 2016-02-08 | 2016-10-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-24 | 2019-07-24 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-03-01 | 2016-03-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 177 |  | Complete | 100% | 18 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.02 | Cryostat Handling Equipment | 18 | 18 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat I&T (TEC)
FALSE |  | ITC19400 | Update Defining Documentation - Integration Stand | LSST Forecast - B57 - B1 | 10 | 0 | 2016-02-08 | 2017-10-24 | 0 | 2016-02-08 | 2017-10-24 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-03 | 2019-06-03 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-08-01 | 2016-08-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 424 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.01 | Camera Integration Stand | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Camera I&T (TEC)
FALSE |  | CR220620 | Prep for C_FDR - Corner raft tower, tooling, shipping container | LSST Forecast - B57 - B1 | 11 | 0 | 2016-02-11 | 2016-02-26 | 0 | 2016-02-11 | 2016-02-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-02-11 | 2016-02-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 11 | 10 |  | Complete | 100% | 60 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 60 | 60 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Tower Module (CRTM) (TEC) | CRTM Final Design | [5 empty] | Corner Raft Tower Module (CRTM)
FALSE |  | OP522320 | AWARD: Procure Filter Blank (5 blanks) | LSST Forecast - B57 - B1 | 1 | 0 | 2016-02-11 | 2016-02-11 | 0 | 2016-02-11 | 2016-02-11 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-28 | 2020-01-28 | 127725 | 127725 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-03-14 | 2016-03-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 127725 | 127725 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | B1 Procurement Commitment (C5.1) |  | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 18% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Filters (TEC) | Production Filters Blank | [5 empty] | Filter Optics
FALSE |  | DAQ360900 | Update Documentation - Pre-Production - IMS/IMC | LSST Forecast - B57 - B1 | 20 | 0 | 2016-02-12 | 2016-05-28 | 0 | 2016-02-12 | 2016-05-28 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-04-12 | 2016-05-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 75 |  | Complete | 100% | 20 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.09.01 | Image Management/Server/Client Software | 20 | 20 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Testing/Integration |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | DAQ Readout Systems (TEC)
FALSE |  | CR220820 | AVAIL: Prototype - corner raft test setup EM revision (sidewall, cooling bars, support rods) | LSST Forecast - B57 - B1 | 0 | 0 | 2016-02-25 | 2016-02-25 | 0 | 2016-02-25 | 2016-02-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2016-02-19 | 2016-02-19 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% | Level 5 Milestone | Engineering Test/Validation | [8 empty] | CRTM Prototype EM Revision
FALSE |  | SR343700 | Assemble at Vendor, Clean & Test (15) First Article REB4 boards (ETU 1 & 2) | LSST Forecast - B57 - B1 | 25 | 0 | 2016-02-26 | 2016-04-29 | 0 | 2016-02-26 | 2016-04-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-02-26 | 2016-03-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 45 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation | [7 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [6 empty] | Assembly at Vendor (ETU 1 & 2) |  | Science Raft System
FALSE |  | CR211720 | C_FDR - Comp. Final Design Review - Corner Raft | LSST Forecast - B57 - B1 | 1 | 0 | 2016-02-29 | 2016-03-01 | 0 | 2016-02-29 | 2016-03-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-02-29 | 2016-02-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 6 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 1 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.01 | Corner Raft System Integration and Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  |  | Design/Engineering | [8 empty] | Management
FALSE |  | CR240700 | C_FDR - Comp. Final Design Review - WEB | LSST Forecast - B57 - B1 | 1 | 0 | 2016-02-29 | 2016-03-01 | 0 | 2016-02-29 | 2016-03-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-02-29 | 2016-02-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 1 |  | Complete | 100% | 8 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.01 | Wavefront Electronics Board (WEB) | 8 | 8 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Design Reviews | [5 empty] | Corner Raft Electronics (TEC) | WEB EM
FALSE |  | CR242000 | C_FDR - Comp. Final Design Review - GEB | LSST Forecast - B57 - B1 | 1 | 0 | 2016-02-29 | 2016-03-01 | 0 | 2016-02-29 | 2016-03-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-02-29 | 2016-02-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 8 | 0 | 8 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 1 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.02 | Guider Electronics Board (GEB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  |  | Design/Engineering | [8 empty] | GEB EM
FALSE |  | DAQ900160 | Fabricate Prototype Hybrid RTM (8) | LSST Forecast - B57 - B1 | 15 | 0 | 2016-03-01 | 2016-07-30 | 0 | 2016-03-01 | 2016-07-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-04-01 | 2016-04-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 3 | 2 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 107 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.13.03 | DAQ Version 2.0 | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer |  |  |  | Engineering Test/Validation
FALSE |  | CRYO11720 | Final Design & Engineering - Faro Arm Stand - Cryostat Assembly | LSST Forecast - B57 - B1 | 40 | 0 | 2016-03-07 | 2016-06-26 | 0 | 2016-03-07 | 2016-06-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-04-07 | 2016-06-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 30 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 79 |  | Complete | 100% | 26 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 26 | 26 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Housing & Assembly (TEC)
FALSE |  | OP522085 | AWARD: Filter First Article fabrication (Phase 1) | LSST Forecast - B57 - B1 | 1 | 0 | 2016-03-21 | 2016-03-21 | 0 | 2016-03-21 | 2016-03-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-25 | 2019-07-25 | 250700 | 250700 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-04-01 | 2016-04-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 250700 | 250700 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | B1 Procurement Commitment (C5.1) |  | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 18% | Level 4 Milestone | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Filters (TEC) | First Article Substrate Finishing | [5 empty] | Filter Optics
FALSE |  | SR345900 | COMP: REB Test Board (RTB) - Production REB Testing | LSST Forecast - B57 - B1 | 0 | 0 | 2016-03-31 | 2016-03-31 | 0 | 2016-03-31 | 2016-03-31 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2016-05-20 | 2016-05-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.06 | Electronics Production Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% | Level 4 Milestone | Design/Engineering | [21 empty] | RTB - Testing |  | Science Raft System
FALSE |  | ITC12900 | Finalize Ops and Maint procedures for I&T Facility | LSST Forecast - B57 - B1 | 47 | 0 | 2016-04-04 | 2016-09-30 | 0 | 2016-04-04 | 2016-09-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-05-02 | 2016-07-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 47 | 126 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.03 | IR2 Facility and Operations | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) |  | Integration Test and Calibration |  |  |  | Camera I&T (TEC) | [6 empty] | I&T Facility
FALSE |  | CR230590 | Check & approve Drawings - Corner raft sensor assembly | LSST Forecast - B57 - B1 | 30 | 0 | 2016-04-04 | 2016-05-31 | 0 | 2016-04-04 | 2016-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-05-02 | 2016-06-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 40 |  | Complete | 100% | 20 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 20 | 20 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | OP521780 | AWARD: Contract - Filter Development and Witness Sample (Phase 1) | LSST Forecast - B57 - B1 | 1 | 0 | 2016-04-05 | 2016-04-05 | 0 | 2016-04-05 | 2016-04-05 | 0 | 2019-06-01 | 2019-06-01 | 2019-12-12 | 2019-12-12 | 971000 | 971000 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2016-05-02 | 2016-05-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 971000 | 971000 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | B1 Procurement Commitment (C5.1) |  | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 18% | Level 4 Milestone | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Filters (TEC) | Witness Sample | [5 empty] | Filter Optics
FALSE |  | SR530930 | TS5 - Revise scripting and software | LSST Forecast - B57 - B1 | 25 | 0 | 2016-04-11 | 2016-11-30 | 0 | 2016-04-11 | 2016-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-05-10 | 2016-06-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 162 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.02 | RSA & RTM Warm-Cold Metrology (TS5) | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 5 - Assembly & Commissioning |  | Science Raft System
FALSE |  | CRYO22870 | Vendor Lead Time - Final Machining (Step 1) | LSST Forecast - B57 - B1 | 56 | 0 | 2016-04-18 | 2016-11-18 | 0 | 2016-04-18 | 2016-11-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-05-18 | 2016-08-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 56 | 151 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.04 | Grid Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor | [11 empty] | Grid Assembly | [5 empty] | CP - CAMM2160 (Cryostat Assy Ready for Integration)
FALSE |  | CRYO60855 | Test - Polyimide Hose Compatibility Test - Hose | LSST Forecast - B57 - B1 | 20 | 0 | 2016-04-23 | 2016-04-30 | 0 | 2016-04-23 | 2016-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-05-23 | 2016-06-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 5 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 16% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | CRYO22100 | COMP: Final Design and Engineering Phase - Grid Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2016-04-27 | 2016-04-27 | 0 | 2016-04-27 | 2016-04-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2016-06-01 | 2016-06-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.04 | Grid Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Design/Engineering
FALSE |  | CRYO60870 | COMP: Hose and Fitting Test Stand | LSST Forecast - B57 - B1 | 0 | 0 | 2016-04-30 | 2016-04-30 | 0 | 2016-04-30 | 2016-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | FALSE | 2016-06-20 | 2016-06-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Engineering Test/Validation
FALSE |  | AE211110 | Design Pre-Production Cryostat HCU | LSST Forecast - B57 - B1 | 25 | 0 | 2016-05-01 | 2016-09-28 | 0 | 2016-05-01 | 2016-09-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-06-01 | 2016-07-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 104 |  | Complete | 100% | 20 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.02.11 | Cryostat HCU | 20 | 20 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Gunther Haller | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Aux Elec Components (TEC) | [6 empty] | Power Control Monitoring
FALSE |  | SR550040 | RTM ETU #1 - Assembly and Test | LSST Forecast - B57 - B1 | 50 | 0 | 2016-05-02 | 2016-12-30 | 0 | 2016-05-02 | 2016-12-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-06-22 | 2016-08-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 4 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 30 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 50 | 167 |  | Complete | 100% | 800 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 800 | 800 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM ETU #1 |  | Science Raft System
FALSE |  | OP540900 | L3 Assembly - Phase 3 (Flat Assy - Fine Grind) | LSST Forecast - B57 - B1 | 82 | 0 | 2016-05-02 | 2016-12-08 | 0 | 2016-05-02 | 2016-12-08 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-14 | 2019-05-14 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-06-01 | 2016-09-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 82 | 153 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor | [11 empty] | L1-L2 Opto-Mechanics
FALSE |  | SE223128 | Sub-system FDR camera thermal integrated analysis - Camera Body, Carousel, Autochanger & Purge | LSST Forecast - B57 - B1 | 33 | 0 | 2016-05-02 | 2016-10-28 | 0 | 2016-05-02 | 2016-10-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-09 | 2019-09-09 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-07-21 | 2016-09-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 2 | 2 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 33 | 126 |  | Complete | 100% | 100 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.03 | Thermal and contamination system analysis | 100 | 100 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | SR343740 | AVAIL: (15) REB4 fully tested boards ready for ETU Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2016-05-02 | 2016-05-02 | 0 | 2016-05-02 | 2016-05-02 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2016-06-01 | 2016-06-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% | Level 5 Milestone | Engineering Test/Validation | [7 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [6 empty] | Assembly at Vendor (ETU 1 & 2) |  | Science Raft System
FALSE |  | SR330165 | RCV: First Articles Sensor - V1 (1 Set, Batch 1b, 4 Sensors, 2-5) | LSST Forecast - B57 - B1 | 5 | 0 | 2016-05-10 | 2016-11-10 | 0 | 2016-05-10 | 2016-11-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 490000 | 490000 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-06-01 | 2016-06-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 129 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 490000 | 490000 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 20% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC) | [5 empty] | Sensor | [7 empty] | Sensors Vendor 1 |  | Science Sensors
FALSE |  | CCS207800 | Develop Simple Camera Command Simulator for Use by OCS - CCS/OCS | LSST Forecast - B57 - B1 | 15 | 0 | 2016-05-11 | 2016-05-29 | 0 | 2016-05-11 | 2016-05-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-17 | 2019-10-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-11-28 | 2016-12-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 13 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.04 | CCS/OCS Bridge | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Testing/Integration | [7 empty] | CCS Core (TEC)
FALSE |  | SR344395 | Ready: Test stand ready for use | LSST Forecast - B57 - B1 | 0 | 0 | 2016-05-13 | 2016-05-13 | 0 | 2016-05-13 | 2016-05-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2016-06-14 | 2016-06-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% | Level 4 Milestone | Engineering Test/Validation | [7 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [6 empty] | REB4 Test Stand Development (TS-REB) |  | Science Raft System
FALSE |  | CBM45500 | Develop Test/Equip Prelim Design (Shutter Proto) | LSST Forecast - B57 - B1 | 20 | 0 | 2016-05-15 | 2016-09-30 | 0 | 2016-05-15 | 2016-09-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-06 | 2019-08-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-06-01 | 2016-06-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 96 |  | Complete | 100% | 140.4 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.02.02 | Shutter Development | 140.4 | 140.4 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 5% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Shutter Development (TEC) | [6 empty] | Shutter Prototype
FALSE |  | CRYO53060 | COMP: Charge and Recovery for SLAC System (Link to FDR#2) | LSST Forecast - B57 - B1 | 0 | 0 | 2016-05-19 | 2016-05-19 | 0 | 2016-05-19 | 2016-05-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2016-06-01 | 2016-06-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Engineering Test/Validation
FALSE |  | DAQ361000 | COMP: Pre-Production - IMS/IMC | LSST Forecast - B57 - B1 | 0 | 0 | 2016-05-28 | 2016-05-28 | 0 | 2016-05-28 | 2016-05-28 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2016-06-28 | 2016-06-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.09.01 | Image Management/Server/Client Software | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer |  |  | Level 4 Milestone | Testing/Integration
FALSE |  | CR306611 | COMP: Corner Raft Assy Test Station | LSST Forecast - B57 - B1 | 0 | 0 | 2016-05-31 | 2016-05-31 | 0 | 2016-05-31 | 2016-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2016-06-29 | 2016-06-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.05 | Corner Raft Assembly and Test Station | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 4 Milestone | Testing/Integration | [8 empty] | CR Assy/Test Station Development
FALSE |  | CR230600 | Prep for Manufacturing Readiness Review - Corner raft sensor assembly | LSST Forecast - B57 - B1 | 33 | 0 | 2016-06-01 | 2016-07-18 | 0 | 2016-06-01 | 2016-07-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-07-01 | 2016-08-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 33 | 32 |  | Complete | 100% | 20 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 20 | 20 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | SR552159 | AWARD: RSA base plate (24 Production Units) | LSST Forecast - B57 - B1 | 10 | 0 | 2016-06-01 | 2016-06-14 | 0 | 2016-06-01 | 2016-06-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 573240 | 573240 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-07-01 | 2016-07-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.02 | Science Raft Sensor Assembly (SRSA) | 0 | 0 | 0 | 573240 | 573240 | 0 | PercentComplete | 6% | CP_Phys |  | B1 Procurement Commitment (C5.1) | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Raft Tower Module (SRTM) (TEC) | [13 empty] | Sensor Assembly |  | Science Raft System
FALSE |  | ITC31785 | Analysis Software - Early Hardware Procurements | LSST Forecast - B57 - B1 | 20 | 0 | 2016-06-06 | 2016-06-30 | 0 | 2016-06-06 | 2016-06-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 35000 | 35000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-07-01 | 2016-07-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 18 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.04 | Verification Software Development | 0 | 0 | 0 | 35000 | 35000 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Other (specify) | [5 empty] | Verification Test Systems (TEC)
FALSE |  | CR234390 | COMP: MRR - Wavefront Sensor | LSST Forecast - B57 - B1 | 0 | 0 | 2016-06-10 | 2016-06-10 | 0 | 2016-06-10 | 2016-06-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2016-09-08 | 2016-09-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.02 | Wavefront Sensor | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 4 Milestone | Design/Engineering
FALSE |  | CAMM6306 | AVAIL: Start testing of targeted components for refrigerator utilities | LSST Forecast - B57 - B1 | 0 | 0 | 2016-06-13 | 2016-06-13 | 0 | 2016-06-13 | 2016-06-13 | 0 | 2019-06-01 | 2019-06-01 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Start Milestone | FALSE | 2016-11-01 | 2016-11-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 0 | 6 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.03 | NSF Interface Milestone (NSF Needs) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration
FALSE |  | CR234400 | Prepare PO - Phase 2 Production 2Kx4K Wavefront Sensor (14 2kx4k sensors) | LSST Forecast - B57 - B1 | 10 | 0 | 2016-06-13 | 2016-06-17 | 0 | 2016-06-13 | 2016-06-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-09-09 | 2016-09-22 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 4 |  | Complete | 100% | 16 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.02 | Wavefront Sensor | 16 | 16 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 1% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | [6 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | SR561000 | Prepare C/C Material (24 Rafts) | LSST Forecast - B57 - B1 | 1 | 0 | 2016-06-15 | 2016-06-16 | 0 | 2016-06-15 | 2016-06-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-07-18 | 2016-07-18 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 1 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.02 | Science Raft Sensor Assembly (SRSA) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Bill Wahl | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement | [21 empty] | Sensor Assembly |  | Science Raft System
FALSE |  | ITC25640 | Test Definition Review - Prep - BOT | LSST Forecast - B57 - B1 | 10 | 0 | 2016-06-20 | 2016-07-19 | 0 | 2016-06-20 | 2016-07-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-08-24 | 2016-09-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 20 |  | Complete | 100% | 50 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.02.01 | Bench For Optical Testing (BOT) | 50 | 50 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC)
FALSE |  | SR343743_3 | Close MRR Action Items | LSST Forecast - B57 - B1 | 8 | 0 | 2016-06-27 | 2016-09-09 | 0 | 2016-06-27 | 2016-09-09 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-07-05 | 2016-07-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 0 | 0 | 0 | 6 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 8 | 52 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Bill Wahl | [25 empty] | First Article REB-5 Build |  | Science Raft System
FALSE |  | CBM44000 | Recv, Prep, Assemble, Test (Drive Train) | LSST Forecast - B57 - B1 | 60 | 0 | 2016-07-01 | 2017-04-15 | 0 | 2016-07-01 | 2017-04-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-06 | 2019-08-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-08-01 | 2016-10-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 4 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 189 |  | Complete | 100% | 432 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.02.02 | Shutter Development | 432 | 432 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 7% |  | Engineering Test/Validation |  | Commissioning and Testing | [5 empty] | Shutter Development (TEC) | [6 empty] | Drive Train Test Unit
FALSE |  | CCS200000 | Port TS8 to SLAC - Single Bay HCU | LSST Forecast - B57 - B1 | 30 | 0 | 2016-07-01 | 2016-12-15 | 0 | 2016-07-01 | 2016-12-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-08-01 | 2016-09-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 115 |  | Complete | 100% | 240 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.08.01 | Single Bay HCU | 240 | 240 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Expert Opinion (Engineering Allowance) | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 6% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | CCS HCU (TEC) | [6 empty] | Camera I&T Hardware Control Unit
FALSE |  | CR233050 | Prep for Manufacturing Readiness Review - Shipping/Storage Container | LSST Forecast - B57 - B1 | 11 | 0 | 2016-07-01 | 2016-07-18 | 0 | 2016-07-01 | 2016-07-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-08-01 | 2016-08-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 11 | 10 |  | Complete | 100% | 16 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 16 | 16 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Shipping Container Design/Prod | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | SR330705 | Sensors Production Lot 1 - V2- Backside Batch and Test (21-65) | LSST Forecast - B57 - B1 | 65 | 0 | 2016-07-01 | 2016-07-26 | 0 | 2016-07-01 | 2016-07-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 10 | FALSE | Normal | FALSE | 2016-08-01 | 2016-10-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 10 | 0 | 1 | 9 | 0 | 0 | 1 | 0 | 3 | 0 | 0 | 49 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 65 | 16 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien |  |  |  | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 14% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor | [10 empty] | Sensor | [7 empty] | Sensors Vendor 2
FALSE |  | OP540680 | C_FDR/MRR--L3 Assembly | LSST Forecast - B57 - B1 | 1 | 0 | 2016-07-07 | 2016-07-21 | 0 | 2016-07-07 | 2016-07-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-14 | 2019-05-14 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-09-01 | 2016-09-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 10 |  | Complete | 100% | 88 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 88 | 88 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 14% |  | Procurement | [7 empty] | L3 Assembly (TEC) |  |  | Critical Path #2 (L1_L2 Assembly) |  |  |  | L1-L2 Opto-Mechanics
FALSE |  | CR240780 | Prepare PROC - WEB EM (PCB & components) | LSST Forecast - B57 - B1 | 5 | 0 | 2016-07-11 | 2016-07-22 | 0 | 2016-07-11 | 2016-07-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2016-08-08 | 2016-08-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 9 |  | Complete | 100% | 15 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.01 | Wavefront Electronics Board (WEB) | 15 | 15 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Procurement | [7 empty] | Corner Raft Electronics (TEC) | WEB EM
FALSE |  | CR242220 | Additional custom software and engineering support for GEB EM testing | LSST Forecast - B57 - B1 | 30 | 0 | 2016-07-11 | 2017-03-17 | 0 | 2016-07-11 | 2017-03-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2016-08-29 | 2016-10-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 2 | 0 | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 163 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.02 | Guider Electronics Board (GEB) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Fabrication/Assembly | [7 empty] | Corner Raft Electronics (TEC) | GEB EM
FALSE |  | CR242240 | Functional Testing - GEB EM | LSST Forecast - B57 - B1 | 30 | 0 | 2016-07-11 | 2016-09-23 | 0 | 2016-07-11 | 2016-09-23 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-08-29 | 2016-10-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 2 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 53 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.02 | Guider Electronics Board (GEB) | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Testing/Integration | [7 empty] | Corner Raft Electronics (TEC) | GEB EM
FALSE |  | SR332675 | Prod. Testing - Sensors V2 (Sensors #21-24) | LSST Forecast - B57 - B1 | 4 | 0 | 2016-07-11 | 2016-07-15 | 0 | 2016-07-11 | 2016-07-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-10-10 | 2016-10-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 4 |  | Complete | 100% | 30 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 30 | 30 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Catalog Listing or Industrial Construction Databases | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [6 empty] | Science Sensors Acceptance | [6 empty] | Sensors Vendor 2 |  | Science Sensors
FALSE |  | OP522420 | Prepare procurement for Filter fabrication | LSST Forecast - B57 - B1 | 20 | 0 | 2016-07-12 | 2016-08-16 | 0 | 2016-07-12 | 2016-08-16 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-08-30 | 2016-09-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 25 |  | Complete | 100% | 56 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 56 | 56 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 18% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Filters (TEC) | Production Filters Polish and integration | [5 empty] | Filter Optics
FALSE |  | SR332680 | Prod. Testing - Sensors V2 (Sensors #25-28) | LSST Forecast - B57 - B1 | 7 | 0 | 2016-07-18 | 2016-07-22 | 0 | 2016-07-18 | 2016-07-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-10-14 | 2016-10-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 7 | 4 |  | Complete | 100% | 30 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 30 | 30 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Catalog Listing or Industrial Construction Databases | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [6 empty] | Science Sensors Acceptance | [6 empty] | Sensors Vendor 2 |  | Science Sensors
FALSE |  | CR233070 | COMP: MRR - Shipping/Storage Container | LSST Forecast - B57 - B1 | 0 | 0 | 2016-07-19 | 2016-07-19 | 0 | 2016-07-19 | 2016-07-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2016-08-16 | 2016-08-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 4 Milestone | Design/Engineering | [8 empty] | CRSA Shipping Container Design/Prod
FALSE |  | SR530070 | TS8 - fabrication/assy - CCS controller | LSST Forecast - B57 - B1 | 28 | 0 | 2016-07-28 | 2016-10-28 | 0 | 2016-07-28 | 2016-10-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-08-11 | 2016-09-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 2 | 0 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 28 | 65 |  | Complete | 100% | 16 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.05 | RTM Electro-Optical Testing (TS8) | 16 | 16 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 8 - Procurement & Fabrication |  | Science Raft System
FALSE |  | OP540700 | COMP: C_FDR/MRR-L3 Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2016-07-29 | 2016-07-29 | 0 | 2016-07-29 | 2016-07-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-14 | 2019-05-14 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2016-09-01 | 2016-09-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  | Level 4 Milestone | Procurement | [10 empty] | Critical Path #2 (L1_L2 Assembly)
FALSE |  | CRYO60770 | COMP: Subscale Test Stand (Final Details) | LSST Forecast - B57 - B1 | 0 | 0 | 2016-07-30 | 2016-07-30 | 0 | 2016-07-30 | 2016-07-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | FALSE | 2016-08-29 | 2016-08-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 2 | 0 | 0 | 2 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Engineering Test/Validation
FALSE |  | SR330950 | AWARD: Sensor Production Lot 2 | LSST Forecast - B57 - B1 | 1 | 0 | 2016-08-02 | 2016-08-02 | 0 | 2016-08-02 | 2016-08-02 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 427671 | 427671 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-10-03 | 2016-10-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 427671 | 427671 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien | B1 Procurement Commitment (C5.1) |  | TEC Non-ARRA | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 14% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Sensor | Science Sensors Procurement |  |  |  |  | CP - CAMM2130 (Award of Sensor Lot #2) |  | Lot 2 Primary Vendor
FALSE |  | SR332685 | Prod. Testing - Sensors V2 (Sensors #29-32) | LSST Forecast - B57 - B1 | 10 | 0 | 2016-08-18 | 2016-08-31 | 0 | 2016-08-18 | 2016-08-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-09-01 | 2016-09-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 30 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 30 | 30 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Catalog Listing or Industrial Construction Databases | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [6 empty] | Science Sensors Acceptance | [6 empty] | Sensors Vendor 2 |  | Science Sensors
FALSE |  | CR234475 | Vendor Effort - Phase 2 Production 2Kx4K Wavefront Sensor (Remaining 13 2kx4k sensors) - Delivery | LSST Forecast - B57 - B1 | 73 | 0 | 2016-08-19 | 2016-12-20 | 0 | 2016-08-19 | 2016-12-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-09-02 | 2016-12-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 73 | 83 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.02 | Wavefront Sensor | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  |  | Procurement
FALSE |  | SR550110 | RTM ETU #2 - Assembly and Test | LSST Forecast - B57 - B1 | 74 | 0 | 2016-08-22 | 2017-02-15 | 0 | 2016-08-22 | 2017-02-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-11-01 | 2017-02-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 74 | 120 |  | Complete | 100% | 680 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 680 | 680 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM ETU #2 |  | Science Raft System
FALSE |  | CR240820 | RCV: WEB EM (PCB & components) | LSST Forecast - B57 - B1 | 0 | 0 | 2016-08-26 | 2016-08-26 | 0 | 2016-08-26 | 2016-08-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2016-09-29 | 2016-09-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.01 | Wavefront Electronics Board (WEB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 4 Milestone | Procurement | [8 empty] | WEB EM
FALSE |  | CRYO31000 | Procurement Process - Feedthru Flange Rings/Pump Plate - Cryostat Back End | LSST Forecast - B57 - B1 | 20 | 0 | 2016-09-03 | 2016-09-30 | 0 | 2016-09-03 | 2016-09-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-10-03 | 2016-10-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 18 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.01 | Cryostat Back End | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  |  | Procurement
FALSE |  | CCS109900 | Install visualization system in IR-2- Diagnostic Cluster for CCS Suite 2 | LSST Forecast - B57 - B1 | 66 | 0 | 2016-09-03 | 2016-12-16 | 0 | 2016-09-03 | 2016-12-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-10-03 | 2017-01-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 66 | 71 |  | Complete | 100% | 350 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.09 | CCS Diagnostic Cluster and Visualization | 350 | 350 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 11% |  | Engineering Test/Validation | [7 empty] | CCS Core (TEC)
FALSE |  | CCS109905 | Install visualization system in IR-2- Diagnostic Cluster for I&T | LSST Forecast - B57 - B1 | 90 | 0 | 2016-09-03 | 2017-03-15 | 0 | 2016-09-03 | 2017-03-15 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-10-03 | 2017-02-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 2 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 90 | 121 |  | Complete | 100% | 350 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.09 | CCS Diagnostic Cluster and Visualization | 350 | 350 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 11% |  | Engineering Test/Validation | [7 empty] | CCS Core (TEC)
FALSE |  | CR242260 | Electrical performance validation - GEB EM | LSST Forecast - B57 - B1 | 60 | 0 | 2016-09-05 | 2017-03-17 | 0 | 2016-09-05 | 2017-03-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-10-03 | 2017-01-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 0 | 2 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 123 |  | Complete | 100% | 320 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.02 | Guider Electronics Board (GEB) | 320 | 320 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Testing/Integration | [7 empty] | Corner Raft Electronics (TEC) | GEB EM
FALSE |  | OP520980 | Assemble and test filter mass simulator | LSST Forecast - B57 - B1 | 60 | 0 | 2016-09-05 | 2016-12-05 | 0 | 2016-09-05 | 2016-12-05 | 0 | 2019-06-01 | 2019-06-01 | 2018-10-30 | 2018-10-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-10-20 | 2017-01-19 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 63 |  | Complete | 100% | 240 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 240 | 240 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 18% |  | Fabrication/Assembly |  | Commissioning and Testing | [5 empty] | Filters (TEC) | Prototype Filter Assemblies |  |  | Maybe |  |  | Filter Opto-Mechanics
FALSE |  | SR332690 | Prod. Testing - Sensors V2 (Sensors #33-36) | LSST Forecast - B57 - B1 | 13 | 0 | 2016-09-07 | 2016-09-23 | 0 | 2016-09-07 | 2016-09-23 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-10-03 | 2016-10-19 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 13 | 12 |  | Complete | 100% | 30 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 30 | 30 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Catalog Listing or Industrial Construction Databases | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [6 empty] | Science Sensors Acceptance | [6 empty] | Sensors Vendor 2 |  | Science Sensors
FALSE |  | CR233090 | AWARD: Contract - Misc Parts - Shipping/Storage Container | LSST Forecast - B57 - B1 | 1 | 0 | 2016-09-08 | 2016-09-08 | 0 | 2016-09-08 | 2016-09-08 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 4000 | 4000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-11-14 | 2016-11-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 0 | 0 | 0 | 4000 | 4000 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | B1 Procurement Commitment (C5.1) |  | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% | Level 4 Milestone | Procurement |  | Other (specify) | Subcontractor |  |  |  |  | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Shipping Container Design/Prod | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CBM45100 | Recv, Prep, Assemble, Test (Blade Proto) | LSST Forecast - B57 - B1 | 7 | 0 | 2016-09-12 | 2017-04-28 | 0 | 2016-09-12 | 2017-04-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-06 | 2019-08-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-10-03 | 2016-10-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 7 | 149 |  | Complete | 100% | 228 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.02.02 | Shutter Development | 228 | 228 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 9% |  | Engineering Test/Validation |  | Commissioning and Testing | [5 empty] | Shutter Development (TEC) | [6 empty] | Blade Prototype Test Unit
FALSE |  | DAQ900075 | COMP: DAQ V1.0 | LSST Forecast - B57 - B1 | 0 | 0 | 2016-09-15 | 2016-09-15 | 0 | 2016-09-15 | 2016-09-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 5 | FALSE | Finish Milestone | FALSE | 2017-01-04 | 2017-01-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.13.01 | DAQ Version 1.0 | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer |  |  | Level 4 Milestone | Engineering Test/Validation
FALSE |  | CBM25200 | Prep for C_FDR - Camera Body | LSST Forecast - B57 - B1 | 10 | 0 | 2016-09-16 | 2016-09-23 | 0 | 2016-09-16 | 2016-09-23 | 0 | 2019-06-01 | 2019-06-01 | 2018-09-07 | 2018-09-07 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-10-03 | 2016-10-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 9 | 0 | 8 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 5 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.01.02 | Camera Body Development | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 15% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Camera Body Development (TEC) | [6 empty] | Cam Body/Purge Test Units
FALSE |  | CCS124900 | AVAIL: Deliver CCS software for drive-train prototype | LSST Forecast - B57 - B1 | 0 | 0 | 2016-09-16 | 2016-09-16 | 0 | 2016-09-16 | 2016-09-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-06 | 2019-08-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2016-11-01 | 2016-11-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.06 | Shutter HCU | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | OPC Non-ARRA | Tony Johnson |  |  | Level 5 Milestone | Engineering Test/Validation
FALSE |  | CR240940 | Functional Testing - WEB EM | LSST Forecast - B57 - B1 | 30 | 0 | 2016-09-19 | 2016-10-28 | 0 | 2016-09-19 | 2016-10-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-10-03 | 2016-11-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 29 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.01 | Wavefront Electronics Board (WEB) | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Testing/Integration | [7 empty] | Corner Raft Electronics (TEC) | WEB EM
FALSE |  | CBM44020 | CCS drive train testing | LSST Forecast - B57 - B1 | 20 | 0 | 2016-10-01 | 2016-12-14 | 0 | 2016-10-01 | 2016-12-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-06 | 2019-08-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-11-16 | 2016-12-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 50 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.02.02 | Shutter Development | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Martin Nordby |  |  |  | Engineering Test/Validation
FALSE |  | CCS100700 | Management FY17 - CCS | LSST Forecast - B57 - B1 | 242 | 0 | 2016-10-01 | 2017-09-29 | 0 | 2016-10-01 | 2017-09-29 | 0 | 2019-06-01 | 2019-06-01 | 2021-11-15 | 2021-11-15 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-11-01 | 2017-10-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 242 | 241 |  | Complete | 100% | 580 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.01 | CCS Integration & Management | 580 | 580 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Drtn | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Management/Administration |  | Construction Management | [5 empty] | CCS Integration & Management (TEC) | [6 empty] | Camera Control System
FALSE |  | ITC33346 | Test Definition Review - Prep - Gantry | LSST Forecast - B57 - B1 | 17 | 0 | 2016-10-01 | 2016-10-27 | 0 | 2016-10-01 | 2016-10-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-11-01 | 2016-11-23 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 17 | 18 |  | Complete | 100% | 29 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.01 | Integration Gantry | 29 | 29 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat I&T (TEC)
FALSE |  | OP10785 | Optics Sub-System Travel - FY17 | LSST Forecast - B57 - B1 | 250 | 0 | 2016-10-03 | 2017-09-29 | 0 | 2016-10-03 | 2017-09-29 | 0 | 2019-06-01 | 2019-06-01 | 2021-07-29 | 2021-07-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-11-01 | 2017-10-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 250 | 249 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.01 | Optics Integration & Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Drtn | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 0% |  | Management/Administration |  | Construction Management | [5 empty] | Optics System Management (TEC) | [6 empty] | Optics System Management
FALSE |  | CR234490 | Inspect Procured Parts - Wavefront Sensor | LSST Forecast - B57 - B1 | 60 | 0 | 2016-10-03 | 2017-03-31 | 0 | 2016-10-03 | 2017-03-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2017-02-15 | 2017-05-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 114 |  | Complete | 100% | 48 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.02 | Wavefront Sensor | 48 | 48 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 1% |  | Fabrication/Assembly |  | Other (specify) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | [6 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CRYO53130 | COMP: System Flushing for SLAC System (Link to FDR#2) | LSST Forecast - B57 - B1 | 0 | 0 | 2016-10-15 | 2016-10-15 | 0 | 2016-10-15 | 2016-10-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-04-18 | 2017-04-18 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Engineering Test/Validation
FALSE |  | CR240980 | Electrical performance validation - WEB EM | LSST Forecast - B57 - B1 | 30 | 0 | 2016-10-24 | 2017-02-24 | 0 | 2016-10-24 | 2017-02-24 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-11-01 | 2016-12-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 74 |  | Complete | 100% | 320 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.01 | Wavefront Electronics Board (WEB) | 320 | 320 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Testing/Integration | [7 empty] | Corner Raft Electronics (TEC) | WEB EM
FALSE |  | SR550270 | RTM #1 (1st Article) - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 20 | 0 | 2016-10-25 | 2017-01-10 | 0 | 2016-10-25 | 2017-01-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-11-16 | 2016-12-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 4 | 0 | 0 | 3 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 36 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 50 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #1 (First Article) |  | Science Raft System
FALSE |  | CRYO11730 | COMP: Assembly Mandrel- Cryostat Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2016-10-31 | 2016-10-31 | 0 | 2016-10-31 | 2016-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | FALSE | 2016-12-15 | 2016-12-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Fabrication/Assembly
FALSE |  | CRYO60940 | Prep for C_PDR - Refrigeration System | LSST Forecast - B57 - B1 | 20 | 0 | 2016-11-01 | 2016-11-14 | 0 | 2016-11-01 | 2016-11-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-12-01 | 2017-01-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 14 | 0 | 14 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 9 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.01 | Refrigeration System - Pre IR2 (System Design & Integration) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment |  | TEC Non-ARRA | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Refrigeration System
FALSE |  | CRYO30150 | Generate Manufacturing Docs - Cryostat Back End | LSST Forecast - B57 - B1 | 8 | 0 | 2016-11-01 | 2016-11-30 | 0 | 2016-11-01 | 2016-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-01-20 | 2017-01-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 8 | 19 |  | Complete | 100% | 32 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.01 | Cryostat Back End | 32 | 32 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Backend & Vacuum Systems (TEC) | [6 empty] | Cryostat Back End
FALSE |  | CRYO31030 | Procurement Process - Feedthru Flange Subcomponents - Cryostat Back End | LSST Forecast - B57 - B1 | 20 | 0 | 2016-11-01 | 2016-11-10 | 0 | 2016-11-01 | 2016-11-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-12-01 | 2017-01-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 7 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.01 | Cryostat Back End | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  |  | Procurement
FALSE |  | CR240920 | Additional custom software and engineering support for WEB EM testing | LSST Forecast - B57 - B1 | 15 | 0 | 2016-11-01 | 2017-02-24 | 0 | 2016-11-01 | 2017-02-24 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-12-01 | 2017-01-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 68 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.01 | Wavefront Electronics Board (WEB) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Testing/Integration | [7 empty] | Corner Raft Electronics (TEC) | WEB EM
FALSE |  | CR222710 | Clean Cold Raft Electronics test stand machined parts | LSST Forecast - B57 - B1 | 5 | 0 | 2016-11-01 | 2017-03-24 | 0 | 2016-11-01 | 2017-03-24 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-12-01 | 2016-12-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 88 |  | Complete | 100% | 16 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 16 | 16 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | [11 empty] | Corner Raft Tower Module (CRTM) (TEC)
FALSE |  | CRYO35070 | Stressed skin cover panels / attachment to UT structure | LSST Forecast - B57 - B1 | 65 | 0 | 2016-11-01 | 2017-05-31 | 0 | 2016-11-01 | 2017-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-12-01 | 2017-03-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 65 | 135 |  | Complete | 100% | 128 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.05.02 | Utility Trunk Thermo-Mechanical and Assembly | 128 | 128 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Utility Trunk Thermo-Mechanical and Assembly (TEC) | [6 empty] | Utility Trunk
FALSE |  | CCS124050 | NEED: Raft Electronics Board (REB5) | LSST Forecast - B57 - B1 | 0 | 0 | 2016-11-03 | 2016-11-03 | 0 | 2016-11-03 | 2016-11-03 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-01-03 | 2017-01-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.01.01 | REB Driver | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  | Level 5 Milestone | Design/Engineering
FALSE |  | CR222910 | Assemble the I&T TS-7 Dewar | LSST Forecast - B57 - B1 | 15 | 0 | 2016-11-09 | 2017-04-28 | 0 | 2016-11-09 | 2017-04-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-01-09 | 2017-01-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 107 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Procurement | [7 empty] | Corner Raft Tower Module (CRTM) (TEC)
FALSE |  | CRYO60670 | COMP: Subscale Test Stand (Second CRYO) | LSST Forecast - B57 - B1 | 0 | 0 | 2016-11-15 | 2016-11-15 | 0 | 2016-11-15 | 2016-11-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Finish Milestone | FALSE | 2016-12-15 | 2016-12-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 8 | 0 | 4 | 0 | 0 | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Engineering Test/Validation
FALSE |  | SR332695 | Prod. Testing - Sensors V2 (Sensors #37-40) | LSST Forecast - B57 - B1 | 20 | 0 | 2016-11-15 | 2016-12-30 | 0 | 2016-11-15 | 2016-12-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-01-17 | 2017-02-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 29 |  | Complete | 100% | 30 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 30 | 30 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Catalog Listing or Industrial Construction Databases | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [6 empty] | Science Sensors Acceptance | [6 empty] | Sensors Vendor 2 |  | Science Sensors
FALSE |  | CR221920 | Vendor Fab & Machine - Corner raft tower | LSST Forecast - B57 - B1 | 40 | 0 | 2016-11-27 | 2017-04-28 | 0 | 2016-11-27 | 2017-04-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 164360 | 164360 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-03-27 | 2017-05-19 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 96 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 164360 | 164360 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Fabrication/Assembly |  | Other (specify) | [5 empty] | Corner Raft Tower Module (CRTM) (TEC) | CRTM Fab CRT | [5 empty] | Corner Raft Tower Module (CRTM)
FALSE |  | SR530130 | TS8 - practice test on engineering grade RTM | LSST Forecast - B57 - B1 | 20 | 0 | 2016-12-01 | 2016-12-30 | 0 | 2016-12-01 | 2016-12-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-01-03 | 2017-01-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 19 |  | Complete | 100% | 240 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.05 | RTM Electro-Optical Testing (TS8) | 240 | 240 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 8 - Assembly & Commissioning |  | Science Raft System
FALSE |  | AE220530 | Assemble Cables - Science/Corner Raft Test Stands Power Supplies | LSST Forecast - B57 - B1 | 30 | 0 | 2016-12-01 | 2017-01-11 | 0 | 2016-12-01 | 2017-01-11 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-01-30 | 2017-03-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 18 |  | Complete | 100% | 48 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.02.02 | Custom Raft Supply Boards | 48 | 48 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Gunther Haller | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Fabrication/Assembly |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Aux Elec Components (TEC)
FALSE |  | CR222780 | Assemble Enhanced Components into Cold Raft Electronics test stand | LSST Forecast - B57 - B1 | 10 | 0 | 2016-12-05 | 2017-02-24 | 0 | 2016-12-05 | 2017-02-24 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-02-15 | 2017-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 46 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot |  |  |  | Fabrication/Assembly | [7 empty] | Corner Raft Tower Module (CRTM) (TEC)
FALSE |  | CAMF660050 | COMP: Final Design & Assembly Drawings - Auto Changer | LSST Forecast - B57 - B1 | 0 | 0 | 2016-12-15 | 2016-12-15 | 0 | 2016-12-15 | 2016-12-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-01-03 | 2017-01-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.01 | Auto Changer | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  | Level 4 Milestone | Design/Engineering
FALSE |  | CRYO11724 | COMP: Faro Arm Stand - Cryostat Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2016-12-16 | 2016-12-16 | 0 | 2016-12-16 | 2016-12-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2017-02-06 | 2017-02-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Fabrication/Assembly
FALSE |  | SR552690 | Install & Commission Test Stand 6 | LSST Forecast - B57 - B1 | 20 | 0 | 2016-12-20 | 2017-02-17 | 0 | 2016-12-20 | 2017-02-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-01-30 | 2017-02-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 39 |  | Complete | 100% | 320 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.07.01 | Cleanroom Development & Commissioning | 320 | 320 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Assembly and Test Facility (TEC) | Test Stand Effort | [5 empty] | Science Raft - Assembly and Test Facility | [6 empty] | Test Stand 6 - Assembly & Commissioning |  | Science Raft System
FALSE |  | SR530095 | NEED: CCS Controller - Production | LSST Forecast - B57 - B1 | 0 | 0 | 2016-12-30 | 2016-12-30 | 0 | 2016-12-30 | 2016-12-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-01-31 | 2017-01-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.05 | RTM Electro-Optical Testing (TS8) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% | Level 5 Milestone | Fabrication/Assembly | [14 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 8 - Assembly & Commissioning |  | Science Raft System
FALSE |  | SR531180 | AVAIL: TS8 Ready for commissioning | LSST Forecast - B57 - B1 | 0 | 0 | 2016-12-30 | 2016-12-30 | 0 | 2016-12-30 | 2016-12-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2017-02-15 | 2017-02-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 4 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.05 | RTM Electro-Optical Testing (TS8) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% | Level 5 Milestone | Testing/Integration | [14 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 8 - Assembly & Commissioning |  | Science Raft System
FALSE |  | OP522475 | Five Remaining Filters Complete and Ready to Ship (MS5) - Filter Fabrication | LSST Forecast - B57 - B1 | 444 | 92 | 2017-01-02 | 2019-10-10 | 163 | 2017-01-02 |  | 0 | 2019-06-03 | 2019-10-10 | 2020-01-28 | 2020-06-05 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-03-01 | 2018-11-30 |  |  |  |  | 0.73 | 0 | FALSE | FALSE | None |  | None |  | 2019-10-10 |  |  |  |  | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 444 | 607 |  | InProgress | 73% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  |  | Procurement
FALSE |  | SR333395 | Batch Sensor Testing (RTM #2) | LSST Forecast - B57 - B1 | 5 | 0 | 2017-01-03 | 2017-03-15 | 0 | 2017-01-03 | 2017-03-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-02-08 | 2017-02-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 0 | 0 | 0 | 5 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 49 |  | Complete | 100% | 156 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 156 | 156 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | CR241000 | Performance validation with single CCD - WEB EM | LSST Forecast - B57 - B1 | 30 | 0 | 2017-01-09 | 2017-02-24 | 0 | 2017-01-09 | 2017-02-24 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-02-27 | 2017-04-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 2 | 0 | 0 | 2 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 32 |  | Complete | 100% | 320 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.01 | Wavefront Electronics Board (WEB) | 320 | 320 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Testing/Integration | [7 empty] | Corner Raft Electronics (TEC) | WEB EM
FALSE |  | SR330170 | RCV: First Article Sensors - V1 (Sensor #6) | LSST Forecast - B57 - B1 | 17 | 0 | 2017-01-09 | 2017-01-27 | 0 | 2017-01-09 | 2017-01-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 122500 | 122500 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-02-01 | 2017-02-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 17 | 13 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 122500 | 122500 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 14% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC) | [5 empty] | Sensor | Science Sensors Procurement | [6 empty] | Sensors Vendor 1 |  | Science Sensors
FALSE |  | SR552560 | COMP: Design and Engineering Phase | LSST Forecast - B57 - B1 | 0 | 0 | 2017-01-10 | 2017-01-10 | 0 | 2017-01-10 | 2017-01-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2017-02-08 | 2017-02-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 9 | 0 | 9 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.01 | Science Raft Tower Module (SRTM) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Bill Wahl |  |  | Level 4 Milestone | Design/Engineering | [14 empty] | Science Raft - Test Stands | [6 empty] | Tower Module |  | Science Raft System
FALSE |  | SR529835 | AVAIL: TS8a for SLAC I&T | LSST Forecast - B57 - B1 | 0 | 0 | 2017-01-13 | 2017-01-13 | 0 | 2017-01-13 | 2017-01-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-02-13 | 2017-02-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 8 | 0 | 8 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.06 | RTM Electro-Optical Testing (TS8a) For SLAC | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% | Level 5 Milestone | Fabrication/Assembly | [14 empty] | Science Raft - Test Stands |  | Science Raft System |  |  |  |  | Test Stand 8a - Assembly & Commissioning |  | Science Raft System
FALSE |  | CRYO11706 | COMP: Station 1 Assy - Cryostat Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2017-01-17 | 2017-01-17 | 0 | 2017-01-17 | 2017-01-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | FALSE | 2017-03-01 | 2017-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Fabrication/Assembly
FALSE |  | CRYO11712 | COMP: Station 2 Assy - Cryostat Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2017-01-17 | 2017-01-17 | 0 | 2017-01-17 | 2017-01-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | FALSE | 2017-03-01 | 2017-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Fabrication/Assembly
FALSE |  | SR530460 | TS6 - Revise eTraveler | LSST Forecast - B57 - B1 | 14 | 0 | 2017-01-26 | 2017-01-31 | 0 | 2017-01-26 | 2017-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-03-01 | 2017-03-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 14 | 3 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.03 | RTM Assembly (TS6) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 6 - Procurement & Fabrication |  | Science Raft System
FALSE |  | CRYO117471 | COMP: Other Lift Devices/Equipment - Cryostat Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2017-01-31 | 2017-01-31 | 0 | 2017-01-31 | 2017-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2017-03-01 | 2017-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Fabrication/Assembly
FALSE |  | SR530950 | Prep for C_MRR-TS5 | LSST Forecast - B57 - B1 | 11 | 0 | 2017-02-01 | 2017-02-15 | 0 | 2017-02-01 | 2017-02-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-03-01 | 2017-03-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 4 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 11 | 10 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.02 | RSA & RTM Warm-Cold Metrology (TS5) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 5 - Assembly & Commissioning |  | Science Raft System
FALSE |  | SR529775 | Prep for C_MRR-TS8a | LSST Forecast - B57 - B1 | 11 | 0 | 2017-02-01 | 2017-02-15 | 0 | 2017-02-01 | 2017-02-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-03-01 | 2017-03-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 11 | 10 |  | Complete | 100% | 12 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.06 | RTM Electro-Optical Testing (TS8a) For SLAC | 12 | 12 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 8a - Reviews |  | Science Raft System
FALSE |  | SR330280 | RCV: Production Lot 1 Sensors - V1 (Sensor #21) | LSST Forecast - B57 - B1 | 5 | 0 | 2017-02-01 | 2017-03-31 | 0 | 2017-02-01 | 2017-03-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 97200 | 97200 | 0 | 0 | 0 | 5 | FALSE | Normal | FALSE | 2017-03-08 | 2017-03-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 1 | 0 | 0 | 5 | 0 | 2 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 41 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 97200 | 97200 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 14% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC) | [5 empty] | Sensor | Science Sensors Procurement | [6 empty] | Sensors Vendor 1 |  | Science Sensors
FALSE |  | CRYO11766 | Generate Assembly Drawings - Cryostat Assembly | LSST Forecast - B57 - B1 | 54 | 0 | 2017-02-01 | 2017-05-31 | 0 | 2017-02-01 | 2017-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-03-01 | 2017-05-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 54 | 85 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package |  | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 10% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Cryostat Housing & Assembly (TEC)
FALSE |  | SR531140 | Prep for C_MRR-TS7 | LSST Forecast - B57 - B1 | 11 | 0 | 2017-02-01 | 2017-02-15 | 0 | 2017-02-01 | 2017-02-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-02-01 | 2017-02-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 11 | 11 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.04 | RTM Cryostat Integration (TS7) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 7 - Assembly & Commissioning |  | Science Raft System
FALSE |  | SR550274 | RTM1_RTM Construction at TS6 | LSST Forecast - B57 - B1 | 19 | 0 | 2017-02-02 | 2017-03-06 | 0 | 2017-02-02 | 2017-03-06 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-03-07 | 2017-03-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 3 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 19 | 21 |  | Complete | 100% | 64 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 64 | 64 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #1 (First Article) |  | Science Raft System
FALSE |  | SR330840 | AWARD: Sensor Production Lot 2 (V1, 30 Sensors) | LSST Forecast - B57 - B1 | 1 | 0 | 2017-02-10 | 2017-02-10 | 0 | 2017-02-10 | 2017-02-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 3680056 | 3680056 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2017-03-01 | 2017-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 3680056 | 3680056 | 0 | PercentComplete | 4% | CP_Phys |  | B1 Procurement Commitment (C5.1) |  | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR515050 | C_MRR--TS4-8 | LSST Forecast - B57 - B1 | 2 | 0 | 2017-02-14 | 2017-02-15 | 0 | 2017-02-14 | 2017-02-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-03-14 | 2017-03-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 6 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 2 |  | Complete | 100% | 96 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05 | Science Raft Test Stands (Dev & Commissioning) | 96 | 96 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering | [7 empty] | Science Raft - Test Stands (TEC) | Test Stand Effort | [5 empty] | Science Raft - Test Stands | [6 empty] | Test Stands - Review |  | Science Raft System
FALSE |  | SR552810 | C_MRR--Assembly & Test Facility | LSST Forecast - B57 - B1 | 2 | 0 | 2017-02-14 | 2017-02-15 | 0 | 2017-02-14 | 2017-02-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-02-14 | 2017-02-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 2 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.07.01 | Cleanroom Development & Commissioning | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Assembly and Test Facility (TEC) | Test Stand Effort | [5 empty] | Science Raft - Assembly and Test Facility | [6 empty] | Test Stand - Reviews |  | Science Raft System
FALSE |  | SR343870 | Assemble at Vendor, Clean & Test REB5 Batch 1 at vendor (10 units - RTM 1-3) | LSST Forecast - B57 - B1 | 14 | 0 | 2017-02-14 | 2017-03-06 | 0 | 2017-02-14 | 2017-03-06 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2017-02-14 | 2017-03-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 4 | 0 | 0 | 1 | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 8 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 14 | 13 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation | [7 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [6 empty] | Prodcution REB-5 Build |  | Science Raft System
FALSE |  | SR529990 | COMP: C_TRR - Test Stand 8 | LSST Forecast - B57 - B1 | 0 | 0 | 2017-02-15 | 2017-02-15 | 0 | 2017-02-15 | 2017-02-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-03-15 | 2017-03-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.05 | RTM Electro-Optical Testing (TS8) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% | Level 4 Milestone | Design/Engineering | [14 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 8 - Reviews |  | Science Raft System
FALSE |  | CCS200200 | AVAIL: CCS Suite 1 (+HCU) Available for I&T | LSST Forecast - B57 - B1 | 0 | 0 | 2017-02-16 | 2017-02-16 | 0 | 2017-02-16 | 2017-02-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2017-03-16 | 2017-03-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.08.01 | Single Bay HCU | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  | Level 5 Milestone | Design/Engineering
FALSE |  | SR531090 | AVAIL: Test Stand 6 - Ready for Production | LSST Forecast - B57 - B1 | 0 | 0 | 2017-02-17 | 2017-02-17 | 0 | 2017-02-17 | 2017-02-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2017-03-17 | 2017-03-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.03 | RTM Assembly (TS6) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% | Level 5 Milestone | Testing/Integration | [14 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 6 - Assembly & Commissioning |  | Science Raft System
FALSE |  | SR340055 | Cold Probe Wafers at ITL (Lot A) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 10 | 0 | 2017-02-20 | 2017-04-12 | 0 | 2017-02-20 | 2017-04-12 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-04-07 | 2017-04-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 36 |  | Complete | 100% | 768 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 768 | 768 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR550390 | RTM #3 (1st Article) - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 46 | 0 | 2017-02-21 | 2017-04-17 | 0 | 2017-02-21 | 2017-04-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-02-21 | 2017-04-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 3 | 1 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 20 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 46 | 39 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [5 empty] | Critical Path to CD-2 | Science Raft - Test Stands | [6 empty] | RTM #3 |  | Science Raft System
FALSE |  | SR552680 | NEED: Test Stand 6 Ready for Test Facility Installation | LSST Forecast - B57 - B1 | 0 | 0 | 2017-02-28 | 2017-02-28 | 0 | 2017-02-28 | 2017-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-03-27 | 2017-03-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.07.01 | Cleanroom Development & Commissioning | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% | Level 5 Milestone | Testing/Integration | [8 empty] | Test Stand Effort | [5 empty] | Science Raft - Assembly and Test Facility | [6 empty] | Test Stand 6 - Assembly & Commissioning |  | Science Raft System
FALSE |  | CRYO11718 | COMP: Off-Load Frame - Cryostat Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2017-02-28 | 2017-02-28 | 0 | 2017-02-28 | 2017-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2017-03-01 | 2017-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 4 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Fabrication/Assembly
FALSE |  | CRYO11736 | COMP: Grid Handling Fixture - Cryostat Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2017-02-28 | 2017-02-28 | 0 | 2017-02-28 | 2017-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2017-03-01 | 2017-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Fabrication/Assembly
FALSE |  | CRYO11742 | COMP: Test Fixtures - Cryostat Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2017-02-28 | 2017-02-28 | 0 | 2017-02-28 | 2017-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2017-03-01 | 2017-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Fabrication/Assembly
FALSE |  | CRYO11762 | COMP: Purge Box - Cryostat Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2017-02-28 | 2017-02-28 | 0 | 2017-02-28 | 2017-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2017-03-01 | 2017-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Fabrication/Assembly
FALSE |  | CCS103800 | Sustained Engineering - Code management | LSST Forecast - B57 - B1 | 240 | 0 | 2017-03-01 | 2018-03-28 | 0 | 2017-03-01 | 2018-03-28 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-04-03 | 2018-03-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 240 | 262 |  | Complete | 100% | 60 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.01 | CCS Developer Tools | 60 | 60 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering | [7 empty] | CCS Core (TEC)
FALSE |  | SR531000 | Incorporate TS5 -MRR changes | LSST Forecast - B57 - B1 | 14 | 0 | 2017-03-01 | 2017-03-20 | 0 | 2017-03-01 | 2017-03-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-18 | 2019-09-18 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-04-03 | 2017-04-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 14 | 13 |  | Complete | 100% | 8 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.02 | RSA & RTM Warm-Cold Metrology (TS5) | 8 | 8 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 5 - Assembly & Commissioning |  | Science Raft System
FALSE |  | CR241020 | WEB EM prototype to WEB workshop | LSST Forecast - B57 - B1 | 5 | 0 | 2017-03-06 | 2017-03-20 | 0 | 2017-03-06 | 2017-03-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2017-04-03 | 2017-04-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 10 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.01 | Wavefront Electronics Board (WEB) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Testing/Integration | [7 empty] | Corner Raft Electronics (TEC) | WEB
FALSE |  | SR340215 | Backside Processing (Batch 1) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 35 | 0 | 2017-03-06 | 2017-04-27 | 0 | 2017-03-06 | 2017-04-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-05-02 | 2017-06-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 0 | 4 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 35 | 38 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | OP531110 | L2 Initial TWE Test Complete - L1-L2 Assembly - Phase 4b | LSST Forecast - B57 - B1 | 22 | 0 | 2017-03-10 | 2017-03-31 | 0 | 2017-03-10 | 2017-03-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-03 | 2019-09-03 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-04-03 | 2017-05-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 22 | 15 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Scott Winters | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor | [5 empty] | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly) |  |  |  | L1-L2 Opto-Mechanics
FALSE |  | CRYO19800 | AWARD: P.O. - Off the Shelf Items - Cryo & Cold Plate | LSST Forecast - B57 - B1 | 0 | 0 | 2017-03-13 | 2017-03-13 | 0 | 2017-03-13 | 2017-03-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 243100 | 243100 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2017-04-17 | 2017-04-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.03 | Cryo and Cold Plates | 0 | 0 | 0 | 243100 | 243100 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | B1 Procurement Commitment (C5.1) |  | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 3% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Cryo and Cold Plates (TEC) | [6 empty] | Cryo and Cold Plates
FALSE |  | CR223160 | Perform Initial Verification of TS-8 with CCS and DAQ | LSST Forecast - B57 - B1 | 15 | 0 | 2017-03-13 | 2017-06-09 | 0 | 2017-03-13 | 2017-06-09 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-04-13 | 2017-05-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 6 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 63 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Procurement | [7 empty] | Corner Raft Tower Module (CRTM) (TEC)
FALSE |  | AE210160 | Fabricate Prototype brackets, enclosures, filters | LSST Forecast - B57 - B1 | 40 | 0 | 2017-03-14 | 2017-07-11 | 0 | 2017-03-14 | 2017-07-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-04-10 | 2017-06-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 83 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.02.01 | AC and DC Power Distribution | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Gunther Haller | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Engineering Test/Validation |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Aux Elec Components (TEC) | [6 empty] | Power Control Monitoring
FALSE |  | CCS123600 | AVAIL: Diagnostic Cluster for I&T | LSST Forecast - B57 - B1 | 0 | 0 | 2017-03-15 | 2017-03-15 | 0 | 2017-03-15 | 2017-03-15 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2017-04-11 | 2017-04-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 4 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.09 | CCS Diagnostic Cluster and Visualization | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  | Level 5 Milestone | Design/Engineering
FALSE |  | CR234485 | COMP: Production 2Kx4K Wavefront Sensor (Phase 2) | LSST Forecast - B57 - B1 | 0 | 0 | 2017-03-17 | 2017-03-17 | 0 | 2017-03-17 | 2017-03-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2017-05-03 | 2017-05-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.02 | Wavefront Sensor | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 4 Milestone | Design/Engineering
FALSE |  | CR242300 | GEB EM prototype to GEB workshop | LSST Forecast - B57 - B1 | 5 | 0 | 2017-03-20 | 2017-03-31 | 0 | 2017-03-20 | 2017-03-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2017-04-20 | 2017-04-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 9 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.02 | Guider Electronics Board (GEB) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Testing/Integration | [7 empty] | Corner Raft Electronics (TEC) | GEB
FALSE |  | SR550450 | RTM #4 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2017-03-21 | 2017-05-16 | 0 | 2017-03-21 | 2017-05-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-06-01 | 2017-07-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 3 | 2 | 0 | 1 | 2 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 40 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #4 |  | Science Raft System
FALSE |  | SR550510 | RTM #5 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2017-03-21 | 2017-07-07 | 0 | 2017-03-21 | 2017-07-07 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-04-26 | 2017-05-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 76 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #5 |  | Science Raft System
FALSE |  | SR550570 | RTM #6 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2017-03-21 | 2017-08-15 | 0 | 2017-03-21 | 2017-08-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2017-05-22 | 2017-06-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 1 | 0 | 2 | 3 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 103 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #6 |  | Science Raft System
FALSE |  | SR550630 | RTM #7 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2017-03-21 | 2017-08-11 | 0 | 2017-03-21 | 2017-08-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-07-10 | 2017-08-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 0 | 1 | 0 | 3 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 101 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #7 |  | Science Raft System
FALSE |  | SR550690 | RTM #8 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2017-03-21 | 2017-09-11 | 0 | 2017-03-21 | 2017-09-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-06-20 | 2017-07-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 0 | 1 | 0 | 3 | 2 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 121 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #8 |  | Science Raft System
FALSE |  | SR550750 | RTM #9 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2017-03-21 | 2017-10-13 | 0 | 2017-03-21 | 2017-10-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-09-13 | 2017-10-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 1 | 0 | 2 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 145 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #9 |  | Science Raft System
FALSE |  | SR550870 | RTM #11 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2017-03-21 | 2017-11-30 | 0 | 2017-03-21 | 2017-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-23 | 2019-07-23 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-10-25 | 2017-11-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 1 | 0 | 2 | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 177 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #11 |  | Science Raft System
FALSE |  | SR550930 | RTM #12 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2017-03-21 | 2018-01-23 | 0 | 2017-03-21 | 2018-01-23 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-23 | 2019-07-23 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-12-15 | 2018-01-23 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 1 | 0 | 2 | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 212 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #12 |  | Science Raft System
FALSE |  | SR550990 | RTM #13 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2017-03-21 | 2018-02-13 | 0 | 2017-03-21 | 2018-02-13 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-12-13 | 2018-01-19 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 1 | 0 | 2 | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 227 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #13 |  | Science Raft System
FALSE |  | CRYO61075 | System Level Test - Cryo - B750 | LSST Forecast - B57 - B1 | 45 | 0 | 2017-03-24 | 2017-10-25 | 0 | 2017-03-24 | 2017-10-25 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-06-28 | 2017-08-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 45 | 150 |  | Complete | 100% | 200 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.01 | Refrigeration System - Pre IR2 (System Design & Integration) | 200 | 200 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | SR333405 | Batch Sensor Testing (RTM #3) | LSST Forecast - B57 - B1 | 15 | 0 | 2017-03-28 | 2017-04-14 | 0 | 2017-03-28 | 2017-04-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-04-28 | 2017-05-18 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 9 | 0 | 0 | 0 | 0 | 9 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 13 |  | Complete | 100% | 306 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 306 | 306 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | SR333415 | Batch Sensor Testing (RTM #4) | LSST Forecast - B57 - B1 | 5 | 0 | 2017-03-28 | 2017-04-20 | 0 | 2017-03-28 | 2017-04-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-04-28 | 2017-05-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 9 | 0 | 0 | 0 | 0 | 9 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 17 |  | Complete | 100% | 103 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 103 | 103 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | SR333425 | Batch Sensor Testing (RTM #5) | LSST Forecast - B57 - B1 | 5 | 0 | 2017-03-28 | 2017-04-25 | 0 | 2017-03-28 | 2017-04-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-04-18 | 2017-04-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 9 | 0 | 0 | 0 | 0 | 9 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 20 |  | Complete | 100% | 103 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 103 | 103 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | CR234520 | AVAIL: Wavefront Sensors | LSST Forecast - B57 - B1 | 0 | 0 | 2017-03-31 | 2017-03-31 | 0 | 2017-03-31 | 2017-03-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2017-05-31 | 2017-05-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.02 | Wavefront Sensor | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 5 Milestone | Fabrication/Assembly
FALSE |  | CBM47500 | Finalize Design - Shutter | LSST Forecast - B57 - B1 | 30 | 0 | 2017-04-01 | 2017-05-31 | 0 | 2017-04-01 | 2017-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-06 | 2019-08-06 | 0 | 0 | 0 | 0 | 0 | 6 | FALSE | Normal | FALSE | 2017-05-01 | 2017-06-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 0 | 0 | 1 | 6 | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 41 |  | Complete | 100% | 190 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.02.02 | Shutter Development | 190 | 190 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Shutter Development (TEC) | [6 empty] | Shutter Prod Sprt |  |  | Final Design Link
FALSE |  | DAQ900140 | Integrate DAQ V2.0 (TDS, PGP) | LSST Forecast - B57 - B1 | 5 | 0 | 2017-04-03 | 2017-04-21 | 0 | 2017-04-03 | 2017-04-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-07-03 | 2017-07-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 5 | 1 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 14 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.13.03 | DAQ Version 2.0 | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Engineering Test/Validation | [7 empty] | DAQ Readout Systems (TEC)
FALSE |  | SR550274_1 | RTM1_RTM Qualification at TS8 | LSST Forecast - B57 - B1 | 17 | 0 | 2017-04-03 | 2017-04-25 | 0 | 2017-04-03 | 2017-04-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-05-01 | 2017-05-23 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 17 | 16 |  | Complete | 100% | 139 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 139 | 139 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #1 (First Article) |  | Science Raft System
FALSE |  | SR343932 | Perform Mech. Assy/Tcycling/burnin-Test/Vac-Prep/RGA/ Prep for Ship at SLAC (10) REB5 boards | LSST Forecast - B57 - B1 | 35 | 0 | 2017-04-03 | 2017-04-28 | 0 | 2017-04-03 | 2017-04-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-05-01 | 2017-06-19 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 35 | 19 |  | Complete | 100% | 50 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 50 | 50 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | [11 empty] | Science Raft Electronics (TEC) | [13 empty] | Prodcution REB-5 Build |  | Science Raft System
FALSE |  | CRYO61088 | Install & Test Hx - Cold - B750 | LSST Forecast - B57 - B1 | 15 | 0 | 2017-04-03 | 2017-04-14 | 0 | 2017-04-03 | 2017-04-14 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-05-01 | 2017-05-19 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 9 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.01 | Refrigeration System - Pre IR2 (System Design & Integration) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | SR550334 | RTM2_RTM Construction at TS6 | LSST Forecast - B57 - B1 | 11 | 0 | 2017-04-06 | 2017-04-20 | 0 | 2017-04-06 | 2017-04-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-05-04 | 2017-05-18 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 11 | 10 |  | Complete | 100% | 64 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 64 | 64 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #2 |  | Science Raft System
FALSE |  | CRYO20550 | Inspect Parts - Cryo & Cold Plate | LSST Forecast - B57 - B1 | 20 | 0 | 2017-04-10 | 2017-07-28 | 0 | 2017-04-10 | 2017-07-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-07-05 | 2017-08-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 77 |  | Complete | 100% | 172 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.03 | Cryo and Cold Plates | 172 | 172 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 11% |  | Fabrication/Assembly |  | Other (specify) | [5 empty] | Cryo and Cold Plates (TEC) | [5 empty] | Critical Path to CD-2 | Cryo and Cold Plates
FALSE |  | CRYO23500 | Inspect Grid Assembly | LSST Forecast - B57 - B1 | 20 | 0 | 2017-04-10 | 2017-05-31 | 0 | 2017-04-10 | 2017-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-05-01 | 2017-05-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 10 | 0 | 10 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 36 |  | Complete | 100% | 179 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.04 | Grid Assembly | 179 | 179 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Fabrication/Assembly |  | Other (specify) | [5 empty] | Grid Assembly (TEC) | [6 empty] | Grid Assembly | [5 empty] | CP - CAMM2160 (Cryostat Assy Ready for Integration)
FALSE |  | ITC33440 | Verification Planning - Gantry | LSST Forecast - B57 - B1 | 10 | 0 | 2017-04-10 | 2017-10-26 | 0 | 2017-04-10 | 2017-10-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-05-30 | 2017-06-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 140 |  | Complete | 100% | 116 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.01 | Integration Gantry | 116 | 116 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2
FALSE |  | CRYO61210 | Prep for C_FDR - Refrigeration System - IR2 | LSST Forecast - B57 - B1 | 10 | 0 | 2017-04-14 | 2017-05-19 | 0 | 2017-04-14 | 2017-05-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-06-06 | 2017-06-19 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 7 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 5 | 5 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 25 |  | Complete | 100% | 320 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.01 | Refrigeration System - Pre IR2 (System Design & Integration) | 320 | 320 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) | [6 empty] | Refrigeration System
FALSE |  | ITC17760 | Preliminary Testing - SBMS | LSST Forecast - B57 - B1 | 20 | 0 | 2017-04-24 | 2017-06-16 | 0 | 2017-04-24 | 2017-06-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-05-22 | 2017-06-19 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 4 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 38 |  | Complete | 100% | 328 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.01.01 | Single Bay Metrology Tests | 328 | 328 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC)
FALSE |  | CRYO13950 | Prep for Manufacturing Readiness Review - Cryostat Housing | LSST Forecast - B57 - B1 | 10 | 0 | 2017-05-01 | 2017-05-04 | 0 | 2017-05-01 | 2017-05-04 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-06-01 | 2017-06-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 10 | 0 | 10 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 3 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.01 | Cryostat Housing | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  |  | Design/Engineering
FALSE |  | CRYO31380 | Procurement Process - Other items - Cryostat Back End | LSST Forecast - B57 - B1 | 20 | 0 | 2017-05-01 | 2017-05-12 | 0 | 2017-05-01 | 2017-05-12 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-06-01 | 2017-06-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 9 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.01 | Cryostat Back End | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  |  | Procurement
FALSE |  | DAQ341400 | Design - Production - RDS/RDC | LSST Forecast - B57 - B1 | 100 | 0 | 2017-05-01 | 2017-06-09 | 0 | 2017-05-01 | 2017-06-09 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-08-30 | 2018-02-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 100 | 28 |  | Complete | 100% | 96 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.09.02 | Raft Data Server/Client Software (RDS/RDC) | 96 | 96 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | DAQ Readout Systems (TEC) |  | ICD's for Phase 3 |  |  |  |  | DAQ Readout Systems
FALSE |  | CCS125000 | Develop use-case and specification for shutter prototype | LSST Forecast - B57 - B1 | 20 | 0 | 2017-05-01 | 2017-06-28 | 0 | 2017-05-01 | 2017-06-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-06 | 2019-08-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-06-01 | 2017-06-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 41 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.06 | Shutter HCU | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 11% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | CCS HCU (TEC) | [6 empty] | Camera I&T Hardware Control Unit
FALSE |  | OP540940 | L3 Assembly - Phase 3 (Flat Assy - Assembly) | LSST Forecast - B57 - B1 | 34 | 0 | 2017-05-01 | 2017-12-12 | 0 | 2017-05-01 | 2017-12-12 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-14 | 2019-05-14 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-06-01 | 2017-07-19 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 34 | 156 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor | [11 empty] | L1-L2 Opto-Mechanics
FALSE |  | CR222740 | Integrated EO testing with cold raft electronics with single CCD cold | LSST Forecast - B57 - B1 | 31 | 0 | 2017-05-01 | 2017-06-16 | 0 | 2017-05-01 | 2017-06-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-07-03 | 2017-08-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 31 | 33 |  | Complete | 100% | 160 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 160 | 160 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | [11 empty] | Corner Raft Tower Module (CRTM) (TEC)
FALSE |  | ITC33335 | Procurement Prep - Test Raft | LSST Forecast - B57 - B1 | 22 | 0 | 2017-05-01 | 2017-05-30 | 0 | 2017-05-01 | 2017-05-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-06-01 | 2017-06-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 10 | 10 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 22 | 20 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.02.02 | Pathfinder / Test Raft Program | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC)
FALSE |  | OP521805 | Sub-scale Sample Metrology and Coating Report (MS3) - Filter Development and Witness Sample | LSST Forecast - B57 - B1 | 42 | 0 | 2017-05-01 | 2017-08-18 | 0 | 2017-05-01 | 2017-08-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-12-12 | 2019-12-12 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-06-01 | 2017-07-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 42 | 77 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  |  | Procurement
FALSE |  | CRYO35236 | NEED: Camera subsystems HCU architecture/design/hardware designation - Cryo UT | LSST Forecast - B57 - B1 | 0 | 0 | 2017-05-03 | 2017-05-03 | 0 | 2017-05-03 | 2017-05-03 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-06-01 | 2017-06-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.05.02 | Utility Trunk Thermo-Mechanical and Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 5 Milestone | Design/Engineering
FALSE |  | CAMM6265 | AVAIL: Preliminary glycol budget | LSST Forecast - B57 - B1 | 0 | 0 | 2017-05-03 | 2017-05-03 | 0 | 2017-05-03 | 2017-05-03 | 0 | 2019-06-01 | 2019-06-01 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-06-01 | 2017-06-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.03 | NSF Interface Milestone (NSF Needs) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration
FALSE |  | CR223190 | Commission TS-8 at SLAC with ETU | LSST Forecast - B57 - B1 | 10 | 0 | 2017-05-15 | 2017-06-09 | 0 | 2017-05-15 | 2017-06-09 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-06-08 | 2017-06-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 18 |  | Complete | 100% | 340 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 340 | 340 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Procurement | [7 empty] | Corner Raft Tower Module (CRTM) (TEC)
FALSE |  | CBM47800 | Prep for C_FDR - Shutter | LSST Forecast - B57 - B1 | 10 | 0 | 2017-05-22 | 2017-06-19 | 0 | 2017-05-22 | 2017-06-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-06 | 2019-08-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-07-28 | 2017-08-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 5 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 19 |  | Complete | 100% | 100 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.02.02 | Shutter Development | 100 | 100 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Shutter Development (TEC) | [6 empty] | Shutter Prod Sprt
FALSE |  | CRYO61220 | C_FDR - Final Design Review - Refrigeration System - IR2 | LSST Forecast - B57 - B1 | 2 | 0 | 2017-05-22 | 2017-05-22 | 0 | 2017-05-22 | 2017-05-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2017-06-01 | 2017-06-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.01 | Refrigeration System - Pre IR2 (System Design & Integration) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Design Reviews | [5 empty] | Refrigeration System (TEC) | [6 empty] | Refrigeration System
FALSE |  | CRYO31500 | Integrate & Test Hardware - Cryostat Back End | LSST Forecast - B57 - B1 | 40 | 0 | 2017-05-22 | 2017-07-28 | 0 | 2017-05-22 | 2017-07-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-07-26 | 2017-09-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 47 |  | Complete | 100% | 748 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.01 | Cryostat Back End | 748 | 748 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly |  | Other (specify) | [5 empty] | Cryostat Backend & Vacuum Systems (TEC) | [6 empty] | Cryostat Back End
FALSE |  | SR333435 | Batch Sensor Testing (RTM #6) | LSST Forecast - B57 - B1 | 5 | 0 | 2017-05-22 | 2017-06-26 | 0 | 2017-05-22 | 2017-06-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-06-15 | 2017-06-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 9 | 0 | 2 | 0 | 0 | 7 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 24 |  | Complete | 100% | 103 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 103 | 103 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | SR344132 | Perform Mech. Assy/Tcycling/burnin-Test/Vac-Prep/RGA/ Prep for Ship at SLAC (25) REB5 boards | LSST Forecast - B57 - B1 | 48 | 0 | 2017-05-23 | 2017-09-11 | 0 | 2017-05-23 | 2017-09-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-23 | 2019-07-23 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-06-01 | 2017-08-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 48 | 76 |  | Complete | 100% | 100 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 100 | 100 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | [11 empty] | Science Raft Electronics (TEC) | [13 empty] | Prodcution REB-5 Build |  | Science Raft System
FALSE |  | CRYO31060 | Procurement Process - Pump Plate Vac Sys Subcomponents - Cryostat Back End | LSST Forecast - B57 - B1 | 15 | 0 | 2017-06-01 | 2017-06-09 | 0 | 2017-06-01 | 2017-06-09 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-07-17 | 2017-08-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 6 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.01 | Cryostat Back End | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  |  | Procurement
FALSE |  | CRYO84000 | Finalize Design - Cryostat Utility Trunk | LSST Forecast - B57 - B1 | 52 | 0 | 2017-06-01 | 2017-11-13 | 0 | 2017-06-01 | 2017-11-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-07-03 | 2017-09-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 13 | 0 | 13 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 52 | 115 |  | Complete | 100% | 533 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.05.02 | Utility Trunk Thermo-Mechanical and Assembly | 533 | 533 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Utility Trunk Thermo-Mechanical and Assembly (TEC) |  | ICD's for Phase 3 |  |  |  |  | Utility Trunk
FALSE |  | CCS126940 | COMP: CCS Core 4.5 Release | LSST Forecast - B57 - B1 | 0 | 0 | 2017-06-06 | 2017-06-06 | 0 | 2017-06-06 | 2017-06-06 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-31 | 2019-05-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-07-07 | 2017-07-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.02.06 | CCS Core 5.0 Release (Support Lock Manager) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  | Level 4 Milestone | Design/Engineering
FALSE |  | DAQ900525 | COMP: DAQ V2.0 | LSST Forecast - B57 - B1 | 0 | 0 | 2017-06-09 | 2017-06-09 | 0 | 2017-06-09 | 2017-06-09 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | FALSE | 2017-08-09 | 2017-08-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.13.03 | DAQ Version 2.0 | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer |  |  | Level 4 Milestone | Testing/Integration
FALSE |  | CRYO53270 | COMP: Oil Reservoirs to Compressors (6 Units) - B750 | LSST Forecast - B57 - B1 | 0 | 0 | 2017-06-16 | 2017-06-16 | 0 | 2017-06-16 | 2017-06-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-07-03 | 2017-07-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 3 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.01 | Refrigeration System - Pre IR2 (System Design & Integration) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Engineering Test/Validation
FALSE |  | ITC13010 | AVAIL: I&T Facility Equipment Ready for Clean Room | LSST Forecast - B57 - B1 | 0 | 0 | 2017-06-23 | 2017-06-23 | 0 | 2017-06-23 | 2017-06-23 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2017-07-21 | 2017-07-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.03 | IR2 Facility and Operations | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | CAMF660200 | MRR - Manufacturing Readiness Review - Auto Changer | LSST Forecast - B57 - B1 | 3 | 0 | 2017-06-27 | 2017-06-29 | 0 | 2017-06-27 | 2017-06-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-07-25 | 2017-07-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 3 | 2 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.01 | Auto Changer | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Design/Engineering
FALSE |  | CAMF664000 | MRR - Manufacturing Readiness Review - Filter Loader | LSST Forecast - B57 - B1 | 3 | 0 | 2017-06-27 | 2017-06-29 | 0 | 2017-06-27 | 2017-06-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-07-25 | 2017-07-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 3 | 2 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.02 | Filter Loader | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Design/Engineering
FALSE |  | CAMF667650 | COMP: Final Design & Assembly Drawings - Carousel | LSST Forecast - B57 - B1 | 0 | 0 | 2017-07-03 | 2017-07-03 | 0 | 2017-07-03 | 2017-07-03 | 0 | 2019-06-01 | 2019-06-01 | 2018-10-16 | 2018-10-16 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-08-01 | 2017-08-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  | Level 4 Milestone | Design/Engineering
FALSE |  | CRYO15300 | Assemble Cryostat Housing | LSST Forecast - B57 - B1 | 78 | 0 | 2017-07-03 | 2017-12-11 | 0 | 2017-07-03 | 2017-12-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-08-01 | 2017-11-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 78 | 111 |  | Complete | 100% | 60 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.01 | Cryostat Housing | 60 | 60 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Fabrication/Assembly |  | Other (specify) | [5 empty] | Cryostat Housing & Assembly (TEC) | [6 empty] | Cryostat Housing
FALSE |  | SR550150 | SHIPPING: Ship RTM ETU #2 to SLAC | LSST Forecast - B57 - B1 | 4 | 0 | 2017-07-03 | 2017-07-07 | 0 | 2017-07-03 | 2017-07-07 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-08-01 | 2017-08-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 3 |  | Complete | 100% | 8 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 8 | 8 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration |  | Other (specify) | [5 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM ETU #2 |  | Science Raft System
FALSE |  | SR550274_2 | RTM1_RTM Qualification at TS5 | LSST Forecast - B57 - B1 | 19 | 0 | 2017-07-03 | 2017-07-28 | 0 | 2017-07-03 | 2017-07-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-18 | 2019-09-18 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-08-01 | 2017-08-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 19 | 18 |  | Complete | 100% | 45 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 45 | 45 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #1 (First Article) |  | Science Raft System
FALSE |  | ITC30580 | Perform Engineering RTM Receiving Test #2 | LSST Forecast - B57 - B1 | 25 | 0 | 2017-07-10 | 2017-09-15 | 0 | 2017-07-10 | 2017-09-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-08-07 | 2017-09-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 4 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 48 |  | Complete | 100% | 330 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.03 | Raft Acceptance Testing | 330 | 330 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [6 empty] | Cryostat I&T
FALSE |  | SR330840_5 | Vendor Lead Time - Backthinning Completion - V1 Prod Lot 2 (30 Sensors) | LSST Forecast - B57 - B1 | 107 | 0 | 2017-07-10 | 2017-11-10 | 0 | 2017-07-10 | 2017-11-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 10 | FALSE | Normal | FALSE | 2017-08-01 | 2018-01-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 4 | 1 | 0 | 0 | 10 | 0 | 1 | 8 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 107 | 88 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  |  | Procurement | [23 empty] | Science Sensors
FALSE |  | CBM46400 | Recv, Prep, Assemble (Shutter Proto) | LSST Forecast - B57 - B1 | 40 | 0 | 2017-07-14 | 2018-07-31 | 0 | 2017-07-14 | 2018-07-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-06 | 2019-08-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-09-18 | 2017-11-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 254 |  | Complete | 100% | 641 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.02.02 | Shutter Development | 641 | 641 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 5% |  | Engineering Test/Validation |  | Commissioning and Testing | [5 empty] | Shutter Development (TEC) | [6 empty] | Shutter Prototype
FALSE |  | CRYO35075 | COMP: Preliminary Design/Analysis - Cryostat Utility Trunk | LSST Forecast - B57 - B1 | 0 | 0 | 2017-07-18 | 2017-07-18 | 0 | 2017-07-18 | 2017-07-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-08-01 | 2017-08-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 4 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.05.02 | Utility Trunk Thermo-Mechanical and Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Design/Engineering
FALSE |  | SR333445 | Batch Sensor Testing (RTM #7) | LSST Forecast - B57 - B1 | 5 | 0 | 2017-07-25 | 2017-07-31 | 0 | 2017-07-25 | 2017-07-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-08-28 | 2017-09-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 9 | 0 | 9 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 4 |  | Complete | 100% | 83 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 83 | 83 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | SR333455 | Batch Sensor Testing (RTM #8) | LSST Forecast - B57 - B1 | 5 | 0 | 2017-07-28 | 2017-08-18 | 0 | 2017-07-28 | 2017-08-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-08-28 | 2017-09-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 15 |  | Complete | 100% | 103 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 103 | 103 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | SR550574 | RTM6_RTM Construction at TS6 | LSST Forecast - B57 - B1 | 15 | 0 | 2017-08-01 | 2017-08-21 | 0 | 2017-08-01 | 2017-08-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-09-01 | 2017-09-22 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 14 |  | Complete | 100% | 64 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 64 | 64 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #6 |  | Science Raft System
FALSE |  | CR222930 | Assemble the ComCam TS-7 Dewar | LSST Forecast - B57 - B1 | 15 | 0 | 2017-08-08 | 2017-08-25 | 0 | 2017-08-08 | 2017-08-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-16 | 2019-05-16 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-09-01 | 2017-09-22 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 3 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 13 |  | Complete | 100% | 100 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 100 | 100 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Procurement | [7 empty] | Corner Raft Tower Module (CRTM) (TEC)
FALSE |  | CR230900 | CRSA warm-cold metrology - practice CRSA metrology with fixtures | LSST Forecast - B57 - B1 | 15 | 0 | 2017-08-14 | 2017-12-15 | 0 | 2017-08-14 | 2017-12-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-09-18 | 2017-10-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 7 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 86 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.45) Task/item is a conceptual design and/or advances the state of the art | 0% |  | Testing/Integration |  | Other (specify) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Integration (Baseplate, thermal straps) | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CR223025 | AVAIL: Corner Raft TS-7 for I&T | LSST Forecast - B57 - B1 | 0 | 0 | 2017-08-18 | 2017-08-18 | 0 | 2017-08-18 | 2017-08-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-09-21 | 2017-09-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | SR330845_2 | RCV: 2nd Set Sensor Delivery - V1 Prod Lot 2 (Sensor 72) | LSST Forecast - B57 - B1 | 21 | 0 | 2017-08-21 | 2017-10-13 | 0 | 2017-08-21 | 2017-10-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 61335.6 | 61335.6 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2017-09-01 | 2017-10-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 0 | 7 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 21 | 38 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 61335.6 | 61335.6 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR333465 | Batch Sensor Testing (RTM #9) | LSST Forecast - B57 - B1 | 5 | 0 | 2017-08-21 | 2017-08-31 | 0 | 2017-08-21 | 2017-08-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2017-10-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 8 | 0 | 8 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 8 |  | Complete | 100% | 83 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 83 | 83 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | CRYO71120 | Prep for C_FDR - Chile System | LSST Forecast - B57 - B1 | 28 | 0 | 2017-08-21 | 2017-10-31 | 0 | 2017-08-21 | 2017-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-17 | 2019-06-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2017-11-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 3 | 3 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 28 | 50 |  | Complete | 100% | 140 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.01 | Refrigeration System - Chile System (System Design & Integration) | 140 | 140 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC)
FALSE |  | SR340395 | Backside Processing (Batch 10) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 25 | 0 | 2017-09-01 | 2017-09-15 | 0 | 2017-09-01 | 2017-09-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-10-02 | 2017-11-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 9 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR340415 | Backside Processing (Batch 11) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 27 | 0 | 2017-09-01 | 2017-09-15 | 0 | 2017-09-01 | 2017-09-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-10-05 | 2017-11-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 27 | 9 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | DAQ342900 | Update Documentation - Pre-Production - FES | LSST Forecast - B57 - B1 | 15 | 0 | 2017-09-04 | 2017-09-29 | 0 | 2017-09-04 | 2017-09-29 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2017-10-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 18 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.11 | FPA Emulation Server Software (FES) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Testing/Integration |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | DAQ Readout Systems (TEC) |  | ICD's for Phase 3 |  |  |  |  | DAQ Readout Systems
FALSE |  | CAMF660600 | Requisition - Other Items - Auto Changer | LSST Forecast - B57 - B1 | 5 | 0 | 2017-09-05 | 2018-07-02 | 0 | 2017-09-05 | 2018-07-02 | 0 | 2019-06-01 | 2019-06-01 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2017-10-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 198 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.01 | Auto Changer | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Procurement
FALSE |  | CRYO32300 | Prep for Prelim Design Review - Cryostat Vacuum Purge | LSST Forecast - B57 - B1 | 5 | 0 | 2017-09-05 | 2017-09-11 | 0 | 2017-09-05 | 2017-09-11 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2017-10-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 4 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.03 | Vacuum Processing and Ground Support | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Cryostat Utillities
FALSE |  | CR241300 | WEB Assembly of PCB Boards (8 Units) | LSST Forecast - B57 - B1 | 25 | 0 | 2017-09-11 | 2017-12-20 | 0 | 2017-09-11 | 2017-12-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-10-02 | 2017-11-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 68 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.01 | Wavefront Electronics Board (WEB) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Fabrication/Assembly | [7 empty] | Corner Raft Electronics (TEC) | WEB
FALSE |  | CR241320 | Additional custom software and engineering support for WEB screening | LSST Forecast - B57 - B1 | 40 | 0 | 2017-09-11 | 2018-01-19 | 0 | 2017-09-11 | 2018-01-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-11-06 | 2018-01-18 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 2 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 80 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.01 | Wavefront Electronics Board (WEB) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Testing/Integration | [7 empty] | Corner Raft Electronics (TEC) | WEB
FALSE |  | CR242580 | GEB Assembly of PCB Boards (8 Units) | LSST Forecast - B57 - B1 | 20 | 0 | 2017-09-11 | 2017-12-22 | 0 | 2017-09-11 | 2017-12-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-10-30 | 2017-11-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 68 |  | Complete | 100% | 125 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.02 | Guider Electronics Board (GEB) | 125 | 125 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Fabrication/Assembly | [7 empty] | Corner Raft Electronics (TEC) | GEB
FALSE |  | SR550515 | RTM5_RTM Qualification at TS8 | LSST Forecast - B57 - B1 | 15 | 0 | 2017-09-11 | 2017-10-06 | 0 | 2017-09-11 | 2017-10-06 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-10-02 | 2017-10-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 19 |  | Complete | 100% | 139 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 139 | 139 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [5 empty] | Critical Path to CD-2 | Science Raft - Test Stands | [6 empty] | RTM #5 |  | Science Raft System
FALSE |  | ITC30612 | C_IRR- Raft Acceptance Testing | LSST Forecast - B57 - B1 | 1 | 0 | 2017-09-18 | 2017-09-18 | 0 | 2017-09-18 | 2017-09-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-16 | 2017-10-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 64 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.03 | Raft Acceptance Testing | 64 | 64 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Other (specify) | [5 empty] | Cryostat I&T (TEC)
FALSE |  | SR340455 | Backside Processing (Batch 13) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 21 | 0 | 2017-09-18 | 2017-10-30 | 0 | 2017-09-18 | 2017-10-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-10-30 | 2017-12-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 21 | 30 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR554120 | Testing of all Flex Cables | LSST Forecast - B57 - B1 | 15 | 0 | 2017-09-25 | 2018-04-25 | 0 | 2017-09-25 | 2018-04-25 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-11-10 | 2017-12-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 137 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.00) Task/item is fully invoiced/completed | 14% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | DAQ330000 | COMP: Prototype - SSD-RTM | LSST Forecast - B57 - B1 | 0 | 0 | 2017-09-29 | 2017-09-29 | 0 | 2017-09-29 | 2017-09-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-25 | 2019-07-25 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-12-08 | 2017-12-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.05 | SSD-RTM (Rear Transistion Module, incl Drives) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer |  |  | Level 4 Milestone | Engineering Test/Validation | [9 empty] | ICD's for Phase 3
FALSE |  | CR221420 | COMP: Corner raft tower tooling | LSST Forecast - B57 - B1 | 0 | 0 | 2017-09-29 | 2017-09-29 | 0 | 2017-09-29 | 2017-09-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-10-04 | 2017-10-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% | Level 4 Milestone | Fabrication/Assembly | [8 empty] | CRTM Fab/assy Tooling/shipping
FALSE |  | DAQ338460 | COMP: Production - Timing Distribution System | LSST Forecast - B57 - B1 | 0 | 0 | 2017-09-29 | 2017-09-29 | 0 | 2017-09-29 | 2017-09-29 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-10-31 | 2017-10-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 6 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.10 | Timing Distribution Server Hardware&Software (TDS) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer |  |  | Level 4 Milestone | Testing/Integration
FALSE |  | CRYO32550 | Prep for C_FDR - Cryostat Vacuum Purge | LSST Forecast - B57 - B1 | 5 | 0 | 2017-10-02 | 2017-10-13 | 0 | 2017-10-02 | 2017-10-13 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-11-01 | 2017-11-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 9 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.03 | Vacuum Processing and Ground Support | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Cryostat Utillities
FALSE |  | OP522180 | Prepare procurement for Filter First Article coating option | LSST Forecast - B57 - B1 | 20 | 0 | 2017-10-02 | 2017-10-11 | 0 | 2017-10-02 | 2017-10-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-25 | 2019-07-25 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-29 | 2018-04-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 7 |  | Complete | 100% | 56 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 56 | 56 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 18% |  | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Filters (TEC) | First Article Coating | [5 empty] | Filter Optics
FALSE |  | SR333475 | Batch Sensor Testing (RTM #10) | LSST Forecast - B57 - B1 | 10 | 0 | 2017-10-02 | 2017-10-13 | 0 | 2017-10-02 | 2017-10-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-11-01 | 2017-11-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 83 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 83 | 83 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | DAQ342400 | Generate Documentation - Prototype - FES | LSST Forecast - B57 - B1 | 10 | 0 | 2017-10-03 | 2017-10-13 | 0 | 2017-10-03 | 2017-10-13 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-11-01 | 2017-11-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 8 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.11 | FPA Emulation Server Software (FES) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | DAQ Readout Systems (TEC) |  | ICD's for Phase 3 |  |  |  |  | DAQ Readout Systems
FALSE |  | SR550516 | RTM5_RTM Qualification at TS5 | LSST Forecast - B57 - B1 | 5 | 0 | 2017-10-09 | 2017-10-16 | 0 | 2017-10-09 | 2017-10-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-11-08 | 2017-11-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 5 |  | Complete | 100% | 45 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 45 | 45 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #5 |  | Science Raft System
FALSE |  | ITC25840 | RCV: Outside Fabrication Procurement - BOT | LSST Forecast - B57 - B1 | 4 | 0 | 2017-10-10 | 2017-10-13 | 0 | 2017-10-10 | 2017-10-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 12097 | 12097 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-11-01 | 2017-11-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 3 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.02.01 | Bench For Optical Testing (BOT) | 0 | 0 | 0 | 12097 | 12097 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC)
FALSE |  | SR333485 | Batch Sensor Testing (RTM #11) | LSST Forecast - B57 - B1 | 10 | 0 | 2017-10-16 | 2017-11-30 | 0 | 2017-10-16 | 2017-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-11-01 | 2017-11-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 31 |  | Complete | 100% | 83 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 83 | 83 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | SR333605 | Batch Sensor Testing (CRRTM) | LSST Forecast - B57 - B1 | 20 | 0 | 2017-10-16 | 2017-10-31 | 0 | 2017-10-16 | 2017-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-11-01 | 2017-11-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 9 | 0 | 9 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 11 |  | Complete | 100% | 204 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 204 | 204 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | ITC25870 | Initial Integration - BOT | LSST Forecast - B57 - B1 | 2 | 0 | 2017-10-17 | 2017-12-15 | 0 | 2017-10-17 | 2017-12-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-11-21 | 2017-11-22 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 5 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 41 |  | Complete | 100% | 912 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.02.01 | Bench For Optical Testing (BOT) | 912 | 912 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC)
FALSE |  | DAQ341700 | Update Documentation - Production - RDS/RDC | LSST Forecast - B57 - B1 | 40 | 0 | 2017-10-23 | 2017-10-31 | 0 | 2017-10-23 | 2017-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-12 | 2018-05-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 6 |  | Complete | 100% | 20 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.09.02 | Raft Data Server/Client Software (RDS/RDC) | 20 | 20 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Testing/Integration |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | DAQ Readout Systems (TEC) |  | ICD's for Phase 3 |  |  |  |  | DAQ Readout Systems
FALSE |  | DAQ361400 | Update Documentation - Production - IMS/IMC | LSST Forecast - B57 - B1 | 40 | 0 | 2017-10-23 | 2017-10-31 | 0 | 2017-10-23 | 2017-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-12 | 2018-05-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 6 |  | Complete | 100% | 20 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.09.01 | Image Management/Server/Client Software | 20 | 20 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Testing/Integration |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | DAQ Readout Systems (TEC)
FALSE |  | CAMF668450 | RCV: other items - Carousel | LSST Forecast - B57 - B1 | 99 | 0 | 2017-10-23 | 2019-05-20 | 0 | 2017-10-23 | 2019-05-20 | 0 | 2019-06-01 | 2019-06-01 | 2018-10-16 | 2018-10-16 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-10-23 | 2018-03-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 99 | 378 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Procurement
FALSE |  | ITC25880 | Preliminary Testing - BOT | LSST Forecast - B57 - B1 | 42 | 0 | 2017-10-25 | 2017-12-15 | 0 | 2017-10-25 | 2017-12-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2017-11-27 | 2018-02-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 4 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 42 | 35 |  | Complete | 100% | 352 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.02.01 | Bench For Optical Testing (BOT) | 352 | 352 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC)
FALSE |  | CBM26200 | Prep for Manufacturing Readiness Review - Camera Body | LSST Forecast - B57 - B1 | 11 | 0 | 2017-11-01 | 2017-11-16 | 0 | 2017-11-01 | 2017-11-16 | 0 | 2019-06-01 | 2019-06-01 | 2018-09-07 | 2018-09-07 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-12-01 | 2017-12-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 11 | 11 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.01.02 | Camera Body Development | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 15% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Camera Body Development (TEC) | [6 empty] | Cam Body/Purge Prod Sprt
FALSE |  | CCS310800 | Test Integration Gantry Proof of Concept Subsystem - Gantry HCU | LSST Forecast - B57 - B1 | 4 | 0 | 2017-11-01 | 2017-11-06 | 0 | 2017-11-01 | 2017-11-06 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-12-01 | 2017-12-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 3 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.08.04 | Gantry HCU | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Design Support (i.e, soil testing, vibration testing, seismic analysis, etc needed for design) | [5 empty] | CCS HCU (TEC) | [5 empty] | Critical Path to CD-2
FALSE |  | SR340555 | Backside Processing (Batch 18) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 25 | 0 | 2017-11-01 | 2017-11-17 | 0 | 2017-11-01 | 2017-11-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-12-01 | 2018-01-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 12 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | CRYO71160 | COMP: C_FDR - Chile System | LSST Forecast - B57 - B1 | 0 | 0 | 2017-11-03 | 2017-11-03 | 0 | 2017-11-03 | 2017-11-03 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-17 | 2019-06-17 | 0 | 0 | 0 | 0 | 0 | 16 | FALSE | Finish Milestone | FALSE | 2017-12-04 | 2017-12-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 16 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 17 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.01 | Refrigeration System - Chile System (System Design & Integration) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Alice Callen |  |  | Level 4 Milestone | Design/Engineering
FALSE |  | CRYO84250 | COMP: Final Design/Analysis - Cryostat Utility Trunk | LSST Forecast - B57 - B1 | 0 | 0 | 2017-11-13 | 2017-11-13 | 0 | 2017-11-13 | 2017-11-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-12-13 | 2017-12-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.05.02 | Utility Trunk Thermo-Mechanical and Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Design/Engineering
FALSE |  | CRYO84600 | Incorporate C_FDR - Changes - Cryostat Utilities Trunk | LSST Forecast - B57 - B1 | 20 | 0 | 2017-11-15 | 2017-12-15 | 0 | 2017-11-15 | 2017-12-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2018-02-21 | 2018-03-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 20 |  | Complete | 100% | 94 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.05.02 | Utility Trunk Thermo-Mechanical and Assembly | 94 | 94 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Utility Trunk Thermo-Mechanical and Assembly (TEC) | [6 empty] | Utility Trunk
FALSE |  | SR333495 | Batch Sensor Testing (RTM #12) | LSST Forecast - B57 - B1 | 20 | 0 | 2017-11-15 | 2017-12-11 | 0 | 2017-11-15 | 2017-12-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-12-01 | 2017-12-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 16 |  | Complete | 100% | 83 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 83 | 83 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | ITC30640 | Perform Science RTM Receiving Test #1 | LSST Forecast - B57 - B1 | 13 | 0 | 2017-11-17 | 2018-01-12 | 0 | 2017-11-17 | 2018-01-12 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-12-01 | 2018-01-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 13 | 27 |  | Complete | 100% | 165 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.03 | Raft Acceptance Testing | 165 | 165 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | Raft Delivery to SLAC
FALSE |  | SR340735 | COMP: Production Lot 2 Phase A Complete | LSST Forecast - B57 - B1 | 0 | 0 | 2017-11-17 | 2017-11-17 | 0 | 2017-11-17 | 2017-11-17 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-12-01 | 2017-12-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 12 | 0 | 12 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% | Level 4 Milestone | Procurement |  |  | Subcontractor | [20 empty] | Science Sensors
FALSE |  | CRYO56190 | AWARD: P.O. - Heat Exchanger Cryo/Cold - Cryostat | LSST Forecast - B57 - B1 | 1 | 0 | 2017-11-17 | 2017-11-17 | 0 | 2017-11-17 | 2017-11-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 216504 | 216504 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-11-22 | 2017-11-22 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.04 | Refrigeration System - Pre IR2 (HX) | 0 | 0 | 0 | 216504 | 216504 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | B1 Procurement Commitment (C5.1) |  | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 20% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Refrigeration System (TEC)
FALSE |  | CRYO25630 | Generate Manufacturing Docs - Sieve | LSST Forecast - B57 - B1 | 20 | 0 | 2017-11-22 | 2017-11-22 | 0 | 2017-11-22 | 2017-11-22 | 0 | 2019-06-01 | 2019-06-01 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-08-29 | 2018-09-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.02 | Getter Pumps | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  |  | Design/Engineering
FALSE |  | CRYO23850 | AVAIL: Ready for Integration - Grid Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2017-12-01 | 2017-12-01 | 0 | 2017-12-01 | 2017-12-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Finish Milestone | FALSE | 2018-01-12 | 2018-01-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.04 | Grid Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 5 Milestone | Fabrication/Assembly | [24 empty] | Clean Room at SLAC
FALSE |  | CRYO33850 | Requisition - Rough and Purge Sys - Cryostat Vacuum Purge | LSST Forecast - B57 - B1 | 20 | 0 | 2017-12-01 | 2017-12-01 | 0 | 2017-12-01 | 2017-12-01 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-01-02 | 2018-01-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.03 | Vacuum Processing and Ground Support | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  |  | Procurement
FALSE |  | DAQ307500 | Procurement Process - Production Parts OTM and Cabling | LSST Forecast - B57 - B1 | 5 | 0 | 2017-12-01 | 2018-01-26 | 0 | 2017-12-01 | 2018-01-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-01-02 | 2018-01-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 28 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.01 | Optical Transition Module (OTM) and Cabling | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [7 empty] | ICD's for Phase 3 |  |  |  |  | DAQ Readout Systems
FALSE |  | ITC33580 | Preliminary Testing - Gantry | LSST Forecast - B57 - B1 | 11 | 0 | 2017-12-01 | 2018-03-16 | 0 | 2017-12-01 | 2018-03-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2018-02-13 | 2018-02-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 2 | 0 | 0 | 2 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 4 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 11 | 62 |  | Complete | 100% | 176 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.01 | Integration Gantry | 176 | 176 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2
FALSE |  | DAQ900535 | Kitting and Testing of DAQ System to support 2 rafts | LSST Forecast - B57 - B1 | 20 | 0 | 2017-12-01 | 2017-12-22 | 0 | 2017-12-01 | 2017-12-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-01-02 | 2018-01-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 11 |  | Complete | 100% | 8 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.13.03 | DAQ Version 2.0 | 8 | 8 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Testing/Integration | [7 empty] | DAQ Readout Systems (TEC)
FALSE |  | SR340935 | Backside Processing (Batch 23) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 25 | 0 | 2017-12-04 | 2017-12-15 | 0 | 2017-12-04 | 2017-12-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-01-10 | 2018-02-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 9 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | CRYO25660 | COMP: Design and Documentation - Sieve | LSST Forecast - B57 - B1 | 0 | 0 | 2017-12-20 | 2017-12-20 | 0 | 2017-12-20 | 2017-12-20 | 0 | 2019-06-01 | 2019-06-01 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2018-01-02 | 2018-01-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.02 | Getter Pumps | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Design/Engineering
FALSE |  | CR230960 | CRSA baseplate lot 1 - Metrology (height/flatness/hole location) on test station 5 | LSST Forecast - B57 - B1 | 10 | 0 | 2018-01-02 | 2018-01-16 | 0 | 2018-01-02 | 2018-01-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-02-01 | 2018-02-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.45) Task/item is a conceptual design and/or advances the state of the art | 0% |  | Testing/Integration |  | Other (specify) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Integration (Baseplate, thermal straps) | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | ITC22250 | I&T Vacuum Qualification Test | LSST Forecast - B57 - B1 | 69 | 0 | 2018-01-02 | 2018-02-02 | 0 | 2018-01-02 | 2018-02-02 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-02-01 | 2018-05-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 6 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 69 | 22 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.01.03 | Vacuum Qualification Tests | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC)
FALSE |  | SR333505 | Batch Sensor Testing (RTM #13) | LSST Forecast - B57 - B1 | 9 | 0 | 2018-01-02 | 2018-01-12 | 0 | 2018-01-02 | 2018-01-12 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-02-01 | 2018-02-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 9 | 8 |  | Complete | 100% | 83 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 83 | 83 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | CRYO20750 | Test and Verify Cryo & Cold Plate | LSST Forecast - B57 - B1 | 20 | 0 | 2018-01-08 | 2018-01-31 | 0 | 2018-01-08 | 2018-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-02-02 | 2018-03-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 16 |  | Complete | 100% | 350 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.03 | Cryo and Cold Plates | 350 | 350 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 11% |  | Fabrication/Assembly |  | Other (specify) | [5 empty] | Cryo and Cold Plates (TEC) | [5 empty] | Critical Path to CD-2 | Cryo and Cold Plates
FALSE |  | CRYO24950 | Prep for C_FDR - Evaporable Getter Pumps | LSST Forecast - B57 - B1 | 5 | 0 | 2018-01-08 | 2018-01-30 | 0 | 2018-01-08 | 2018-01-30 | 0 | 2019-06-01 | 2019-06-01 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-04-11 | 2018-04-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 15 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.02 | Getter Pumps | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Cryostat Getter Pumps
FALSE |  | SR550540 | SHIPPING: Ship RTM #5 to SLAC | LSST Forecast - B57 - B1 | 4 | 0 | 2018-01-09 | 2018-01-12 | 0 | 2018-01-09 | 2018-01-12 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-02-08 | 2018-02-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 3 |  | Complete | 100% | 8 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 8 | 8 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration |  | Other (specify) | [5 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #5 |  | Science Raft System
FALSE |  | CRYO15250 | Clean Cryostat Housing | LSST Forecast - B57 - B1 | 22 | 0 | 2018-01-10 | 2018-01-29 | 0 | 2018-01-10 | 2018-01-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-02-01 | 2018-03-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 22 | 12 |  | Complete | 100% | 64 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.01 | Cryostat Housing | 64 | 64 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Fabrication/Assembly |  | Other (specify) | [5 empty] | Cryostat Housing & Assembly (TEC) | [6 empty] | Cryostat Housing
FALSE |  | SR330845_3 | RCV: 3rd Set Sensor Delivery - V1 Prod Lot 2 (Sensor 78) | LSST Forecast - B57 - B1 | 21 | 0 | 2018-01-10 | 2018-03-02 | 0 | 2018-01-10 | 2018-03-02 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 61335.6 | 61335.6 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-01 | 2018-03-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 7 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 21 | 35 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 61335.6 | 61335.6 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | ITC92140 | Equipment Procurement Review - Prep - Com Cam | LSST Forecast - B57 - B1 | 2 | 0 | 2018-01-10 | 2018-01-12 | 0 | 2018-01-10 | 2018-01-12 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-16 | 2019-05-16 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-02-22 | 2018-02-23 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 2 |  | Complete | 100% | 14 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.06.01 | Commissioning Camera Hardware | 14 | 14 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Kevin Reil | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | R&D | [5 empty] | Commissioning Camera (TEC)
FALSE |  | CRYO70320 | Pre-Clean IR2 Hoses (linked to RQD Hose Fitting Installed) | LSST Forecast - B57 - B1 | 12 | 0 | 2018-01-10 | 2018-01-26 | 0 | 2018-01-10 | 2018-01-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-01-10 | 2018-01-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 12 | 12 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.03 | Refrigeration System - Pre IR2 (Long Lines) | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | CCS120205 | Plan configuration database & telemetry support for ComCam/Full Camera | LSST Forecast - B57 - B1 | 40 | 0 | 2018-01-11 | 2018-06-29 | 0 | 2018-01-11 | 2018-06-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-31 | 2019-05-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-02-01 | 2018-03-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 118 |  | Complete | 100% | 220 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.02.07 | CCS Core 6.0 Release (Comcam Ship) | 220 | 220 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering | [7 empty] | CCS Core (TEC)
FALSE |  | CRYO84700 | Generate Detail and Assembly Drawings Cryostat Utility Trunk | LSST Forecast - B57 - B1 | 80 | 20 | 2018-01-12 | 2019-06-28 | 27 | 2018-01-12 |  | 0 | 2019-06-03 | 2019-06-28 | 2019-07-11 | 2019-08-07 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-02-01 | 2018-05-24 |  |  |  |  | 0.9 | 0 | FALSE | FALSE | None |  | None |  | 2019-06-28 |  |  |  |  | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 80 | 341 |  | InProgress | 90% | 819 | 0 | 819 | 819 | LSST Forecast - B57 - B1.3.06.05.02 | Utility Trunk Thermo-Mechanical and Assembly | 737.1 | 819 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Utility Trunk Thermo-Mechanical and Assembly (TEC) | [6 empty] | Utility Trunk
FALSE |  | ITC25890 | Final Testing - BOT | LSST Forecast - B57 - B1 | 28 | 0 | 2018-01-15 | 2018-04-10 | 0 | 2018-01-15 | 2018-04-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-04-02 | 2018-05-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 1 | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 4 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 28 | 59 |  | Complete | 100% | 416 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.02.01 | Bench For Optical Testing (BOT) | 416 | 416 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC)
FALSE |  | SR340995 | Backside Processing (Batch 26) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 20 | 0 | 2018-01-16 | 2018-01-26 | 0 | 2018-01-16 | 2018-01-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-02-01 | 2018-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 8 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | CR231000 | AVAIL: Pre-Assembled CRSA - 4 production units, 4 I&T units | LSST Forecast - B57 - B1 | 0 | 0 | 2018-01-17 | 2018-01-17 | 0 | 2018-01-17 | 2018-01-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2018-03-01 | 2018-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 5 Milestone | Testing/Integration | [8 empty] | CRSA Integration (Baseplate, thermal straps)
FALSE |  | DAQ328200 | Procurement Process - Production Parts - FPA-RTM | LSST Forecast - B57 - B1 | 10 | 0 | 2018-01-29 | 2018-02-14 | 0 | 2018-01-29 | 2018-02-14 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2018-01-29 | 2018-02-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 12 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.04 | DAQ FPA-RTM (Rear Transistion Module) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [7 empty] | ICD's for Phase 3 |  |  |  |  | DAQ Readout Systems
FALSE |  | CAMF665250 | Inspect Procured Parts - Filter Loader | LSST Forecast - B57 - B1 | 5 | 0 | 2018-02-01 | 2018-07-18 | 0 | 2018-02-01 | 2018-07-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-28 | 2018-04-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 1 | 1 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 116 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.02 | Filter Loader | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Fabrication/Assembly
FALSE |  | ITC22440 | AVAIL: Vacuum Qualification Test Ready for Cryostat Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2018-02-02 | 2018-02-02 | 0 | 2018-02-02 | 2018-02-02 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-04-10 | 2018-04-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.01.03 | Vacuum Qualification Tests | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration | [16 empty] | Integration and Test
FALSE |  | CRYO73160 | Detailed Drawings Hx - Chile System Configuration - Cryo | LSST Forecast - B57 - B1 | 9 | 0 | 2018-02-05 | 2018-03-20 | 0 | 2018-02-05 | 2018-03-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-17 | 2019-06-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-01 | 2018-03-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 9 | 30 |  | Complete | 100% | 30 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.04 | Refrigeration System - Chile System (HX) | 30 | 30 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | SR550600 | SHIPPING: Ship RTM #6 to SLAC | LSST Forecast - B57 - B1 | 4 | 0 | 2018-02-12 | 2018-02-15 | 0 | 2018-02-12 | 2018-02-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-03-12 | 2018-03-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 3 |  | Complete | 100% | 8 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 8 | 8 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration |  | Other (specify) | [5 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #6 |  | Science Raft System
FALSE |  | OP541620 | AWARD: Phase 3 BBAR Coating of L3 (Option 2) | LSST Forecast - B57 - B1 | 1 | 0 | 2018-02-12 | 2018-02-12 | 0 | 2018-02-12 | 2018-02-12 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 81000 | 81000 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-04-24 | 2018-04-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 8 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 0 | 0 | 0 | 81000 | 81000 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | B1 Procurement Commitment (C5.1) |  | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 14% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | L3 Assembly (TEC) | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly) |  |  |  | L1-L2 Optics
FALSE |  | CR235190 | Guide Sensor Readout Study - CCD First Article | LSST Forecast - B57 - B1 | 5 | 10 | 2018-02-20 | 2019-10-01 | 510 | 2018-02-20 |  | 0 | 2019-09-18 | 2019-10-01 | 2021-10-18 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-05-22 | 2018-05-29 |  |  |  |  | 0.2917 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 4 | 0 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 316 |  | InProgress | 29.17% | 200 | 0 | 200 | 200 | LSST Forecast - B57 - B1.3.04.02.03.03 | Guide Sensors | 58.34 | 200 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Engineering Test/Validation |  | Other (specify) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | Guide Sensor study & testbed | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | DAQ313360 | Fabricate & Load 2 prototype boards - COB Production Candidate | LSST Forecast - B57 - B1 | 19 | 0 | 2018-02-20 | 2018-03-23 | 0 | 2018-02-20 | 2018-03-23 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-31 | 2019-10-31 | 30000 | 30000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-14 | 2018-04-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 19 | 23 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.02 | DAQ COB (Main ATCA DAQ Module) | 0 | 0 | 0 | 30000 | 30000 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | DAQ Readout Systems (TEC)
FALSE |  | CRYO73420 | Requisition - Hx Can Vac Sys Cryostat - Chile System | LSST Forecast - B57 - B1 | 5 | 0 | 2018-02-22 | 2018-02-28 | 0 | 2018-02-22 | 2018-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-15 | 2019-10-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-01 | 2018-03-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 4 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.04 | Refrigeration System - Chile System (HX) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Alice Callen |  |  |  | Procurement
FALSE |  | CBM49800 | AWARD: Contract - Shutter Blades | LSST Forecast - B57 - B1 | 1 | 0 | 2018-02-27 | 2018-02-27 | 0 | 2018-02-27 | 2018-02-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-22 | 2019-08-22 | 261854 | 261854 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-04-26 | 2018-04-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.02.02 | Shutter Development | 0 | 0 | 0 | 261854 | 261854 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | B1 Procurement Commitment (C5.1) |  | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 5% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Shutter Development (TEC) | [6 empty] | Shutter Prod Sprt
FALSE |  | SR333330 | COMP: Fallout sensor testing | LSST Forecast - B57 - B1 | 0 | 0 | 2018-02-28 | 2018-02-28 | 0 | 2018-02-28 | 2018-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-07-05 | 2018-07-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Catalog Listing or Industrial Construction Databases |  |  |  | Bill Wahl |  |  | Level 4 Milestone | Testing/Integration | [6 empty] | e2v | Science Sensors Acceptance (TEC) | [6 empty] | Science Sensors Acceptance | [6 empty] | Lot 3 Primary Vendor |  | Science Sensors
FALSE |  | SR341055 | Backside Processing (Batch 29) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 26 | 0 | 2018-02-28 | 2018-03-15 | 0 | 2018-02-28 | 2018-03-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-03-01 | 2018-04-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 26 | 11 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | CRYO73042 | Prep for Manufacturing Readiness Review - Hx Chile | LSST Forecast - B57 - B1 | 20 | 0 | 2018-03-12 | 2018-04-25 | 0 | 2018-03-12 | 2018-04-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-17 | 2019-06-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-04-11 | 2018-05-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 32 |  | Complete | 100% | 236 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.04 | Refrigeration System - Chile System (HX) | 236 | 236 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  | Percent Complete on Work Package |  | Brian J. Langton |  |  |  | Design/Engineering | [7 empty] | Refrigeration System (TEC)
FALSE |  | CCS250040 | Test complete BOT system under eTraveler control - BOT HCU | LSST Forecast - B57 - B1 | 12 | 0 | 2018-03-16 | 2018-06-15 | 0 | 2018-03-16 | 2018-06-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-04-17 | 2018-05-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 12 | 64 |  | Complete | 100% | 300 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.08.02 | BOT HCU | 300 | 300 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Expert Opinion (Engineering Allowance) | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 6% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | CCS HCU (TEC) | [6 empty] | Camera I&T Hardware Control Unit
FALSE |  | ITC33590 | Final Testing - Gantry | LSST Forecast - B57 - B1 | 11 | 0 | 2018-03-19 | 2018-04-25 | 0 | 2018-03-19 | 2018-04-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-05-02 | 2018-05-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 8 | 0 | 8 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 4 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 11 | 27 |  | Complete | 100% | 248 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.01 | Integration Gantry | 248 | 248 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat I&T (TEC)
FALSE |  | OP531260 | Procure L2 Coating | LSST Forecast - B57 - B1 | 25 | 0 | 2018-03-27 | 2018-06-15 | 0 | 2018-03-27 | 2018-06-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-03 | 2019-09-03 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2018-04-02 | 2018-05-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 4 | 0 | 0 | 1 | 3 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 57 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment |  | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 0% |  | Procurement | [7 empty] | L1-L2 Assembly (TEC) | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly) |  |  |  | L1-L2 Optics
FALSE |  | CBM46500 | Test Shutter Proto--Mech, Light, Env, Life (Shutter Proto) | LSST Forecast - B57 - B1 | 8 | 0 | 2018-03-28 | 2018-10-15 | 0 | 2018-03-28 | 2018-10-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-06 | 2019-08-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-04-27 | 2018-05-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 4 | 2 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 8 | 140 |  | Complete | 100% | 360 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.02.02 | Shutter Development | 360 | 360 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 5% |  | Engineering Test/Validation |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Shutter Development (TEC) | [6 empty] | Shutter Prototype
FALSE |  | CR241360 | AVAIL: WEB Ready for Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2018-03-30 | 2018-03-30 | 0 | 2018-03-30 | 2018-03-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2018-04-02 | 2018-04-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.01 | Wavefront Electronics Board (WEB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 5 Milestone | Testing/Integration | [8 empty] | WEB
FALSE |  | CR242640 | AVAIL: GEB Ready for Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2018-03-30 | 2018-03-30 | 0 | 2018-03-30 | 2018-03-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2018-04-02 | 2018-04-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.02 | Guider Electronics Board (GEB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 5 Milestone | Testing/Integration | [8 empty] | GEB
FALSE |  | ITC25860 | NEED: CCS Suite 10 (+HCU) | LSST Forecast - B57 - B1 | 0 | 0 | 2018-03-30 | 2018-03-30 | 0 | 2018-03-30 | 2018-03-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-12-03 | 2018-12-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.02.01 | Bench For Optical Testing (BOT) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | DAQ345280 | COMP: SATA Firmware | LSST Forecast - B57 - B1 | 0 | 0 | 2018-03-30 | 2018-03-30 | 0 | 2018-03-30 | 2018-03-30 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2018-04-02 | 2018-04-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.12 | Storage Array Software (SAS/SAC) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer |  |  | Level 4 Milestone | Testing/Integration
FALSE |  | CRYO25400 | COMP: Design and Documentation - Evaporable Getter Pump | LSST Forecast - B57 - B1 | 0 | 0 | 2018-04-02 | 2018-04-02 | 0 | 2018-04-02 | 2018-04-02 | 0 | 2019-06-01 | 2019-06-01 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-06-06 | 2018-06-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.02 | Getter Pumps | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Design/Engineering
FALSE |  | DAQ900260 | Fabricate Prototype flash (100) | LSST Forecast - B57 - B1 | 30 | 0 | 2018-04-02 | 2018-05-15 | 0 | 2018-04-02 | 2018-05-15 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-05-01 | 2018-06-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 31 |  | Complete | 100% | 8 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.13.09 | DAQ Assembled Hardware | 8 | 8 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Engineering Test/Validation | [7 empty] | DAQ Readout Systems (TEC)
FALSE |  | SR550991 | RTM13_RSA Construction at TS4 | LSST Forecast - B57 - B1 | 6 | 0 | 2018-04-02 | 2018-04-09 | 0 | 2018-04-02 | 2018-04-09 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-05-01 | 2018-05-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 6 | 5 |  | Complete | 100% | 44 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 44 | 44 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #13 |  | Science Raft System
FALSE |  | SR330845_4 | RCV: 4th Set Sensor Delivery - V1 Prod Lot 2 (Sensor 84) | LSST Forecast - B57 - B1 | 23 | 0 | 2018-04-02 | 2018-04-30 | 0 | 2018-04-02 | 2018-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 61335.6 | 61335.6 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2018-05-01 | 2018-06-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 7 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 23 | 20 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 61335.6 | 61335.6 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | CCS300012 | CCS Testing with External Power Supplies | LSST Forecast - B57 - B1 | 20 | 0 | 2018-04-02 | 2018-06-26 | 0 | 2018-04-02 | 2018-06-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-05-01 | 2018-05-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 60 |  | Complete | 100% | 180 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.08.03 | CCOB HCU | 180 | 180 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | CCS HCU (TEC)
FALSE |  | SR333515 | Batch Sensor Testing (RTM #14) | LSST Forecast - B57 - B1 | 18 | 0 | 2018-04-10 | 2018-05-09 | 0 | 2018-04-10 | 2018-05-09 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2018-05-01 | 2018-05-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 3 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 8 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 18 | 21 |  | Complete | 100% | 83 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 83 | 83 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | CR231060 | CRSA#1 Guide Sensor #1 - pin locating fixture installation | LSST Forecast - B57 - B1 | 0 | 0 | 2018-04-13 | 2018-04-13 | 0 | 2018-04-13 | 2018-04-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-04-13 | 2018-04-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 8 | 0 | 8 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 0 | 1 |  | Complete | 100% | 4 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 4 | 4 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.45) Task/item is a conceptual design and/or advances the state of the art | 0% |  | Testing/Integration |  | Other (specify) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Integration (Guide/Wavefront Sensors) | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CR222040 | CRTM#1 - In-House Assembly - Corner raft tower | LSST Forecast - B57 - B1 | 10 | 0 | 2018-04-23 | 2018-05-16 | 0 | 2018-04-23 | 2018-05-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-05-22 | 2018-06-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 7 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 17 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.45) Task/item is a conceptual design and/or advances the state of the art | 0% |  | Testing/Integration |  | Other (specify) | [5 empty] | Corner Raft Tower Module (CRTM) (TEC) | CRTM Assy CRT | [5 empty] | Corner Raft Tower Module (CRTM)
FALSE |  | SR554200 | COMP: ITL Flex Cables | LSST Forecast - B57 - B1 | 0 | 0 | 2018-04-25 | 2018-04-25 | 0 | 2018-04-25 | 2018-04-25 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-05-01 | 2018-05-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% | Level 4 Milestone | Procurement |  |  | Subcontractor | [20 empty] | Science Sensors
FALSE |  | DAQ900560 | Integrate DAQ V3.0 (SAS, FPA/SSD-RTM) | LSST Forecast - B57 - B1 | 10 | 0 | 2018-05-01 | 2018-05-01 | 0 | 2018-05-01 | 2018-05-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-25 | 2019-07-25 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2018-12-07 | 2018-12-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 0 |  | Complete | 100% | 72 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.13.05 | DAQ Version 3.0 | 72 | 72 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Testing/Integration | [7 empty] | DAQ Readout Systems (TEC)
FALSE |  | DAQ900580 | Integrate DAQ V4.0 (SAS, FPA/SSD-RTM) | LSST Forecast - B57 - B1 | 20 | 0 | 2018-05-01 | 2018-05-01 | 0 | 2018-05-01 | 2018-05-01 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-05-01 | 2019-05-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.13.06 | DAQ Version 4.0 | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Testing/Integration | [7 empty] | DAQ Readout Systems (TEC)
FALSE |  | DAQ900680 | Integrate & Test DAQ V5.0 | LSST Forecast - B57 - B1 | 55 | 0 | 2018-05-01 | 2018-05-01 | 0 | 2018-05-01 | 2018-05-01 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-13 | 2019-08-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 55 | 0 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.13.07 | DAQ Version 5.0 | 80 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Testing/Integration | [7 empty] | DAQ Readout Systems (TEC)
FALSE |  | ITC20055 | Initial Integration - Handling Equipment | LSST Forecast - B57 - B1 | 40 | 0 | 2018-05-01 | 2018-05-31 | 0 | 2018-05-01 | 2018-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-11-28 | 2019-02-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 21 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.02 | Camera Handling Equipment | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Camera I&T (TEC)
FALSE |  | ITC20085 | Test Readiness Review - Prep - Handling Equipment | LSST Forecast - B57 - B1 | 10 | 0 | 2018-05-01 | 2018-05-31 | 0 | 2018-05-01 | 2018-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-03-08 | 2019-03-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 21 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.02 | Camera Handling Equipment | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Camera I&T (TEC)
FALSE |  | SR550871 | RTM11_RSA Construction at TS4 | LSST Forecast - B57 - B1 | 6 | 0 | 2018-05-01 | 2018-05-08 | 0 | 2018-05-01 | 2018-05-08 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-06-01 | 2018-06-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 6 | 5 |  | Complete | 100% | 44 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 44 | 44 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #11 |  | Science Raft System
FALSE |  | SR330845_5 | RCV: 5th Set Sensor Delivery - V1 Prod Lot 2 (Sensor 90) | LSST Forecast - B57 - B1 | 21 | 0 | 2018-05-04 | 2018-06-04 | 0 | 2018-05-04 | 2018-06-04 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 30667.8 | 30667.8 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-06-04 | 2018-07-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 3 | 3 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 21 | 20 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 30667.8 | 30667.8 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | ITC25910 | Test Readiness Review - Prep - BOT | LSST Forecast - B57 - B1 | 10 | 0 | 2018-05-09 | 2018-06-06 | 0 | 2018-05-09 | 2018-06-06 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-06-11 | 2018-06-22 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 19 |  | Complete | 100% | 50 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.02.01 | Bench For Optical Testing (BOT) | 50 | 50 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC)
FALSE |  | SR550720 | SHIPPING: Ship RTM #8 to SLAC | LSST Forecast - B57 - B1 | 2 | 0 | 2018-05-10 | 2018-05-11 | 0 | 2018-05-10 | 2018-05-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-19 | 2019-07-19 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-06-12 | 2018-06-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 1 |  | Complete | 100% | 8 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 8 | 8 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration |  | Other (specify) | [5 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #8 |  | Science Raft System
FALSE |  | SR333525 | Batch Sensor Testing (RTM #15) | LSST Forecast - B57 - B1 | 17 | 0 | 2018-05-10 | 2018-05-18 | 0 | 2018-05-10 | 2018-05-18 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-07-02 | 2018-07-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 7 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 17 | 6 |  | Complete | 100% | 83 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 83 | 83 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | CBM28320 | Pack Back Flange - Camera Body | LSST Forecast - B57 - B1 | 5 | 0 | 2018-05-17 | 2018-06-22 | 0 | 2018-05-17 | 2018-06-22 | 0 | 2019-06-01 | 2019-06-01 | 2018-09-07 | 2018-09-07 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-06-19 | 2018-06-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 25 |  | Complete | 100% | 68 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.01.02 | Camera Body Development | 68 | 68 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly |  | Other (specify) | [5 empty] | Camera Body Development (TEC)
FALSE |  | SR333535 | Batch Sensor Testing (RTM #16) | LSST Forecast - B57 - B1 | 15 | 0 | 2018-05-19 | 2018-05-31 | 0 | 2018-05-19 | 2018-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-06-21 | 2018-07-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 10 | 0 | 9 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 3 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 7 |  | Complete | 100% | 83 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 83 | 83 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | OP531240 | Procure L1 Coating | LSST Forecast - B57 - B1 | 40 | 0 | 2018-05-21 | 2018-11-21 | 0 | 2018-05-21 | 2018-11-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-03 | 2019-09-03 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-07-17 | 2018-09-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 5 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 129 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment |  | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 0% |  | Procurement | [7 empty] | L1-L2 Assembly (TEC) | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly) |  |  |  | L1-L2 Optics
FALSE |  | CR222080 | CRTM#1 - Test - CRTM Performance test and optimization | LSST Forecast - B57 - B1 | 20 | 0 | 2018-05-25 | 2019-04-29 | 0 | 2018-05-25 | 2019-04-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 5 | FALSE | Normal | FALSE | 2018-07-24 | 2018-08-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 5 | 0 | 2 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 224 |  | Complete | 100% | 240 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 240 | 240 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.45) Task/item is a conceptual design and/or advances the state of the art | 0% |  | Testing/Integration |  | Other (specify) | [5 empty] | Corner Raft Tower Module (CRTM) (TEC) | CRTM Assy CRT |  |  |  |  | Critical Path to CD-2 | Corner Raft Tower Module (CRTM)
FALSE |  | ITC14080 | COMP: IR2 Services Upgrades | LSST Forecast - B57 - B1 | 0 | 0 | 2018-05-29 | 2018-05-29 | 0 | 2018-05-29 | 2018-05-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-14 | 2019-05-14 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-06-28 | 2018-06-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.03 | IR2 Facility and Operations | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Procurement |  |  | Subcontractor
FALSE |  | CRYO20900 | AVAIL: Ready for Integration - Cryo & Cold Plate | LSST Forecast - B57 - B1 | 0 | 0 | 2018-05-31 | 2018-05-31 | 0 | 2018-05-31 | 2018-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | FALSE | 2018-06-13 | 2018-06-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.03 | Cryo and Cold Plates | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 5 Milestone | Fabrication/Assembly
FALSE |  | SR550274_3 | RTM1_Prepare for Shipment | LSST Forecast - B57 - B1 | 15 | 0 | 2018-05-31 | 2018-06-19 | 0 | 2018-05-31 | 2018-06-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-18 | 2019-09-18 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-06-01 | 2018-06-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 13 |  | Complete | 100% | 45 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 45 | 45 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #1 (First Article) |  | Science Raft System
FALSE |  | DAQ331400 | Procurement Process - Production Parts - SSD-RTM | LSST Forecast - B57 - B1 | 10 | 0 | 2018-06-01 | 2018-06-08 | 0 | 2018-06-01 | 2018-06-08 | 0 | 2019-06-01 | 2019-06-01 | 2020-05-26 | 2020-05-26 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-07-02 | 2018-07-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 5 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.05 | SSD-RTM (Rear Transistion Module, incl Drives) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [7 empty] | ICD's for Phase 3 |  |  |  |  | DAQ Readout Systems
FALSE |  | SR551051 | RTM14_RSA Construction at TS4 | LSST Forecast - B57 - B1 | 5 | 0 | 2018-06-01 | 2018-06-07 | 0 | 2018-06-01 | 2018-06-07 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-07-02 | 2018-07-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 4 |  | Complete | 100% | 44 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 44 | 44 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #14 |  | Science Raft System
FALSE |  | SR341125 | COMP: Batch 32 - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 0 | 0 | 2018-06-01 | 2018-06-01 | 0 | 2018-06-01 | 2018-06-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-07-02 | 2018-07-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% | Level 4 Milestone | Procurement |  |  | Subcontractor | [20 empty] | Science Sensors
FALSE |  | SR341205 | COMP: Batch 36 - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 0 | 0 | 2018-06-01 | 2018-06-01 | 0 | 2018-06-01 | 2018-06-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2018-07-02 | 2018-07-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% | Level 4 Milestone | Procurement |  |  | Subcontractor | [20 empty] | Science Sensors
FALSE |  | CRYO73055 | AWARD: P.O. - Heat Exchanger Cryo/Cold - Cryostat | LSST Forecast - B57 - B1 | 1 | 0 | 2018-06-01 | 2018-06-01 | 0 | 2018-06-01 | 2018-06-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-17 | 2019-06-17 | 188357 | 188357 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-07-02 | 2018-07-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.04 | Refrigeration System - Chile System (HX) | 0 | 0 | 0 | 188357 | 188357 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | B1 Procurement Commitment (C5.1) |  | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 20% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Refrigeration System (TEC)
FALSE |  | CRYO25250 | Generate Manufacturing Docs - Evaporable Getter Pump | LSST Forecast - B57 - B1 | 20 | 0 | 2018-06-04 | 2018-06-08 | 0 | 2018-06-04 | 2018-06-08 | 0 | 2019-06-01 | 2019-06-01 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-09-27 | 2018-10-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 4 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.02 | Getter Pumps | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  |  | Design/Engineering
FALSE |  | CRYO71320 | COMP: Chile System - Design and Intergration | LSST Forecast - B57 - B1 | 0 | 0 | 2018-06-04 | 2018-06-04 | 0 | 2018-06-04 | 2018-06-04 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-31 | 2019-10-31 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2018-07-03 | 2018-07-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.01 | Refrigeration System - Chile System (System Design & Integration) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Alice Callen |  |  | Level 4 Milestone | Design/Engineering
FALSE |  | ITC31752 | C_IRR--Cryostat I&T | LSST Forecast - B57 - B1 | 1 | 0 | 2018-06-06 | 2018-06-07 | 0 | 2018-06-06 | 2018-06-07 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-07-09 | 2018-07-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 8 | 0 | 8 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 1 |  | Complete | 100% | 64 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 64 | 64 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Other (specify) |  | Fabrication and Assembly |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T
FALSE |  | ITC31754 | COMP: C_IRR--Cryostat I&T | LSST Forecast - B57 - B1 | 0 | 0 | 2018-06-07 | 2018-06-07 | 0 | 2018-06-07 | 2018-06-07 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2018-08-06 | 2018-08-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 7 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Testing/Integration |  |  |  | Fabrication and Assembly | [12 empty] | Integration and Test
FALSE |  | ITC33620 | C_TRR - Test Readiness Review - Gantry | LSST Forecast - B57 - B1 | 1 | 0 | 2018-06-07 | 2018-06-07 | 0 | 2018-06-07 | 2018-06-07 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-07-09 | 2018-07-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 8 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.01 | Integration Gantry | 8 | 8 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat I&T (TEC)
FALSE |  | ITC31645 | NEED: BOT Ready for Cryostat I&T | LSST Forecast - B57 - B1 | 0 | 0 | 2018-06-08 | 2018-06-08 | 0 | 2018-06-08 | 2018-06-08 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-08-06 | 2018-08-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | OP540980 | RCV: L3 Assembly - Phase 3 (Flat Assy) | LSST Forecast - B57 - B1 | 1 | 0 | 2018-06-14 | 2018-06-14 | 0 | 2018-06-14 | 2018-06-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-14 | 2019-05-14 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-07-02 | 2018-07-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | 0-100% Method | TEC Non-ARRA | Scott Winters | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% | Level 4 Milestone | Procurement | [7 empty] | L3 Assembly (TEC)
FALSE |  | CCS126100 | Stress test and validate Purge Unit - Camera Body HCU | LSST Forecast - B57 - B1 | 15 | 0 | 2018-06-18 | 2018-09-28 | 0 | 2018-06-18 | 2018-09-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-19 | 2019-07-19 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-07-18 | 2018-08-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 72 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.07 | Camera Body HCU | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | CCS HCU (TEC) | [6 empty] | Camera I&T Hardware Control Unit
FALSE |  | OP531270_1 | L1_L2 Lens - Coating Performance Verification - Phase 2 | LSST Forecast - B57 - B1 | 40 | 0 | 2018-06-19 | 2019-01-18 | 0 | 2018-06-19 | 2019-01-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-05 | 2019-09-05 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-10-12 | 2018-12-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 146 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | L1-L2 Assembly (TEC)
FALSE |  | SR333545 | Batch Sensor Testing (RTM #17) | LSST Forecast - B57 - B1 | 10 | 0 | 2018-06-20 | 2018-07-06 | 0 | 2018-06-20 | 2018-07-06 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-07-03 | 2018-07-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 10 | 0 | 3 | 6 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 11 |  | Complete | 100% | 83 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 83 | 83 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | CRYO72240 | COMP: Compressors Oil Reservoirs - Cryo - Chile System (6 Unts) | LSST Forecast - B57 - B1 | 0 | 0 | 2018-06-22 | 2018-06-22 | 0 | 2018-06-22 | 2018-06-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-31 | 2019-10-31 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | FALSE | 2018-11-07 | 2018-11-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.02 | Refrigeration System - Chile System (Compressor Cabinet) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Alice Callen |  |  | Level 4 Milestone | Engineering Test/Validation
FALSE |  | CRYO61406 | Move cryostat assembly to IR-2 clean room - Cryostat Assembly | LSST Forecast - B57 - B1 | 5 | 0 | 2018-06-27 | 2018-06-29 | 0 | 2018-06-27 | 2018-06-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2018-07-02 | 2018-07-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 2 | 0 | 0 | 2 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 2 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.04 | Refrigeration System - Pre IR2 (HX) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Fabrication/Assembly |  | Other (specify) | [5 empty] | Refrigeration System (TEC)
FALSE |  | ITC92300 | Final Testing (Pre-Raft) - Com Cam | LSST Forecast - B57 - B1 | 19 | 0 | 2018-06-28 | 2019-01-15 | 0 | 2018-06-28 | 2019-01-15 | 0 | 2019-06-03 | 2019-06-03 | 2019-05-31 | 2019-05-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-02-26 | 2019-03-22 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 3 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 19 | 129 |  | Complete | 100% | 304 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.06.01 | Commissioning Camera Hardware | 304 | 304 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Kevin Reil | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | R&D | [5 empty] | Commissioning Camera (TEC)
FALSE |  | CRYO61405 | NEED: Cryostat Assembly Ready for Hx Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2018-06-28 | 2018-06-28 | 0 | 2018-06-28 | 2018-06-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-07-11 | 2018-07-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.04 | Refrigeration System - Pre IR2 (HX) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 5 Milestone | Fabrication/Assembly | [16 empty] | Cryostat
FALSE |  | ITC31814 | Cryostat Prep (pre Quad Box) | LSST Forecast - B57 - B1 | 49 | 0 | 2018-07-02 | 2019-04-19 | 0 | 2018-07-02 | 2019-04-19 | 0 | 2019-06-07 | 2019-06-07 | 2019-05-14 | 2019-05-14 | 0 | 0 | 0 | 0 | 0 | 1 | TRUE | Normal | FALSE | 2018-08-01 | 2018-10-09 |  |  |  |  | 1 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 8 | 0 | 3 | 0 | 0 | 5 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 49 | 193 |  | Complete | 100% | 216 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 216 | 216 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T
FALSE |  | SR551111 | RTM15_RSA Construction at TS4 | LSST Forecast - B57 - B1 | 10 | 0 | 2018-07-02 | 2018-07-16 | 0 | 2018-07-02 | 2018-07-16 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-08-01 | 2018-08-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 44 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 44 | 44 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #15 |  | Science Raft System
FALSE |  | CAMF669235 | Integration and Test - Carousel | LSST Forecast - B57 - B1 | 75 | 55 | 2018-07-06 | 2019-08-19 | -176 | 2018-07-06 |  | 0 | 2019-06-03 | 2019-08-19 | 2018-09-07 | 2018-11-26 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-08-01 | 2018-11-14 |  |  |  |  | 0.8 | 0 | FALSE | FALSE | None |  | None |  | 2019-08-19 |  |  |  |  | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 75 | 220 |  | InProgress | 80% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Fabrication/Assembly | [15 empty] | CP #03 (Carousel/Camera Integration)
FALSE |  | SR333555 | Batch Sensor Testing (RTM #18) | LSST Forecast - B57 - B1 | 10 | 0 | 2018-07-09 | 2018-07-20 | 0 | 2018-07-09 | 2018-07-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-08-07 | 2018-08-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 83 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 83 | 83 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | CBM48575 | Detail Config Assy Drawings - Shutter | LSST Forecast - B57 - B1 | 17 | 0 | 2018-07-10 | 2018-09-28 | 0 | 2018-07-10 | 2018-09-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-06 | 2019-08-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-08-22 | 2018-09-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 17 | 57 |  | Complete | 100% | 112 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.02.02 | Shutter Development | 112 | 112 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Shutter Development (TEC) | [6 empty] | Shutter Prod Sprt
FALSE |  | SR339525 | RCV: 2nd Set Sensor Delivery - V1 Prod Lot 3 (Sensor 102) | LSST Forecast - B57 - B1 | 19 | 0 | 2018-07-10 | 2018-08-28 | 0 | 2018-07-10 | 2018-08-28 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 51937 | 51937 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-09-04 | 2018-09-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 1 | 0 | 0 | 5 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 19 | 35 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 51937 | 51937 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC)
FALSE |  | ITC31813 | START: Engineering Raft Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2018-07-11 | 2018-07-11 | 0 | 2018-07-11 | 2018-07-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-14 | 2019-05-14 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2018-08-01 | 2018-08-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Testing/Integration
FALSE |  | SR333565 | Batch Sensor Testing (RTM #19) | LSST Forecast - B57 - B1 | 10 | 0 | 2018-07-12 | 2018-07-25 | 0 | 2018-07-12 | 2018-07-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-08-10 | 2018-08-23 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 103 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 103 | 103 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | SR551231 | RTM17_RSA Construction at TS4 | LSST Forecast - B57 - B1 | 8 | 0 | 2018-08-01 | 2018-08-10 | 0 | 2018-08-01 | 2018-08-10 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-09-04 | 2018-09-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 8 | 7 |  | Complete | 100% | 44 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 44 | 44 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #17 |  | Science Raft System
FALSE |  | CAMM6900 | COMP: Utilities & Services ICD Phase 3 (LSE-64) | LSST Forecast - B57 - B1 | 0 | 0 | 2018-08-01 | 2018-08-01 | 0 | 2018-08-01 | 2018-08-01 | 0 | 2019-06-01 | 2019-06-01 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2018-08-01 | 2018-08-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 24 | 0 | 24 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.03 | NSF Interface Milestone (NSF Needs) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration | [9 empty] | ICD's for Phase 3
FALSE |  | CAMM6930 | COMP: Mechanical & Thermal ICD Phase 3 (LSE-80) | LSST Forecast - B57 - B1 | 0 | 0 | 2018-08-01 | 2018-08-01 | 0 | 2018-08-01 | 2018-08-01 | 0 | 2019-06-01 | 2019-06-01 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-08-01 | 2018-08-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 9 | 0 | 9 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.03 | NSF Interface Milestone (NSF Needs) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration | [9 empty] | ICD's for Phase 3
FALSE |  | CAMM6935 | COMP: Camera to Telescope Interface Drawing ICD Phase 3 (LSE-18) | LSST Forecast - B57 - B1 | 0 | 0 | 2018-08-01 | 2018-08-01 | 0 | 2018-08-01 | 2018-08-01 | 0 | 2019-06-01 | 2019-06-01 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-08-01 | 2018-08-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 9 | 0 | 9 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.03 | NSF Interface Milestone (NSF Needs) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration | [9 empty] | ICD's for Phase 3
FALSE |  | CAMM6345 | AVAIL: Finish testing of targeted components for refrigerator uttilities | LSST Forecast - B57 - B1 | 0 | 0 | 2018-08-01 | 2018-08-01 | 0 | 2018-08-01 | 2018-08-01 | 0 | 2019-06-01 | 2019-06-01 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-08-01 | 2018-08-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.03 | NSF Interface Milestone (NSF Needs) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration
FALSE |  | CAMM6335 | AVAIL: Finish large scale refrigeration prototype (Ops & Maint) | LSST Forecast - B57 - B1 | 0 | 0 | 2018-08-01 | 2018-08-01 | 0 | 2018-08-01 | 2018-08-01 | 0 | 2019-06-01 | 2019-06-01 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-08-01 | 2018-08-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.03 | NSF Interface Milestone (NSF Needs) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration
FALSE |  | CAMM6355 | AVAIL: Final on-telescope electrical power budget | LSST Forecast - B57 - B1 | 0 | 0 | 2018-08-01 | 2018-08-01 | 0 | 2018-08-01 | 2018-08-01 | 0 | 2019-06-01 | 2019-06-01 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-08-01 | 2018-08-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 8 | 0 | 8 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.03 | NSF Interface Milestone (NSF Needs) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration
FALSE |  | CAMM6365 | AVAIL: Final glycol budget | LSST Forecast - B57 - B1 | 0 | 0 | 2018-08-01 | 2018-08-01 | 0 | 2018-08-01 | 2018-08-01 | 0 | 2019-06-01 | 2019-06-01 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-08-01 | 2018-08-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.03 | NSF Interface Milestone (NSF Needs) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration
FALSE |  | SR339555 | RCV: 3rd Set Sensor Delivery - V1 Prod Lot 3 (Sensor 108) | LSST Forecast - B57 - B1 | 23 | 0 | 2018-08-03 | 2018-08-28 | 0 | 2018-08-03 | 2018-08-28 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 51937 | 51937 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-10-01 | 2018-10-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 23 | 17 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 51937 | 51937 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC)
FALSE |  | DAQ334600 | Procurement Process - Production Parts - ATCA Shelves | LSST Forecast - B57 - B1 | 10 | 0 | 2018-08-20 | 2018-08-27 | 0 | 2018-08-20 | 2018-08-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-24 | 2019-05-24 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-09-04 | 2018-09-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 5 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.06 | ATCA Shelves | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [7 empty] | ICD's for Phase 3 |  |  |  |  | DAQ Readout Systems
FALSE |  | CRYO61563 | Populate IR2 Compressor Cabinets | LSST Forecast - B57 - B1 | 15 | 0 | 2018-08-24 | 2019-03-29 | 0 | 2018-08-24 | 2019-03-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-09-27 | 2018-10-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 9 | 0 | 5 | 0 | 0 | 4 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 140 |  | Complete | 100% | 838 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.02 | Refrigeration System - Pre IR2 (Compressor Cabinet) | 838 | 838 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  | Percent Complete on Work Package |  | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | SR333575 | Batch Sensor Testing (RTM #20) | LSST Forecast - B57 - B1 | 15 | 0 | 2018-08-28 | 2018-09-24 | 0 | 2018-08-28 | 2018-09-24 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-09-04 | 2018-09-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 9 | 0 | 9 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 18 |  | Complete | 100% | 83 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 83 | 83 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | SR337410 | COMP: Sensor Production - Long Lead V2 for Phase C | LSST Forecast - B57 - B1 | 0 | 0 | 2018-08-31 | 2018-08-31 | 0 | 2018-08-31 | 2018-08-31 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-09-04 | 2018-09-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% | Level 4 Milestone | Procurement | [23 empty] | Science Sensors
FALSE |  | AE100480 | Prep for C_FDR - Auxiliary Electronics | LSST Forecast - B57 - B1 | 40 | 0 | 2018-09-03 | 2018-09-21 | 0 | 2018-09-03 | 2018-09-21 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-10-01 | 2018-11-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 13 |  | Complete | 100% | 20 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.01 | Aux Electronics Integration & Management | 20 | 20 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Gunther Haller | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Aux Elec Integration & Management (TEC) | Management | [5 empty] | Corner Raft System Integration and Management
FALSE |  | SR339615 | RCV: 5th Set Sensor Delivery - V1 Prod Lot 3 (Sensor 120) | LSST Forecast - B57 - B1 | 20 | 0 | 2018-09-03 | 2018-11-07 | 0 | 2018-09-03 | 2018-11-07 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 51937 | 51937 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-11-01 | 2018-11-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 13 | 0 | 8 | 5 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 46 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 51937 | 51937 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC)
FALSE |  | SR551351 | RTM19_RSA Construction at TS4 | LSST Forecast - B57 - B1 | 5 | 0 | 2018-09-04 | 2018-09-10 | 0 | 2018-09-04 | 2018-09-10 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-10-01 | 2018-10-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 4 |  | Complete | 100% | 44 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 44 | 44 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #19 |  | Science Raft System
FALSE |  | SR333585 | Batch Sensor Testing (RTM #21) | LSST Forecast - B57 - B1 | 17 | 0 | 2018-09-04 | 2018-09-26 | 0 | 2018-09-04 | 2018-09-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-10-01 | 2018-10-23 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 17 | 16 |  | Complete | 100% | 103 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 103 | 103 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | SR551080 | SHIPPING: Ship RTM #14 to SLAC | LSST Forecast - B57 - B1 | 2 | 0 | 2018-09-13 | 2018-09-14 | 0 | 2018-09-13 | 2018-09-14 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2018-10-10 | 2018-10-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 1 |  | Complete | 100% | 8 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 8 | 8 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration |  | Other (specify) | [5 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #14 |  | Science Raft System
FALSE |  | SR551200 | SHIPPING: Ship RTM #16 to SLAC | LSST Forecast - B57 - B1 | 2 | 0 | 2018-09-13 | 2018-09-14 | 0 | 2018-09-13 | 2018-09-14 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-10-10 | 2018-10-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 1 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 1 |  | Complete | 100% | 8 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 8 | 8 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration |  | Other (specify) | [5 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #16 |  | Science Raft System
FALSE |  | CCS300025 | AVAIL: Support for 2 rafts on focal plane in IR2 | LSST Forecast - B57 - B1 | 0 | 0 | 2018-09-14 | 2018-09-14 | 0 | 2018-09-14 | 2018-09-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2018-09-14 | 2018-09-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.08.03 | CCOB HCU | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  | Level 5 Milestone | Design/Engineering
FALSE |  | CRYO31700 | Write Test and Verification Reports Cryostat Backend | LSST Forecast - B57 - B1 | 6 | 0 | 2018-09-17 | 2018-10-08 | 0 | 2018-09-17 | 2018-10-08 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2018-10-01 | 2018-10-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 6 | 15 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.01 | Cryostat Back End | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Brian J. Langton |  |  |  | Fabrication/Assembly
FALSE |  | AE212320 | AVAIL: Populated Quad Box Assy from Aux Elec | LSST Forecast - B57 - B1 | 0 | 0 | 2018-09-21 | 2018-09-21 | 0 | 2018-09-21 | 2018-09-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-10-09 | 2018-10-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.02.12 | Heater Ex, UT Cooling HCU | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Auxiliary Electronics
FALSE |  | ITC19660 | Initial Integration - Integration Stand | LSST Forecast - B57 - B1 | 60 | 32 | 2018-09-24 | 2019-07-17 | 0 | 2018-09-24 |  | 0 | 2019-06-03 | 2019-07-17 | 2019-06-03 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-12-04 | 2019-03-13 |  |  |  |  | 0.8 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 165 |  | InProgress | 80% | 532 | 0 | 532 | 532 | LSST Forecast - B57 - B1.3.08.04.01 | Camera Integration Stand | 425.6 | 532 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Camera I&T (TEC) | [7 empty] | CP #04 (Integration Stand, Camera IRR/Assy)
FALSE |  | CBM46800 | COMP: Shutter Proto Testing Complete | LSST Forecast - B57 - B1 | 0 | 0 | 2018-09-28 | 2018-09-28 | 0 | 2018-09-28 | 2018-09-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-06 | 2019-08-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-10-01 | 2018-10-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.02.02 | Shutter Development | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Martin Nordby | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 5% | Level 4 Milestone | Engineering Test/Validation | [14 empty] | Cam Body/Purge Engin/Dsn
FALSE |  | AE210320 | AVAIL: Production UT AC/DC components | LSST Forecast - B57 - B1 | 0 | 0 | 2018-09-28 | 2018-09-28 | 0 | 2018-09-28 | 2018-09-28 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-11-28 | 2018-11-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 9 | 0 | 9 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.02.01 | AC and DC Power Distribution | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Gunther Haller |  |  | Level 5 Milestone | Fabrication/Assembly | [16 empty] | Auxiliary Electronics
FALSE |  | SR333595 | Batch Sensor Testing (RTM #22) | LSST Forecast - B57 - B1 | 19 | 0 | 2018-10-01 | 2018-10-25 | 0 | 2018-10-01 | 2018-10-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-11-01 | 2018-11-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 19 | 18 |  | Complete | 100% | 83 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 83 | 83 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | SR551140 | SHIPPING: Ship RTM #15 to SLAC | LSST Forecast - B57 - B1 | 2 | 0 | 2018-10-11 | 2018-10-12 | 0 | 2018-10-11 | 2018-10-12 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-11-13 | 2018-11-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 1 |  | Complete | 100% | 8 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 8 | 8 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration |  | Other (specify) | [5 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #15 |  | Science Raft System
FALSE |  | SR551320 | SHIPPING: Ship RTM #18 to SLAC | LSST Forecast - B57 - B1 | 2 | 0 | 2018-10-11 | 2018-10-12 | 0 | 2018-10-11 | 2018-10-12 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-11-13 | 2018-11-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 1 |  | Complete | 100% | 8 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 8 | 8 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration |  | Other (specify) | [5 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #18 |  | Science Raft System
FALSE |  | DAQ910060 | SCI Firmware (Finalize LAM Behavior) - GDS | LSST Forecast - B57 - B1 | 48 | 0 | 2018-10-14 | 2018-11-30 | 0 | 2018-10-14 | 2018-11-30 | 0 | 2019-06-03 | 2019-06-03 | 2020-03-30 | 2020-03-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-03-04 | 2019-05-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 48 | 32 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.15 | Guiding Data System (GDS) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | DAQ Readout Systems (TEC)
FALSE |  | ITC31720 | NEED: UT Aux Electronics (pre-production) | LSST Forecast - B57 - B1 | 0 | 0 | 2018-10-15 | 2018-10-15 | 0 | 2018-10-15 | 2018-10-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-11-01 | 2018-11-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 11 | 0 | 11 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Auxiliary Electronics
FALSE |  | CRYO70350 | Install Long Lines, Run utilities/install mounting hardware in IR-2 | LSST Forecast - B57 - B1 | 12 | 0 | 2018-10-15 | 2018-10-30 | 0 | 2018-10-15 | 2018-10-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-11-01 | 2018-11-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 12 | 11 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.03 | Refrigeration System - Pre IR2 (Long Lines) | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | SR551414 | RTM20_RTM Construction at TS6 | LSST Forecast - B57 - B1 | 2 | 0 | 2018-10-16 | 2018-10-31 | 0 | 2018-10-16 | 2018-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-11-09 | 2018-11-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 11 |  | Complete | 100% | 64 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 64 | 64 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #20 |  | Science Raft System
FALSE |  | CRYO61050 | Check Drawings - Evacuate, Purge & Charge HW - Refrigeration | LSST Forecast - B57 - B1 | 2 | 0 | 2018-10-22 | 2018-10-23 | 0 | 2018-10-22 | 2018-10-23 | 0 | 2019-06-03 | 2019-06-03 | 2020-06-02 | 2020-06-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-01-15 | 2019-01-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 1 |  | Complete | 100% | 53 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.05 | Refrigeration System - Chile System (Equipment & Refrigeration) | 53 | 53 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 3 |  |  |  |  | Refrigeration System
FALSE |  | OP521815 | Phase 1- r-band repeatability and Phase 1 deliverables (MS4) - Filter Coating | LSST Forecast - B57 - B1 | 10 | 0 | 2018-10-29 | 2019-02-26 | 0 | 2018-10-29 | 2019-02-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-12-12 | 2019-12-12 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-02-01 | 2019-02-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 2 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 79 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  |  | Procurement | [8 empty] | Witness Sample
FALSE |  | OP522105 | RCV: Filter First Article TWF testing data received (MS2) | LSST Forecast - B57 - B1 | 1 | 0 | 2018-10-31 | 2018-10-31 | 0 | 2018-10-31 | 2018-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-25 | 2019-07-25 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-11-12 | 2018-11-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | 0-100% Method | TEC Non-ARRA | Scott Winters |  |  | Level 4 Milestone | Procurement | [7 empty] | Filters (TEC)
FALSE |  | AE213160 | AVAIL: Production Cables/Networking | LSST Forecast - B57 - B1 | 0 | 0 | 2018-11-01 | 2018-11-01 | 0 | 2018-11-01 | 2018-11-01 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-12-03 | 2018-12-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.02.13 | Cables/Networking | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Gunther Haller |  |  | Level 5 Milestone | Fabrication/Assembly | [16 empty] | Auxiliary Electronics
FALSE |  | AE214230 | AVAIL: Production Protection PLC System Components | LSST Forecast - B57 - B1 | 0 | 0 | 2018-11-01 | 2018-11-01 | 0 | 2018-11-01 | 2018-11-01 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-12-03 | 2018-12-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.02.14 | Protection PLC System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Gunther Haller |  |  | Level 5 Milestone | Fabrication/Assembly | [16 empty] | Auxiliary Electronics
FALSE |  | SE221370 | Prep camera FEA model for export to Obs; deliver and run verification checks | LSST Forecast - B57 - B1 | 40 | 0 | 2018-11-01 | 2018-11-30 | 0 | 2018-11-01 | 2018-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-13 | 2019-06-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-12-03 | 2019-02-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 19 |  | Complete | 100% | 20 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.01 | Structural System Analysis | 20 | 20 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | CAMF703000 | Clean - Production Units - Filter Blocks | LSST Forecast - B57 - B1 | 29 | 0 | 2018-11-01 | 2018-12-13 | 0 | 2018-11-01 | 2018-12-13 | 0 | 2019-06-01 | 2019-06-01 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-12-03 | 2019-01-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 29 | 28 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.02 | Filter Loader | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Fabrication/Assembly
FALSE |  | ITC31727 | NEED: All DAQ OTM's | LSST Forecast - B57 - B1 | 0 | 0 | 2018-11-02 | 2018-11-02 | 0 | 2018-11-02 | 2018-11-02 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-12-03 | 2018-12-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Auxiliary Electronics
FALSE |  | CRYO61334 | Move Compressor Cabinets to IR2 | LSST Forecast - B57 - B1 | 5 | 0 | 2018-11-08 | 2019-03-29 | 0 | 2018-11-08 | 2019-03-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-01-07 | 2019-01-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 87 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.02 | Refrigeration System - IR2 | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  | Percent Complete on Work Package |  | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | SR300150 | COMP: Sensor Production Complete | LSST Forecast - B57 - B1 | 0 | 0 | 2018-11-16 | 2018-11-16 | 0 | 2018-11-16 | 2018-11-16 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-12-03 | 2018-12-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 18 | 0 | 18 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03 | Science Sensors | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Bill Wahl |  |  | Level 3 Milestone | Management/Administration | [21 empty] | Milestones |  | Science Sensors
FALSE |  | OP541640 | Procure L3 Lens Coating | LSST Forecast - B57 - B1 | 59 | 0 | 2018-12-03 | 2019-02-22 | 0 | 2018-12-03 | 2019-02-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-01-02 | 2019-03-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 59 | 54 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement | [8 empty] | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly) |  |  |  | L1-L2 Optics
FALSE |  | CRYO646030 | Assemble, Braze, Solder Ceramic Break Assemblies - 2 Cold | LSST Forecast - B57 - B1 | 0 | 0 | 2018-12-03 | 2018-12-21 | 0 | 2018-12-03 | 2018-12-21 | 0 | 2019-06-01 | 2019-06-01 | 2018-12-13 | 2018-12-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2019-01-07 | 2019-01-07 |  |  |  |  | 1 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 0 | 14 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.04.01 | 2 Cryo/2 Cold HeX Vacuum Vessel Intgr | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys
FALSE |  | OP531310 | Pre-Bonded L1 Lens TWE Test Complete - L1-L2 Assembly - Phase 4b | LSST Forecast - B57 - B1 | 20 | 0 | 2018-12-19 | 2018-12-19 | 0 | 2018-12-19 | 2018-12-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-03 | 2019-09-03 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-01-02 | 2019-01-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Scott Winters | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor | [5 empty] | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly) |  |  |  | L1-L2 Opto-Mechanics
FALSE |  | OP541140 | COMP: L3 Assembly - Lens Ready for Coating | LSST Forecast - B57 - B1 | 0 | 0 | 2018-12-21 | 2018-12-21 | 0 | 2018-12-21 | 2018-12-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2019-01-02 | 2019-01-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  | Level 4 Milestone | Procurement
FALSE |  | OP522115 | RCV: All Phase 1 deliverables received (MS3) - Filter First Article fabrication | LSST Forecast - B57 - B1 | 1 | 0 | 2018-12-21 | 2018-12-21 | 0 | 2018-12-21 | 2018-12-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-25 | 2019-07-25 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2019-01-22 | 2019-01-22 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | 0-100% Method | TEC Non-ARRA | Scott Winters |  |  | Level 4 Milestone | Procurement | [7 empty] | Filters (TEC)
FALSE |  | SR551531 | RTM22_RSA Construction at TS4 | LSST Forecast - B57 - B1 | 10 | 0 | 2019-01-02 | 2019-01-15 | 0 | 2019-01-02 | 2019-01-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-02-01 | 2019-02-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 44 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 44 | 44 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #22 |  | Science Raft System
FALSE |  | CAMF665450 | Verification Testing - Filter Loader | LSST Forecast - B57 - B1 | 33 | 0 | 2019-01-07 | 2019-04-12 | 0 | 2019-01-07 | 2019-04-12 | 0 | 2019-06-01 | 2019-06-01 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2019-02-05 | 2019-03-22 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 33 | 67 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.02 | Filter Loader | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Fabrication/Assembly
FALSE |  | DAQ900350 | Assemble Production COBs | LSST Forecast - B57 - B1 | 24 | 0 | 2019-01-07 | 2019-04-15 | 0 | 2019-01-07 | 2019-04-15 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-01-07 | 2019-02-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 4 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 24 | 68 |  | Complete | 100% | 180 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.02 | DAQ COB (Main ATCA DAQ Module) | 180 | 180 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | [11 empty] | DAQ Readout Systems (TEC)
FALSE |  | CRYO61410 | Install Heat-X cans into cryostat and Leak Check - Cryostat Assembly | LSST Forecast - B57 - B1 | 5 | 0 | 2019-01-14 | 2019-04-15 | 0 | 2019-01-14 | 2019-04-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2019-02-11 | 2019-02-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 1 | 3 | 0 | 0 | 3 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 63 |  | Complete | 100% | 35 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.04 | Refrigeration System - Pre IR2 (HX) | 35 | 35 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Fabrication/Assembly |  | Other (specify) | [5 empty] | Refrigeration System (TEC)
FALSE |  | CRYO61337 | Install/Interconnect compressor cabinets with Power, Utility & Refrigeration Lines in IR-2 | LSST Forecast - B57 - B1 | 20 | 0 | 2019-01-14 | 2019-03-29 | 0 | 2019-01-14 | 2019-03-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-02-11 | 2019-03-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 52 |  | Complete | 100% | 200 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.02 | Refrigeration System - IR2 | 200 | 200 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | CBM28900 | Assemble and Inspect - Purge Cabinets | LSST Forecast - B57 - B1 | 20 | 0 | 2019-01-21 | 2019-03-29 | 0 | 2019-01-21 | 2019-03-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-12 | 2019-08-12 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-02-01 | 2019-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 5 | 5 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 47 |  | Complete | 100% | 450 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.01.02 | Camera Body Development | 450 | 450 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 15% |  | Fabrication/Assembly |  | Other (specify) | [5 empty] | Camera Body Development (TEC) | [6 empty] | Camera Body and Purge Production
FALSE |  | SR300030 | COMP: Ready for CD-4 - Science Sensors | LSST Forecast - B57 - B1 | 0 | 0 | 2019-01-31 | 2019-01-31 | 0 | 2019-01-31 | 2019-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-04-26 | 2019-04-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03 | Science Sensors | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Bill Wahl |  |  | Level 3 Milestone | Management/Administration | [21 empty] | Milestones |  | Science Sensors
FALSE |  | CRYO61635_1 | Pump Down Vacuums | LSST Forecast - B57 - B1 | 2 | 0 | 2019-02-01 | 2019-04-30 | 0 | 2019-02-01 | 2019-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2019-04-02 | 2019-04-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 2 | 0 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 61 |  | Complete | 100% | 114 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.02 | Refrigeration System - IR2 | 114 | 114 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | CAMF661650 | Verification Testing - Auto Changer | LSST Forecast - B57 - B1 | 33 | 0 | 2019-02-01 | 2019-04-12 | 0 | 2019-02-01 | 2019-04-12 | 0 | 2019-06-01 | 2019-06-01 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2019-02-01 | 2019-03-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 33 | 49 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.01 | Auto Changer | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Fabrication/Assembly
FALSE |  | ITC31660 | NEED: Vacuum System (pre-production) | LSST Forecast - B57 - B1 | 0 | 0 | 2019-02-07 | 2019-02-07 | 0 | 2019-02-07 | 2019-02-07 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-02-07 | 2019-02-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Cryostat
FALSE |  | CBM28350 | Assemble and Inspect - Housing - Camera Body | LSST Forecast - B57 - B1 | 33 | 19 | 2019-02-13 | 2019-06-27 | 42 | 2019-02-13 |  | 0 | 2019-06-03 | 2019-06-27 | 2019-08-01 | 2019-08-27 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-03-13 | 2019-04-26 |  |  |  |  | 0.9 | 0 | FALSE | FALSE | None |  | None |  | 2019-05-28 |  |  |  |  | 5 | 0 | 4 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 33 | 76 |  | InProgress | 90% | 120 | 0 | 120 | 120 | LSST Forecast - B57 - B1.3.06.01.02 | Camera Body Development | 108 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly |  | Other (specify) | [5 empty] | Camera Body Development (TEC)
FALSE |  | ITC35010 | RTM01_Receive, Install in TS7 & Cool Down | LSST Forecast - B57 - B1 | 2 | 0 | 2019-02-22 | 2019-02-26 | 0 | 2019-02-22 | 2019-02-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 1500 | 1500 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-02-22 | 2019-02-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 2 |  | Complete | 100% | 60 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.03 | Raft Acceptance Testing | 60 | 60 | 0 | 1500 | 1500 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC)
FALSE |  | DAQ900410 | Receive Production flash | LSST Forecast - B57 - B1 | 59 | 0 | 2019-03-04 | 2019-04-30 | 0 | 2019-03-04 | 2019-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 74700 | 74700 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-04-01 | 2019-06-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 59 | 41 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.13.09 | DAQ Assembled Hardware | 0 | 0 | 0 | 74700 | 55708.47 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Fabrication/Assembly | [7 empty] | DAQ Readout Systems (TEC)
FALSE |  | CBM50800 | Receive, Inspect, Clean, Prep Procured Parts - Shutter | LSST Forecast - B57 - B1 | 12 | 10 | 2019-03-18 | 2019-06-17 | 56 | 2019-03-18 |  | 0 | 2019-06-04 | 2019-06-17 | 2019-08-22 | 2019-09-05 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-05-30 | 2019-06-14 |  |  |  |  | 0.955 | 0 | FALSE | FALSE | None |  | None |  | 2019-06-14 |  |  |  |  | 4 | 0 | 1 | 1 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 12 | 54 |  | InProgress | 95.5% | 232 | 0 | 232 | 232 | LSST Forecast - B57 - B1.3.06.02.02 | Shutter Development | 221.56 | 38.6667 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly |  | Other (specify) | [5 empty] | Shutter Development (TEC) | [6 empty] | Shutter Production
FALSE |  | OP522215 | Phase 2 deliverables per the SOW completed and received (MS6) - First Article Filter Coat | LSST Forecast - B57 - B1 | 31 | 27 | 2019-03-18 | 2019-07-10 | 37 | 2019-03-18 |  | 0 | 2019-06-03 | 2019-07-10 | 2019-07-25 | 2019-08-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-04-01 | 2019-05-13 |  |  |  |  | 0.85 | 0 | FALSE | FALSE | None |  | None |  | 2019-07-10 |  |  |  |  | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 31 | 54 |  | InProgress | 85% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters | (1.10) Task/item is a modification of an existing design | 7% |  | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc)
FALSE |  | CRYO646155 | AVAIL: Cryostat Assembly with Refrigeration for Integration (2 Cryo/2 Cold) | LSST Forecast - B57 - B1 | 0 | 0 | 2019-03-29 | 2019-03-29 | 0 | 2019-03-29 | 2019-03-29 | 0 | 2019-06-01 | 2019-06-01 | 2018-12-13 | 2018-12-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2019-04-22 | 2019-04-22 |  |  |  |  | 1 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.04.02 | 2 Cryo/2 Cold Heat Airside Assy | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | [7 empty] | Level 5 Milestone
FALSE |  | SE222452 | Finalize camera assy dwg's and BOM's for IRR (Camera I&T IRR) | LSST Forecast - B57 - B1 | 20 | 0 | 2019-04-01 | 2019-04-19 | 0 | 2019-04-01 | 2019-04-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-16 | 2019-09-16 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-05-20 | 2019-06-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | AsLateAsPossible |  | None | [6 empty] | 7 | 0 | 6 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 14 |  | Complete | 100% | 32 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.02 | Mechanical Integration | 32 | 14.4 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC)
FALSE |  | OP522485 | COMP: 1st Production Filter Complete and Ready to Ship - Filter Fabrication | LSST Forecast - B57 - B1 | 0 | 0 | 2019-04-17 | 2019-04-17 | 0 | 2019-04-17 | 2019-04-17 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-06-03 | 2019-06-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters | (1.10) Task/item is a modification of an existing design | 7% | Level 4 Milestone | Procurement |  |  | Subcontractor
FALSE |  | CBM29200 | Perform Full System Verif Testing - Camera Body | LSST Forecast - B57 - B1 | 10 | 22 | 2019-04-21 | 2019-07-02 | 42 | 2019-04-21 |  | 0 | 2019-06-03 | 2019-07-02 | 2019-08-01 | 2019-08-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-03 | 2019-06-14 |  |  |  |  | 0.5 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 29 |  | InProgress | 50% | 96 | 0 | 96 | 96 | LSST Forecast - B57 - B1.3.06.01.02 | Camera Body Development | 48 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 15% |  | Testing/Integration |  | Other (specify) | [5 empty] | Camera Body Development (TEC) | [6 empty] | Camera Body and Purge Production
FALSE |  | CRYO61685 | AVAIL: Cryostat Assembly with Refrigeration for Integration (2 Cryo/2 Cold) | LSST Forecast - B57 - B1 | 0 | 0 | 2019-04-30 | 2019-04-30 | 0 | 2019-04-30 | 2019-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | FALSE | 2019-05-15 | 2019-05-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 0 | 0 | 1 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.02 | Refrigeration System - IR2 | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 5 Milestone | Fabrication/Assembly | [16 empty] | Cryostat
FALSE |  | CRYO72560 | COMP: Compressor Cabinet Components Ready for Chile System | LSST Forecast - B57 - B1 | 0 | 0 | 2019-04-30 | 2019-04-30 | 0 | 2019-04-30 | 2019-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-31 | 2019-10-31 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | FALSE | 2019-05-01 | 2019-05-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 7 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.02 | Refrigeration System - Chile System (Compressor Cabinet) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Alice Callen |  |  | Level 4 Milestone
FALSE |  | OP521840 | Validation of Vendor Results - Witness Sample | LSST Forecast - B57 - B1 | 32 | 0 | 2019-05-01 | 2019-05-24 | 0 | 2019-05-01 | 2019-05-24 | 0 | 2019-06-01 | 2019-06-01 | 2019-12-12 | 2019-12-12 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-03 | 2019-07-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 9 | 0 | 9 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 32 | 17 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 80 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 18% |  | Procurement | [7 empty] | Filters (TEC) | Witness Sample
FALSE |  | CRYO70185 | Analyze Data - Cold System Verification Test | LSST Forecast - B57 - B1 | 8 | 5 | 2019-05-20 | 2019-06-07 | -18 | 2019-05-20 |  | 0 | 2019-06-03 | 2019-06-07 | 2019-05-07 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-06-10 | 2019-06-19 |  |  |  |  | 0.5 | 0 | FALSE | TRUE | None |  | None |  | 2019-06-07 |  |  |  |  | 3 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 8 | 9 |  | InProgress | 50% | 40 | 0 | 40 | 40 | LSST Forecast - B57 - B1.3.06.04.06.02 | Refrigeration System - IR2 | 20 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) | [6 empty] | Utility Trunk
FALSE |  | OP531470 | TRR Complete - L1-L2 Assembly - Phase 5 | LSST Forecast - B57 - B1 | 10 | 2 | 2019-05-21 | 2019-06-04 | 64 | 2019-05-21 |  | 0 | 2019-06-03 | 2019-06-04 | 2019-09-03 | 2019-09-05 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-06-03 | 2019-06-14 |  |  |  |  | 0.2 | 0 | FALSE | FALSE | None |  | None |  | 2019-06-04 |  |  |  |  | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 8 |  | InProgress | 20% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Scott Winters | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor | [5 empty] | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly) |  |  |  | L1-L2 Opto-Mechanics
FALSE |  | OP531464 | COMP: L1-L2 Assembly Phase 4b | LSST Forecast - B57 - B1 | 0 | 0 | 2019-05-24 | 2019-05-24 | 0 | 2019-05-24 | 2019-05-24 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-05 | 2019-09-05 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | FALSE | 2019-06-03 | 2019-06-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 8 | 0 | 8 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  | Level 4 Milestone | Procurement | [8 empty] | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly)
FALSE |  | ITC92360 | Prep for Pre Ship Review - Com Cam | LSST Forecast - B57 - B1 | 10 | 0 | 2019-05-27 | 2019-05-28 | 0 | 2019-05-27 | 2019-05-28 | 0 | 2019-06-03 | 2019-06-03 | 2019-05-31 | 2019-05-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-07-02 | 2019-07-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 11 | 0 | 11 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 0 |  | Complete | 100% | 48 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.06.01 | Commissioning Camera Hardware | 48 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Kevin Reil | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Construction Management | [5 empty] | Commissioning Camera (TEC)
FALSE |  | DAQ900600 | AVAIL: DAQ V3.0 for ComCam, Camera | LSST Forecast - B57 - B1 | 0 | 0 | 2019-05-31 | 2019-05-31 | 0 | 2019-05-31 | 2019-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-31 | 2019-10-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-06-03 | 2019-06-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.13.05 | DAQ Version 3.0 | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer |  |  | Level 5 Milestone
FALSE |  | DAQ900620 | AVAIL: DAQ V3.0 for DM Data Challenge | LSST Forecast - B57 - B1 | 0 | 0 | 2019-05-31 | 2019-05-31 | 0 | 2019-05-31 | 2019-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2019-06-03 | 2019-06-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.13.05 | DAQ Version 3.0 | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer |  |  | Level 5 Milestone
FALSE |  | DAQ900635 | COMP: DAQ V3.0 | LSST Forecast - B57 - B1 | 0 | 0 | 2019-05-31 | 2019-05-31 | 0 | 2019-05-31 | 2019-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-25 | 2019-07-25 | 0 | 0 | 0 | 0 | 0 | 8 | FALSE | Finish Milestone | FALSE | 2019-06-03 | 2019-06-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.13.05 | DAQ Version 3.0 | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer |  |  | Level 4 Milestone
FALSE |  | CRYO62080 | Requisition - Refrigerant - Chile Hardware | LSST Forecast - B57 - B1 | 20 | 20 | 2019-06-03 | 2019-06-28 | 103 |  |  | 0 | 2019-06-03 | 2019-06-28 | 2019-10-28 | 2019-11-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-03 | 2019-06-28 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.05 | Refrigeration System - Chile System (Equipment & Refrigeration) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  |  | Procurement
FALSE |  | OP521100 | Assemble test stand and prep (Phase 2) | LSST Forecast - B57 - B1 | 30 | 30 | 2019-06-03 | 2019-07-15 | 166 |  |  | 0 | 2019-06-03 | 2019-07-15 | 2020-01-31 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-06-03 | 2019-07-15 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 0 |  | Planned | 0% | 128 | 0 | 128 | 128 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 18% |  | Fabrication/Assembly |  | Other (specify) | [5 empty] | Filters (TEC) | Production Filter Frames | [5 empty] | Filter Opto-Mechanics
FALSE |  | OP522650 | Support Filter coating | LSST Forecast - B57 - B1 | 140 | 140 | 2019-06-03 | 2019-12-19 | 136 |  |  | 29 | 2019-06-03 | 2019-12-19 | 2019-12-16 | 2020-07-07 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-03 | 2019-12-19 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 140 | 0 |  | Planned | 0% | 392 | 0 | 392 | 392 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 18% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Filters (TEC) | Production Filters Coating | [5 empty] | Filter Optics
FALSE |  | DAQ900675 | COMP: DAQ V4.0 | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-03 | 2019-06-03 | 259 |  |  | 0 | 2019-06-03 | 2019-06-03 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2019-06-03 | 2019-06-03 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.13.06 | DAQ Version 4.0 | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer |  |  | Level 4 Milestone
FALSE |  | ITC31813_1 | START: Cryostat Vacuum Testing | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-03 | 2019-06-03 | -14 |  |  | 4 | 2019-06-03 | 2019-06-03 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-06-03 | 2019-06-03 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Testing/Integration
FALSE |  | OP531490 | Final Alignment/Integration Complete - L1-L2 Assembly - Phase 5 | LSST Forecast - B57 - B1 | 10 | 10 | 2019-06-05 | 2019-06-18 | 64 |  |  | 0 | 2019-06-05 | 2019-06-18 | 2019-09-05 | 2019-09-19 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-05 | 2019-06-18 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Scott Winters | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor | [5 empty] | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly) |  |  |  | L1-L2 Opto-Mechanics
FALSE |  | ITC32730 | COMP: Prepare for Cryostat Vacuum bake-out and pum/vent | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-05 | 2019-06-05 | 98 |  |  | 116 | 2019-06-05 | 2019-06-05 | 2019-10-23 | 2019-10-23 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-06-05 | 2019-06-05 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Martin Nordby |  |  | Level 4 Milestone
FALSE |  | CRYO70205 | COMP: Cold System Verification Test | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-07 | 2019-06-07 | -18 |  |  | 0 | 2019-06-07 | 2019-06-07 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2019-06-07 | 2019-06-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.02 | Refrigeration System - IR2 | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% | Level 4 Milestone | Design/Engineering
FALSE |  | CRYO61685_1 | AVAIL: Cryostat Assembly with Refrigeration for Integration (4 Cryo) | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-07 | 2019-06-07 | -18 |  |  | 0 | 2019-06-07 | 2019-06-07 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2019-06-07 | 2019-06-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.02 | Refrigeration System - IR2 | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 5 Milestone | Fabrication/Assembly | [16 empty] | Cryostat
FALSE |  | ITC31835 | NEED: Completion of Run Single-Circuit Cryo/Cold System Tests (4 Cryo) | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-07 | 2019-06-07 | -18 |  |  | 0 | 2019-06-07 | 2019-06-07 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | TRUE | 2019-06-07 | 2019-06-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Fabrication and Assembly | [12 empty] | Integration and Test
FALSE |  | CCS300035 | NEED: DAQ with support for 9 rafts in IR2 | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-10 | 2019-06-10 | -9 |  |  | 0 | 2019-06-10 | 2019-06-10 | 2019-05-24 | 2019-05-24 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-06-10 | 2019-06-10 |  |  |  |  | 0 | 0 | FALSE | FALSE | FinishOnOrAfter | 2019-06-10 | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.08.03 | CCOB HCU | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Tony Johnson |  |  | Level 5 Milestone | Design/Engineering | [15 empty] | CP #02 (CCS Focal Plane Software)
FALSE |  | CCS300040 | Second release of full focal plane software in IR2 with support for 9+ rafts | LSST Forecast - B57 - B1 | 41 | 41 | 2019-06-10 | 2019-08-06 | -9 |  |  | 0 | 2019-06-10 | 2019-08-06 | 2019-05-28 | 2019-07-24 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-06-10 | 2019-08-06 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 41 | 0 |  | Planned | 0% | 360 | 0 | 360 | 360 | LSST Forecast - B57 - B1.3.07.01.03.08.03 | CCOB HCU | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | CCS HCU (TEC) | [7 empty] | CP #02 (CCS Focal Plane Software)
FALSE |  | ITC31820_1 | ETU De-integration | LSST Forecast - B57 - B1 | 12 | 12 | 2019-06-10 | 2019-06-25 | -18 |  |  | 0 | 2019-06-10 | 2019-06-25 | 2019-05-14 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2019-06-10 | 2019-06-25 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 12 | 0 |  | Planned | 0% | 238 | 0 | 238 | 238 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC00550 | COMP: Commissioning Camera Shipped to Tucson | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-14 | 2019-06-14 | -10 |  |  | 0 | 2019-06-14 | 2019-06-14 | 2019-05-31 | 2019-05-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-06-14 | 2019-06-14 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration
FALSE |  | ITC32170 | NEED: Corner Raft Tower/RCM #1 thru #4 | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-21 | 2019-06-21 | 2 |  |  | 20 | 2019-06-21 | 2019-06-21 | 2019-06-25 | 2019-06-25 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-06-21 | 2019-06-21 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 7 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration | [16 empty] | Corner Raft System
FALSE |  | SR000040 | COMP: Ready for CD-4 - Science Rafts | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-21 | 2019-06-21 | 593 |  |  | 375 | 2019-06-21 | 2019-06-21 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-06-21 | 2019-06-21 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 21 | 0 | 21 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01 | Science Raft System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Bill Wahl |  |  | Level 3 Milestone | Management/Administration | [21 empty] | Milestones |  | Science Raft System
FALSE |  | SR000950 | COMP: Last Production RTM (#21) Available for I&T | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-21 | 2019-06-21 | 181 |  |  | 0 | 2019-06-21 | 2019-06-21 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2019-06-21 | 2019-06-21 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 12 | 0 | 12 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01 | Science Raft System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Bill Wahl |  |  | Level 3 Milestone | Management/Administration | [21 empty] | Milestones |  | Science Raft System
FALSE |  | CCS126740 | Finalize CCS Camera Body drivers, subsystem, gui - Camera Body HCU | LSST Forecast - B57 - B1 | 20 | 20 | 2019-06-25 | 2019-07-23 | 33 |  |  | 0 | 2019-06-25 | 2019-07-23 | 2019-08-12 | 2019-09-09 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-25 | 2019-07-23 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 120 | 0 | 120 | 120 | LSST Forecast - B57 - B1.3.07.01.03.07 | Camera Body HCU | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Testing/Integration | [7 empty] | CCS HCU (TEC) | [7 empty] | CP #11 (CCS, Camera Body HCU)
FALSE |  | OP530845 | Phase 4a Close-out | LSST Forecast - B57 - B1 | 5 | 5 | 2019-06-25 | 2019-07-01 | 85 |  |  | 0 | 2019-06-25 | 2019-07-01 | 2019-10-24 | 2019-10-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-25 | 2019-07-01 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 0 |  | Planned | 0% | 16 | 0 | 16 | 16 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 0% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | L1-L2 Assembly (TEC) | L1_L2 Summary | [5 empty] | L1-L2 Optics
FALSE |  | CAMF669245 | Combined Test Assembly (Carousel + Loader 1+ Auto Changer 1) | LSST Forecast - B57 - B1 | 4 | 4 | 2019-06-25 | 2019-06-28 | -159 |  |  | 0 | 2019-06-25 | 2019-06-28 | 2018-10-24 | 2018-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-25 | 2019-06-28 |  |  |  |  | 0 | 0 | FALSE | FALSE | StartOnOrAfter | 2019-06-25 | None | [6 empty] | 6 | 0 | 5 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Fabrication/Assembly
FALSE |  | ITC35870 | RTM19_Receive, Install in TS7 & Cool Down | LSST Forecast - B57 - B1 | 5 | 5 | 2019-06-25 | 2019-07-01 | 8 |  |  | 0 | 2019-06-25 | 2019-07-01 | 2019-07-08 | 2019-07-12 | 1500 | 1500 | 0 | 1500 | 1500 | 1 | FALSE | Normal | FALSE | 2019-06-25 | 2019-07-01 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 0 |  | Planned | 0% | 60 | 0 | 60 | 60 | LSST Forecast - B57 - B1.3.08.03.03 | Raft Acceptance Testing | 0 | 0 | 0 | 0 | 0 | 1500 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [7 empty] | CP #08 (I&T RTM Test)
FALSE |  | ITC31840 | START: Science Raft Tower Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-25 | 2019-06-25 | -18 |  |  | 0 | 2019-06-25 | 2019-06-25 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | TRUE | 2019-06-25 | 2019-06-25 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 10 | 0 | 10 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [11 empty] | CP #01 (Cryostat/Camera Integration)
FALSE |  | CRYO02900 | COMP: Cryostat Early Hardware & Software Ready for Summit | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-28 | 2019-06-28 | 86 |  |  | 60 | 2019-06-28 | 2019-06-28 | 2019-10-31 | 2019-10-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-06-28 | 2019-06-28 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04 | Cryostat | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 3 Milestone | Management/Administration
FALSE |  | OP541380 | AVAIL: L3 Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-28 | 2019-06-28 | -42 |  |  | 0 | 2019-06-28 | 2019-06-28 | 2019-04-30 | 2019-04-30 | 0 | 0 | 0 | 0 | 0 | 6 | FALSE | Finish Milestone | FALSE | 2019-06-28 | 2019-06-28 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  | Level 5 Milestone | Procurement | [10 empty] | Critical Path #2 (L1_L2 Assembly) | [5 empty] | Optics
FALSE |  | CRYO02875 | COMP: Chile Compressor System Ready for Pathfinder | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-28 | 2019-06-28 | 575 |  |  | 122 | 2019-06-28 | 2019-06-28 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-06-28 | 2019-06-28 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04 | Cryostat | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 3 Milestone | Management/Administration
FALSE |  | CAMF669250 | Combined Functionality and Performance Tests (Carousel + Loader 1 + Auto Changer 1) | LSST Forecast - B57 - B1 | 18 | 18 | 2019-07-01 | 2019-07-25 | -159 |  |  | 0 | 2019-07-01 | 2019-07-25 | 2018-10-30 | 2018-11-26 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2019-07-01 | 2019-07-25 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 8 | 0 | 8 | 0 | 0 | 0 | 3 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 18 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Fabrication/Assembly
FALSE |  | CAMF650350 | START: Filter Exchange System Testing | LSST Forecast - B57 - B1 | 0 | 0 | 2019-07-01 | 2019-07-01 | -104 |  |  | 0 | 2019-07-01 | 2019-07-01 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 5 | FALSE | Finish Milestone | FALSE | 2019-07-01 | 2019-07-01 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 0 | 3 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03 | Exchange System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  | Level 3 Milestone | Management/Administration
FALSE |  | CCS320500 | Vendor Lead Time - Hardware - Camera Rotator HCU | LSST Forecast - B57 - B1 | 20 | 20 | 2019-07-01 | 2019-07-29 | 18 |  |  | 0 | 2019-07-01 | 2019-07-29 | 2019-07-26 | 2019-08-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-07-01 | 2019-07-29 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.08.05 | Camera Rotator HCU | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  |  | Procurement
FALSE |  | DAQ910040 | Client Readout Software - GDS | LSST Forecast - B57 - B1 | 44 | 44 | 2019-07-01 | 2019-08-30 | 135 |  |  | 4 | 2019-07-01 | 2019-08-30 | 2020-01-27 | 2020-03-27 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-07-01 | 2019-08-30 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 44 | 0 |  | Planned | 0% | 40 | 0 | 40 | 40 | LSST Forecast - B57 - B1.3.07.02.02.15 | Guiding Data System (GDS) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | DAQ Readout Systems (TEC)
FALSE |  | DAQ910050 | Client API Software - GDS | LSST Forecast - B57 - B1 | 48 | 48 | 2019-07-01 | 2019-09-06 | 131 |  |  | 0 | 2019-07-01 | 2019-09-06 | 2020-01-21 | 2020-03-27 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-07-01 | 2019-09-06 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 48 | 0 |  | Planned | 0% | 72 | 0 | 72 | 72 | LSST Forecast - B57 - B1.3.07.02.02.15 | Guiding Data System (GDS) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | DAQ Readout Systems (TEC)
FALSE |  | OP530850 | COMP: L1-L2 Assembly Phase 4a | LSST Forecast - B57 - B1 | 0 | 0 | 2019-07-01 | 2019-07-01 | 85 |  |  | 0 | 2019-07-01 | 2019-07-01 | 2019-10-31 | 2019-10-31 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2019-07-01 | 2019-07-01 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  | Level 4 Milestone | Procurement | [8 empty] | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly)
FALSE |  | ITC31880 | Integrate Science Raft Tower #2 of 21 | LSST Forecast - B57 - B1 | 4 | 4 | 2019-07-02 | 2019-07-08 | -18 |  |  | 0 | 2019-07-02 | 2019-07-08 | 2019-06-06 | 2019-06-11 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-07-02 | 2019-07-08 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 102 | 0 | 102 | 102 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | CBM29300 | Prepare for Pre-Ship Review - Camera Body | LSST Forecast - B57 - B1 | 10 | 10 | 2019-07-03 | 2019-07-17 | 37 |  |  | 4 | 2019-07-03 | 2019-07-17 | 2019-08-26 | 2019-09-09 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-07-03 | 2019-07-17 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 0 |  | Planned | 0% | 344 | 0 | 344 | 344 | LSST Forecast - B57 - B1.3.06.01.02 | Camera Body Development | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 15% |  | Testing/Integration |  | Other (specify) | [5 empty] | Camera Body Development (TEC) | [6 empty] | Camera Body and Purge Production
FALSE |  | CBM51500 | Assemble and Test Shutter Units - Shutter | LSST Forecast - B57 - B1 | 40 | 40 | 2019-07-03 | 2019-08-28 | 45 |  |  | 0 | 2019-07-03 | 2019-08-28 | 2019-09-06 | 2019-10-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-07-03 | 2019-08-28 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 0 |  | Planned | 0% | 448 | 0 | 448 | 448 | LSST Forecast - B57 - B1.3.06.02.02 | Shutter Development | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Testing/Integration |  | Other (specify) | [5 empty] | Shutter Development (TEC) | [6 empty] | Shutter Production | CP #13 (Shutter)
FALSE |  | OP522270 | Mount filters in frame - First Article | LSST Forecast - B57 - B1 | 45 | 45 | 2019-07-11 | 2019-09-12 | 124 |  |  | 0 | 2019-07-11 | 2019-09-12 | 2020-01-09 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-07-11 | 2019-09-12 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 45 | 0 |  | Planned | 0% | 116 | 0 | 116 | 116 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 18% |  | Testing/Integration |  | Other (specify) | [5 empty] | Filters (TEC) | Production Filters Polish and integration | [5 empty] | Filter Opto-Mechanics
FALSE |  | OP522550 | Production Readiness Confirmation (MS7) - Filter Coating | LSST Forecast - B57 - B1 | 20 | 20 | 2019-07-11 | 2019-08-07 | 107 |  |  | 0 | 2019-07-11 | 2019-08-07 | 2019-12-12 | 2020-01-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-07-11 | 2019-08-07 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  |  | Procurement
FALSE |  | ITC31940 | Integrate Science Raft Tower #4 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-07-15 | 2019-07-16 | -18 |  |  | 0 | 2019-07-15 | 2019-07-16 | 2019-06-18 | 2019-06-19 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-07-15 | 2019-07-16 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | CR221720 | COMP: Corner raft tower shipping container | LSST Forecast - B57 - B1 | 0 | 0 | 2019-07-15 | 2019-07-15 | 565 |  |  | 55 | 2019-07-15 | 2019-07-15 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-07-15 | 2019-07-15 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% | Level 4 Milestone | Fabrication/Assembly | [8 empty] | CRTM Fab/assy Tooling/shipping
FALSE |  | DAQ920100 | COMP: Remote FPGA Reprogramming | LSST Forecast - B57 - B1 | 0 | 0 | 2019-07-15 | 2019-07-15 | 275 |  |  | 293 | 2019-07-15 | 2019-07-15 | 2020-08-26 | 2020-08-26 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-07-15 | 2019-07-15 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.16 | Remote FPGA Reprogramming | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment |  | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% | Level 5 Milestone | Design/Engineering
FALSE |  | ITC32225 | Integrate Corner Raft Tower #1 of 4 | LSST Forecast - B57 - B1 | 4 | 4 | 2019-07-23 | 2019-07-26 | -18 |  |  | 0 | 2019-07-23 | 2019-07-26 | 2019-06-26 | 2019-07-01 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-07-23 | 2019-07-26 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 119 | 0 | 119 | 119 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | CBM29400 | PSR - Pre-Ship Review - Camera Body | LSST Forecast - B57 - B1 | 5 | 5 | 2019-07-24 | 2019-07-30 | 33 |  |  | 0 | 2019-07-24 | 2019-07-30 | 2019-09-10 | 2019-09-16 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2019-07-24 | 2019-07-30 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 0 |  | Planned | 0% | 100 | 0 | 100 | 100 | LSST Forecast - B57 - B1.3.06.01.02 | Camera Body Development | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 15% |  | Testing/Integration |  | Other (specify) | [5 empty] | Camera Body Development (TEC) | [6 empty] | Camera Body and Purge Production | CP #11 (CCS, Camera Body HCU)
FALSE |  | ITC33950 | Initial Integration - Cryo-Equip | LSST Forecast - B57 - B1 | 28 | 28 | 2019-07-24 | 2019-08-30 | 36 |  |  | 0 | 2019-07-24 | 2019-08-30 | 2019-09-13 | 2019-10-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-07-24 | 2019-08-30 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None |  | 2019-08-30 |  |  |  |  | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 28 | 0 |  | Planned | 0% | 280 | 0 | 280 | 280 | LSST Forecast - B57 - B1.3.08.03.02 | Cryostat Handling Equipment | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat I&T (TEC) | [7 empty] | CP #12 (Cryo Equip)
FALSE |  | SE224070 | LCA-17 as-built allocation | LSST Forecast - B57 - B1 | 60 | 60 | 2019-07-25 | 2019-10-17 | 218 |  |  | 106 | 2019-07-25 | 2019-10-17 | 2020-06-17 | 2020-09-10 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2019-07-25 | 2019-10-17 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 0 |  | Planned | 0% | 110 | 0 | 110 | 110 | LSST Forecast - B57 - B1.3.02.02.04 | Optics system analysis | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | OP531590 | COMP: L1-L2 Assembly Phase 5 | LSST Forecast - B57 - B1 | 0 | 0 | 2019-07-31 | 2019-07-31 | 64 |  |  | 0 | 2019-07-31 | 2019-07-31 | 2019-10-31 | 2019-10-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-07-31 | 2019-07-31 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  | Level 4 Milestone | Procurement | [8 empty] | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly)
FALSE |  | CRYO90050 | Inspect Cryostat Utility Trunk | LSST Forecast - B57 - B1 | 15 | 15 | 2019-08-06 | 2019-08-26 | 19 |  |  | 0 | 2019-08-06 | 2019-08-26 | 2019-09-03 | 2019-09-23 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-08-06 | 2019-08-26 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 0 |  | Planned | 0% | 141 | 0 | 141 | 141 | LSST Forecast - B57 - B1.3.06.05.02 | Utility Trunk Thermo-Mechanical and Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Fabrication/Assembly |  | Other (specify) | [5 empty] | Utility Trunk Thermo-Mechanical and Assembly (TEC) | [6 empty] | Utility Trunk | CP #10 (Utility Trunk)
FALSE |  | ITC32000 | Integrate Science Raft Tower #7 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-08-12 | 2019-08-13 | -18 |  |  | 0 | 2019-08-12 | 2019-08-13 | 2019-07-17 | 2019-07-18 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-08-12 | 2019-08-13 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32020 | Integrate Science Raft Tower #8 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-08-14 | 2019-08-15 | -18 |  |  | 0 | 2019-08-14 | 2019-08-15 | 2019-07-19 | 2019-07-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-08-14 | 2019-08-15 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32040 | Integrate Science Raft Tower #9 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-08-16 | 2019-08-19 | -18 |  |  | 0 | 2019-08-16 | 2019-08-19 | 2019-07-23 | 2019-07-24 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-08-16 | 2019-08-19 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | SE222432 | IRR Analyze Interfaces & Impacts - SEs (Camera I&T IRR) | LSST Forecast - B57 - B1 | 20 | 20 | 2019-08-16 | 2019-09-13 | 0 |  |  | 0 | 2019-08-16 | 2019-09-13 | 2019-08-16 | 2019-09-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-08-16 | 2019-09-13 |  |  |  |  | 0 | 0 | FALSE | FALSE | AsLateAsPossible |  | None | [6 empty] | 6 | 0 | 5 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 8 | 0 | 8 | 8 | LSST Forecast - B57 - B1.3.02.02.02 | Mechanical Integration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC)
FALSE |  | CCS117450 | Support deployment of FCS at SLAC | LSST Forecast - B57 - B1 | 100 | 100 | 2019-08-19 | 2020-01-23 | 35 |  |  | 53 | 2019-08-19 | 2020-01-23 | 2019-10-08 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-08-19 | 2020-01-23 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 7 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 100 | 0 |  | Planned | 0% | 200 | 0 | 200 | 200 | LSST Forecast - B57 - B1.3.07.01.03.05 | Filter/Carousel HCU | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering | [7 empty] | CCS HCU (TEC)
FALSE |  | ITC32140 | BOT Testing with Raft Tower #1-9 | LSST Forecast - B57 - B1 | 38 | 38 | 2019-08-20 | 2019-10-11 | -18 |  |  | 0 | 2019-08-20 | 2019-10-11 | 2019-07-25 | 2019-09-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2019-08-20 | 2019-10-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 38 | 0 |  | Planned | 0% | 517 | 0 | 517 | 517 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | CAMF669270 | Subsystem Packaging - Carousel | LSST Forecast - B57 - B1 | 4 | 4 | 2019-08-20 | 2019-08-23 | -176 |  |  | 0 | 2019-08-20 | 2019-08-23 | 2018-11-27 | 2018-11-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-08-20 | 2019-08-23 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 9 | 0 | 9 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Fabrication/Assembly | [15 empty] | CP #03 (Carousel/Camera Integration)
FALSE |  | ITC21550 | Assemble and Test CCOB | LSST Forecast - B57 - B1 | 30 | 30 | 2019-08-27 | 2019-10-08 | 55 |  |  | 0 | 2019-08-27 | 2019-10-08 | 2019-11-13 | 2020-01-10 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-08-27 | 2019-10-08 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.03.02 | CCOB (France) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  | TEC Non-ARRA | Tim Bond |  |  |  | Testing/Integration |  |  |  | Fabrication and Assembly
FALSE |  | ITC35930 | RTM21_Receive, Install in TS7 & Cool Down | LSST Forecast - B57 - B1 | 3 | 3 | 2019-08-30 | 2019-09-04 | 8 |  |  | 0 | 2019-08-30 | 2019-09-04 | 2019-09-12 | 2019-09-16 | 1500 | 1500 | 0 | 1500 | 1500 | 2 | FALSE | Normal | FALSE | 2019-08-30 | 2019-09-04 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 3 | 0 |  | Planned | 0% | 60 | 0 | 60 | 60 | LSST Forecast - B57 - B1.3.08.03.03 | Raft Acceptance Testing | 0 | 0 | 0 | 0 | 0 | 1500 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [7 empty] | CP #08 (I&T RTM Test)
FALSE |  | ITC19395 | NEED: Rotator from Telescope | LSST Forecast - B57 - B1 | 0 | 0 | 2019-09-04 | 2019-09-04 | 2 |  |  | 2 | 2019-09-04 | 2019-09-04 | 2019-09-06 | 2019-09-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-09-04 | 2019-09-04 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  |  | Rotator fromTelescope
FALSE |  | ITC35600 | RTM13_Receive, Install in TS7 & Cool Down | LSST Forecast - B57 - B1 | 5 | 5 | 2019-09-05 | 2019-09-11 | 8 |  |  | 0 | 2019-09-05 | 2019-09-11 | 2019-09-17 | 2019-09-23 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-09-05 | 2019-09-11 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 0 |  | Planned | 0% | 60 | 0 | 60 | 60 | LSST Forecast - B57 - B1.3.08.03.03 | Raft Acceptance Testing | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [7 empty] | CP #08 (I&T RTM Test)
FALSE |  | ITC19415 | Prep for C_IRR - Camera I&T | LSST Forecast - B57 - B1 | 5 | 5 | 2019-09-09 | 2019-09-13 | 0 |  |  | 0 | 2019-09-09 | 2019-09-13 | 2019-09-09 | 2019-09-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-09-09 | 2019-09-13 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 11 | 0 | 11 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 0 |  | Planned | 0% | 140 | 0 | 140 | 140 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Commissioning and Testing | [5 empty] | Camera I&T (TEC) | [7 empty] | CP #04 (Integration Stand, Camera IRR/Assy)
FALSE |  | DAQ910070 | Integration & Test - GDS | LSST Forecast - B57 - B1 | 60 | 60 | 2019-09-09 | 2019-12-03 | 131 |  |  | 0 | 2019-09-09 | 2019-12-03 | 2020-03-30 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-09-09 | 2019-12-03 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 0 |  | Planned | 0% | 224 | 0 | 224 | 224 | LSST Forecast - B57 - B1.3.07.02.02.15 | Guiding Data System (GDS) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | DAQ Readout Systems (TEC)
FALSE |  | ITC19425 | C_IRR - Camera I&T | LSST Forecast - B57 - B1 | 1 | 1 | 2019-09-16 | 2019-09-16 | 0 |  |  | 0 | 2019-09-16 | 2019-09-16 | 2019-09-16 | 2019-09-16 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-09-16 | 2019-09-16 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 8 | 0 | 8 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Planned | 0% | 64 | 0 | 64 | 64 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Commissioning and Testing | [5 empty] | Camera I&T (TEC) | [7 empty] | CP #04 (Integration Stand, Camera IRR/Assy)
FALSE |  | ITC19445 | START: Camera I&T | LSST Forecast - B57 - B1 | 0 | 0 | 2019-09-16 | 2019-09-16 | 0 |  |  | 0 | 2019-09-16 | 2019-09-16 | 2019-09-16 | 2019-09-16 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2019-09-16 | 2019-09-16 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Testing/Integration |  |  |  | Fabrication and Assembly
FALSE |  | ITC19500 | Camera Assembly - Main Body Acceptance | LSST Forecast - B57 - B1 | 10 | 10 | 2019-09-17 | 2019-09-30 | 0 |  |  | 8 | 2019-09-17 | 2019-09-30 | 2019-09-17 | 2019-09-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-09-17 | 2019-09-30 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 0 |  | Planned | 0% | 40 | 0 | 40 | 40 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Camera I&T (TEC) | [6 empty] | Camera I&T | CP #04 (Integration Stand, Camera IRR/Assy)
FALSE |  | CCS120370 | Install OS/Software, Test Prior to Ship (Other) | LSST Forecast - B57 - B1 | 20 | 20 | 2019-09-17 | 2019-10-14 | 594 |  |  | 0 | 2019-09-17 | 2019-10-14 | 2022-03-02 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-09-17 | 2019-10-14 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 60 | 0 | 60 | 60 | LSST Forecast - B57 - B1.3.07.01.02.02.07 | CCS Core 6.0 Release (Comcam Ship) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | CCS Core (TEC)
FALSE |  | CAMM9230 | COMP: RTM22 acceptance package available in eTraveler | LSST Forecast - B57 - B1 | 0 | 0 | 2019-09-20 | 2019-09-20 | 610 |  |  | 305 | 2019-09-20 | 2019-09-20 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-09-20 | 2019-09-20 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.07 | NSF New Interface Milestones (Watch) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration
FALSE |  | CAMM2260 | COMP: Early Hardware & Software Ready for Summit | LSST Forecast - B57 - B1 | 0 | 0 | 2019-09-24 | 2019-09-24 | 26 |  |  | 303 | 2019-09-24 | 2019-09-24 | 2019-10-31 | 2019-10-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-09-24 | 2019-09-24 |  |  |  |  | 0 | 0 | FALSE | FALSE | FinishOnOrBefore | 2019-10-31 | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.01 | DOE Project Milestones | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 2 Milestone | Management/Administration
FALSE |  | CR010200 | COMP: Ready for CD-4 - Corner Raft | LSST Forecast - B57 - B1 | 0 | 0 | 2019-10-01 | 2019-10-01 | 510 |  |  | 298 | 2019-10-01 | 2019-10-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-10-01 | 2019-10-01 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 8 | 0 | 8 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02 | Corner Raft System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 3 Milestone | Management/Administration
FALSE |  | OP522630 | Procure Filter coating (MS9) - Remaining Production Filters | LSST Forecast - B57 - B1 | 80 | 80 | 2019-10-08 | 2020-02-04 | 107 |  |  | 0 | 2019-10-08 | 2020-02-04 | 2020-03-16 | 2020-07-07 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-10-08 | 2020-02-04 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 3 | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 80 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  |  | Procurement | [8 empty] | Production Filters Coating
FALSE |  | CAMF650300 | COMP: Ready for CD-4 - Exchange System | LSST Forecast - B57 - B1 | 0 | 0 | 2019-10-10 | 2019-10-10 | 515 |  |  | 263 | 2019-10-10 | 2019-10-10 | 2021-11-16 | 2021-11-16 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-10-10 | 2019-10-10 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03 | Exchange System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  | Level 3 Milestone | Management/Administration
FALSE |  | CAMF661700 | AVAIL: Ready for Integration - Auto Changer | LSST Forecast - B57 - B1 | 0 | 0 | 2019-10-10 | 2019-10-10 | 9 |  |  | 0 | 2019-10-10 | 2019-10-10 | 2019-10-23 | 2019-10-23 | 0 | 0 | 0 | 0 | 0 | 5 | FALSE | Finish Milestone | FALSE | 2019-10-10 | 2019-10-10 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.01 | Auto Changer | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  | Level 5 Milestone | Fabrication/Assembly | [16 empty] | Exchange System
FALSE |  | CAMF665500 | AVAIL: Ready for Integration - Filter Loader | LSST Forecast - B57 - B1 | 0 | 0 | 2019-10-10 | 2019-10-10 | 153 |  |  | 0 | 2019-10-10 | 2019-10-10 | 2020-06-02 | 2020-06-02 | 0 | 0 | 0 | 0 | 0 | 5 | FALSE | Finish Milestone | FALSE | 2019-10-10 | 2019-10-10 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.02 | Filter Loader | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  | Level 5 Milestone | Fabrication/Assembly | [16 empty] | Exchange System
FALSE |  | CAMM7065 | COMP: Filter Exchange System | LSST Forecast - B57 - B1 | 0 | 0 | 2019-10-10 | 2019-10-10 | 596 |  |  | 291 | 2019-10-10 | 2019-10-10 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-10-10 | 2019-10-10 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.02 | NSF Watched Milestones | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration |  |  |  |  | Rotator fromTelescope
FALSE |  | OP522495 | All Phase 2 Deliverables Received (MS6) - Filter Fabrication | LSST Forecast - B57 - B1 | 20 | 20 | 2019-10-11 | 2019-11-07 | 163 |  |  | 0 | 2019-10-11 | 2019-11-07 | 2020-06-08 | 2020-07-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-10-11 | 2019-11-07 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 6 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  |  | Procurement | [8 empty] | Production Filters Polish and integration
FALSE |  | ITC32180 | Integrate Science Raft Tower #10 of 21 | LSST Forecast - B57 - B1 | 6 | 6 | 2019-10-14 | 2019-10-21 | -18 |  |  | 0 | 2019-10-14 | 2019-10-21 | 2019-09-18 | 2019-09-25 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-10-14 | 2019-10-21 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 6 | 0 |  | Planned | 0% | 147 | 0 | 147 | 147 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing | [5 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | CRYO91100 | Test and Verify - Cryostat Utility Trunk | LSST Forecast - B57 - B1 | 20 | 20 | 2019-11-19 | 2019-12-18 | 10 |  |  | 0 | 2019-11-19 | 2019-12-18 | 2019-12-05 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-11-19 | 2019-12-18 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 532 | 0 | 532 | 532 | LSST Forecast - B57 - B1.3.06.05.02 | Utility Trunk Thermo-Mechanical and Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Fabrication/Assembly |  | Other (specify) | [5 empty] | Utility Trunk Thermo-Mechanical and Assembly (TEC) | [6 empty] | Utility Trunk | CP #09 (Cryo Chile System for Ready for UT)
FALSE |  | ITC32400 | Integrate Science Raft Tower #21 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-11-19 | 2019-11-20 | -18 |  |  | 0 | 2019-11-19 | 2019-11-20 | 2019-10-24 | 2019-10-25 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-11-19 | 2019-11-20 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | OP522700 | Mount filters in frame - 1 filter | LSST Forecast - B57 - B1 | 40 | 40 | 2019-11-19 | 2020-01-21 | 107 |  |  | 0 | 2019-11-19 | 2020-01-21 | 2020-04-27 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-11-19 | 2020-01-21 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 0 |  | Planned | 0% | 116 | 0 | 116 | 116 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 18% |  | Testing/Integration |  | Other (specify) | [5 empty] | Filters (TEC) | Production Filters Polish and integration | [5 empty] | Filter Opto-Mechanics
FALSE |  | ITC00330 | START: Integrated Cryostat Testing | LSST Forecast - B57 - B1 | 0 | 0 | 2019-11-21 | 2019-11-21 | -18 |  |  | 0 | 2019-11-21 | 2019-11-21 | 2019-10-25 | 2019-10-25 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | TRUE | 2019-11-21 | 2019-11-21 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration
FALSE |  | ITC19760 | Camera Assembly - Shutter | LSST Forecast - B57 - B1 | 27 | 27 | 2019-12-19 | 2020-02-10 | -8 |  |  | 0 | 2019-12-19 | 2020-02-10 | 2019-12-09 | 2020-01-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-12-19 | 2020-02-10 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 27 | 0 |  | Planned | 0% | 407 | 0 | 407 | 407 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Camera I&T (TEC) | [6 empty] | Camera I&T | CP #03 (Carousel/Camera Integration)
FALSE |  | CRYO00300 | COMP: Ready for CD-4- Cryostat | LSST Forecast - B57 - B1 | 0 | 0 | 2020-01-06 | 2020-01-06 | 474 |  |  | 248 | 2020-01-06 | 2020-01-06 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2020-01-06 | 2020-01-06 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 31 | 0 | 31 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04 | Cryostat | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 3 Milestone | Management/Administration
FALSE |  | CRYO62130 | COMP: CRYO Equipment & Refigeration - Chile System Ready for Summit | LSST Forecast - B57 - B1 | 0 | 0 | 2020-01-06 | 2020-01-06 | 103 |  |  | 0 | 2020-01-06 | 2020-01-06 | 2020-06-02 | 2020-06-02 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Finish Milestone | FALSE | 2020-01-06 | 2020-01-06 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.05 | Refrigeration System - Chile System (Equipment & Refrigeration) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Fabrication/Assembly
FALSE |  | SE223250 | System engineering contamination as-built design inputs for optics throughput | LSST Forecast - B57 - B1 | 60 | 60 | 2020-01-07 | 2020-04-01 | 103 |  |  | 0 | 2020-01-07 | 2020-04-01 | 2020-06-03 | 2020-08-26 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2020-01-07 | 2020-04-01 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 11 | 0 | 11 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 0 |  | Planned | 0% | 20 | 0 | 20 | 20 | LSST Forecast - B57 - B1.3.02.02.03 | Thermal and contamination system analysis | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | OP522800 | Mount filters in frame - Remaining filter | LSST Forecast - B57 - B1 | 60 | 60 | 2020-01-08 | 2020-04-02 | 107 |  |  | 0 | 2020-01-08 | 2020-04-02 | 2020-06-10 | 2020-09-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2020-01-08 | 2020-04-02 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 0 |  | Planned | 0% | 346 | 0 | 346 | 346 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 18% |  | Testing/Integration |  | Other (specify) | [5 empty] | Filters (TEC) | Production Filters Polish and integration | [5 empty] | Filter Opto-Mechanics
FALSE |  | ITC32460 | NEED: L3 Lens Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2020-01-30 | 2020-01-30 | -18 |  |  | 0 | 2020-01-30 | 2020-01-30 | 2019-12-20 | 2019-12-20 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | TRUE | 2020-01-30 | 2020-01-30 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Optics
FALSE |  | ITC32480 | Mount L3 Lens Assembly | LSST Forecast - B57 - B1 | 8 | 8 | 2020-01-31 | 2020-02-11 | -18 |  |  | 0 | 2020-01-31 | 2020-02-11 | 2020-01-06 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-01-31 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 8 | 0 |  | Planned | 0% | 65 | 0 | 65 | 65 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | SE224080 | LCA-18 as-built allocation | LSST Forecast - B57 - B1 | 40 | 40 | 2020-02-06 | 2020-04-02 | 112 |  |  | 0 | 2020-02-06 | 2020-04-02 | 2020-07-16 | 2020-09-10 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2020-02-06 | 2020-04-02 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 0 |  | Planned | 0% | 50 | 0 | 50 | 50 | LSST Forecast - B57 - B1.3.02.02.04 | Optics system analysis | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | ITC19775 | Camera Assembly - Integrated Testing | LSST Forecast - B57 - B1 | 26 | 26 | 2020-02-11 | 2020-03-18 | -8 |  |  | 0 | 2020-02-11 | 2020-03-18 | 2020-01-30 | 2020-03-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2020-02-11 | 2020-03-18 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 26 | 0 |  | Planned | 0% | 555 | 0 | 555 | 555 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Commissioning and Testing | [5 empty] | Camera I&T (TEC) | [7 empty] | CP #03 (Carousel/Camera Integration)
FALSE |  | ITC32580 | NEED: UT Aux Electronics | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 14 | 0 | 14 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Auxiliary Electronics
FALSE |  | ITC32570 | NEED: Controls for Utility Trunk | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | ITC32620 | Mount and Populate Utility Trunk | LSST Forecast - B57 - B1 | 40 | 40 | 2020-02-12 | 2020-04-08 | -18 |  |  | 0 | 2020-02-12 | 2020-04-08 | 2020-01-16 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-02-12 | 2020-04-08 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 13 | 0 | 13 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 0 |  | Planned | 0% | 767 | 0 | 767 | 767 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC19800 | Camera Disassembly | LSST Forecast - B57 - B1 | 5 | 5 | 2020-03-19 | 2020-03-25 | -8 |  |  | 10 | 2020-03-19 | 2020-03-25 | 2020-03-09 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2020-03-19 | 2020-03-25 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 0 |  | Planned | 0% | 108 | 0 | 108 | 108 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Commissioning and Testing | [5 empty] | Camera I&T (TEC) | [7 empty] | CP #03 (Carousel/Camera Integration)
FALSE |  | SE224085 | COMP: Optics System Analysis | LSST Forecast - B57 - B1 | 0 | 0 | 2020-04-02 | 2020-04-02 | 392 |  |  | 114 | 2020-04-02 | 2020-04-02 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2020-04-02 | 2020-04-02 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.04 | Optics system analysis | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% | Level 4 Milestone | Design/Engineering
FALSE |  | ITC32660 | AVAIL: Loaded Cryostat Ready for Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2020-04-08 | 2020-04-08 | -18 |  |  | 0 | 2020-04-08 | 2020-04-08 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | TRUE | 2020-04-08 | 2020-04-08 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration | [16 empty] | Integration and Test
FALSE |  | ITC19900 | Camera / Cryostat Integration | LSST Forecast - B57 - B1 | 30 | 30 | 2020-04-09 | 2020-05-20 | -18 |  |  | 0 | 2020-04-09 | 2020-05-20 | 2020-03-16 | 2020-04-24 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2020-04-09 | 2020-05-20 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 7 | 0 | 7 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 0 |  | Planned | 0% | 518 | 0 | 518 | 518 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration | Stanford University | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Camera I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Camera I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | SE221650 | Generate End Item Data Package materials and charts for PSR | LSST Forecast - B57 - B1 | 42 | 42 | 2020-04-16 | 2020-06-15 | 103 |  |  | 63 | 2020-04-16 | 2020-06-15 | 2020-09-11 | 2020-11-09 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2020-04-16 | 2020-06-15 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 13 | 0 | 13 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 42 | 0 |  | Planned | 0% | 60 | 0 | 60 | 60 | LSST Forecast - B57 - B1.3.02.02.01 | Structural System Analysis | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | ITC20000 | NEED: L1-L2 Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2020-05-20 | 2020-05-20 | -18 |  |  | 0 | 2020-05-20 | 2020-05-20 | 2020-04-24 | 2020-04-24 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-05-20 | 2020-05-20 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Optics
FALSE |  | OP00160 | COMP: Ready for CD-4 - Optics | LSST Forecast - B57 - B1 | 0 | 0 | 2020-05-29 | 2020-05-29 | 358 |  |  | 140 | 2020-05-29 | 2020-05-29 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2020-05-29 | 2020-05-29 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05 | Optics | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  | Level 3 Milestone | Management/Administration
FALSE |  | OP522840 | AVAIL: Remaining Filters | LSST Forecast - B57 - B1 | 0 | 0 | 2020-05-29 | 2020-05-29 | 107 |  |  | 0 | 2020-05-29 | 2020-05-29 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | FALSE | 2020-05-29 | 2020-05-29 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  | Level 5 Milestone | Testing/Integration | [8 empty] | Production Filters Polish and integration | [7 empty] | Optics
FALSE |  | DAQ100130 | COMP: Ready for CD-4 - DAQ | LSST Forecast - B57 - B1 | 0 | 0 | 2020-06-16 | 2020-06-16 | 340 |  |  | 128 | 2020-06-16 | 2020-06-16 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2020-06-16 | 2020-06-16 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 19 | 0 | 19 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02 | Data Acquisition System (DAQ) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer |  |  | Level 3 Milestone | Management/Administration
FALSE |  | ITC20065 | NEED: OCS & CCS Ready for I&T Testing (CCS Suite #9) | LSST Forecast - B57 - B1 | 0 | 0 | 2020-07-17 | 2020-07-17 | -18 |  |  | 0 | 2020-07-17 | 2020-07-17 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-07-17 | 2020-07-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 11 | 0 | 11 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration | [16 empty] | Project Management
FALSE |  | ITC20076 | NEED: DAQ Production V5.0 | LSST Forecast - B57 - B1 | 0 | 0 | 2020-07-17 | 2020-07-17 | -18 |  |  | 0 | 2020-07-17 | 2020-07-17 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-07-17 | 2020-07-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 10 | 0 | 10 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | ITC20125 | Camera Functional Testing | LSST Forecast - B57 - B1 | 46 | 46 | 2020-07-20 | 2020-09-22 | -18 |  |  | 0 | 2020-07-20 | 2020-09-22 | 2020-06-23 | 2020-08-26 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2020-07-20 | 2020-09-22 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 46 | 0 |  | Planned | 0% | 1432 | 0 | 1432 | 1432 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration | Stanford University | Commissioning and Testing | [5 empty] | Camera I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Camera I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | SE222640 | Generate charts for camera-level PSR, Status Director's and DOE Review | LSST Forecast - B57 - B1 | 40 | 40 | 2020-07-20 | 2020-09-14 | 40 |  |  | 0 | 2020-07-20 | 2020-09-14 | 2020-09-15 | 2020-11-09 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2020-07-20 | 2020-09-14 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 0 |  | Planned | 0% | 40 | 0 | 40 | 40 | LSST Forecast - B57 - B1.3.02.02.02 | Mechanical Integration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | SE01210 | COMP: Ready for CD-4 Review - SI | LSST Forecast - B57 - B1 | 0 | 0 | 2020-09-14 | 2020-09-14 | 278 |  |  | 66 | 2020-09-14 | 2020-09-14 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2020-09-14 | 2020-09-14 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 8 | 0 | 8 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02 | Systems Integration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 3 Milestone | Management/Administration
FALSE |  | SE222650 | AVAIL: As-built Documentation | LSST Forecast - B57 - B1 | 0 | 0 | 2020-09-14 | 2020-09-14 | 40 |  |  | 0 | 2020-09-14 | 2020-09-14 | 2020-11-09 | 2020-11-09 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2020-09-14 | 2020-09-14 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 8 | 0 | 8 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.02 | Mechanical Integration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% | Level 5 Milestone | Design/Engineering
FALSE |  | ITC20150 | Camera Verification Testing | LSST Forecast - B57 - B1 | 45 | 45 | 2020-09-23 | 2020-11-24 | -18 |  |  | 0 | 2020-09-23 | 2020-11-24 | 2020-08-27 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | TRUE | 2020-09-23 | 2020-11-24 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 7 | 0 | 5 | 0 | 0 | 2 | 3 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 45 | 0 |  | Planned | 0% | 1468 | 0 | 1468 | 1468 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration | Stanford University | Commissioning and Testing | [5 empty] | Camera I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Camera I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC20180 | Recover from tests, secure Camera for shipping | LSST Forecast - B57 - B1 | 7 | 7 | 2020-11-25 | 2020-12-07 | -18 |  |  | 0 | 2020-11-25 | 2020-12-07 | 2020-10-30 | 2020-11-09 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-11-25 | 2020-12-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 7 | 0 |  | Planned | 0% | 392 | 0 | 392 | 392 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration | Stanford University | Commissioning and Testing | [5 empty] | Camera I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Camera I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC20350 | Prep for C_PSR/ORR--Camera | LSST Forecast - B57 - B1 | 6 | 6 | 2020-12-08 | 2020-12-15 | -18 |  |  | 0 | 2020-12-08 | 2020-12-15 | 2020-11-10 | 2020-11-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-12-08 | 2020-12-15 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 10 | 0 | 10 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 6 | 0 |  | Planned | 0% | 120 | 0 | 120 | 120 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration | Stanford University | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Camera I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Camera I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | CAMM2300 | COMP: KPPs achieved (Camera Readiness Review, Ready for CD-4) | LSST Forecast - B57 - B1 | 0 | 0 | 2020-12-17 | 2020-12-17 | 212 |  |  | 53 | 2020-12-17 | 2020-12-17 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2020-12-17 | 2020-12-17 |  |  |  |  | 0 | 0 | FALSE | FALSE | FinishOnOrBefore | 2021-10-29 | None | [6 empty] | 37 | 0 | 37 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.01 | DOE Project Milestones | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 2 Milestone | Management/Administration
FALSE |  | ITC00100 | COMP: Ready for CD-4 - I&T | LSST Forecast - B57 - B1 | 0 | 0 | 2020-12-17 | 2020-12-17 | 212 |  |  | 0 | 2020-12-17 | 2020-12-17 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-12-17 | 2020-12-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 31 | 0 | 31 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration
FALSE |  | CAM112800 | COMP: Project Ready for CD-4/CRR | LSST Forecast - B57 - B1 | 0 | 0 | 2020-12-17 | 2020-12-17 | 212 |  |  | 0 | 2020-12-17 | 2020-12-17 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-12-17 | 2020-12-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 13 | 0 | 13 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01.01.02 | Reviews & Collaboration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Vincent Riot | (1.10) Task/item is a modification of an existing design | 0% | Level 4 Milestone | Management/Administration | [12 empty] | CD-3b | Critical Path to CD-3b | Project Management
FALSE |  | CAMM6050 | APPROVED: CD-4 - Project Completion - Camera | LSST Forecast - B57 - B1 | 0 | 0 | 2020-12-17 | 2020-12-17 | 305 |  |  | 53 | 2020-12-17 | 2020-12-17 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 0 | FALSE | Finish Milestone | FALSE | 2020-12-17 | 2020-12-17 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 149 | 0 | 149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.02 | NSF Watched Milestones | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration |  |  |  |  | CD-4 Project Close
FALSE |  | CAMC8700 | COMP: Project Level of Effort Support | LSST Forecast - B57 - B1 | 0 | 0 | 2020-12-18 | 2020-12-18 | 304 |  |  | 52 | 2020-12-18 | 2020-12-18 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 0 | FALSE | Finish Milestone | FALSE | 2020-12-18 | 2020-12-18 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 151 | 0 | 151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01 | Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 3 Milestone | Management/Administration
FALSE |  | CAMM1060 | COMP: CD-4, Approve Project Completion | LSST Forecast - B57 - B1 | 0 | 0 | 2021-03-17 | 2021-03-17 | 252 |  |  | 0 | 2021-03-17 | 2021-03-17 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 0 | FALSE | Finish Milestone | TRUE | 2021-03-17 | 2021-03-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | FinishOnOrBefore | 2022-03-31 | None | [6 empty] | 17 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  |  | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.01 | DOE Project Milestones | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 1 Milestone | Management/Administration

## Phase Analysis
Fuse® Analyst Report
Workbook: Workbook1 - 8168 Activities
Schedule Quality
Created on: 8/5/2019
Created by: brackett
Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis
Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis
|  | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line
|  | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Phase Analyzer | Missing Logic | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2
Phase Analyzer | Logic Density™ | 2.82 | 2.97 | 2.53 | 2.81 | 2.87 | 3.1 | 2.99 | 3.02 | 2.87 | 2.98 | 6.14 | 4
Phase Analyzer | Critical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 47 | 53 | 8
Phase Analyzer | Hard Constraints | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase Analyzer | Negative Float | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 51 | 0
Phase Analyzer | Insufficient Detail™ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase Analyzer | Number of Lags | 0 | 0 | 0 | 1 | 25 | 65 | 84 | 121 | 108 | 56 | 3 | 1
Phase Analyzer | Number of Leads | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase Analyzer | Merge Hotspot | 1 | 12 | 1 | 13 | 61 | 127 | 116 | 153 | 136 | 106 | 34 | 1
Phase Analyzer | Score | 99 | 96 | 100 | 96 | 93 | 88 | 88 | 86 | 86 | 79 | 56 | 75
Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis
|  | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line
|  | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Phase Analyzer | Missing Logic | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 25%
Phase Analyzer | Logic Density™
Phase Analyzer | Critical | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 8% | 33% | 100%
Phase Analyzer | Hard Constraints | bar: 2010 to 2021
Phase Analyzer | Negative Float | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 15% | 32% | 0%
Phase Analyzer | Insufficient Detail™ | bar: 2010 to 2021
Phase Analyzer | Number of Lags | 0% | 0% | 0% | 0% | 2% | 5% | 7% | 8% | 8% | 7% | 2% | 14%
Phase Analyzer | Number of Leads | bar: 2010 to 2021
Phase Analyzer | Merge Hotspot | 1% | 5% | 1% | 5% | 6% | 10% | 10% | 10% | 11% | 13% | 25% | 14%
Phase Analyzer | Score | bar: 2020 to 2021

## 2010 Details
Fuse® Analyst Report
Workbook: Workbook1 - 8168 Activities
Schedule Quality
Created on: 8/5/2019
Created by: brackett
2010: Detailed View | 2010: Detailed View
Merge Hotspot
The total number of activities with a high number of predecessor links.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | Previous Start | Previous Finish | Percent Complete | Previous Remaining Duration | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | IsLevelOfEffort | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | Global_Basis of Estimate | Global_Cobra Cost Class | Cobra PMT (EV Method)_Global | Global_Color of Money | Global_Control Account Manager | Global_Design Maturity | Global_Judgement Factor | Global_Milestone Levels | Global_Project Phase | Global_Funding Source | Global_EDIA Survey | Global_MS Type | Phase | NSF Milestones | Loading Curve | Sensor Vendor | LSST_CA | Summary Schedule | ICD for NSF Input | LSST Camera Critical Paths | CD2 Budget Changes | DOE Reviews | Critical Path (CD Reviews) | LSST WP Summary | Critical Path (Camera Delivery) | AWARD / NEED Sub-System | Final Design Key Links | CP - CAMM2100 | CP - CAMM2130 | CP - CAMM2160 | BNL Work Org | Last ETC Update | BNL WBS | LSST Story List | Sum Sch 01 (Camera) | Sum Sch 02 (IT w/Needs) | Sum Sch 03 (Sensors_RTM_IT) | LSST Raft Particulate Mitigation | LSST RTM
FALSE |  | SE222025 | Prep for C_CDR - Mechanical Integration | LSST Forecast - B57 - B1 | 286 | 0 | 2010-10-01 | 2011-12-01 | 0 | 2010-10-01 | 2011-12-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2010-10-01 | 2011-12-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 286 | 285 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.02 | Mechanical Integration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  |  | Development (includes R&D)

## 2011 Details
Fuse® Analyst Report
Workbook: Workbook1 - 8168 Activities
Schedule Quality
Created on: 8/5/2019
Created by: brackett
2011: Detailed View | 2011: Detailed View | 2011: Detailed View
Missing Logic
Total number of activities that are missing a predecessor, a successor, or both. This number should not exceed 5%.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | Previous Start | Previous Finish | Percent Complete | Previous Remaining Duration | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | IsLevelOfEffort | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | Global_Basis of Estimate | Global_Cobra Cost Class | Cobra PMT (EV Method)_Global | Global_Color of Money | Global_Control Account Manager | Global_Design Maturity | Global_Judgement Factor | Global_Milestone Levels | Global_Project Phase | Global_Funding Source | Global_EDIA Survey | Global_MS Type | Phase | NSF Milestones | Loading Curve | Sensor Vendor | LSST_CA | Summary Schedule | ICD for NSF Input | LSST Camera Critical Paths | CD2 Budget Changes | DOE Reviews | Critical Path (CD Reviews) | LSST WP Summary | Critical Path (Camera Delivery) | AWARD / NEED Sub-System | Final Design Key Links | CP - CAMM2100 | CP - CAMM2130 | CP - CAMM2160 | BNL Work Org | Last ETC Update | BNL WBS | LSST Story List | Sum Sch 01 (Camera) | Sum Sch 02 (IT w/Needs) | Sum Sch 03 (Sensors_RTM_IT) | LSST Raft Particulate Mitigation | LSST RTM
FALSE |  | CAMM1010 | COMP: CD-0, Approve Mission Need | LSST Forecast - B57 - B1 | 0 | 0 | 2011-06-20 | 2011-06-20 | 0 | 2011-06-20 | 2011-06-20 | 0 | 2019-06-01 | 2019-06-01 | 2018-09-07 | 2018-09-07 | 0 | 0 | 0 | 0 | 0 | 72 | FALSE | Finish Milestone | FALSE | 2011-06-20 | 2011-06-20 |  |  |  |  | 1 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 0 | 71 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.01 | DOE Project Milestones | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 1 Milestone | Management/Administration
Merge Hotspot
The total number of activities with a high number of predecessor links.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | Previous Start | Previous Finish | Percent Complete | Previous Remaining Duration | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | IsLevelOfEffort | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | Global_Basis of Estimate | Global_Cobra Cost Class | Cobra PMT (EV Method)_Global | Global_Color of Money | Global_Control Account Manager | Global_Design Maturity | Global_Judgement Factor | Global_Milestone Levels | Global_Project Phase | Global_Funding Source | Global_EDIA Survey | Global_MS Type | Phase | NSF Milestones | Loading Curve | Sensor Vendor | LSST_CA | Summary Schedule | ICD for NSF Input | LSST Camera Critical Paths | CD2 Budget Changes | DOE Reviews | Critical Path (CD Reviews) | LSST WP Summary | Critical Path (Camera Delivery) | AWARD / NEED Sub-System | Final Design Key Links | CP - CAMM2100 | CP - CAMM2130 | CP - CAMM2160 | BNL Work Org | Last ETC Update | BNL WBS | LSST Story List | Sum Sch 01 (Camera) | Sum Sch 02 (IT w/Needs) | Sum Sch 03 (Sensors_RTM_IT) | LSST Raft Particulate Mitigation | LSST RTM
FALSE |  | CBM41000 | Prep for Comp. Conceptual Design Review | LSST Forecast - B57 - B1 | 10 | 0 | 2011-03-11 | 2011-03-24 | 0 | 2011-03-11 | 2011-03-24 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2011-03-11 | 2011-03-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.02.02 | Shutter Development | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Martin Nordby |  |  |  | Development (includes R&D)
FALSE |  | CAMF658550 | COMP: C_CDR - Auto Changer | LSST Forecast - B57 - B1 | 0 | 0 | 2011-03-25 | 2011-03-25 | 0 | 2011-03-25 | 2011-03-25 | 0 | 2019-06-01 | 2019-06-01 | 2018-10-16 | 2018-10-16 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | FALSE | 2011-03-25 | 2011-03-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.01 | Auto Changer | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  | Level 4 Milestone | Development (includes R&D)
FALSE |  | CBM21200 | COMP: C_CDR - Camera Body | LSST Forecast - B57 - B1 | 0 | 0 | 2011-03-25 | 2011-03-25 | 0 | 2011-03-25 | 2011-03-25 | 0 | 2019-06-01 | 2019-06-01 | 2018-09-07 | 2018-09-07 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Finish Milestone | FALSE | 2011-03-25 | 2011-03-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.01.02 | Camera Body Development | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Martin Nordby |  |  | Level 4 Milestone | Development (includes R&D)
FALSE |  | CAMF662250 | Prep for Comp. Conceptual Design Review - Filter Loader | LSST Forecast - B57 - B1 | 10 | 0 | 2011-04-08 | 2011-04-21 | 0 | 2011-04-08 | 2011-04-21 | 0 | 2019-06-01 | 2019-06-01 | 2018-10-16 | 2018-10-16 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2011-04-08 | 2011-04-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.02 | Filter Loader | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Development (includes R&D)
FALSE |  | CRYO00100 | COMP: Ready for NSF FDR - Cryostat | LSST Forecast - B57 - B1 | 0 | 0 | 2011-08-11 | 2011-08-11 | 0 | 2011-08-11 | 2011-08-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2011-08-11 | 2011-08-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 11 | 0 | 11 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04 | Cryostat | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 3 Milestone | Management/Administration
FALSE |  | CAMF650050 | COMP: Ready for CD-1 - Exchange System | LSST Forecast - B57 - B1 | 0 | 0 | 2011-08-18 | 2011-08-18 | 0 | 2011-08-18 | 2011-08-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2011-08-18 | 2011-08-18 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03 | Exchange System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  | Level 3 Milestone | Management/Administration
FALSE |  | CRYO00150 | COMP: Ready for CD-1 - Cryostat | LSST Forecast - B57 - B1 | 0 | 0 | 2011-08-18 | 2011-08-18 | 0 | 2011-08-18 | 2011-08-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2011-08-18 | 2011-08-18 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 14 | 0 | 14 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04 | Cryostat | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 3 Milestone | Management/Administration
FALSE |  | OP00100 | COMP: Ready for CD-1 - Optics | LSST Forecast - B57 - B1 | 0 | 0 | 2011-08-18 | 2011-08-18 | 0 | 2011-08-18 | 2011-08-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2011-08-18 | 2011-08-18 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05 | Optics | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  | Level 3 Milestone | Management/Administration
FALSE |  | OP10925 | C_CDR - Optics | LSST Forecast - B57 - B1 | 1 | 0 | 2011-08-18 | 2011-08-18 | 0 | 2011-08-18 | 2011-08-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2011-08-18 | 2011-08-18 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.01 | Optics Integration & Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  |  | Development (includes R&D)
FALSE |  | CAMF5100 | QA Technical Support FY12 | LSST Forecast - B57 - B1 | 242 | 0 | 2011-10-01 | 2012-09-28 | 0 | 2011-10-01 | 2012-09-28 | 0 | 2019-06-01 | 2019-06-01 | 2021-11-12 | 2021-11-12 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2011-10-03 | 2012-09-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 242 | 241 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01.03.02 | Quality Assurance | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Drtn |  |  |  | OPC Non-ARRA | Vincent Riot | (1.00) Task/item is fully invoiced/completed | 0% |  | Management/Administration |  | QA Inspection/Testing/Acceptance | [12 empty] | Performance Safety & Assurance
FALSE |  | CR010140 | COMP: Ready for CD-1 - Corner Raft | LSST Forecast - B57 - B1 | 0 | 0 | 2011-11-30 | 2011-11-30 | 0 | 2011-11-30 | 2011-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2011-11-30 | 2011-11-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02 | Corner Raft System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 3 Milestone | Management/Administration
FALSE |  | CAMC01000 | COMP: Ready for CD-1 Lehman Review - Camera | LSST Forecast - B57 - B1 | 0 | 0 | 2011-11-30 | 2011-11-30 | 0 | 2011-11-30 | 2011-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | FALSE | 2011-11-30 | 2011-11-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 7 | 0 | 0 | 0 | 3 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01 | Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 3 Milestone | Management/Administration

## 2012 Details
Fuse® Analyst Report
Workbook: Workbook1 - 8168 Activities
Schedule Quality
Created on: 8/5/2019
Created by: brackett
2012: Detailed View | 2012: Detailed View
Merge Hotspot
The total number of activities with a high number of predecessor links.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | Previous Start | Previous Finish | Percent Complete | Previous Remaining Duration | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | IsLevelOfEffort | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | Global_Basis of Estimate | Global_Cobra Cost Class | Cobra PMT (EV Method)_Global | Global_Color of Money | Global_Control Account Manager | Global_Design Maturity | Global_Judgement Factor | Global_Milestone Levels | Global_Project Phase | Global_Funding Source | Global_EDIA Survey | Global_MS Type | Phase | NSF Milestones | Loading Curve | Sensor Vendor | LSST_CA | Summary Schedule | ICD for NSF Input | LSST Camera Critical Paths | CD2 Budget Changes | DOE Reviews | Critical Path (CD Reviews) | LSST WP Summary | Critical Path (Camera Delivery) | AWARD / NEED Sub-System | Final Design Key Links | CP - CAMM2100 | CP - CAMM2130 | CP - CAMM2160 | BNL Work Org | Last ETC Update | BNL WBS | LSST Story List | Sum Sch 01 (Camera) | Sum Sch 02 (IT w/Needs) | Sum Sch 03 (Sensors_RTM_IT) | LSST Raft Particulate Mitigation | LSST RTM
FALSE |  | CRYO52100 | COMP: Phase 3b ETU Refrigeration System | LSST Forecast - B57 - B1 | 0 | 0 | 2012-10-01 | 2012-10-01 | 0 | 2012-10-01 | 2012-10-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | FALSE | 2012-10-01 | 2012-10-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Engineering Test/Validation

## 2013 Details
Fuse® Analyst Report
Workbook: Workbook1 - 8168 Activities
Schedule Quality
Created on: 8/5/2019
Created by: brackett
2013: Detailed View | 2013: Detailed View | 2013: Detailed View
Number of Lags
Total number of activities that have lags in their predecessors. This number should not exceed 5%.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | Previous Start | Previous Finish | Percent Complete | Previous Remaining Duration | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | IsLevelOfEffort | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | Global_Basis of Estimate | Global_Cobra Cost Class | Cobra PMT (EV Method)_Global | Global_Color of Money | Global_Control Account Manager | Global_Design Maturity | Global_Judgement Factor | Global_Milestone Levels | Global_Project Phase | Global_Funding Source | Global_EDIA Survey | Global_MS Type | Phase | NSF Milestones | Loading Curve | Sensor Vendor | LSST_CA | Summary Schedule | ICD for NSF Input | LSST Camera Critical Paths | CD2 Budget Changes | DOE Reviews | Critical Path (CD Reviews) | LSST WP Summary | Critical Path (Camera Delivery) | AWARD / NEED Sub-System | Final Design Key Links | CP - CAMM2100 | CP - CAMM2130 | CP - CAMM2160 | BNL Work Org | Last ETC Update | BNL WBS | LSST Story List | Sum Sch 01 (Camera) | Sum Sch 02 (IT w/Needs) | Sum Sch 03 (Sensors_RTM_IT) | LSST Raft Particulate Mitigation | LSST RTM
FALSE |  | SR341060 | Bench Test - ASPIC 3 | LSST Forecast - B57 - B1 | 186 | 0 | 2013-11-01 | 2014-07-31 | 0 | 2013-11-01 | 2014-07-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2013-11-01 | 2014-07-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 186 | 185 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.01 | ASPIC | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | OPC Non-ARRA | Bill Wahl | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Engineering Test/Validation | [14 empty] | Science Raft Electronics | [8 empty] | Science Raft System
Merge Hotspot
The total number of activities with a high number of predecessor links.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | Previous Start | Previous Finish | Percent Complete | Previous Remaining Duration | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | IsLevelOfEffort | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | Global_Basis of Estimate | Global_Cobra Cost Class | Cobra PMT (EV Method)_Global | Global_Color of Money | Global_Control Account Manager | Global_Design Maturity | Global_Judgement Factor | Global_Milestone Levels | Global_Project Phase | Global_Funding Source | Global_EDIA Survey | Global_MS Type | Phase | NSF Milestones | Loading Curve | Sensor Vendor | LSST_CA | Summary Schedule | ICD for NSF Input | LSST Camera Critical Paths | CD2 Budget Changes | DOE Reviews | Critical Path (CD Reviews) | LSST WP Summary | Critical Path (Camera Delivery) | AWARD / NEED Sub-System | Final Design Key Links | CP - CAMM2100 | CP - CAMM2130 | CP - CAMM2160 | BNL Work Org | Last ETC Update | BNL WBS | LSST Story List | Sum Sch 01 (Camera) | Sum Sch 02 (IT w/Needs) | Sum Sch 03 (Sensors_RTM_IT) | LSST Raft Particulate Mitigation | LSST RTM
FALSE |  | CRYO51520 | Phase 3 ETU Review Heat Exchanger & Stand | LSST Forecast - B57 - B1 | 5 | 0 | 2013-01-15 | 2013-01-21 | 0 | 2013-01-15 | 2013-01-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2013-01-15 | 2013-01-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 4 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | OPC Non-ARRA | Brian J. Langton | (1.00) Task/item is fully invoiced/completed | 0% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Refrigeration System
FALSE |  | SR343070 | Bench Test Raft Electronics Board 1 | LSST Forecast - B57 - B1 | 209 | 0 | 2013-03-04 | 2013-12-30 | 0 | 2013-03-04 | 2013-12-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2013-03-04 | 2013-12-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 209 | 208 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | OPC Non-ARRA | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 0% |  | Development (includes R&D) | [14 empty] | Science Raft Electronics | [6 empty] | Raft Electronics Board 1 |  | Science Raft System
FALSE |  | SE223020 | Thermal Analysis of Loaded Cryostat - SE | LSST Forecast - B57 - B1 | 106 | 0 | 2013-04-01 | 2013-08-28 | 0 | 2013-04-01 | 2013-08-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2013-04-01 | 2013-08-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 106 | 105 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.03 | Thermal and contamination system analysis | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot | (1.00) Task/item is fully invoiced/completed | 0% |  | Development (includes R&D) |  | Design Management | [12 empty] | System Analysis
FALSE |  | SE223040 | Assess impact of Cryo, Exch, Shtr prelim design and power budget changes/ heat loads on camera thermal design - SE | LSST Forecast - B57 - B1 | 22 | 0 | 2013-04-01 | 2013-04-30 | 0 | 2013-04-01 | 2013-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2013-04-01 | 2013-04-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 5 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 22 | 21 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.03 | Thermal and contamination system analysis | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot | (1.00) Task/item is fully invoiced/completed | 0% |  | Development (includes R&D) |  | Design Management
FALSE |  | SE222070 | Preliminary Science Raft - Mechanical Integration | LSST Forecast - B57 - B1 | 38 | 0 | 2013-07-01 | 2013-08-22 | 0 | 2013-07-01 | 2013-08-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2013-07-01 | 2013-08-22 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 38 | 37 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.02 | Mechanical Integration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  |  | Development (includes R&D)
FALSE |  | SR342110 | Design - CABAC 1 | LSST Forecast - B57 - B1 | 202 | 0 | 2013-07-08 | 2014-04-25 | 0 | 2013-07-08 | 2014-04-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2013-07-08 | 2014-04-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 202 | 201 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.02 | CABAC | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | OPC Non-ARRA | Bill Wahl | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Engineering Test/Validation | [14 empty] | Science Raft Electronics | [8 empty] | Science Raft System
FALSE |  | SR331035 | Prep for C_PDR - RSA | LSST Forecast - B57 - B1 | 39 | 0 | 2013-07-15 | 2013-09-06 | 0 | 2013-07-15 | 2013-09-06 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2013-07-15 | 2013-09-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 0 | 3 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 39 | 38 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.02 | Science Raft Sensor Assembly (SRSA) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | OPC Non-ARRA | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 0% |  | Development (includes R&D) |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Raft Sensor Assembly (RSA) | [8 empty] | Science Raft System
FALSE |  | SR000020 | COMP: Ready for CD-2 - Science Raft System | LSST Forecast - B57 - B1 | 0 | 0 | 2013-09-10 | 2013-09-10 | 0 | 2013-09-10 | 2013-09-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2013-09-10 | 2013-09-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01 | Science Raft System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Bill Wahl |  |  | Level 3 Milestone | Management/Administration | [23 empty] | Science Raft System
FALSE |  | SR343120 | Design - Raft Electronics Board 2 (REB2) | LSST Forecast - B57 - B1 | 100 | 0 | 2013-10-01 | 2014-02-26 | 0 | 2013-10-01 | 2014-02-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2013-10-01 | 2014-02-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 100 | 99 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | OPC Non-ARRA | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 0% |  | Engineering Test/Validation | [14 empty] | Science Raft Electronics | [6 empty] | Raft Electronics Board 2 |  | Science Raft System
FALSE |  | CAMF659050 | Prep for Prelim Design Review - Auto Changer | LSST Forecast - B57 - B1 | 2 | 0 | 2013-11-02 | 2013-11-03 | 0 | 2013-11-02 | 2013-11-03 | 0 | 2019-06-01 | 2019-06-01 | 2018-10-16 | 2018-10-16 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2013-11-04 | 2013-11-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.01 | Auto Changer | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Design/Engineering
FALSE |  | CAMF662850 | Prep for Prelim Design Review - Filter Loader | LSST Forecast - B57 - B1 | 2 | 0 | 2013-11-02 | 2013-11-03 | 0 | 2013-11-02 | 2013-11-03 | 0 | 2019-06-01 | 2019-06-01 | 2018-10-16 | 2018-10-16 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2013-11-04 | 2013-11-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.02 | Filter Loader | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Design/Engineering
FALSE |  | CAMF666650 | Prep for Prelim Design Review - Carousel | LSST Forecast - B57 - B1 | 2 | 0 | 2013-11-02 | 2013-11-03 | 0 | 2013-11-02 | 2013-11-03 | 0 | 2019-06-01 | 2019-06-01 | 2018-10-16 | 2018-10-16 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2013-11-04 | 2013-11-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Design/Engineering
FALSE |  | CAMF659150 | COMP: C_PDR - Auto Changer | LSST Forecast - B57 - B1 | 0 | 0 | 2013-11-05 | 2013-11-05 | 0 | 2013-11-05 | 2013-11-05 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 6 | FALSE | Finish Milestone | FALSE | 2013-11-05 | 2013-11-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.01 | Auto Changer | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  | Level 4 Milestone | Design/Engineering

## 2014 Details
Fuse® Analyst Report
Workbook: Workbook1 - 8168 Activities
Schedule Quality
Created on: 8/5/2019
Created by: brackett
2014: Detailed View | 2014: Detailed View | 2014: Detailed View
Number of Lags
Total number of activities that have lags in their predecessors. This number should not exceed 5%.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | Previous Start | Previous Finish | Percent Complete | Previous Remaining Duration | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | IsLevelOfEffort | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | Global_Basis of Estimate | Global_Cobra Cost Class | Cobra PMT (EV Method)_Global | Global_Color of Money | Global_Control Account Manager | Global_Design Maturity | Global_Judgement Factor | Global_Milestone Levels | Global_Project Phase | Global_Funding Source | Global_EDIA Survey | Global_MS Type | Phase | NSF Milestones | Loading Curve | Sensor Vendor | LSST_CA | Summary Schedule | ICD for NSF Input | LSST Camera Critical Paths | CD2 Budget Changes | DOE Reviews | Critical Path (CD Reviews) | LSST WP Summary | Critical Path (Camera Delivery) | AWARD / NEED Sub-System | Final Design Key Links | CP - CAMM2100 | CP - CAMM2130 | CP - CAMM2160 | BNL Work Org | Last ETC Update | BNL WBS | LSST Story List | Sum Sch 01 (Camera) | Sum Sch 02 (IT w/Needs) | Sum Sch 03 (Sensors_RTM_IT) | LSST Raft Particulate Mitigation | LSST RTM
FALSE |  | SR521055 | TS1- Computer, Network and Storage system final design | LSST Forecast - B57 - B1 | 9 | 0 | 2014-02-18 | 2014-02-28 | 0 | 2014-02-18 | 2014-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2014-02-18 | 2014-02-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 9 | 8 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.01 | Sensor Receiving & Inspection (TS1) - eLog, eTraveler | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | TEC Non-ARRA | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Science Sensors Test Stands | [8 empty] | Science Sensors
FALSE |  | SR523380 | TS3 - Dewer Cryostat (includes int fitting and flange) - final design drawing package | LSST Forecast - B57 - B1 | 102 | 0 | 2014-03-10 | 2014-07-31 | 0 | 2014-03-10 | 2014-07-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-03-10 | 2014-07-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 102 | 101 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.03 | Sensor Electro-Optical (TS3) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [6 empty] | Test Stand Effort | [5 empty] | Science Sensors Test Stands | [8 empty] | Science Sensors
FALSE |  | SR523390 | TS3 - XED (X-Ray exposure device) FE55 actuator - final design drawing package | LSST Forecast - B57 - B1 | 102 | 0 | 2014-03-10 | 2014-07-31 | 0 | 2014-03-10 | 2014-07-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-03-10 | 2014-07-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 102 | 101 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.03 | Sensor Electro-Optical (TS3) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [6 empty] | Test Stand Effort | [5 empty] | Science Sensors Test Stands | [8 empty] | Science Sensors
FALSE |  | SR523410 | TS3 - MOTS (miniture optical test stand) system - final design drawing package | LSST Forecast - B57 - B1 | 102 | 0 | 2014-03-10 | 2014-07-31 | 0 | 2014-03-10 | 2014-07-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-03-10 | 2014-07-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 102 | 101 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.03 | Sensor Electro-Optical (TS3) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [6 empty] | Test Stand Effort | [5 empty] | Science Sensors Test Stands | [8 empty] | Science Sensors
FALSE |  | SR522440 | TS2 - MF03 (raft hold down fixture) - final design drawing package | LSST Forecast - B57 - B1 | 46 | 0 | 2014-05-28 | 2014-07-31 | 0 | 2014-05-28 | 2014-07-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-05-28 | 2014-07-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 46 | 45 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.02 | Sensor Dimensional Metrology (TS2) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Science Sensors Test Stands | [8 empty] | Science Sensors
FALSE |  | SR529880 | TS8 - Source optical train layout | LSST Forecast - B57 - B1 | 22 | 0 | 2014-07-01 | 2014-07-31 | 0 | 2014-07-01 | 2014-07-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-07-01 | 2014-07-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 22 | 21 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.05 | RTM Electro-Optical Testing (TS8) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment |  | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering | [14 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 8 - Design |  | Science Raft System
FALSE |  | SR529555 | TS9 - Generate Test Plan - PT2 | LSST Forecast - B57 - B1 | 9 | 0 | 2014-08-01 | 2014-08-13 | 0 | 2014-08-01 | 2014-08-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-08-01 | 2014-08-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 9 | 8 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.07 | Mechanical Test Stand (TS9) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [8 empty] | Science Raft System
FALSE |  | SR330110 | Sensors First Articles - V1 - Back-thin | LSST Forecast - B57 - B1 | 119 | 0 | 2014-08-01 | 2015-01-23 | 0 | 2014-08-01 | 2015-01-23 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2014-08-01 | 2015-01-23 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 119 | 118 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien |  |  |  | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 14% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor | [10 empty] | Sensor
FALSE |  | SR344045 | Procurement of Equipment and Service (Infrastructure items including TS1-TS8 and service contracts) | LSST Forecast - B57 - B1 | 171 | 0 | 2014-08-22 | 2016-04-29 | 0 | 2014-08-22 | 2016-04-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 5 | FALSE | Normal | FALSE | 2014-08-22 | 2015-04-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 5 | 0 | 1 | 4 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 20 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 171 | 422 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.07.01 | Cleanroom Development & Commissioning | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Procurement | [7 empty] | Assembly and Test Facility (TEC) | Test Stand Effort | [5 empty] | Science Raft - Assembly and Test Facility | [6 empty] | Clean Room - Set Up & Assembly |  | Science Raft System
FALSE |  | CRYO60605 | Fab and Assembly - Subscale Test Stand (Elevation Articulation) | LSST Forecast - B57 - B1 | 130 | 0 | 2014-08-23 | 2015-08-15 | 0 | 2014-08-23 | 2015-08-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2014-08-25 | 2015-03-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 15 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 130 | 238 |  | Complete | 100% | 708 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 708 | 708 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 16% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | SR525120 | TS5 - generate final test stand requirements document | LSST Forecast - B57 - B1 | 165 | 0 | 2014-08-29 | 2015-05-28 | 0 | 2014-08-29 | 2015-05-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 5 | FALSE | Normal | FALSE | 2014-08-29 | 2015-04-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 10 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 165 | 185 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.02 | RSA & RTM Warm-Cold Metrology (TS5) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering | [7 empty] | Science Raft - Test Stands (TEC) | Test Stand Effort | [5 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 5 - Design |  | Science Raft System
FALSE |  | CRYO60616 | Test - Subscale Test Stand (Elevation Articulation) | LSST Forecast - B57 - B1 | 129 | 0 | 2014-09-01 | 2015-11-25 | 0 | 2014-09-01 | 2015-11-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2014-09-02 | 2015-03-19 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 40 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 129 | 304 |  | Complete | 100% | 148 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 148 | 148 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 16% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | CRYO60590 | Procurement - Subscale Test Stand (Elevation Articulation) | LSST Forecast - B57 - B1 | 125 | 0 | 2014-09-01 | 2015-08-15 | 0 | 2014-09-01 | 2015-08-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 8000 | 8000 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2014-09-02 | 2015-03-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 15 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 125 | 233 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 8000 | 8000 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 16% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | SR344065 | Installation and Setup of Infrastructure Equipment and TS1-TS3 large equipment | LSST Forecast - B57 - B1 | 139 | 0 | 2014-09-22 | 2015-04-13 | 0 | 2014-09-22 | 2015-04-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2014-09-22 | 2015-04-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 139 | 139 |  | Complete | 100% | 100 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.07.01 | Cleanroom Development & Commissioning | 100 | 100 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Assembly and Test Facility (TEC) | Test Stand Effort | [5 empty] | Science Raft - Assembly and Test Facility | [8 empty] | Science Raft System
FALSE |  | SR345150 | Fab/Assy Raft Electronics Board (DREB2) | LSST Forecast - B57 - B1 | 25 | 0 | 2014-09-29 | 2014-10-31 | 0 | 2014-09-29 | 2014-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-09-29 | 2014-10-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 24 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.04 | Digital Readout Electronics Board (DREB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [8 empty] | Science Raft System
FALSE |  | SR524125 | TS4 - generate prototype measurement test scripts - PT2 | LSST Forecast - B57 - B1 | 58 | 0 | 2014-10-06 | 2014-12-30 | 0 | 2014-10-06 | 2014-12-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-10-06 | 2014-12-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 58 | 57 |  | Complete | 100% | 28 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.01 | RSA Assembly (TS4) | 28 | 28 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | OPC BCR Impact Assessment (LSST ONLY) | Percent Complete on Work Package | OPC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering | [7 empty] | Science Raft - Test Stands (OPC) | Test Stand Effort | [5 empty] | Science Raft - Test Stands | [8 empty] | Science Raft System
FALSE |  | SR552480 | Final Design Drawings - RTM Mechanical | LSST Forecast - B57 - B1 | 196 | 0 | 2014-10-06 | 2016-12-29 | 0 | 2014-10-06 | 2016-12-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2014-10-06 | 2015-07-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 4 | 0 | 1 | 3 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 196 | 559 |  | Complete | 100% | 480 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.01 | Science Raft Tower Module (SRTM) | 480 | 480 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Science Raft Tower Module (SRTM) (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Tower Module |  | Science Raft System
FALSE |  | SR343182 | Firmware for REB3 | LSST Forecast - B57 - B1 | 106 | 0 | 2014-10-13 | 2015-06-26 | 0 | 2014-10-13 | 2015-06-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-10-13 | 2015-03-18 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 106 | 176 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation | [7 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [6 empty] | Raft Electronics Board 3 |  | Science Raft System
FALSE |  | SR343183 | Software for REB3 | LSST Forecast - B57 - B1 | 156 | 0 | 2014-10-13 | 2015-09-22 | 0 | 2014-10-13 | 2015-09-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-10-13 | 2015-05-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 156 | 236 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation | [7 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [6 empty] | Raft Electronics Board 3 |  | Science Raft System
FALSE |  | SR330422 | RCV: First Articles Sensor - V2 - Manufacturing Readiness Review (MRR) | LSST Forecast - B57 - B1 | 1 | 0 | 2014-10-21 | 2014-10-21 | 0 | 2014-10-21 | 2014-10-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 438093 | 438093 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-10-21 | 2014-10-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 438093 | 438093 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 14% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC) | [5 empty] | Sensor | Science Sensors Procurement
FALSE |  | CR241660 | PROC: WGEB mech. model (PCB & components) | LSST Forecast - B57 - B1 | 9 | 0 | 2014-11-01 | 2014-11-13 | 0 | 2014-11-01 | 2014-11-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 1000 | 1000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-11-03 | 2014-11-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 9 | 8 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.02 | Guider Electronics Board (GEB) | 0 | 0 | 0 | 1000 | 1000 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Engineering Test/Validation | [7 empty] | Corner Raft Electronics (TEC) | GEB Prototype
FALSE |  | CR220320 | Design Prototype - corner raft test setup prototype (sidewall, cooling bars, support rods) | LSST Forecast - B57 - B1 | 42 | 0 | 2014-11-06 | 2015-01-10 | 0 | 2014-11-06 | 2015-01-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2014-11-06 | 2015-01-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 42 | 42 |  | Complete | 100% | 160 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 160 | 160 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Tower Module (CRTM) (TEC) | CRTM Prelim Design | [5 empty] | Corner Raft Tower Module (CRTM)
FALSE |  | OP520480 | Procurement Prep - Components for filter frame testing | LSST Forecast - B57 - B1 | 78 | 0 | 2014-12-03 | 2015-02-27 | 0 | 2014-12-03 | 2015-02-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2014-12-03 | 2015-03-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 78 | 57 |  | Complete | 100% | 20 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 20 | 20 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 18% |  | Design/Engineering |  | Commissioning and Testing | [5 empty] | Filters (TEC) | Prototype Filter Assemblies | [5 empty] | Filter Opto-Mechanics
FALSE |  | CRYO60790 | Procurement - Heat Ex Test Stand #2 | LSST Forecast - B57 - B1 | 68 | 0 | 2014-12-10 | 2015-10-01 | 0 | 2014-12-10 | 2015-10-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 52450 | 52450 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-12-10 | 2015-03-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 68 | 196 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 52450 | 52450 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 16% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | CR220420 | Update Camera System Specifications CD-3 - Corner raft tower | LSST Forecast - B57 - B1 | 69 | 0 | 2014-12-15 | 2015-04-15 | 0 | 2014-12-15 | 2015-04-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2014-12-15 | 2015-03-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 20 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 69 | 82 |  | Complete | 100% | 20 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 20 | 20 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Tower Module (CRTM) (TEC) | CRTM Final Design | [5 empty] | Corner Raft Tower Module (CRTM)
Merge Hotspot
The total number of activities with a high number of predecessor links.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | Previous Start | Previous Finish | Percent Complete | Previous Remaining Duration | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | IsLevelOfEffort | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | Global_Basis of Estimate | Global_Cobra Cost Class | Cobra PMT (EV Method)_Global | Global_Color of Money | Global_Control Account Manager | Global_Design Maturity | Global_Judgement Factor | Global_Milestone Levels | Global_Project Phase | Global_Funding Source | Global_EDIA Survey | Global_MS Type | Phase | NSF Milestones | Loading Curve | Sensor Vendor | LSST_CA | Summary Schedule | ICD for NSF Input | LSST Camera Critical Paths | CD2 Budget Changes | DOE Reviews | Critical Path (CD Reviews) | LSST WP Summary | Critical Path (Camera Delivery) | AWARD / NEED Sub-System | Final Design Key Links | CP - CAMM2100 | CP - CAMM2130 | CP - CAMM2160 | BNL Work Org | Last ETC Update | BNL WBS | LSST Story List | Sum Sch 01 (Camera) | Sum Sch 02 (IT w/Needs) | Sum Sch 03 (Sensors_RTM_IT) | LSST Raft Particulate Mitigation | LSST RTM
FALSE |  | SE222075 | Preliminary Filter/Exchange System - Mechanical Integration | LSST Forecast - B57 - B1 | 81 | 0 | 2014-01-03 | 2014-04-30 | 0 | 2014-01-03 | 2014-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2018-10-16 | 2018-10-16 | 0 | 0 | 0 | 0 | 0 | 5 | FALSE | Normal | FALSE | 2014-01-06 | 2014-04-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 81 | 80 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.02 | Mechanical Integration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  |  | Development (includes R&D)
FALSE |  | CRYO11260 | Preliminary Eng & Analysis A - Cryostat Assembly | LSST Forecast - B57 - B1 | 107 | 0 | 2014-03-01 | 2014-07-31 | 0 | 2014-03-01 | 2014-07-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2014-03-03 | 2014-07-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 107 | 106 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | TEC Non-ARRA | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Cryostat Assembly
FALSE |  | SR522475 | TS2 - MF05a (sensor removal fixture) - generate prototype analysis report | LSST Forecast - B57 - B1 | 78 | 0 | 2014-03-24 | 2014-07-11 | 0 | 2014-03-24 | 2014-07-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2014-03-24 | 2014-07-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 2 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 78 | 77 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.02 | Sensor Dimensional Metrology (TS2) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [6 empty] | Test Stand Effort | [5 empty] | Science Sensors Test Stands | [8 empty] | Science Sensors
FALSE |  | CBM22500 | Prep for Prelim Design Review - Camera Body | LSST Forecast - B57 - B1 | 29 | 0 | 2014-04-15 | 2014-05-23 | 0 | 2014-04-15 | 2014-05-23 | 0 | 2019-06-01 | 2019-06-01 | 2018-09-07 | 2018-09-07 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-04-15 | 2014-05-23 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 29 | 28 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.01.02 | Camera Body Development | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | TEC Non-ARRA | Martin Nordby | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Cam Body/Purge Engin/Dsn
FALSE |  | CBM42400 | Prep for Prelim Design Review - Shutter | LSST Forecast - B57 - B1 | 31 | 0 | 2014-04-15 | 2014-05-28 | 0 | 2014-04-15 | 2014-05-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-04-15 | 2014-05-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 31 | 30 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.02.02 | Shutter Development | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | TEC Non-ARRA | Martin Nordby | (1.00) Task/item is fully invoiced/completed | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Shutter Engin/Dsn
FALSE |  | OP520200 | Prep for C_PDR - Filter Assembly | LSST Forecast - B57 - B1 | 48 | 0 | 2014-05-17 | 2014-07-25 | 0 | 2014-05-17 | 2014-07-25 | 0 | 2019-06-01 | 2019-06-01 | 2018-10-30 | 2018-10-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-05-19 | 2014-07-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 2 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 48 | 47 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | OPC Non-ARRA | Scott Winters | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [6 empty] | Filter Design | [5 empty] | Filter Opto-Mechanics
FALSE |  | CAMF650100 | COMP: Ready for PDR - Exchange System | LSST Forecast - B57 - B1 | 0 | 0 | 2014-05-23 | 2014-05-23 | 0 | 2014-05-23 | 2014-05-23 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2014-05-23 | 2014-05-23 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03 | Exchange System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  | Level 3 Milestone | Management/Administration
FALSE |  | OP11050 | Support Prep for C_PDR--Optics - Management (need links to all PDRs) | LSST Forecast - B57 - B1 | 41 | 0 | 2014-05-29 | 2014-07-25 | 0 | 2014-05-29 | 2014-07-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2014-05-29 | 2014-07-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 41 | 40 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.01 | Optics Integration & Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | OPC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Optics System Management
FALSE |  | SR552220 | Documentation - Update Camera Design Manuel (Sensors and RTM chapters) | LSST Forecast - B57 - B1 | 43 | 0 | 2014-06-02 | 2014-07-31 | 0 | 2014-06-02 | 2014-07-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-06-02 | 2014-07-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 43 | 42 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.01 | Science Raft Tower Module (SRTM) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment |  | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering | [14 empty] | Science Raft - Test Stands | [8 empty] | Science Raft System
FALSE |  | SR529900 | Procurement - prototype components | LSST Forecast - B57 - B1 | 22 | 0 | 2014-07-01 | 2014-07-31 | 0 | 2014-07-01 | 2014-07-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-07-01 | 2014-07-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 0 | 4 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 22 | 21 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.05 | RTM Electro-Optical Testing (TS8) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment |  | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering | [14 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 8 - Design |  | Science Raft System
FALSE |  | SR522480 | COMP: TS2 - MF05a (sensor removal fixture) prototype | LSST Forecast - B57 - B1 | 0 | 0 | 2014-07-11 | 2014-07-11 | 0 | 2014-07-11 | 2014-07-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2014-07-11 | 2014-07-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.02 | Sensor Dimensional Metrology (TS2) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Bill Wahl |  |  | Level 4 Milestone | Engineering Test/Validation | [8 empty] | Test Stand Effort | [14 empty] | Science Sensors
FALSE |  | SR343170 | Performance bench test of REB2 | LSST Forecast - B57 - B1 | 14 | 0 | 2014-07-14 | 2014-07-31 | 0 | 2014-07-14 | 2014-07-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-11-19 | 2020-11-19 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-07-14 | 2014-07-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 2 | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 14 | 13 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | TEC Non-ARRA | Bill Wahl | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Engineering Test/Validation | [14 empty] | Science Raft Electronics | [6 empty] | Raft Electronics Board 2 |  | Science Raft System
FALSE |  | OP540180 | C_PDR--L3 Opto-Mechanics | LSST Forecast - B57 - B1 | 2 | 0 | 2014-07-28 | 2014-07-29 | 0 | 2014-07-28 | 2014-07-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-07-28 | 2014-07-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 1 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  |  | Design/Engineering
FALSE |  | CAMF650150 | COMP: Ready for CD-2 - Exchange System | LSST Forecast - B57 - B1 | 0 | 0 | 2014-08-01 | 2014-08-01 | 0 | 2014-08-01 | 2014-08-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2014-08-01 | 2014-08-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03 | Exchange System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  | Level 3 Milestone | Management/Administration
FALSE |  | SR552180 | Documentation - Finalize requirments | LSST Forecast - B57 - B1 | 124 | 0 | 2014-08-01 | 2015-01-30 | 0 | 2014-08-01 | 2015-01-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2014-08-01 | 2015-01-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 4 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 124 | 123 |  | Complete | 100% | 320 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.01 | Science Raft Tower Module (SRTM) | 320 | 320 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Science Raft Tower Module (SRTM) (TEC) | [6 empty] | Science Raft - Test Stands | [8 empty] | Science Raft System
FALSE |  | SR551850 | Prepare RSA Test Plan | LSST Forecast - B57 - B1 | 16 | 0 | 2014-08-01 | 2014-08-22 | 0 | 2014-08-01 | 2014-08-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-08-01 | 2014-08-22 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 16 | 0 | 16 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 16 | 15 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.02 | Science Raft Sensor Assembly (SRSA) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation |  | Construction Management | [5 empty] | Science Raft Tower Module (SRTM) (TEC) | [6 empty] | Science Raft - Test Stands | [8 empty] | Science Raft System
FALSE |  | SR344040 | Final Design and Layout | LSST Forecast - B57 - B1 | 165 | 0 | 2014-08-01 | 2015-03-31 | 0 | 2014-08-01 | 2015-03-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2014-08-01 | 2015-03-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 15 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 165 | 164 |  | Complete | 100% | 160 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.07.01 | Cleanroom Development & Commissioning | 160 | 160 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Assembly and Test Facility (TEC) | [15 empty] | Science Raft System
FALSE |  | CR211120 | Final Update for CD CD-2 - Corner Raft ICD's | LSST Forecast - B57 - B1 | 54 | 0 | 2014-08-01 | 2014-10-16 | 0 | 2014-08-01 | 2014-10-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-08-01 | 2014-10-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 54 | 53 |  | Complete | 100% | 30 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.01 | Corner Raft System Integration and Management | 30 | 30 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft System Integration and Management (TEC) | Management | [5 empty] | Corner Raft System Integration and Management
FALSE |  | CRYO60550 | Prep for Prelim Design Review - Refrigeration System | LSST Forecast - B57 - B1 | 15 | 0 | 2014-08-02 | 2014-08-22 | 0 | 2014-08-02 | 2014-08-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-08-04 | 2014-08-22 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 7 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 14 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | TEC Non-ARRA | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Refrigeration System
FALSE |  | SR530170 | TS7 - generate final test stand requirements document | LSST Forecast - B57 - B1 | 82 | 0 | 2014-08-02 | 2014-11-28 | 0 | 2014-08-02 | 2014-11-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2014-08-04 | 2014-11-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 82 | 82 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.04 | RTM Cryostat Integration (TS7) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 7 - Design |  | Science Raft System
FALSE |  | CRYO11300 | Prep for Preliminary Review - Cryostat Assembly | LSST Forecast - B57 - B1 | 15 | 0 | 2014-08-10 | 2014-08-31 | 0 | 2014-08-10 | 2014-08-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-08-11 | 2014-08-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 15 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Cryostat Assembly
FALSE |  | CRYO21450 | C_PDR - Prelim Design Review - Grid Assembly | LSST Forecast - B57 - B1 | 1 | 0 | 2014-08-24 | 2014-08-24 | 0 | 2014-08-24 | 2014-08-24 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-08-25 | 2014-08-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.04 | Grid Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Brian J. Langton | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Grid Assembly
FALSE |  | SE223060 | Sub-system PDR camera thermal integrated analysis - camera internal & purge | LSST Forecast - B57 - B1 | 137 | 0 | 2014-08-27 | 2015-02-06 | 0 | 2014-08-27 | 2015-02-06 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2014-08-27 | 2015-03-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 137 | 103 |  | Complete | 100% | 200 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.03 | Thermal and contamination system analysis | 200 | 200 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | CR211360 | Prep for C_PDR - Corner Raft | LSST Forecast - B57 - B1 | 20 | 0 | 2014-08-29 | 2014-09-26 | 0 | 2014-08-29 | 2014-09-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-08-29 | 2014-09-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 12 | 0 | 3 | 0 | 0 | 9 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 19 |  | Complete | 100% | 48 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.01 | Corner Raft System Integration and Management | 48 | 48 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft System Integration and Management (TEC) | Management | [5 empty] | Corner Raft System Integration and Management
FALSE |  | OP531670 | RCV: Anti-Reflection Coating Study (Vendor 1) | LSST Forecast - B57 - B1 | 1 | 0 | 2014-08-29 | 2014-08-29 | 0 | 2014-08-29 | 2014-08-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 34686 | 34686 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-08-29 | 2014-08-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 34686 | 34686 | 0 | PercentComplete | 6% | CP_Phys | Existing Lien | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Engineering Test/Validation | [7 empty] | L1-L2 Assembly (TEC)
FALSE |  | ITC24250 | Prep for C_CDR--BOT | LSST Forecast - B57 - B1 | 21 | 0 | 2014-09-01 | 2014-09-30 | 0 | 2014-09-01 | 2014-09-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2014-09-02 | 2014-09-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 2 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 21 | 20 |  | Complete | 100% | 16 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.02.01 | Bench For Optical Testing (BOT) | 16 | 16 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 13% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC) | [6 empty] | Verification Test Systems
FALSE |  | SR552370 | Fabrication - RTM Qualificaiton Unit | LSST Forecast - B57 - B1 | 9 | 0 | 2014-09-05 | 2014-09-17 | 0 | 2014-09-05 | 2014-09-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2014-09-05 | 2014-09-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 13 | 0 | 13 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 9 | 9 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.01 | Science Raft Tower Module (SRTM) | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation |  | R&D | [5 empty] | Science Raft Tower Module (SRTM) (TEC) | [6 empty] | Science Raft - Test Stands | [8 empty] | Science Raft System
FALSE |  | CRYO13325 | COMP: Preliminary Design/Analysis - Cryostat Housing | LSST Forecast - B57 - B1 | 0 | 0 | 2014-09-15 | 2014-09-15 | 0 | 2014-09-15 | 2014-09-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2014-09-15 | 2014-09-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.01 | Cryostat Housing | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Design/Engineering
FALSE |  | ITC22080 | Prep for C_CDR--MTF | LSST Forecast - B57 - B1 | 11 | 0 | 2014-09-16 | 2014-09-30 | 0 | 2014-09-16 | 2014-09-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2014-09-16 | 2014-09-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 11 | 10 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.01.03 | Vacuum Qualification Tests | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC) | [6 empty] | Verification Test Systems
FALSE |  | CR240200 | Prep for Prelim Design Review - WEB | LSST Forecast - B57 - B1 | 5 | 0 | 2014-09-22 | 2014-09-26 | 0 | 2014-09-22 | 2014-09-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-09-22 | 2014-09-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 4 |  | Complete | 100% | 48 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.01 | Wavefront Electronics Board (WEB) | 48 | 48 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Design Reviews | [5 empty] | Corner Raft Electronics (TEC) | WEB Prototype | [5 empty] | Corner Raft Electronics
FALSE |  | CR241580 | Prep for Prelim Design Review - GEB | LSST Forecast - B57 - B1 | 5 | 0 | 2014-09-22 | 2014-09-26 | 0 | 2014-09-22 | 2014-09-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-09-22 | 2014-09-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 4 |  | Complete | 100% | 48 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.02 | Guider Electronics Board (GEB) | 48 | 48 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Design Reviews | [5 empty] | Corner Raft Electronics (TEC) | GEB Prototype | [5 empty] | Corner Raft Electronics
FALSE |  | CR234130 | Prep for C_PDR - Wavefront Sensor | LSST Forecast - B57 - B1 | 5 | 0 | 2014-09-22 | 2014-09-26 | 0 | 2014-09-22 | 2014-09-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-09-22 | 2014-09-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 3 | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 4 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.02 | Wavefront Sensor | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | WFS Mech Design |  | Critical Path #3 |  |  |  | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CR235115 | Prep for Prelim Design Review - Guide Sensor | LSST Forecast - B57 - B1 | 5 | 0 | 2014-09-22 | 2014-09-26 | 0 | 2014-09-22 | 2014-09-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-09-22 | 2014-09-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 4 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 4 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.03 | Guide Sensors | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Design Reviews | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | Guide Prelim Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CR230210 | Prep for C_PDR - Corner raft sensor assembly | LSST Forecast - B57 - B1 | 5 | 0 | 2014-09-22 | 2014-09-26 | 0 | 2014-09-22 | 2014-09-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-09-22 | 2014-09-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 13 | 0 | 2 | 0 | 0 | 11 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 4 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Prelim Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CR220260 | Prep for C_PDR - Corner raft tower | LSST Forecast - B57 - B1 | 5 | 0 | 2014-09-22 | 2014-09-26 | 0 | 2014-09-22 | 2014-09-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-09-22 | 2014-09-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 1 | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 4 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Tower Module (CRTM) (TEC) | CRTM Prelim Design | [5 empty] | Corner Raft Tower Module (CRTM)
FALSE |  | CRYO00200 | COMP: Ready for CD-2 - Cryostat | LSST Forecast - B57 - B1 | 0 | 0 | 2014-09-29 | 2014-09-29 | 0 | 2014-09-29 | 2014-09-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 13 | FALSE | Finish Milestone | FALSE | 2014-09-29 | 2014-09-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 9 | 0 | 9 | 0 | 0 | 0 | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04 | Cryostat | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 3 Milestone | Management/Administration
FALSE |  | CR211400 | COMP: C_PDR - Corner Raft | LSST Forecast - B57 - B1 | 0 | 0 | 2014-10-01 | 2014-10-01 | 0 | 2014-10-01 | 2014-10-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 6 | FALSE | Finish Milestone | FALSE | 2014-10-01 | 2014-10-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 0 | 0 | 0 | 5 | 6 | 0 | 5 | 0 | 0 | 1 | 0 | 0 | 4 | 0 | 0 | 140 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.01 | Corner Raft System Integration and Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 4 Milestone | Design/Engineering | [8 empty] | Management
FALSE |  | SE222090 | Prelim Design - Analyze Interfaces & Impacts - SE | LSST Forecast - B57 - B1 | 3 | 0 | 2014-10-01 | 2014-10-03 | 0 | 2014-10-01 | 2014-10-03 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-10-01 | 2014-10-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 3 | 2 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.02 | Mechanical Integration | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Design Management | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | SR523460 | Prep for C_FDR--TS3 | LSST Forecast - B57 - B1 | 22 | 0 | 2014-10-01 | 2014-10-30 | 0 | 2014-10-01 | 2014-10-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-10-01 | 2014-10-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 13 | 0 | 12 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 22 | 21 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.03 | Sensor Electro-Optical (TS3) | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Design Reviews | [5 empty] | Science Sensors Test Stands (TEC) | Test Stand Effort | [5 empty] | Science Sensors Test Stands | [8 empty] | Science Sensors
FALSE |  | ITC10150 | C_PDR - I&T | LSST Forecast - B57 - B1 | 2 | 0 | 2014-10-15 | 2014-10-16 | 0 | 2014-10-15 | 2014-10-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-10-15 | 2014-10-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 1 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.01 | I&T Integration & Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  |  | Management/Administration |  |  |  | Engineering
FALSE |  | CAM112475 | COMP: Design Ready for CD-2 | LSST Forecast - B57 - B1 | 0 | 0 | 2014-10-16 | 2014-10-16 | 0 | 2014-10-16 | 2014-10-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2014-10-16 | 2014-10-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 12 | 0 | 12 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01.01.02 | Reviews & Collaboration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Vincent Riot | (1.10) Task/item is a modification of an existing design | 0% | Level 4 Milestone | Management/Administration | [12 empty] | CD-3a | Critical Path to CD-2 | Project Management
FALSE |  | CRYO11450 | Finalize Design Phase 1 - Cryostat Assembly | LSST Forecast - B57 - B1 | 122 | 0 | 2014-10-17 | 2015-05-08 | 0 | 2014-10-17 | 2015-05-08 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2014-10-17 | 2015-04-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 122 | 131 |  | Complete | 100% | 128 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 128 | 128 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Housing & Assembly (TEC) |  | ICD's for Phase 3 |  |  |  |  | Cryostat Assembly |  |  | Final Design Link
FALSE |  | CRYO16550 | Finalize Design - Cryo Plate & Cold Plate | LSST Forecast - B57 - B1 | 110 | 0 | 2014-10-17 | 2015-06-07 | 0 | 2014-10-17 | 2015-06-07 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 5 | FALSE | Normal | FALSE | 2014-10-17 | 2015-04-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 5 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 20 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 110 | 151 |  | Complete | 100% | 634 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.03 | Cryo and Cold Plates | 634 | 634 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryo and Cold Plates (TEC) | [6 empty] | Cryo and Cold Plates
FALSE |  | CAM112480 | COMP: CD-2 DOE/SC Review - Doc Sumbitted | LSST Forecast - B57 - B1 | 0 | 0 | 2014-10-17 | 2014-10-17 | 0 | 2014-10-17 | 2014-10-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2014-10-17 | 2014-10-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 9 | 0 | 9 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01.01.02 | Reviews & Collaboration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Vincent Riot | (1.10) Task/item is a modification of an existing design | 0% | Level 4 Milestone | Management/Administration | [12 empty] | CD-3a | Critical Path to CD-3a | Project Management
FALSE |  | CRYO21600 | Finalize Analysis - Grid Assembly | LSST Forecast - B57 - B1 | 144 | 0 | 2014-10-19 | 2015-06-07 | 0 | 2014-10-19 | 2015-06-07 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 5 | FALSE | Normal | FALSE | 2014-10-20 | 2015-05-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 5 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 144 | 150 |  | Complete | 100% | 224 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.04 | Grid Assembly | 224 | 224 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Grid Assembly (TEC) | [6 empty] | Grid Assembly
FALSE |  | SR530330 | Procurement - Prototype material | LSST Forecast - B57 - B1 | 127 | 0 | 2014-10-27 | 2015-05-27 | 0 | 2014-10-27 | 2015-05-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-10-27 | 2015-04-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 3 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 127 | 144 |  | Complete | 100% | 8 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.03 | RTM Assembly (TS6) | 8 | 8 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 6 - Procurement & Fabrication |  | Science Raft System
FALSE |  | SR522695 | COMP: TS2 - MF02 (Platen Baseplate for OGP) | LSST Forecast - B57 - B1 | 0 | 0 | 2014-10-30 | 2014-10-30 | 0 | 2014-10-30 | 2014-10-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2014-10-30 | 2014-10-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.02 | Sensor Dimensional Metrology (TS2) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl |  |  | Level 4 Milestone | Fabrication/Assembly | [8 empty] | Test Stand Effort | [14 empty] | Science Sensors
FALSE |  | SR522430 | COMP: TS2 - MF03 (raft hold down fixture) prototype | LSST Forecast - B57 - B1 | 0 | 0 | 2014-10-31 | 2014-10-31 | 0 | 2014-10-31 | 2014-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2014-10-31 | 2014-10-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.02 | Sensor Dimensional Metrology (TS2) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl |  |  | Level 4 Milestone | Engineering Test/Validation | [8 empty] | Test Stand Effort | [14 empty] | Science Sensors
FALSE |  | SR523590 | RCV: Test Stand TS3 fabrication (dewar+xray arm+MOTS)(2 units) | LSST Forecast - B57 - B1 | 0 | 0 | 2014-10-31 | 2014-10-31 | 0 | 2014-10-31 | 2014-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2014-10-31 | 2014-10-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.03 | Sensor Electro-Optical (TS3) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl |  |  | Level 4 Milestone | Fabrication/Assembly | [8 empty] | Test Stand Effort | [14 empty] | Science Sensors
FALSE |  | ITC24210 | Develop BOT prototype plans and design | LSST Forecast - B57 - B1 | 19 | 0 | 2014-11-01 | 2014-12-01 | 0 | 2014-11-01 | 2014-12-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-11-03 | 2014-12-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 19 | 18 |  | Complete | 100% | 85 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.02.01 | Bench For Optical Testing (BOT) | 85 | 85 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 13% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC) | [6 empty] | Verification Test Systems
FALSE |  | CAM112500 | CD-2 DOE/SC Review | LSST Forecast - B57 - B1 | 3 | 0 | 2014-11-04 | 2014-11-06 | 0 | 2014-11-04 | 2014-11-06 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2014-11-04 | 2014-11-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 3 | 2 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01.01.02 | Reviews & Collaboration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Vincent Riot | (1.10) Task/item is a modification of an existing design | 0% |  | Management/Administration | [12 empty] | CD-3a | Critical Path to CD-3a | Project Management
FALSE |  | CCS104400 | Update console for new command structure (LSSTCCS-156) - Core 1.6 | LSST Forecast - B57 - B1 | 22 | 0 | 2014-11-11 | 2014-12-14 | 0 | 2014-11-11 | 2014-12-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-11-11 | 2014-12-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 22 | 22 |  | Complete | 100% | 140 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.02.02 | CCS Core 1.6 Release | 140 | 140 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering | [7 empty] | CCS Core (TEC)
FALSE |  | SR521130 | Prep for C_FDR--TS1 | LSST Forecast - B57 - B1 | 100 | 0 | 2014-11-17 | 2015-05-14 | 0 | 2014-11-17 | 2015-05-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-11-17 | 2015-04-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 100 | 121 |  | Complete | 100% | 8 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.01 | Sensor Receiving & Inspection (TS1) - eLog, eTraveler | 8 | 8 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Design Reviews | [5 empty] | Science Sensors Test Stands (TEC) | [6 empty] | Science Sensors Test Stands | [6 empty] | Test Stand 1 - Reviews |  | Science Sensors
FALSE |  | SR522570 | Prep for C_FDR--TS2 | LSST Forecast - B57 - B1 | 112 | 0 | 2014-11-17 | 2015-05-22 | 0 | 2014-11-17 | 2015-05-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2014-11-17 | 2015-04-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 15 | 0 | 12 | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 112 | 127 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.02 | Sensor Dimensional Metrology (TS2) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Design Reviews | [5 empty] | Science Sensors Test Stands (TEC) | [6 empty] | Science Sensors Test Stands | [6 empty] | Test Stand 2 - Reviews | Baseline | Science Sensors
FALSE |  | CCS115600 | COMP: TS3 Prototype Test-Stand Delivered | LSST Forecast - B57 - B1 | 0 | 0 | 2014-11-26 | 2014-11-26 | 0 | 2014-11-26 | 2014-11-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2014-11-26 | 2014-11-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.01.03 | Test Stand 3 (Reflex/Archon Controller Based) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  | Level 4 Milestone | Design/Engineering
FALSE |  | CRYO13500 | Finalize Design - Cryostat Housing | LSST Forecast - B57 - B1 | 93 | 0 | 2014-12-01 | 2015-05-05 | 0 | 2014-12-01 | 2015-05-05 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 5 | FALSE | Normal | FALSE | 2014-12-01 | 2015-04-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 5 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 93 | 99 |  | Complete | 100% | 522 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.01 | Cryostat Housing | 522 | 522 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Housing & Assembly (TEC) | [6 empty] | Cryostat Housing
FALSE |  | CRYO21550 | Finalize Design - Grid Assembly | LSST Forecast - B57 - B1 | 112 | 0 | 2014-12-05 | 2015-06-07 | 0 | 2014-12-05 | 2015-06-07 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 7 | FALSE | Normal | FALSE | 2014-12-05 | 2015-05-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 7 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 20 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 112 | 118 |  | Complete | 100% | 194 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.04 | Grid Assembly | 194 | 194 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Grid Assembly (TEC) | [6 empty] | Grid Assembly
FALSE |  | CCS104700 | COMP: CCS Core 1.6.0 | LSST Forecast - B57 - B1 | 0 | 0 | 2014-12-15 | 2014-12-15 | 0 | 2014-12-15 | 2014-12-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2014-12-15 | 2014-12-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.02.02 | CCS Core 1.6 Release | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  | Level 4 Milestone | Design/Engineering
FALSE |  | SR551910 | RSA base plate thermal characterization | LSST Forecast - B57 - B1 | 83 | 0 | 2014-12-15 | 2015-05-08 | 0 | 2014-12-15 | 2015-05-08 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2014-12-15 | 2015-04-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 83 | 99 |  | Complete | 100% | 160 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.02 | Science Raft Sensor Assembly (SRSA) | 160 | 160 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation |  | R&D | [5 empty] | Science Raft Tower Module (SRTM) (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Sensor Assembly |  | Science Raft System
FALSE |  | SE223145 | System engineering contamination final design inputs for optics throughput | LSST Forecast - B57 - B1 | 62 | 0 | 2014-12-15 | 2015-06-26 | 0 | 2014-12-15 | 2015-06-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2014-12-15 | 2015-03-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 62 | 126 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.03 | Thermal and contamination system analysis | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | SE223140 | Sub-system FDR camera subsystem definition of contamination and material requirements | LSST Forecast - B57 - B1 | 62 | 0 | 2014-12-15 | 2015-10-16 | 0 | 2014-12-15 | 2015-10-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 7 | FALSE | Normal | FALSE | 2014-12-15 | 2015-03-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 7 | 0 | 4 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 62 | 204 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.03 | Thermal and contamination system analysis | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis

## 2015 Details
Fuse® Analyst Report
Workbook: Workbook1 - 8168 Activities
Schedule Quality
Created on: 8/5/2019
Created by: brackett
2015: Detailed View | 2015: Detailed View | 2015: Detailed View
Number of Lags
Total number of activities that have lags in their predecessors. This number should not exceed 5%.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | Previous Start | Previous Finish | Percent Complete | Previous Remaining Duration | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | IsLevelOfEffort | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | Global_Basis of Estimate | Global_Cobra Cost Class | Cobra PMT (EV Method)_Global | Global_Color of Money | Global_Control Account Manager | Global_Design Maturity | Global_Judgement Factor | Global_Milestone Levels | Global_Project Phase | Global_Funding Source | Global_EDIA Survey | Global_MS Type | Phase | NSF Milestones | Loading Curve | Sensor Vendor | LSST_CA | Summary Schedule | ICD for NSF Input | LSST Camera Critical Paths | CD2 Budget Changes | DOE Reviews | Critical Path (CD Reviews) | LSST WP Summary | Critical Path (Camera Delivery) | AWARD / NEED Sub-System | Final Design Key Links | CP - CAMM2100 | CP - CAMM2130 | CP - CAMM2160 | BNL Work Org | Last ETC Update | BNL WBS | LSST Story List | Sum Sch 01 (Camera) | Sum Sch 02 (IT w/Needs) | Sum Sch 03 (Sensors_RTM_IT) | LSST Raft Particulate Mitigation | LSST RTM
FALSE |  | CRYO60640 | Procurement - Subscale Test Stand (Second CRYO) | LSST Forecast - B57 - B1 | 80 | 0 | 2015-01-15 | 2015-09-22 | 0 | 2015-01-15 | 2015-09-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 81750 | 81750 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-01-15 | 2015-05-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 80 | 173 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 81750 | 81750 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 16% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | SR344060 | Assembly & Test Facility Personel Development | LSST Forecast - B57 - B1 | 106 | 0 | 2015-01-19 | 2015-07-15 | 0 | 2015-01-19 | 2015-07-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-01-20 | 2015-06-18 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 106 | 123 |  | Complete | 100% | 221 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.07.01 | Cleanroom Development & Commissioning | 221 | 221 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Assembly and Test Facility (TEC) | Test Stand Effort | [5 empty] | Science Raft - Assembly and Test Facility | [6 empty] | Clean Room - Set Up & Assembly |  | Science Raft System
FALSE |  | OP520360 | PROC: Procure parts for filter frame test units | LSST Forecast - B57 - B1 | 26 | 0 | 2015-02-06 | 2015-03-24 | 0 | 2015-02-06 | 2015-03-24 | 0 | 2019-06-01 | 2019-06-01 | 2018-10-30 | 2018-10-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-03-02 | 2015-04-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 26 | 31 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 22% |  | Design/Engineering |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Filters (TEC) | Prototype Filter Assemblies | [5 empty] | Filter Opto-Mechanics
FALSE |  | CR230260 | Final Design & Analysis - Corner raft sensor assembly (Mechanical Aspect) | LSST Forecast - B57 - B1 | 52 | 0 | 2015-02-13 | 2016-02-19 | 0 | 2015-02-13 | 2016-02-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2015-03-30 | 2015-06-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 52 | 247 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | SR414200 | NEED: CCS-DAQ (DAQ V0.0 GEN 1 Multi REB) | LSST Forecast - B57 - B1 | 0 | 0 | 2015-02-16 | 2015-02-16 | 0 | 2015-02-16 | 2015-02-16 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2015-05-01 | 2015-05-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.04 | Raft Optimization And Readout (ROAR) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% | Level 5 Milestone | Engineering Test/Validation | [23 empty] | Science Raft System
FALSE |  | CR230300 | Final Design & Analysis - Wavefront Sensor jig removal fixture | LSST Forecast - B57 - B1 | 60 | 0 | 2015-02-23 | 2015-08-14 | 0 | 2015-02-23 | 2015-08-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-03-30 | 2015-06-22 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 30 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 122 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CR230310 | Final Design & Analysis - Wavefront Sensor protective cover | LSST Forecast - B57 - B1 | 60 | 0 | 2015-02-23 | 2015-08-14 | 0 | 2015-02-23 | 2015-08-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-03-30 | 2015-06-22 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 30 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 122 |  | Complete | 100% | 15 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 15 | 15 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CCS111100 | Procurement Process - Parts - eTraveler test stand Hardware | LSST Forecast - B57 - B1 | 20 | 0 | 2015-03-01 | 2015-04-12 | 0 | 2015-03-01 | 2015-04-12 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-04-01 | 2015-04-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 10 | 10 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 30 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.10 | E Manufacturing | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  |  | Procurement
FALSE |  | CRYO60810 | Test - Heat Ex Test Stand #2 | LSST Forecast - B57 - B1 | 65 | 0 | 2015-03-12 | 2015-10-27 | 0 | 2015-03-12 | 2015-10-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-05-12 | 2015-08-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 65 | 160 |  | Complete | 100% | 213 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 213 | 213 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 16% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | SR330424 | RCV: First Articles Sensor - V2 - Test Readiness Review (TRR) | LSST Forecast - B57 - B1 | 1 | 0 | 2015-03-12 | 2015-03-12 | 0 | 2015-03-12 | 2015-03-12 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 438093 | 438093 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-03-12 | 2015-03-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 1 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 438093 | 438093 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 14% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC) | Sensor Delivery |  |  |  |  | Sensor | Science Sensors Procurement
FALSE |  | SR342220 | Design Review - CABAC 2 | LSST Forecast - B57 - B1 | 3 | 0 | 2015-03-16 | 2015-03-18 | 0 | 2015-03-16 | 2015-03-18 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-04-01 | 2015-04-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 3 | 2 |  | Complete | 100% | 32 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.02 | CABAC | 32 | 32 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation |  | Design Reviews | [5 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [8 empty] | Science Raft System
FALSE |  | CR220440 | Update Camera System Specifications CD-3 - Corner raft tower tooling (Cage Holding Struct, Board Insert Fix, Trans Cart) | LSST Forecast - B57 - B1 | 10 | 0 | 2015-03-16 | 2015-05-29 | 0 | 2015-03-16 | 2015-05-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-04-01 | 2015-04-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 53 |  | Complete | 100% | 36 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 36 | 36 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Tower Module (CRTM) (TEC) | CRTM Final Design | [5 empty] | Corner Raft Tower Module (CRTM)
FALSE |  | CR220460 | Update Camera System Specifications CD-3 - Shipping Container | LSST Forecast - B57 - B1 | 22 | 0 | 2015-03-16 | 2015-05-29 | 0 | 2015-03-16 | 2015-05-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-03-16 | 2015-04-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 22 | 53 |  | Complete | 100% | 32 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 32 | 32 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Tower Module (CRTM) (TEC) | CRTM Final Design | [5 empty] | Corner Raft Tower Module (CRTM)
FALSE |  | CR230290 | Final Design & Analysis - CRSA protective cover | LSST Forecast - B57 - B1 | 60 | 0 | 2015-03-23 | 2015-08-14 | 0 | 2015-03-23 | 2015-08-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-06-10 | 2015-09-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 90 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 102 |  | Complete | 100% | 15 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 15 | 15 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CR230320 | Final Design & Analysis - Wavefront Sensor insertion tool | LSST Forecast - B57 - B1 | 60 | 0 | 2015-03-23 | 2015-08-14 | 0 | 2015-03-23 | 2015-08-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-05-27 | 2015-08-19 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 45 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 102 |  | Complete | 100% | 20 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 20 | 20 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | OP520540 | Assemble test filter frame | LSST Forecast - B57 - B1 | 15 | 0 | 2015-03-30 | 2015-04-22 | 0 | 2015-03-30 | 2015-04-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-04-01 | 2015-04-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 17 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 18% |  | Design/Engineering |  | Commissioning and Testing | [5 empty] | Filters (TEC) | Prototype Filter Assemblies | [5 empty] | Filter Opto-Mechanics
FALSE |  | SR330140 | RCV: First Articles Sensor - V1 - Test Readiness Review (TRR) | LSST Forecast - B57 - B1 | 1 | 0 | 2015-03-30 | 2015-03-30 | 0 | 2015-03-30 | 2015-03-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 735000 | 735000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-03-30 | 2015-03-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 1 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 735000 | 735000 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 14% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC) | Sensor Delivery |  |  |  |  | Sensor | Science Sensors Procurement
FALSE |  | CCS111200 | Vendor Lead Time - Parts - eTraveler test stand Hardware | LSST Forecast - B57 - B1 | 21 | 0 | 2015-04-01 | 2015-04-29 | 0 | 2015-04-01 | 2015-04-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-05-01 | 2015-06-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 10 | 10 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 21 | 20 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.10 | E Manufacturing | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  |  | Procurement
FALSE |  | SR330200 | Prepare Award Documents - Production Lot 1 Sensors V1 (Option 1) | LSST Forecast - B57 - B1 | 10 | 0 | 2015-04-01 | 2015-04-16 | 0 | 2015-04-01 | 2015-04-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-04-01 | 2015-04-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 11 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien |  |  |  | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 14% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [8 empty] | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Sensor
FALSE |  | CR234230 | AWARD: Contract - First article 2Kx4K Wavefront Sensor w package (2+3 2kx4k sensors) | LSST Forecast - B57 - B1 | 1 | 0 | 2015-04-03 | 2015-04-03 | 0 | 2015-04-03 | 2015-04-03 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 1539764 | 1539764 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-05-01 | 2015-05-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.02 | Wavefront Sensor | 0 | 0 | 0 | 1539764 | 1539764 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | B1 Procurement Commitment (C5.1) |  | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 1% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | [6 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CR230330 | Final Design & Analysis - CRSA Warm-Cold Metrology - test stand | LSST Forecast - B57 - B1 | 60 | 0 | 2015-04-06 | 2015-08-14 | 0 | 2015-04-06 | 2015-08-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-04-06 | 2015-06-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 30 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 92 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | SE222210 | Final grid/cryostat - Check & Update IDD | LSST Forecast - B57 - B1 | 11 | 0 | 2015-04-08 | 2015-05-29 | 0 | 2015-04-08 | 2015-05-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 7 | FALSE | Normal | FALSE | 2015-05-01 | 2015-05-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 0 | 4 | 0 | 0 | 7 | 0 | 6 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 11 | 36 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.02 | Mechanical Integration | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | CCS111300 | RCV: Components - Parts - eTraveler test stand Hardware | LSST Forecast - B57 - B1 | 20 | 0 | 2015-04-15 | 2015-04-30 | 0 | 2015-04-15 | 2015-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 20000 | 20000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-05-15 | 2015-06-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 11 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.10 | E Manufacturing | 0 | 0 | 0 | 20000 | 20000 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Procurement | [7 empty] | CCS Core (TEC) | [6 empty] | Shutter Engin/Dsn
FALSE |  | SR530220 | COMP: TS7 part, assy dwg's complete | LSST Forecast - B57 - B1 | 0 | 0 | 2015-04-29 | 2015-04-29 | 0 | 2015-04-29 | 2015-04-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2015-05-12 | 2015-05-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.04 | RTM Cryostat Integration (TS7) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% | Level 4 Milestone | Design/Engineering | [14 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 7 - Design |  | Science Raft System
FALSE |  | CR230450 | RELEASE: RFP - First Article Corner Rafts Baseplate (1 unit) | LSST Forecast - B57 - B1 | 1 | 0 | 2015-05-04 | 2015-05-04 | 0 | 2015-05-04 | 2015-05-04 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-06-01 | 2015-06-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  |  | Procurement | [8 empty] | CRSA Prototype (Baseplate)
FALSE |  | CR211620 | Generate Wavefront sensors final performance allocation budgets - Corner Raft | LSST Forecast - B57 - B1 | 60 | 0 | 2015-05-14 | 2016-02-05 | 0 | 2015-05-14 | 2016-02-05 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-06-01 | 2015-08-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 175 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.01 | Corner Raft System Integration and Management | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft System Integration and Management (TEC) | Management | [5 empty] | Corner Raft System Integration and Management
FALSE |  | CR211640 | Generate guide sensors final performance allocation budgets - Corner Raft | LSST Forecast - B57 - B1 | 49 | 0 | 2015-05-14 | 2016-02-05 | 0 | 2015-05-14 | 2016-02-05 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-06-01 | 2015-08-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 49 | 175 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.01 | Corner Raft System Integration and Management | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft System Integration and Management (TEC) | Management | [5 empty] | Corner Raft System Integration and Management
FALSE |  | CR211660 | Generate Wavefront sensors chain final integrated test plan - Corner Raft | LSST Forecast - B57 - B1 | 60 | 0 | 2015-05-14 | 2016-02-05 | 0 | 2015-05-14 | 2016-02-05 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-06-01 | 2015-08-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 175 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.01 | Corner Raft System Integration and Management | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft System Integration and Management (TEC) | Management | [5 empty] | Corner Raft System Integration and Management
FALSE |  | SR330210 | AWARD: Production Lot 1 Sensors Procurement - Vendor 1 | LSST Forecast - B57 - B1 | 0 | 0 | 2015-05-21 | 2015-05-21 | 0 | 2015-05-21 | 2015-05-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 5400000 | 5400000 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2015-06-01 | 2015-06-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 5400000 | 5400000 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien | B1 Procurement Commitment (C5.1) |  | TEC Non-ARRA | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 14% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Sensor | Science Sensors Procurement |  |  |  |  | CP - CAMM2130 (Award of Sensor Lot #2) |  | Sensors Vendor 1
FALSE |  | CR241780 | Functional Testing - WGEB Protoype (Guider mode) | LSST Forecast - B57 - B1 | 20 | 0 | 2015-06-01 | 2015-06-19 | 0 | 2015-06-01 | 2015-06-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2015-08-13 | 2015-09-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 20 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 14 |  | Complete | 100% | 100 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.02 | Guider Electronics Board (GEB) | 100 | 100 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Engineering Test/Validation | [7 empty] | Corner Raft Electronics (TEC) | GEB Prototype
FALSE |  | CR230580 | Generate Final Drawings - CRSA Warm-Cold Metrology - test stand | LSST Forecast - B57 - B1 | 60 | 0 | 2015-06-01 | 2015-09-30 | 0 | 2015-06-01 | 2015-09-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-10-01 | 2016-01-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 85 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | SE222280 | Final Design - Analyze Interfaces & Impacts - SE | LSST Forecast - B57 - B1 | 5 | 0 | 2015-06-01 | 2015-06-10 | 0 | 2015-06-01 | 2015-06-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-13 | 2019-09-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-07-01 | 2015-07-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 7 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.02 | Mechanical Integration | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | CR240520 | Performance validation with single CCD - WGEB Prototype (WF mode) | LSST Forecast - B57 - B1 | 40 | 0 | 2015-06-08 | 2015-06-30 | 0 | 2015-06-08 | 2015-06-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-07-01 | 2015-08-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 27 | 27 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 16 |  | Complete | 100% | 340 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.01 | Wavefront Electronics Board (WEB) | 340 | 340 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering | [7 empty] | Corner Raft Electronics (TEC) | WEB Prototype
FALSE |  | CR230280 | Final Design & Analysis - Corner raft sensor assembly (Instrumental Aspect) | LSST Forecast - B57 - B1 | 86 | 0 | 2015-06-12 | 2015-09-30 | 0 | 2015-06-12 | 2015-09-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2015-07-01 | 2015-10-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 86 | 76 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CRYO60625 | Test - Subscale Depluggling Test | LSST Forecast - B57 - B1 | 60 | 0 | 2015-06-15 | 2015-08-25 | 0 | 2015-06-15 | 2015-08-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-06-15 | 2015-09-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 50 |  | Complete | 100% | 200 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 200 | 200 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 16% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | CRYO16900 | Check and Release Detail and Assembly Drawings - Cryo & Cold Plate | LSST Forecast - B57 - B1 | 60 | 0 | 2015-06-22 | 2015-10-29 | 0 | 2015-06-22 | 2015-10-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2015-07-17 | 2015-10-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 91 |  | Complete | 100% | 300 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.03 | Cryo and Cold Plates | 300 | 300 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryo and Cold Plates (TEC) | [6 empty] | Cryo and Cold Plates
FALSE |  | OP530600 | L2 Lens Substrate Arrives at AOS - L1-L2 Assembly - Phase 3 | LSST Forecast - B57 - B1 | 25 | 0 | 2015-06-26 | 2015-06-30 | 0 | 2015-06-26 | 2015-06-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-03 | 2019-09-03 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-07-01 | 2015-08-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 2 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Scott Winters | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor | [5 empty] | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly) |  |  |  | L1-L2 Opto-Mechanics
FALSE |  | CCS124820 | Vendor Lead Time - Parts - Shutter HCU | LSST Forecast - B57 - B1 | 30 | 0 | 2015-06-30 | 2015-09-04 | 0 | 2015-06-30 | 2015-09-04 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-06 | 2019-08-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-01-04 | 2016-02-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 10 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 47 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.06 | Shutter HCU | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  |  | Engineering Test/Validation
FALSE |  | CCS124830 | RCV: Components - Parts - Shutter HCU | LSST Forecast - B57 - B1 | 20 | 0 | 2015-08-01 | 2015-09-16 | 0 | 2015-08-01 | 2015-09-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-06 | 2019-08-06 | 4000 | 4000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-09-01 | 2015-09-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 31 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.06 | Shutter HCU | 0 | 0 | 0 | 4000 | 4000 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Engineering Test/Validation | [7 empty] | CCS HCU (TEC) | [6 empty] | Shutter Engin/Dsn
FALSE |  | CCS207500 | Generate XML files for OCS V3 release - CCS/OCS | LSST Forecast - B57 - B1 | 10 | 0 | 2015-08-01 | 2015-10-13 | 0 | 2015-08-01 | 2015-10-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-17 | 2019-10-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-09-01 | 2015-09-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 50 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.04 | CCS/OCS Bridge | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Testing/Integration | [7 empty] | CCS Core (TEC)
FALSE |  | CRYO60750 | Fab and Assembly - Subscale Test Stand (Final Details) | LSST Forecast - B57 - B1 | 50 | 0 | 2015-08-05 | 2016-02-19 | 0 | 2015-08-05 | 2016-02-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-02-02 | 2016-04-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 10 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 50 | 127 |  | Complete | 100% | 430 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 430 | 430 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 16% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | CR220700 | Design prototype - corner raft test setup EM revision (sidewall, cooling bars, support rods) | LSST Forecast - B57 - B1 | 15 | 0 | 2015-08-07 | 2015-10-05 | 0 | 2015-08-07 | 2015-10-05 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2015-08-06 | 2015-08-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 40 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Tower Module (CRTM) (TEC) | CRTM Prototype EM Revision | [5 empty] | Corner Raft Tower Module (CRTM)
FALSE |  | CR230540 | Generate Final Drawings - CRSA protective cover | LSST Forecast - B57 - B1 | 60 | 0 | 2015-08-17 | 2015-08-28 | 0 | 2015-08-17 | 2015-08-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-09-01 | 2015-11-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 9 |  | Complete | 100% | 60 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 60 | 60 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CR230550 | Generate Final Drawings - Wavefront Sensor jig removal fixture | LSST Forecast - B57 - B1 | 60 | 0 | 2015-08-17 | 2015-08-28 | 0 | 2015-08-17 | 2015-08-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-10-01 | 2016-01-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 9 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CR230560 | Generate Final Drawings - Wavefront Sensor protective cover | LSST Forecast - B57 - B1 | 10 | 0 | 2015-08-17 | 2015-08-28 | 0 | 2015-08-17 | 2015-08-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-08-17 | 2015-08-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 10 |  | Complete | 100% | 60 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 60 | 60 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CR230570 | Generate Final Drawings - Wavefront Sensor insertion tool | LSST Forecast - B57 - B1 | 60 | 0 | 2015-08-28 | 2015-09-30 | 0 | 2015-08-28 | 2015-09-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-08-28 | 2015-11-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 22 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CRYO60740 | Procurement - Subscale Test Stand (Final Details) | LSST Forecast - B57 - B1 | 40 | 0 | 2015-10-01 | 2015-11-08 | 0 | 2015-10-01 | 2015-11-08 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 21000 | 21000 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-11-02 | 2016-01-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 10 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 27 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 21000 | 21000 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 16% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | CRYO60745 | Procurement - Refrigerant (4 Recharges) | LSST Forecast - B57 - B1 | 40 | 0 | 2015-10-01 | 2015-10-26 | 0 | 2015-10-01 | 2015-10-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 14000 | 14000 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-10-01 | 2015-11-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 17 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 14000 | 14000 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 16% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | SR345830 | Firmware development for (RTB) | LSST Forecast - B57 - B1 | 42 | 0 | 2015-10-01 | 2016-03-25 | 0 | 2015-10-01 | 2016-03-25 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-10-01 | 2015-12-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 42 | 119 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.06 | Electronics Production Test | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering | [7 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [6 empty] | RTB - Design |  | Science Raft System
FALSE |  | CR240540 | WGEB prototype to WEB EM workshop | LSST Forecast - B57 - B1 | 6 | 0 | 2015-10-05 | 2016-04-22 | 0 | 2015-10-05 | 2016-04-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-11-10 | 2015-11-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 6 | 130 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.01 | Wavefront Electronics Board (WEB) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering | [7 empty] | Corner Raft Electronics (TEC) | WEB EM
FALSE |  | CRYO60850 | Fab and Assembly - Hose and Fitting Test Stand | LSST Forecast - B57 - B1 | 60 | 0 | 2015-10-12 | 2016-04-20 | 0 | 2015-10-12 | 2016-04-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2015-11-09 | 2016-02-18 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 123 |  | Complete | 100% | 352 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 352 | 352 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 16% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | CR230340 | Final requirements and operations documentation - CRSA Warm-Cold Metrology - test stand | LSST Forecast - B57 - B1 | 4 | 0 | 2015-10-12 | 2016-07-18 | 0 | 2015-10-12 | 2016-07-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-11-02 | 2015-11-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 184 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CR222530 | RCV: Procure Cold Single CCD test stand Commercial Components | LSST Forecast - B57 - B1 | 20 | 0 | 2015-10-15 | 2016-02-26 | 0 | 2015-10-15 | 2016-02-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 55000 | 55000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-10-29 | 2015-11-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 82 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 55000 | 55000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | [11 empty] | Corner Raft Tower Module (CRTM) (TEC)
FALSE |  | CR222520 | Procure Cold Single CCD test stand Commercial Components - Vendor Lead Time | LSST Forecast - B57 - B1 | 40 | 19 | 2015-10-15 | 2016-02-26 | 0 | 2015-10-15 | 2016-02-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-10-15 | 2015-12-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 20 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 82 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot
FALSE |  | CRYO60840 | Procurement - Hose and Fitting Test Stand | LSST Forecast - B57 - B1 | 40 | 0 | 2015-10-19 | 2016-03-30 | 0 | 2015-10-19 | 2016-03-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 27100 | 27100 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-10-19 | 2015-12-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 15 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 103 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 27100 | 27100 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 16% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | OP540610 | RCV: L3 Assembly - Phase 1 (Delta PDR) | LSST Forecast - B57 - B1 | 1 | 0 | 2015-10-22 | 2016-02-14 | 0 | 2015-10-22 | 2016-02-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-14 | 2019-05-14 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-11-18 | 2015-11-18 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 76 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% | Level 4 Milestone | Procurement | [7 empty] | L3 Assembly (TEC) |  |  | Critical Path #2 (L1_L2 Assembly) |  |  |  | L1-L2 Opto-Mechanics
FALSE |  | SR530470 | TS5 - generate preliminary measurement test scripts | LSST Forecast - B57 - B1 | 27 | 0 | 2015-11-02 | 2015-12-18 | 0 | 2015-11-02 | 2015-12-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-11-02 | 2015-12-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 27 | 32 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.02 | RSA & RTM Warm-Cold Metrology (TS5) | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 5 - Design |  | Science Raft System
FALSE |  | CR211680 | Generate guide sensors chain final integrated test plan - Corner Raft | LSST Forecast - B57 - B1 | 40 | 0 | 2015-11-09 | 2016-02-05 | 0 | 2015-11-09 | 2016-02-05 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-11-09 | 2016-01-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 51 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.01 | Corner Raft System Integration and Management | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft System Integration and Management (TEC) | Management | [5 empty] | Corner Raft System Integration and Management
FALSE |  | CR230350 | Measurement and analysis software - CRSA Warm-Cold Metrology - test stand | LSST Forecast - B57 - B1 | 44 | 0 | 2015-11-13 | 2018-01-19 | 0 | 2015-11-13 | 2018-01-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-12-01 | 2016-02-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 44 | 521 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CR235200 | Generate final acceptance, verification and test plan - Guide sensor | LSST Forecast - B57 - B1 | 20 | 0 | 2015-11-17 | 2016-07-18 | 0 | 2015-11-17 | 2016-07-18 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-01-04 | 2016-02-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 158 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.03 | Guide Sensors | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | Guide Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | SR341160 | Test - Prod ASPIC | LSST Forecast - B57 - B1 | 49 | 0 | 2015-11-27 | 2015-12-21 | 0 | 2015-11-27 | 2015-12-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 5 | FALSE | Normal | FALSE | 2015-12-15 | 2016-02-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 1 | 0 | 2 | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 140 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 49 | 15 |  | Complete | 100% | 400 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.01 | ASPIC | 400 | 400 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [6 empty] | ASPICS |  | Science Raft System
FALSE |  | CRYO60760 | Test - Subscale Test Stand (Final Details) | LSST Forecast - B57 - B1 | 26 | 0 | 2015-12-01 | 2016-07-30 | 0 | 2015-12-01 | 2016-07-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-01-04 | 2016-02-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 26 | 160 |  | Complete | 100% | 115 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 115 | 115 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 16% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | CR222550 | Procure EO testing support instrumentation - Vendor Lead Time | LSST Forecast - B57 - B1 | 40 | 0 | 2015-12-09 | 2016-09-30 | 0 | 2015-12-09 | 2016-09-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-01-04 | 2016-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 20 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 197 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Vincent Riot
FALSE |  | SR530050 | TS8 - fabrication/assy - X-Y-Z stage controller | LSST Forecast - B57 - B1 | 30 | 0 | 2015-12-14 | 2015-12-28 | 0 | 2015-12-14 | 2015-12-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-01-04 | 2016-02-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 8 |  | Complete | 100% | 60 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.05 | RTM Electro-Optical Testing (TS8) | 60 | 60 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 8 - Procurement & Fabrication |  | Science Raft System
FALSE |  | SR530090 | TS8 - Assembly technical support | LSST Forecast - B57 - B1 | 30 | 0 | 2015-12-21 | 2016-06-30 | 0 | 2015-12-21 | 2016-06-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-01-04 | 2016-02-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 132 |  | Complete | 100% | 128 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.05 | RTM Electro-Optical Testing (TS8) | 128 | 128 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 8 - Procurement & Fabrication |  | Science Raft System
Merge Hotspot
The total number of activities with a high number of predecessor links.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | Previous Start | Previous Finish | Percent Complete | Previous Remaining Duration | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | IsLevelOfEffort | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | Global_Basis of Estimate | Global_Cobra Cost Class | Cobra PMT (EV Method)_Global | Global_Color of Money | Global_Control Account Manager | Global_Design Maturity | Global_Judgement Factor | Global_Milestone Levels | Global_Project Phase | Global_Funding Source | Global_EDIA Survey | Global_MS Type | Phase | NSF Milestones | Loading Curve | Sensor Vendor | LSST_CA | Summary Schedule | ICD for NSF Input | LSST Camera Critical Paths | CD2 Budget Changes | DOE Reviews | Critical Path (CD Reviews) | LSST WP Summary | Critical Path (Camera Delivery) | AWARD / NEED Sub-System | Final Design Key Links | CP - CAMM2100 | CP - CAMM2130 | CP - CAMM2160 | BNL Work Org | Last ETC Update | BNL WBS | LSST Story List | Sum Sch 01 (Camera) | Sum Sch 02 (IT w/Needs) | Sum Sch 03 (Sensors_RTM_IT) | LSST Raft Particulate Mitigation | LSST RTM
FALSE |  | CCS116500 | Build TS8 Distribution - Prototype | LSST Forecast - B57 - B1 | 53 | 0 | 2015-01-02 | 2015-05-19 | 0 | 2015-01-02 | 2015-05-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-01-05 | 2015-03-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 53 | 94 |  | Complete | 100% | 96 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.01.04 | Test Stand 8 (REB Based) | 96 | 96 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 11% |  | Design/Engineering | [7 empty] | CCS HCU (TEC)
FALSE |  | SR522505 | TS2 - MF05b (sensor removal fixture) - fabricate and assemble prototype fixture | LSST Forecast - B57 - B1 | 61 | 0 | 2015-01-02 | 2015-03-31 | 0 | 2015-01-02 | 2015-03-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-01-02 | 2015-03-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 61 | 61 |  | Complete | 100% | 20 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.02 | Sensor Dimensional Metrology (TS2) | 20 | 20 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Science Sensors Test Stands (TEC) | Test Stand Effort | [5 empty] | Science Sensors Test Stands | [7 empty] | Baseline | Science Sensors
FALSE |  | CCS114515 | Integrate REB1 Driver with full raft readout using DREB1 | LSST Forecast - B57 - B1 | 7 | 0 | 2015-01-05 | 2015-01-13 | 0 | 2015-01-05 | 2015-01-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-01-05 | 2015-01-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 7 | 6 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.01.02 | Rafts Subsystem | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering | [7 empty] | CCS HCU (TEC)
FALSE |  | SR332345 | COMP: Science Sensors Prototype & Development | LSST Forecast - B57 - B1 | 0 | 0 | 2015-01-30 | 2015-01-30 | 0 | 2015-01-30 | 2015-01-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2015-01-30 | 2015-01-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 14 | 0 | 14 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.01 | Science Sensors Prototype & Development | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Bill Wahl |  |  | Level 4 Milestone | Design/Engineering | [6 empty] | e2v |  | Prototype & Development | [14 empty] | Science Sensors
FALSE |  | ITC22205 | Finalize MTF equipment design | LSST Forecast - B57 - B1 | 20 | 0 | 2015-02-02 | 2015-02-27 | 0 | 2015-02-02 | 2015-02-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-03-30 | 2015-04-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 2 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 18 |  | Complete | 100% | 160 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.01.03 | Vacuum Qualification Tests | 160 | 160 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC) | [6 empty] | Verification Test Systems
FALSE |  | OP530410 | AWARD: L1-L2 Assembly - Phase 2 | LSST Forecast - B57 - B1 | 1 | 0 | 2015-02-12 | 2015-02-12 | 0 | 2015-02-12 | 2015-02-12 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-13 | 2019-06-13 | 1868008 | 1868008 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2015-03-16 | 2015-03-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 1868008 | 1868008 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | B1 Procurement Commitment (C5.1) | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 0% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | L1-L2 Assembly (TEC) | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly) |  |  |  | L1-L2 Opto-Mechanics
FALSE |  | CCS114513 | Integrate CCS with WREB | LSST Forecast - B57 - B1 | 15 | 0 | 2015-02-15 | 2015-04-15 | 0 | 2015-02-15 | 2015-04-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-03-02 | 2015-03-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 41 |  | Complete | 100% | 70 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.01.02 | Rafts Subsystem | 70 | 70 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering | [7 empty] | CCS HCU (TEC)
FALSE |  | SR530570 | Fabrication - TS5 Cryostat custom components (TS7) | LSST Forecast - B57 - B1 | 20 | 0 | 2015-02-16 | 2015-07-29 | 0 | 2015-02-16 | 2015-07-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-06-25 | 2015-07-23 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 114 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.02 | RSA & RTM Warm-Cold Metrology (TS5) | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 5 - Procurement & Fabrication |  | Science Raft System
FALSE |  | SR552450 | Conduct RSA thermal cycling tests | LSST Forecast - B57 - B1 | 53 | 0 | 2015-02-16 | 2015-05-28 | 0 | 2015-02-16 | 2015-05-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-02-17 | 2015-04-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 2 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 53 | 71 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.01 | Science Raft Tower Module (SRTM) | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation |  | R&D | [5 empty] | Science Raft Tower Module (SRTM) (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Tower Module |  | Science Raft System
FALSE |  | SR414200 | NEED: CCS-DAQ (DAQ V0.0 GEN 1 Multi REB) | LSST Forecast - B57 - B1 | 0 | 0 | 2015-02-16 | 2015-02-16 | 0 | 2015-02-16 | 2015-02-16 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2015-05-01 | 2015-05-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.04 | Raft Optimization And Readout (ROAR) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% | Level 5 Milestone | Engineering Test/Validation | [23 empty] | Science Raft System
FALSE |  | SR523530 | TS3 -Work Flow | LSST Forecast - B57 - B1 | 65 | 0 | 2015-02-16 | 2015-06-25 | 0 | 2015-02-16 | 2015-06-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-03-02 | 2015-06-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 65 | 91 |  | Complete | 100% | 240 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.03 | Sensor Electro-Optical (TS3) | 240 | 240 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Science Sensors Test Stands (TEC) | Test Stand Effort | [5 empty] | Science Sensors Test Stands | [6 empty] | Test Stand 3 - Design |  | Science Sensors
FALSE |  | CR240460 | Functional Testing - WGEB Protoype (WF mode) | LSST Forecast - B57 - B1 | 40 | 0 | 2015-02-17 | 2015-03-27 | 0 | 2015-02-17 | 2015-03-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2015-04-20 | 2015-06-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 20 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 28 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.01 | Wavefront Electronics Board (WEB) | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering | [7 empty] | Corner Raft Electronics (TEC) | WEB Prototype
FALSE |  | CR241825 | Layout DCBS prototype variant A | LSST Forecast - B57 - B1 | 10 | 0 | 2015-02-18 | 2015-02-25 | 0 | 2015-02-18 | 2015-02-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-03-16 | 2015-03-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 5 |  | Complete | 100% | 60 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.02 | Guider Electronics Board (GEB) | 60 | 60 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Engineering Test/Validation | [7 empty] | Corner Raft Electronics (TEC)
FALSE |  | CCS114530 | NEED: REB2 Driver | LSST Forecast - B57 - B1 | 0 | 0 | 2015-03-02 | 2015-03-02 | 0 | 2015-03-02 | 2015-03-02 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2015-04-01 | 2015-04-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.01.02 | Rafts Subsystem | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Tony Johnson |  |  | Level 5 Milestone | Design/Engineering | [14 empty] | CCS Infrastructure
FALSE |  | SE210071 | Prep for SI FDR | LSST Forecast - B57 - B1 | 10 | 0 | 2015-03-02 | 2015-06-10 | 0 | 2015-03-02 | 2015-06-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-06-01 | 2015-06-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 2 | 2 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 71 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.01 | Systems Engineering | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 0% |  | Management/Administration |  | Design Reviews | [5 empty] | Systems Engineering (TEC) | [6 empty] | Systems Engineering
FALSE |  | SE224040 | LCA-17 final allocation | LSST Forecast - B57 - B1 | 40 | 0 | 2015-03-02 | 2016-07-07 | 0 | 2015-03-02 | 2016-07-07 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-17 | 2020-06-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-11-02 | 2016-01-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 334 |  | Complete | 100% | 220 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.04 | Optics system analysis | 220 | 220 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | CRYO18301 | ETU Test and Validate - Cryogenic Feedthrough Test Parts - Cryo & Cold Plate | LSST Forecast - B57 - B1 | 100 | 0 | 2015-03-11 | 2015-09-14 | 0 | 2015-03-11 | 2015-09-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-05-11 | 2015-09-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 2 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 4 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 100 | 130 |  | Complete | 100% | 344 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.03 | Cryo and Cold Plates | 344 | 344 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation |  | Commissioning and Testing | [5 empty] | Cryo and Cold Plates (TEC) | [6 empty] | Cryo and Cold Plates
FALSE |  | SE223200 | Filter exchange sub-system FDR contamination compliance | LSST Forecast - B57 - B1 | 20 | 0 | 2015-03-16 | 2015-10-21 | 0 | 2015-03-16 | 2015-10-21 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-04-28 | 2015-05-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 154 |  | Complete | 100% | 44 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.03 | Thermal and contamination system analysis | 44 | 44 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | CR220480 | Review Camera System Specifications CD-3 - Corner raft tower and tooling | LSST Forecast - B57 - B1 | 22 | 0 | 2015-03-16 | 2015-04-15 | 0 | 2015-03-16 | 2015-04-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-03-16 | 2015-04-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 22 | 22 |  | Complete | 100% | 16 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 16 | 16 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Tower Module (CRTM) (TEC) | CRTM Final Design | [5 empty] | Corner Raft Tower Module (CRTM)
FALSE |  | CCS119700 | COMP: CCS Core 2.0 Release | LSST Forecast - B57 - B1 | 0 | 0 | 2015-03-20 | 2015-03-20 | 0 | 2015-03-20 | 2015-03-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Finish Milestone | FALSE | 2015-04-20 | 2015-04-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.02.03 | CCS Core 2.0 Release | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  | Level 4 Milestone | Design/Engineering
FALSE |  | SR552500 | Prep for Final Design Review - RTM Mechanic | LSST Forecast - B57 - B1 | 16 | 0 | 2015-03-23 | 2015-05-15 | 0 | 2015-03-23 | 2015-05-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-04-20 | 2015-05-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 4 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 16 | 39 |  | Complete | 100% | 240 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.01 | Science Raft Tower Module (SRTM) | 240 | 240 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Design Reviews | [5 empty] | Science Raft Tower Module (SRTM) (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Tower Module |  | Science Raft System
FALSE |  | CR240420 | NEED: corner raft test setup (prototype) | LSST Forecast - B57 - B1 | 0 | 0 | 2015-03-25 | 2015-03-25 | 0 | 2015-03-25 | 2015-03-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2015-04-23 | 2015-04-23 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.01 | Wavefront Electronics Board (WEB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 5 Milestone | Engineering Test/Validation | [8 empty] | WEB Prototype
FALSE |  | SR551970 | Prep for C_FDR - RSA | LSST Forecast - B57 - B1 | 18 | 0 | 2015-03-27 | 2015-05-15 | 0 | 2015-03-27 | 2015-05-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-04-16 | 2015-05-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 2 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 18 | 35 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.02 | Science Raft Sensor Assembly (SRSA) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Design Reviews | [5 empty] | Science Raft Tower Module (SRTM) (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Sensor Assembly |  | Science Raft System
FALSE |  | CR240480 | AVAIL: WGEB prototype | LSST Forecast - B57 - B1 | 0 | 0 | 2015-03-27 | 2015-03-27 | 0 | 2015-03-27 | 2015-03-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Finish Milestone | FALSE | 2015-06-22 | 2015-06-22 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 50 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.01 | Wavefront Electronics Board (WEB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 5 Milestone | Engineering Test/Validation | [8 empty] | WEB Prototype
FALSE |  | OP520540 | Assemble test filter frame | LSST Forecast - B57 - B1 | 15 | 0 | 2015-03-30 | 2015-04-22 | 0 | 2015-03-30 | 2015-04-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-04-01 | 2015-04-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 17 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 18% |  | Design/Engineering |  | Commissioning and Testing | [5 empty] | Filters (TEC) | Prototype Filter Assemblies | [5 empty] | Filter Opto-Mechanics
FALSE |  | CAMF663500 | Prep for C_FDR - Filter Loader | LSST Forecast - B57 - B1 | 10 | 0 | 2015-04-01 | 2015-04-20 | 0 | 2015-04-01 | 2015-04-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-05-18 | 2015-06-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 13 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.02 | Filter Loader | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Design/Engineering
FALSE |  | CAMF667300 | Prep for C_FDR - Carousel | LSST Forecast - B57 - B1 | 10 | 0 | 2015-04-01 | 2015-04-21 | 0 | 2015-04-01 | 2015-04-21 | 0 | 2019-06-01 | 2019-06-01 | 2018-10-16 | 2018-10-16 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-05-18 | 2015-06-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 14 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Design/Engineering
FALSE |  | CRYO29750 | Finalize Design - Cryostat Back End | LSST Forecast - B57 - B1 | 22 | 0 | 2015-04-01 | 2015-06-07 | 0 | 2015-04-01 | 2015-06-07 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 7 | FALSE | Normal | FALSE | 2015-05-01 | 2015-06-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 7 | 0 | 2 | 4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 22 | 47 |  | Complete | 100% | 154 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.01 | Cryostat Back End | 154 | 154 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Backend & Vacuum Systems (TEC) | [6 empty] | Cryostat Back End
FALSE |  | SE223090 | Cryostat Sub-system FDR cryostat thermal analysis integrated material | LSST Forecast - B57 - B1 | 14 | 0 | 2015-04-01 | 2015-05-29 | 0 | 2015-04-01 | 2015-05-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-05-13 | 2015-06-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 3 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 14 | 41 |  | Complete | 100% | 60 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.03 | Thermal and contamination system analysis | 60 | 60 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | SR522900 | COMP: TS2 - MF07a (CCD Cover & Handling fixture) | LSST Forecast - B57 - B1 | 0 | 0 | 2015-04-01 | 2015-04-01 | 0 | 2015-04-01 | 2015-04-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2015-04-01 | 2015-04-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.02 | Sensor Dimensional Metrology (TS2) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl |  |  | Level 4 Milestone | Fabrication/Assembly | [8 empty] | Test Stand Effort | [14 empty] | Science Sensors
FALSE |  | CR234230 | AWARD: Contract - First article 2Kx4K Wavefront Sensor w package (2+3 2kx4k sensors) | LSST Forecast - B57 - B1 | 1 | 0 | 2015-04-03 | 2015-04-03 | 0 | 2015-04-03 | 2015-04-03 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 1539764 | 1539764 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-05-01 | 2015-05-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.02 | Wavefront Sensor | 0 | 0 | 0 | 1539764 | 1539764 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | B1 Procurement Commitment (C5.1) |  | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 1% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | [6 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CAMF659700 | Prep for C_FDR - Auto Changer | LSST Forecast - B57 - B1 | 10 | 0 | 2015-04-07 | 2015-04-20 | 0 | 2015-04-07 | 2015-04-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-05-07 | 2015-05-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.01 | Auto Changer | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Design/Engineering
FALSE |  | SE222210 | Final grid/cryostat - Check & Update IDD | LSST Forecast - B57 - B1 | 11 | 0 | 2015-04-08 | 2015-05-29 | 0 | 2015-04-08 | 2015-05-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 7 | FALSE | Normal | FALSE | 2015-05-01 | 2015-05-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 0 | 4 | 0 | 0 | 7 | 0 | 6 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 11 | 36 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.02 | Mechanical Integration | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | OP520680 | Prep for C_FDR - Filter Assembly | LSST Forecast - B57 - B1 | 28 | 0 | 2015-04-13 | 2015-06-02 | 0 | 2015-04-13 | 2015-06-02 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-05-18 | 2015-06-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 28 | 35 |  | Complete | 100% | 300 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 300 | 300 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 18% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Filters (TEC) | Filter Design | [5 empty] | Filter Opto-Mechanics
FALSE |  | SR523650 | TS3 - Commissioning | LSST Forecast - B57 - B1 | 40 | 0 | 2015-04-20 | 2015-06-29 | 0 | 2015-04-20 | 2015-06-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-06-15 | 2015-08-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 4 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 49 |  | Complete | 100% | 360 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.03 | Sensor Electro-Optical (TS3) | 360 | 360 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Testing/Integration |  | Commissioning and Testing | [5 empty] | Science Sensors Test Stands (TEC) | Test Stand Effort | [5 empty] | Science Sensors Test Stands | [6 empty] | Test Stand 3 - Assembly & Commissioning |  | Science Sensors
FALSE |  | SR330595 | Sensors First Articles - V2- Backside Batch and Test | LSST Forecast - B57 - B1 | 100 | 0 | 2015-04-20 | 2015-04-30 | 0 | 2015-04-20 | 2015-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-05-01 | 2015-09-22 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 4 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 100 | 8 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien |  |  |  | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 14% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor | [10 empty] | Sensor
FALSE |  | CRYO24700 | Prep for Prelim Design Review - Evaporable Getter Pumps | LSST Forecast - B57 - B1 | 4 | 0 | 2015-04-25 | 2015-04-28 | 0 | 2015-04-25 | 2015-04-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-05-04 | 2015-05-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 1 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.02 | Getter Pumps | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Cryostat Getter Pumps
FALSE |  | SR530220 | COMP: TS7 part, assy dwg's complete | LSST Forecast - B57 - B1 | 0 | 0 | 2015-04-29 | 2015-04-29 | 0 | 2015-04-29 | 2015-04-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2015-05-12 | 2015-05-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.04 | RTM Cryostat Integration (TS7) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% | Level 4 Milestone | Design/Engineering | [14 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 7 - Design |  | Science Raft System
FALSE |  | SE222250 | Final Filter/Exchange System - Mechanical Integration | LSST Forecast - B57 - B1 | 4 | 0 | 2015-05-01 | 2015-05-29 | 0 | 2015-05-01 | 2015-05-29 | 0 | 2019-06-01 | 2019-06-01 | 2018-10-16 | 2018-10-16 | 0 | 0 | 0 | 0 | 0 | 6 | FALSE | Normal | FALSE | 2015-06-10 | 2015-06-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 3 | 0 | 0 | 6 | 0 | 5 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 19 |  | Complete | 100% | 96 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.02 | Mechanical Integration | 96 | 96 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | SE223150 | Cryostat sub-system FDR contamination compliance | LSST Forecast - B57 - B1 | 8 | 0 | 2015-05-01 | 2015-05-29 | 0 | 2015-05-01 | 2015-05-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 8 | FALSE | Normal | FALSE | 2015-06-04 | 2015-06-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 2 | 5 | 0 | 0 | 8 | 0 | 7 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 8 | 19 |  | Complete | 100% | 44 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.03 | Thermal and contamination system analysis | 44 | 44 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | SE223160 | Science Raft sub-system FDR contamination compliance | LSST Forecast - B57 - B1 | 14 | 0 | 2015-05-01 | 2015-05-19 | 0 | 2015-05-01 | 2015-05-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-06-19 | 2015-07-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 14 | 12 |  | Complete | 100% | 44 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.03 | Thermal and contamination system analysis | 44 | 44 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | CRYO13600 | Prep for C_FDR - Cryostat Housing | LSST Forecast - B57 - B1 | 17 | 0 | 2015-05-06 | 2015-06-08 | 0 | 2015-05-06 | 2015-06-08 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-06-04 | 2015-06-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 17 | 22 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.01 | Cryostat Housing | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment |  | TEC Non-ARRA | Brian J. Langton | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Cryostat Housing
FALSE |  | CRYO29850 | Prep for C_FDR - Cryostat Back End | LSST Forecast - B57 - B1 | 1 | 0 | 2015-05-08 | 2015-06-08 | 0 | 2015-05-08 | 2015-06-08 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-07-02 | 2015-07-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 2 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 20 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.01 | Cryostat Back End | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Cryostat Back End
FALSE |  | CRYO11550 | Prep for Final Review - Cryostat Assembly | LSST Forecast - B57 - B1 | 1 | 0 | 2015-05-11 | 2015-06-08 | 0 | 2015-05-11 | 2015-06-08 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-06-09 | 2015-06-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 2 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 19 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Cryostat Assembly
FALSE |  | CRYO16650 | Prep for C_FDR - Cryo & Cold Plate | LSST Forecast - B57 - B1 | 1 | 0 | 2015-05-11 | 2015-06-08 | 0 | 2015-05-11 | 2015-06-08 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-06-16 | 2015-06-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 2 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 19 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.03 | Cryo and Cold Plates | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Brian J. Langton | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Cryo and Cold Plates
FALSE |  | DAQ105400 | Prep for C_FDR | LSST Forecast - B57 - B1 | 15 | 0 | 2015-05-15 | 2015-05-30 | 0 | 2015-05-15 | 2015-05-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-06-01 | 2015-06-19 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 10 |  | Complete | 100% | 16 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.01 | DAQ Integration & Management | 16 | 16 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Design/Engineering | [7 empty] | DAQ Integration & Management (TEC)
FALSE |  | CRYO09120 | Prep for Final Design Review - Cryostat | LSST Forecast - B57 - B1 | 10 | 0 | 2015-05-18 | 2015-06-08 | 0 | 2015-05-18 | 2015-06-08 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-06-04 | 2015-06-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 14 |  | Complete | 100% | 200 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.01 | Cryostat Integration & Management | 200 | 200 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Management/Administration |  | Design Reviews | [5 empty] | Cryostat Integration & Management (TEC) | [6 empty] | Utility Trunk
FALSE |  | CRYO13800 | Generate Detail and Assembly Drawings Cryostat Housing | LSST Forecast - B57 - B1 | 56 | 0 | 2015-05-18 | 2015-12-28 | 0 | 2015-05-18 | 2015-12-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-06-11 | 2015-08-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 56 | 150 |  | Complete | 100% | 252 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.01 | Cryostat Housing | 252 | 252 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Housing & Assembly (TEC) | [6 empty] | Cryostat Housing
FALSE |  | CRYO21650 | Prep for C_FDR - Grid Assembly | LSST Forecast - B57 - B1 | 10 | 0 | 2015-05-18 | 2015-06-08 | 0 | 2015-05-18 | 2015-06-08 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-06-16 | 2015-06-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 3 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 14 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.04 | Grid Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Brian J. Langton | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Grid Assembly
FALSE |  | SR330600 | RCV: First Articles Sensor - V2 - Sensor #1 | LSST Forecast - B57 - B1 | 5 | 0 | 2015-05-18 | 2016-05-31 | 0 | 2015-05-18 | 2016-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 73016 | 73016 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-06-01 | 2015-06-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 8 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 260 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 73016 | 73016 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 14% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC) | Sensor Delivery |  |  |  |  | Sensor | Science Sensors Procurement |  |  |  |  | CP - CAMM2130 (Award of Sensor Lot #2) |  | Sensors Vendor 2
FALSE |  | SE221255 | Generate structural report & slides for SI FDR | LSST Forecast - B57 - B1 | 5 | 0 | 2015-05-26 | 2015-05-29 | 0 | 2015-05-26 | 2015-05-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-06-01 | 2015-06-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 3 |  | Complete | 100% | 20 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.01 | Structural System Analysis | 20 | 20 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | CRYO11750 | Generate Detail and Assembly Drawings - Cryostat Assembly | LSST Forecast - B57 - B1 | 40 | 0 | 2015-06-01 | 2015-10-30 | 0 | 2015-06-01 | 2015-10-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-08-12 | 2015-10-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 107 |  | Complete | 100% | 140 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 140 | 140 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Housing & Assembly (TEC) | [6 empty] | Cryostat Assembly
FALSE |  | CRYO30050 | Generate Detail and Assembly Drawings Cryostat Back End | LSST Forecast - B57 - B1 | 45 | 0 | 2015-06-01 | 2016-04-27 | 0 | 2015-06-01 | 2016-04-27 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-11-30 | 2016-02-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 45 | 221 |  | Complete | 100% | 244 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.01 | Cryostat Back End | 244 | 244 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Backend & Vacuum Systems (TEC) | [6 empty] | Cryostat Back End
FALSE |  | CR241780 | Functional Testing - WGEB Protoype (Guider mode) | LSST Forecast - B57 - B1 | 20 | 0 | 2015-06-01 | 2015-06-19 | 0 | 2015-06-01 | 2015-06-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2015-08-13 | 2015-09-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 20 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 14 |  | Complete | 100% | 100 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.02 | Guider Electronics Board (GEB) | 100 | 100 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Engineering Test/Validation | [7 empty] | Corner Raft Electronics (TEC) | GEB Prototype
FALSE |  | SE222290 | Revise layout dwg's for camera-level FDR | LSST Forecast - B57 - B1 | 10 | 0 | 2015-06-01 | 2015-06-10 | 0 | 2015-06-01 | 2015-06-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-13 | 2019-09-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-07-01 | 2015-07-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 7 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.02 | Mechanical Integration | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | OP520700 | C_FDR - Filter Assembly | LSST Forecast - B57 - B1 | 2 | 0 | 2015-06-03 | 2015-06-04 | 0 | 2015-06-03 | 2015-06-04 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-07-06 | 2015-07-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 1 |  | Complete | 100% | 32 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 32 | 32 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 18% |  | Design/Engineering | [7 empty] | Filters (TEC) | Filter Design
FALSE |  | DAQ100125 | COMP: Ready for CD-3 - DAQ | LSST Forecast - B57 - B1 | 0 | 0 | 2015-06-03 | 2015-06-03 | 0 | 2015-06-03 | 2015-06-03 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2015-06-03 | 2015-06-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02 | Data Acquisition System (DAQ) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer |  |  | Level 3 Milestone | Management/Administration
FALSE |  | OP540600 | L3 Assembly - Phase 1 (Engineering & Requirements Defined) | LSST Forecast - B57 - B1 | 167 | 0 | 2015-06-09 | 2016-07-29 | 0 | 2015-06-09 | 2016-07-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-07-02 | 2016-03-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 0 | 0 | 1 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 95 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 167 | 287 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor | [7 empty] | Critical Path #2 (L1_L2 Assembly) |  |  |  | L1-L2 Opto-Mechanics
FALSE |  | CRYO21800 | COMP: C_FDR - Grid Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2015-06-10 | 2015-06-10 | 0 | 2015-06-10 | 2015-06-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2015-07-16 | 2015-07-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.04 | Grid Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Design/Engineering
FALSE |  | CRYO30000 | COMP: C_FDR - Cryostat Back End | LSST Forecast - B57 - B1 | 0 | 0 | 2015-06-10 | 2015-06-10 | 0 | 2015-06-10 | 2015-06-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2015-07-17 | 2015-07-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.01 | Cryostat Back End | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Design/Engineering
FALSE |  | CAM112685 | COMP: Design Ready for CD-3 | LSST Forecast - B57 - B1 | 0 | 0 | 2015-06-12 | 2015-06-12 | 0 | 2015-06-12 | 2015-06-12 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2015-07-01 | 2015-07-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 11 | 0 | 11 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01.01.02 | Reviews & Collaboration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Vincent Riot | (1.10) Task/item is a modification of an existing design | 0% | Level 4 Milestone | Management/Administration | [12 empty] | CD-3b | Critical Path to CD-3b | Project Management
FALSE |  | CAMF650200 | COMP: Ready for CD-3 - Exchange System | LSST Forecast - B57 - B1 | 0 | 0 | 2015-06-15 | 2015-06-15 | 0 | 2015-06-15 | 2015-06-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2015-07-16 | 2015-07-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 8 | 0 | 8 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03 | Exchange System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  | Level 3 Milestone | Management/Administration
FALSE |  | SR530520 | Finalize part, assy dwg's for TS5 | LSST Forecast - B57 - B1 | 10 | 0 | 2015-06-15 | 2015-12-28 | 0 | 2015-06-15 | 2015-12-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-07-01 | 2015-07-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 1 | 0 | 0 | 3 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 134 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.02 | RSA & RTM Warm-Cold Metrology (TS5) | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 5 - Design |  | Science Raft System
FALSE |  | CRYO09180 | Prep for CD3 Review - Cryostat | LSST Forecast - B57 - B1 | 1 | 0 | 2015-06-18 | 2015-07-15 | 0 | 2015-06-18 | 2015-07-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-07-01 | 2015-07-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 18 |  | Complete | 100% | 200 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.01 | Cryostat Integration & Management | 200 | 200 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Management/Administration |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Integration & Management (TEC) | [6 empty] | Utility Trunk
FALSE |  | OP520740 | COMP: C_FDR - Filter Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2015-06-19 | 2015-06-19 | 0 | 2015-06-19 | 2015-06-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 5 | FALSE | Finish Milestone | FALSE | 2015-07-15 | 2015-07-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  | Level 4 Milestone | Design/Engineering | [8 empty] | Filter Design
FALSE |  | SR530850 | TS5 - Optical flat stand - fabricate and assemble fixture | LSST Forecast - B57 - B1 | 10 | 0 | 2015-06-22 | 2015-11-20 | 0 | 2015-06-22 | 2015-11-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-09-16 | 2015-09-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 108 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.02 | RSA & RTM Warm-Cold Metrology (TS5) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 5 - Procurement & Fabrication |  | Science Raft System
FALSE |  | OP521500 | Update Plan Procurement (Post FDR) - Filter Coating (all phases) | LSST Forecast - B57 - B1 | 30 | 0 | 2015-06-22 | 2015-09-30 | 0 | 2015-06-22 | 2015-09-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-12-12 | 2019-12-12 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-07-01 | 2015-08-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 70 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 18% |  | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Filters (TEC) | Witness & First Article RFP | [5 empty] | Filter Optics
FALSE |  | SR343185 | Fab/Assy Raft Electronics Board (REB3) - PT2 | LSST Forecast - B57 - B1 | 16 | 0 | 2015-06-29 | 2015-09-22 | 0 | 2015-06-29 | 2015-09-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-07-21 | 2015-08-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 16 | 59 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [6 empty] | Raft Electronics Board 3 |  | Science Raft System
FALSE |  | SR523710 | AVAIL: Test Stand 3 - Ready for Production | LSST Forecast - B57 - B1 | 0 | 0 | 2015-06-30 | 2015-06-30 | 0 | 2015-06-30 | 2015-06-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2015-07-31 | 2015-07-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.03 | Sensor Electro-Optical (TS3) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl |  |  | Level 5 Milestone | Testing/Integration | [8 empty] | Test Stand Effort | [12 empty] | Test Stand 3 - Assembly & Commissioning |  | Science Sensors
FALSE |  | CRYO22353 | ETU - Design and Analysis - Grid Flexure Tests | LSST Forecast - B57 - B1 | 30 | 0 | 2015-07-01 | 2015-10-30 | 0 | 2015-07-01 | 2015-10-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-10-01 | 2015-11-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 85 |  | Complete | 100% | 50 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.04 | Grid Assembly | 50 | 50 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 11% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Grid Assembly (TEC) | [6 empty] | Grid Assembly
FALSE |  | ITC24400 | Complete BOT prototype design | LSST Forecast - B57 - B1 | 30 | 0 | 2015-07-01 | 2015-09-14 | 0 | 2015-07-01 | 2015-09-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-08-03 | 2015-09-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 51 |  | Complete | 100% | 60 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.02.01 | Bench For Optical Testing (BOT) | 60 | 60 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 13% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC) | [6 empty] | Verification Test Systems
FALSE |  | CR306240 | Procurement Prep - PCRTS Cryostat Mech Comp/Cabling - Corner raft test station | LSST Forecast - B57 - B1 | 10 | 0 | 2015-07-01 | 2015-08-28 | 0 | 2015-07-01 | 2015-08-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-08-31 | 2015-09-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 41 |  | Complete | 100% | 10 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.05 | Corner Raft Assembly and Test Station | 10 | 10 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Assembly and Test Station (TEC) | CR Assy/Test Station Prelim Design | [5 empty] | Corner Raft Assembly and Test Station
FALSE |  | OP530620 | COMP: L1-L2 Assembly Phase 3 | LSST Forecast - B57 - B1 | 0 | 0 | 2015-07-01 | 2015-07-01 | 0 | 2015-07-01 | 2015-07-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-03 | 2019-09-03 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | FALSE | 2015-09-01 | 2015-09-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  | Level 4 Milestone | Procurement | [8 empty] | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly)
FALSE |  | CRYO18230 | ETU Design & Analysis - Cryoplate Flexure Test Article - Cryo & Cold Plate | LSST Forecast - B57 - B1 | 40 | 0 | 2015-07-04 | 2015-10-30 | 0 | 2015-07-04 | 2015-10-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-11-04 | 2016-01-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 83 |  | Complete | 100% | 360 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.03 | Cryo and Cold Plates | 360 | 360 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryo and Cold Plates (TEC) | [6 empty] | Cryo and Cold Plates
FALSE |  | SE224050 | LCA-18 final allocation | LSST Forecast - B57 - B1 | 39 | 0 | 2015-07-06 | 2016-07-29 | 0 | 2015-07-06 | 2016-07-29 | 0 | 2019-06-01 | 2019-06-01 | 2020-07-16 | 2020-07-16 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-03-17 | 2017-05-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 39 | 262 |  | Complete | 100% | 100 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.04 | Optics system analysis | 100 | 100 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | CAM112690 | COMP: CD-3 DOE/SC Review - Doc Sumbitted | LSST Forecast - B57 - B1 | 0 | 0 | 2015-07-17 | 2015-07-17 | 0 | 2015-07-17 | 2015-07-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2015-08-03 | 2015-08-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 10 | 0 | 10 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01.01.02 | Reviews & Collaboration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Vincent Riot | (1.10) Task/item is a modification of an existing design | 0% | Level 4 Milestone | Management/Administration | [12 empty] | CD-3a | Critical Path to CD-3a | Project Management
FALSE |  | SR552590 | Prep for Sensor MRR (TS1-TS3) | LSST Forecast - B57 - B1 | 10 | 0 | 2015-07-20 | 2015-08-21 | 0 | 2015-07-20 | 2015-08-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-08-17 | 2015-08-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 24 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.07.01 | Cleanroom Development & Commissioning | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Assembly and Test Facility (TEC) | Test Stand Effort | [5 empty] | Science Raft - Assembly and Test Facility | [6 empty] | Test Stand - Reviews |  | Science Raft System
FALSE |  | CRYO21950 | Generate Manufacturing Docs - Grid Assembly | LSST Forecast - B57 - B1 | 8 | 0 | 2015-07-24 | 2016-04-27 | 0 | 2015-07-24 | 2016-04-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-02-24 | 2016-03-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 8 | 183 |  | Complete | 100% | 32 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.04 | Grid Assembly | 32 | 32 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Grid Assembly (TEC) | [6 empty] | Grid Assembly
FALSE |  | OP530490 | RCV: Critical Design Review - L1-L2 Assembly - Phase 2 (MS10) | LSST Forecast - B57 - B1 | 1 | 0 | 2015-07-27 | 2015-09-11 | 0 | 2015-07-27 | 2015-09-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-13 | 2019-06-13 | 0 | 0 | 0 | 0 | 0 | 5 | FALSE | Normal | FALSE | 2015-09-11 | 2015-09-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 5 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 33 |  | Complete | 100% | 56 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 56 | 56 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 0% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | L1-L2 Assembly (TEC) | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly) |  |  |  | L1-L2 Opto-Mechanics |  |  |  | CP - CAMM2100 (L1-L2 Assembly Phase 2 FDR)
FALSE |  | CAMF663700 | Final Check & Approve Detail Dwgs - Filter Loader | LSST Forecast - B57 - B1 | 24 | 0 | 2015-08-01 | 2015-08-30 | 0 | 2015-08-01 | 2015-08-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-09-01 | 2015-10-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 24 | 20 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.02 | Filter Loader | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Design/Engineering
FALSE |  | CCS127200 | COMP: Sensor 1st Article & Management Reports - eTraveler | LSST Forecast - B57 - B1 | 0 | 0 | 2015-08-01 | 2015-08-01 | 0 | 2015-08-01 | 2015-08-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2015-09-14 | 2015-09-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.10 | E Manufacturing | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Tony Johnson |  |  | Level 4 Milestone | Design/Engineering | [14 empty] | CCS Infrastructure
FALSE |  | CR230360 | Generate Final ICD - Corner raft sensor assembly to wavefront sensor | LSST Forecast - B57 - B1 | 10 | 0 | 2015-08-03 | 2015-08-14 | 0 | 2015-08-03 | 2015-08-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-10-20 | 2015-11-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 0 | 0 | 0 | 6 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 16 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 16 | 16 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | SR530600 | TS5 - Cryo Supt. Fixture Fab and Assembly | LSST Forecast - B57 - B1 | 10 | 0 | 2015-08-03 | 2015-10-30 | 0 | 2015-08-03 | 2015-10-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-09-01 | 2015-09-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 63 |  | Complete | 100% | 160 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.02 | RSA & RTM Warm-Cold Metrology (TS5) | 160 | 160 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 5 - Procurement & Fabrication |  | Science Raft System
FALSE |  | CR230370 | Generate Final ICD - Corner raft sensor assembly to Guide Sensor | LSST Forecast - B57 - B1 | 10 | 0 | 2015-08-03 | 2015-08-14 | 0 | 2015-08-03 | 2015-08-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-08-03 | 2015-08-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 10 |  | Complete | 100% | 16 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 16 | 16 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CR220700 | Design prototype - corner raft test setup EM revision (sidewall, cooling bars, support rods) | LSST Forecast - B57 - B1 | 15 | 0 | 2015-08-07 | 2015-10-05 | 0 | 2015-08-07 | 2015-10-05 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2015-08-06 | 2015-08-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 40 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Tower Module (CRTM) (TEC) | CRTM Prototype EM Revision | [5 empty] | Corner Raft Tower Module (CRTM)
FALSE |  | CCS105200 | Test/Validate Release 1 - CCS MCM | LSST Forecast - B57 - B1 | 13 | 0 | 2015-08-17 | 2015-08-23 | 0 | 2015-08-17 | 2015-08-23 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-10-07 | 2015-10-23 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 13 | 5 |  | Complete | 100% | 208 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.03 | CCS Master Control Module | 208 | 208 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering | [7 empty] | CCS Core (TEC)
FALSE |  | SR343220 | Perform vendor qualification & Extended VST | LSST Forecast - B57 - B1 | 19 | 0 | 2015-08-17 | 2015-10-30 | 0 | 2015-08-17 | 2015-10-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2015-11-02 | 2015-11-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 3 | 0 | 0 | 2 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 19 | 54 |  | Complete | 100% | 174 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 174 | 174 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation | [7 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [6 empty] | History Activity - Cannot Change |  | Science Raft System
FALSE |  | CRYO60880 | Final Design & Analysis - Sys Architecture and Functional Layout - Refrigeration | LSST Forecast - B57 - B1 | 60 | 0 | 2015-09-01 | 2016-04-30 | 0 | 2015-09-01 | 2016-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2015-10-01 | 2016-01-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 159 |  | Complete | 100% | 220 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 220 | 220 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | CRYO60890 | Final Design & Analysis - Compressor Chassis - Refrigeration | LSST Forecast - B57 - B1 | 60 | 0 | 2015-09-01 | 2016-04-30 | 0 | 2015-09-01 | 2016-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-10-01 | 2016-01-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 159 |  | Complete | 100% | 108 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 108 | 108 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | CRYO60900 | Final Design & Analysis - Valve & Filters/Desiccators - Refrigeration | LSST Forecast - B57 - B1 | 60 | 0 | 2015-09-01 | 2016-04-30 | 0 | 2015-09-01 | 2016-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-10-01 | 2016-01-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 159 |  | Complete | 100% | 108 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 108 | 108 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | CRYO60910 | Final Design & Analysis - Control Chassis and Instrumentation - Refrigeration | LSST Forecast - B57 - B1 | 60 | 0 | 2015-09-01 | 2016-04-30 | 0 | 2015-09-01 | 2016-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-10-01 | 2016-01-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 159 |  | Complete | 100% | 128 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 128 | 128 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | CRYO60920 | Final Design & Analysis - OP Evacuate, Purge & Charge HW - Refrigeration | LSST Forecast - B57 - B1 | 60 | 0 | 2015-09-01 | 2016-04-30 | 0 | 2015-09-01 | 2016-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-10-01 | 2016-01-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 159 |  | Complete | 100% | 264 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 264 | 264 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | CRYO11552 | Finalize Design Phase 2 - Cryostat Assembly | LSST Forecast - B57 - B1 | 50 | 0 | 2015-09-01 | 2015-10-31 | 0 | 2015-09-01 | 2015-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-10-01 | 2015-12-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 50 | 43 |  | Complete | 100% | 105 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 105 | 105 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Housing & Assembly (TEC) |  | ICD's for Phase 3 |  |  |  |  | Cryostat Assembly |  |  | Final Design Link
FALSE |  | CRYO11554 | Finalize Analysis - Phase 2 - Cryostat Assembly | LSST Forecast - B57 - B1 | 47 | 0 | 2015-09-05 | 2015-10-31 | 0 | 2015-09-05 | 2015-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-10-05 | 2015-12-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 47 | 39 |  | Complete | 100% | 88 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 88 | 88 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Housing & Assembly (TEC) | [6 empty] | Cryostat Assembly
FALSE |  | CRYO18302 | COMP: Cryogenic Feedthrough Test Parts - Cryo & Cold Plate | LSST Forecast - B57 - B1 | 0 | 0 | 2015-09-14 | 2015-09-14 | 0 | 2015-09-14 | 2015-09-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2015-12-14 | 2015-12-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.03 | Cryo and Cold Plates | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Engineering Test/Validation
FALSE |  | OP530500 | Critical Design Review Actions Complete - L1-L2 Assembly - Phase 2 | LSST Forecast - B57 - B1 | 20 | 0 | 2015-09-14 | 2015-10-30 | 0 | 2015-09-14 | 2015-10-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-03 | 2019-09-03 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-10-01 | 2015-10-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 2 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 34 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Scott Winters | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor | [5 empty] | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly) |  |  |  | L1-L2 Opto-Mechanics |  |  |  | CP - CAMM2100 (L1-L2 Assembly Phase 2 FDR)
FALSE |  | SR522605 | COMP: Test Stand 2 assy dwg's complete | LSST Forecast - B57 - B1 | 0 | 0 | 2015-09-18 | 2015-09-18 | 0 | 2015-09-18 | 2015-09-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2015-10-29 | 2015-10-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.02 | Sensor Dimensional Metrology (TS2) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl |  |  | Level 4 Milestone | Design/Engineering | [8 empty] | Test Stand Effort | [12 empty] | Test Stand 2 - Design |  | Science Sensors
FALSE |  | SR522935 | AVAIL: Test Stand 2 - Ready for Production | LSST Forecast - B57 - B1 | 0 | 0 | 2015-09-18 | 2015-09-18 | 0 | 2015-09-18 | 2015-09-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2015-10-29 | 2015-10-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 11 | 0 | 11 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.03.02 | Sensor Dimensional Metrology (TS2) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl |  |  | Level 5 Milestone | Fabrication/Assembly | [8 empty] | Test Stand Effort | [12 empty] | Test Stand 2 - Assembly & Commissioning |  | Science Sensors
FALSE |  | CRYO18228 | COMP: Flow/Thermal Design Prototype - Cryo & Cold Plate | LSST Forecast - B57 - B1 | 0 | 0 | 2015-09-25 | 2015-09-25 | 0 | 2015-09-25 | 2015-09-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2015-11-02 | 2015-11-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 2 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.03 | Cryo and Cold Plates | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Engineering Test/Validation
FALSE |  | CAMF806080 | NEED: CCS Pre-Production - Auto Changer | LSST Forecast - B57 - B1 | 0 | 0 | 2015-09-29 | 2015-09-29 | 0 | 2015-09-29 | 2015-09-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-06-19 | 2017-06-19 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.01 | Auto Changer | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  | Level 5 Milestone | Engineering Test/Validation
FALSE |  | OP531730 | AVAIL: Anti-Reflection Coating witness sample | LSST Forecast - B57 - B1 | 0 | 0 | 2015-09-30 | 2015-09-30 | 0 | 2015-09-30 | 2015-09-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2015-10-29 | 2015-10-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  | Level 5 Milestone | Engineering Test/Validation
FALSE |  | CCS119850 | COMP: Core 2.1 Release | LSST Forecast - B57 - B1 | 0 | 0 | 2015-10-01 | 2015-10-01 | 0 | 2015-10-01 | 2015-10-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-31 | 2019-05-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2015-12-01 | 2015-12-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.02.04 | CCS Core 3.0 Release (Support MCM) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  | Level 4 Milestone | Design/Engineering
FALSE |  | CCS100600 | Management FY16 - CCS | LSST Forecast - B57 - B1 | 245 | 0 | 2015-10-01 | 2016-09-30 | 0 | 2015-10-01 | 2016-09-30 | 0 | 2019-06-01 | 2019-06-01 | 2021-11-15 | 2021-11-15 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2015-10-01 | 2016-09-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 3 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 245 | 244 |  | Complete | 100% | 580 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.01 | CCS Integration & Management | 580 | 580 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Management/Administration |  | Construction Management | [5 empty] | CCS Integration & Management (TEC) | [6 empty] | Camera Control System
FALSE |  | SR345850 | Procurement of RTB (Fab and Assembly) | LSST Forecast - B57 - B1 | 7 | 0 | 2015-10-01 | 2015-10-09 | 0 | 2015-10-01 | 2015-10-09 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-10-01 | 2015-10-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 7 | 7 |  | Complete | 100% | 4 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.06 | Electronics Production Test | 4 | 4 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering | [7 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [6 empty] | RTB - Procurement & Fabrication |  | Science Raft System
FALSE |  | SR552650 | Install & Commission Test Stand 4 | LSST Forecast - B57 - B1 | 15 | 0 | 2015-10-01 | 2016-02-15 | 0 | 2015-10-01 | 2016-02-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-10-01 | 2015-10-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 91 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.07.01 | Cleanroom Development & Commissioning | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Assembly and Test Facility (TEC) | Test Stand Effort | [5 empty] | Science Raft - Assembly and Test Facility | [6 empty] | Test Stand 4 - Assembly & Commissioning |  | Science Raft System
FALSE |  | CCS108800 | Procurement Process - Components - Diagnostic Cluster for I&T | LSST Forecast - B57 - B1 | 20 | 0 | 2015-10-02 | 2016-06-15 | 0 | 2015-10-02 | 2016-06-15 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-11-02 | 2015-12-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 10 | 10 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 168 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.09 | CCS Diagnostic Cluster and Visualization | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  |  | Procurement
FALSE |  | ITC24600 | Assemble and test BOT prototype | LSST Forecast - B57 - B1 | 20 | 0 | 2015-10-02 | 2016-06-30 | 0 | 2015-10-02 | 2016-06-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-10-02 | 2015-10-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 179 |  | Complete | 100% | 160 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.02.01 | Bench For Optical Testing (BOT) | 160 | 160 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 13% |  | Engineering Test/Validation |  | Commissioning and Testing | [5 empty] | Verification Test Systems (TEC) | [6 empty] | Verification Test Systems
FALSE |  | CR220800 | Assemble & Test prototype - corner raft test setup EM revision (sidewall, cooling bars, support rods) | LSST Forecast - B57 - B1 | 15 | 0 | 2015-10-07 | 2016-02-25 | 0 | 2015-10-07 | 2016-02-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-12-21 | 2016-01-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 3 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 94 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Tower Module (CRTM) (TEC) | CRTM Prototype EM Revision | [5 empty] | Corner Raft Tower Module (CRTM)
FALSE |  | SR552540 | Prep for SRTM MRR | LSST Forecast - B57 - B1 | 2 | 0 | 2015-10-19 | 2016-09-12 | 0 | 2015-10-19 | 2016-09-12 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2015-12-07 | 2015-12-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 225 |  | Complete | 100% | 160 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.01 | Science Raft Tower Module (SRTM) | 160 | 160 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Construction Management | [5 empty] | Science Raft Tower Module (SRTM) (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Tower Module |  | Science Raft System
FALSE |  | CRYO60820 | COMP: Heat Ex Test Stand #2 | LSST Forecast - B57 - B1 | 0 | 0 | 2015-10-27 | 2015-10-27 | 0 | 2015-10-27 | 2015-10-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2016-01-21 | 2016-01-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Engineering Test/Validation
FALSE |  | OP530650 | AWARD: L1-L2 Assembly - Phase 4a | LSST Forecast - B57 - B1 | 1 | 0 | 2015-10-29 | 2015-10-29 | 0 | 2015-10-29 | 2015-10-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-03 | 2019-09-03 | 2052000 | 2052000 | 0 | 0 | 0 | 5 | FALSE | Normal | FALSE | 2015-11-16 | 2015-11-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 2052000 | 2052000 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | B1 Procurement Commitment (C5.1) | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 2% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | L1-L2 Assembly (TEC) | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly) |  |  |  | L1-L2 Opto-Mechanics
FALSE |  | OP530880 | AWARD: L1-L2 Assembly - Phase 4b | LSST Forecast - B57 - B1 | 1 | 0 | 2015-10-29 | 2015-10-29 | 0 | 2015-10-29 | 2015-10-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-03 | 2019-09-03 | 2921762 | 2921762 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2015-12-02 | 2015-12-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 2921762 | 2921762 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | B1 Procurement Commitment (C5.1) | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 2% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | L1-L2 Assembly (TEC) | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly) |  |  |  | L1-L2 Opto-Mechanics
FALSE |  | SR530650 | TS4 - generate Work-Flow | LSST Forecast - B57 - B1 | 20 | 0 | 2015-11-02 | 2016-01-29 | 0 | 2015-11-02 | 2016-01-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-11-02 | 2015-12-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 59 |  | Complete | 100% | 160 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.01 | RSA Assembly (TS4) | 160 | 160 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 4 - Design |  | Science Raft System
FALSE |  | SE223170 | Corner Raft sub-system FDR contamination compliance | LSST Forecast - B57 - B1 | 19 | 0 | 2015-11-09 | 2016-04-29 | 0 | 2015-11-09 | 2016-04-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-12-01 | 2016-01-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 19 | 110 |  | Complete | 100% | 44 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.03 | Thermal and contamination system analysis | 44 | 44 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | DAQ340800 | AVAIL: Prototype - RDS/RDC | LSST Forecast - B57 - B1 | 0 | 0 | 2015-11-15 | 2015-11-15 | 0 | 2015-11-15 | 2015-11-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | FALSE | 2016-02-17 | 2016-02-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.09.02 | Raft Data Server/Client Software (RDS/RDC) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer |  |  | Level 5 Milestone | Engineering Test/Validation | [9 empty] | ICD's for Phase 3
FALSE |  | CR240680 | Prep for C_FDR - WEB | LSST Forecast - B57 - B1 | 9 | 0 | 2015-11-17 | 2016-02-26 | 0 | 2015-11-17 | 2016-02-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-01-13 | 2016-01-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 8 | 0 | 5 | 0 | 0 | 3 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 9 | 59 |  | Complete | 100% | 48 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.01 | Wavefront Electronics Board (WEB) | 48 | 48 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Electronics (TEC) | WEB EM | [5 empty] | Corner Raft Electronics
FALSE |  | CR241980 | Prep for C_FDR - GEB | LSST Forecast - B57 - B1 | 10 | 0 | 2015-11-17 | 2016-02-26 | 0 | 2015-11-17 | 2016-02-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-02-10 | 2016-02-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 1 | 5 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 59 |  | Complete | 100% | 48 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.02 | Guider Electronics Board (GEB) | 48 | 48 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Electronics (TEC) | GEB EM | [5 empty] | Corner Raft Electronics
FALSE |  | SR530870 | TS5 - Verification testing and commissioning | LSST Forecast - B57 - B1 | 10 | 0 | 2015-11-23 | 2016-11-30 | 0 | 2015-11-23 | 2016-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-12-18 | 2016-01-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 2 | 0 | 0 | 2 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 255 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.02 | RSA & RTM Warm-Cold Metrology (TS5) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 5 - Assembly & Commissioning |  | Science Raft System
FALSE |  | CRYO60620 | COMP: Subscale Test Stand (Elevation Articulation) | LSST Forecast - B57 - B1 | 0 | 0 | 2015-11-25 | 2015-11-25 | 0 | 2015-11-25 | 2015-11-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Finish Milestone | FALSE | 2016-01-25 | 2016-01-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 0 | 0 | 1 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Engineering Test/Validation
FALSE |  | SR341160 | Test - Prod ASPIC | LSST Forecast - B57 - B1 | 49 | 0 | 2015-11-27 | 2015-12-21 | 0 | 2015-11-27 | 2015-12-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 5 | FALSE | Normal | FALSE | 2015-12-15 | 2016-02-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 1 | 0 | 2 | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 140 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 49 | 15 |  | Complete | 100% | 400 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.01 | ASPIC | 400 | 400 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [6 empty] | ASPICS |  | Science Raft System
FALSE |  | CAMF667500 | Final Check & Approve Detail Dwgs - Carousel | LSST Forecast - B57 - B1 | 20 | 0 | 2015-12-01 | 2017-01-27 | 0 | 2015-12-01 | 2017-01-27 | 0 | 2019-06-01 | 2019-06-01 | 2018-10-16 | 2018-10-16 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-01-20 | 2016-02-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 274 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Design/Engineering
FALSE |  | CRYO18244 | COMP: Cryoplate Flexure Test Article - Cryo & Cold Plate | LSST Forecast - B57 - B1 | 0 | 0 | 2015-12-01 | 2015-12-01 | 0 | 2015-12-01 | 2015-12-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2016-01-04 | 2016-01-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.03 | Cryo and Cold Plates | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Engineering Test/Validation
FALSE |  | CCS116680 | Build TS8 - Production | LSST Forecast - B57 - B1 | 25 | 0 | 2015-12-01 | 2016-03-31 | 0 | 2015-12-01 | 2016-03-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-02-09 | 2016-03-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 75 |  | Complete | 100% | 96 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.01.04 | Test Stand 8 (REB Based) | 96 | 96 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 11% |  | Fabrication/Assembly | [7 empty] | CCS HCU (TEC)
FALSE |  | CR222590 | Assemble Cold Single CCD test stand | LSST Forecast - B57 - B1 | 4 | 0 | 2015-12-07 | 2016-02-19 | 0 | 2015-12-07 | 2016-02-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-03-01 | 2016-03-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 1 | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 42 |  | Complete | 100% | 16 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 16 | 16 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | [11 empty] | Corner Raft Tower Module (CRTM) (TEC)
FALSE |  | CRYO17000 | Generate Manufacturing Docs - Cryo & Cold Plate | LSST Forecast - B57 - B1 | 30 | 0 | 2015-12-09 | 2017-04-28 | 0 | 2015-12-09 | 2017-04-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-04-06 | 2016-05-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 332 |  | Complete | 100% | 64 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.03 | Cryo and Cold Plates | 64 | 64 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryo and Cold Plates (TEC) | [6 empty] | Cryo and Cold Plates
FALSE |  | SR530090 | TS8 - Assembly technical support | LSST Forecast - B57 - B1 | 30 | 0 | 2015-12-21 | 2016-06-30 | 0 | 2015-12-21 | 2016-06-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-01-04 | 2016-02-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 132 |  | Complete | 100% | 128 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.05 | RTM Electro-Optical Testing (TS8) | 128 | 128 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 8 - Procurement & Fabrication |  | Science Raft System
FALSE |  | SR530430 | PREP for TS6 MRR | LSST Forecast - B57 - B1 | 8 | 0 | 2015-12-30 | 2015-12-31 | 0 | 2015-12-30 | 2015-12-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2015-12-30 | 2016-01-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 1 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 8 | 1 |  | Complete | 100% | 30 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.03 | RTM Assembly (TS6) | 30 | 30 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 6 - Reviews |  | Science Raft System

## 2016 Details
Fuse® Analyst Report
Workbook: Workbook1 - 8168 Activities
Schedule Quality
Created on: 8/5/2019
Created by: brackett
2016: Detailed View | 2016: Detailed View | 2016: Detailed View
Number of Lags
Total number of activities that have lags in their predecessors. This number should not exceed 5%.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | Previous Start | Previous Finish | Percent Complete | Previous Remaining Duration | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | IsLevelOfEffort | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | Global_Basis of Estimate | Global_Cobra Cost Class | Cobra PMT (EV Method)_Global | Global_Color of Money | Global_Control Account Manager | Global_Design Maturity | Global_Judgement Factor | Global_Milestone Levels | Global_Project Phase | Global_Funding Source | Global_EDIA Survey | Global_MS Type | Phase | NSF Milestones | Loading Curve | Sensor Vendor | LSST_CA | Summary Schedule | ICD for NSF Input | LSST Camera Critical Paths | CD2 Budget Changes | DOE Reviews | Critical Path (CD Reviews) | LSST WP Summary | Critical Path (Camera Delivery) | AWARD / NEED Sub-System | Final Design Key Links | CP - CAMM2100 | CP - CAMM2130 | CP - CAMM2160 | BNL Work Org | Last ETC Update | BNL WBS | LSST Story List | Sum Sch 01 (Camera) | Sum Sch 02 (IT w/Needs) | Sum Sch 03 (Sensors_RTM_IT) | LSST Raft Particulate Mitigation | LSST RTM
FALSE |  | SR332505 | FA Testing - Sensors V1 (1 Set, 5 sensors, 1-5) | LSST Forecast - B57 - B1 | 32 | 0 | 2016-01-04 | 2016-11-25 | 0 | 2016-01-04 | 2016-11-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-02-02 | 2016-03-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 4 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 32 | 228 |  | Complete | 100% | 210 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 210 | 210 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Catalog Listing or Industrial Construction Databases | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [6 empty] | Science Sensors Acceptance | [6 empty] | Sensors Vendor 1 |  | Science Sensors
FALSE |  | SR530060 | TS8 - fabrication/assy - source optical train | LSST Forecast - B57 - B1 | 25 | 0 | 2016-01-04 | 2016-06-30 | 0 | 2016-01-04 | 2016-06-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-02-01 | 2016-03-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 10 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 125 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.05 | RTM Electro-Optical Testing (TS8) | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 8 - Procurement & Fabrication |  | Science Raft System
FALSE |  | SR530080 | TS8 - fabrication/assy - point projector/mask | LSST Forecast - B57 - B1 | 35 | 0 | 2016-01-04 | 2016-06-24 | 0 | 2016-01-04 | 2016-06-24 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-02-01 | 2016-03-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 35 | 121 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.05 | RTM Electro-Optical Testing (TS8) | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 8 - Procurement & Fabrication |  | Science Raft System
FALSE |  | CR220580 | Final Design & Analysis - Corner raft tower tooling (Cage Holding Struct, Board Insert Fix, Trans Cart) | LSST Forecast - B57 - B1 | 33 | 0 | 2016-01-11 | 2016-02-10 | 0 | 2016-01-11 | 2016-02-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-02-01 | 2016-03-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 33 | 21 |  | Complete | 100% | 90 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 90 | 90 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Tower Module (CRTM) (TEC) | CRTM Final Design | [5 empty] | Corner Raft Tower Module (CRTM)
FALSE |  | SE223180 | L3 sub-system FDR contamination compliance | LSST Forecast - B57 - B1 | 20 | 0 | 2016-01-18 | 2016-07-07 | 0 | 2016-01-18 | 2016-07-07 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-02-01 | 2016-02-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 119 |  | Complete | 100% | 44 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.03 | Thermal and contamination system analysis | 44 | 44 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | CRYO53090 | Vendor Lead Time - All Parts - System Flushing for SLAC System | LSST Forecast - B57 - B1 | 30 | 0 | 2016-01-20 | 2016-08-30 | 0 | 2016-01-20 | 2016-08-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-05-24 | 2016-07-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 40 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 156 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc)
FALSE |  | CRYO53100 | RCV: All Parts - System Flushing for SLAC System | LSST Forecast - B57 - B1 | 30 | 0 | 2016-01-25 | 2016-06-24 | 0 | 2016-01-25 | 2016-06-24 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 35000 | 35000 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-07-21 | 2016-08-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 107 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 35000 | 35000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% | Level 4 Milestone | Procurement | [7 empty] | Refrigeration System (TEC)
FALSE |  | DAQ360500 | COMP: Prototype - IMS/IMC | LSST Forecast - B57 - B1 | 0 | 0 | 2016-02-08 | 2016-02-08 | 0 | 2016-02-08 | 2016-02-08 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2016-04-05 | 2016-04-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.09.01 | Image Management/Server/Client Software | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer |  |  | Level 4 Milestone | Engineering Test/Validation
FALSE |  | CR222560 | RCV: Procure EO testing support instrumentation | LSST Forecast - B57 - B1 | 20 | 0 | 2016-02-08 | 2016-10-31 | 0 | 2016-02-08 | 2016-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 49000 | 49000 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2016-02-01 | 2016-02-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 186 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 49000 | 49000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | [11 empty] | Corner Raft Tower Module (CRTM) (TEC)
FALSE |  | CRYO11703 | Fabrication & Assembly - Station 1 Assy - Cryostat Assembly | LSST Forecast - B57 - B1 | 54 | 0 | 2016-03-01 | 2017-01-17 | 0 | 2016-03-01 | 2017-01-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-04-01 | 2016-06-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 54 | 230 |  | Complete | 100% | 48 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 48 | 48 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package |  | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 10% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Cryostat Housing & Assembly (TEC)
FALSE |  | CRYO11749 | Final Design & Engineering - Purge Box - Cryostat Assembly | LSST Forecast - B57 - B1 | 40 | 0 | 2016-03-05 | 2016-12-16 | 0 | 2016-03-05 | 2016-12-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-08-05 | 2016-09-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 199 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Housing & Assembly (TEC)
FALSE |  | CRYO11709 | Fabrication & Assembly - Station 2 Assy - Cryostat Assembly | LSST Forecast - B57 - B1 | 54 | 0 | 2016-03-06 | 2017-01-17 | 0 | 2016-03-06 | 2017-01-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-05-06 | 2016-07-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 40 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 54 | 226 |  | Complete | 100% | 48 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 48 | 48 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package |  | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 10% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Cryostat Housing & Assembly (TEC)
FALSE |  | CR222650 | Procure Cold Raft Electronics test stand Commercial Components - Vendor Lead Time | LSST Forecast - B57 - B1 | 40 | 0 | 2016-03-21 | 2016-09-30 | 0 | 2016-03-21 | 2016-09-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-04-25 | 2016-06-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 20 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 136 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Vincent Riot
FALSE |  | CR222660 | RCV: Procure Cold Raft Electronics test stand Commercial Components | LSST Forecast - B57 - B1 | 20 | 0 | 2016-03-21 | 2016-10-31 | 0 | 2016-03-21 | 2016-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 21000 | 21000 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-05-23 | 2016-06-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 157 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 21000 | 21000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | [11 empty] | Corner Raft Tower Module (CRTM) (TEC)
FALSE |  | OP520960 | PROC: Procure parts for filter mass simulator | LSST Forecast - B57 - B1 | 80 | 0 | 2016-03-25 | 2016-10-11 | 0 | 2016-03-25 | 2016-10-11 | 0 | 2019-06-01 | 2019-06-01 | 2018-10-30 | 2018-10-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-04-01 | 2016-07-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 80 | 139 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 26% |  | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Filters (TEC) | Prototype Filter Assemblies |  |  | Maybe |  |  | Filter Opto-Mechanics
FALSE |  | CRYO11721 | Fabrication & Assembly - Faro Arm Stand - Cryostat Assembly | LSST Forecast - B57 - B1 | 40 | 0 | 2016-04-02 | 2016-12-16 | 0 | 2016-04-02 | 2016-12-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-05-02 | 2016-06-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 10 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 184 |  | Complete | 100% | 32 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 32 | 32 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package |  | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 10% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Cryostat Housing & Assembly (TEC)
FALSE |  | CRYO11740 | Vendor Lead Time - All Parts - Test Fixtures - Cryostat Assembly | LSST Forecast - B57 - B1 | 30 | 0 | 2016-04-02 | 2017-03-28 | 0 | 2016-04-02 | 2017-03-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-05-02 | 2016-06-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 10 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 256 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 10% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor
FALSE |  | SR330270 | Production Lot 1 Sensors - V1 - Assembly & Test | LSST Forecast - B57 - B1 | 50 | 0 | 2016-04-04 | 2017-08-18 | 0 | 2016-04-04 | 2017-08-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 10 | FALSE | Normal | FALSE | 2017-03-01 | 2017-05-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 10 | 0 | 1 | 9 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 50 | 347 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien |  |  |  | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 14% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor | [10 empty] | Sensor | [7 empty] | Sensors Vendor 1 |  | Science Sensors
FALSE |  | CRYO11741 | RCV: All Parts - Test Fixtures - Cryostat Assembly | LSST Forecast - B57 - B1 | 20 | 0 | 2016-04-16 | 2017-02-28 | 0 | 2016-04-16 | 2017-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 10000 | 10000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-05-16 | 2016-06-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 226 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 10000 | 10000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 5% | Level 4 Milestone | Procurement | [7 empty] | Cryostat Housing & Assembly (TEC)
FALSE |  | CCS108900 | Vendor Lead Time - Components - Diagnostic Cluster for I&T | LSST Forecast - B57 - B1 | 45 | 0 | 2016-05-02 | 2016-08-27 | 0 | 2016-05-02 | 2016-08-27 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-05-02 | 2016-07-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 30 | 30 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 45 | 83 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.09 | CCS Diagnostic Cluster and Visualization | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  |  | Procurement
FALSE |  | CRYO60700 | Fab and Assembly - Subscale Test Stand (Add Cold System) | LSST Forecast - B57 - B1 | 50 | 0 | 2016-05-09 | 2016-08-09 | 0 | 2016-05-09 | 2016-08-09 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-06-01 | 2016-08-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 15 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 50 | 64 |  | Complete | 100% | 928 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 928 | 928 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 16% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | SR330165 | RCV: First Articles Sensor - V1 (1 Set, Batch 1b, 4 Sensors, 2-5) | LSST Forecast - B57 - B1 | 5 | 0 | 2016-05-10 | 2016-11-10 | 0 | 2016-05-10 | 2016-11-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 490000 | 490000 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-06-01 | 2016-06-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 129 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 490000 | 490000 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 20% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC) | [5 empty] | Sensor | [7 empty] | Sensors Vendor 1 |  | Science Sensors
FALSE |  | CCS207800 | Develop Simple Camera Command Simulator for Use by OCS - CCS/OCS | LSST Forecast - B57 - B1 | 15 | 0 | 2016-05-11 | 2016-05-29 | 0 | 2016-05-11 | 2016-05-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-17 | 2019-10-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-11-28 | 2016-12-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 13 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.04 | CCS/OCS Bridge | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Testing/Integration | [7 empty] | CCS Core (TEC)
FALSE |  | CR242100 | PROC: GEB EM (PCB & components) | LSST Forecast - B57 - B1 | 10 | 0 | 2016-06-01 | 2016-06-24 | 0 | 2016-06-01 | 2016-06-24 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 22000 | 22000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-07-01 | 2016-07-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 17 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.02 | Guider Electronics Board (GEB) | 0 | 0 | 0 | 22000 | 22000 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Procurement | [7 empty] | Corner Raft Electronics (TEC) | GEB EM
FALSE |  | SR332530 | FA Testing - Sensors V2 (Sensor #1) | LSST Forecast - B57 - B1 | 5 | 0 | 2016-06-10 | 2016-07-11 | 0 | 2016-06-10 | 2016-07-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-07-01 | 2016-07-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 20 |  | Complete | 100% | 42 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 42 | 42 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  | Percent Complete on Work Package |  | Bill Wahl | [5 empty] | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [13 empty] | Sensors Vendor 2 |  | Science Sensors
FALSE |  | CRYO60710 | Test - Subscale Test Stand (Add Cold System) | LSST Forecast - B57 - B1 | 50 | 0 | 2016-06-13 | 2016-12-16 | 0 | 2016-06-13 | 2016-12-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-07-01 | 2016-09-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 50 | 130 |  | Complete | 100% | 177 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 177 | 177 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 16% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | SR561000 | Prepare C/C Material (24 Rafts) | LSST Forecast - B57 - B1 | 1 | 0 | 2016-06-15 | 2016-06-16 | 0 | 2016-06-15 | 2016-06-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-07-18 | 2016-07-18 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 1 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.02 | Science Raft Sensor Assembly (SRSA) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Bill Wahl | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement | [21 empty] | Sensor Assembly |  | Science Raft System
FALSE |  | SR343743_1 | Prepare for REB5 MRR | LSST Forecast - B57 - B1 | 14 | 0 | 2016-06-15 | 2016-08-12 | 0 | 2016-06-15 | 2016-08-12 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-06-15 | 2016-07-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 14 | 41 |  | Complete | 100% | 32 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 32 | 32 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | [11 empty] | Science Raft Electronics (TEC) | [13 empty] | First Article REB-5 Build |  | Science Raft System
FALSE |  | CCS120730 | RCV: Components - Parts - Trending & Configuration Database | LSST Forecast - B57 - B1 | 22 | 0 | 2016-07-01 | 2016-08-13 | 0 | 2016-07-01 | 2016-08-13 | 0 | 2019-06-01 | 2019-06-01 | 2020-02-18 | 2020-02-18 | 13000 | 13000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-08-01 | 2016-08-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 22 | 30 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.06 | CCS Database | 0 | 0 | 0 | 13000 | 13000 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Procurement | [7 empty] | CCS Core (TEC) | [6 empty] | Shutter Engin/Dsn
FALSE |  | CCS109300 | Vendor Lead Time - Components - Visulization System for I&T | LSST Forecast - B57 - B1 | 30 | 0 | 2016-07-01 | 2016-07-12 | 0 | 2016-07-01 | 2016-07-12 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-08-01 | 2016-09-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 10 | 10 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 6 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.09 | CCS Diagnostic Cluster and Visualization | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  |  | Procurement
FALSE |  | CCS200160 | Vendor Lead Time - Parts - Single Bay HCU | LSST Forecast - B57 - B1 | 15 | 0 | 2016-07-01 | 2016-10-21 | 0 | 2016-07-01 | 2016-10-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-12-01 | 2017-01-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 10 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 78 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.08.01 | Single Bay HCU | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  |  | Procurement
FALSE |  | SR530110 | TS8 - exercise apparatus, scripting and analysis | LSST Forecast - B57 - B1 | 10 | 0 | 2016-07-01 | 2016-10-31 | 0 | 2016-07-01 | 2016-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-08-01 | 2016-08-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 84 |  | Complete | 100% | 480 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.05 | RTM Electro-Optical Testing (TS8) | 480 | 480 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 8 - Assembly & Commissioning |  | Science Raft System
FALSE |  | SR330705 | Sensors Production Lot 1 - V2- Backside Batch and Test (21-65) | LSST Forecast - B57 - B1 | 65 | 0 | 2016-07-01 | 2016-07-26 | 0 | 2016-07-01 | 2016-07-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 10 | FALSE | Normal | FALSE | 2016-08-01 | 2016-10-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 10 | 0 | 1 | 9 | 0 | 0 | 1 | 0 | 3 | 0 | 0 | 49 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 65 | 16 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien |  |  |  | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 14% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor | [10 empty] | Sensor | [7 empty] | Sensors Vendor 2
FALSE |  | CRYO11710 | Vendor Lead Time - All Parts - Station 2 Assy - Cryostat Assembly | LSST Forecast - B57 - B1 | 30 | 0 | 2016-07-01 | 2016-11-30 | 0 | 2016-07-01 | 2016-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-08-01 | 2016-09-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 108 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 10% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor
FALSE |  | CRYO11717 | RCV: All Parts - Off-Load Frame - Cryostat Assembly | LSST Forecast - B57 - B1 | 20 | 0 | 2016-07-01 | 2017-02-28 | 0 | 2016-07-01 | 2017-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 25000 | 25000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-08-15 | 2016-09-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 172 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 25000 | 25000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 5% | Level 4 Milestone | Procurement | [7 empty] | Cryostat Housing & Assembly (TEC)
FALSE |  | CRYO11716 | Vendor Lead Time - All Parts - Off-Load Frame - Cryostat Assembly | LSST Forecast - B57 - B1 | 30 | 0 | 2016-07-01 | 2017-02-28 | 0 | 2016-07-01 | 2017-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-08-01 | 2016-09-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 10 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 172 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 10% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor
FALSE |  | CCS109400 | RCV: Components - Visualization System for I&T | LSST Forecast - B57 - B1 | 20 | 0 | 2016-07-15 | 2016-07-30 | 0 | 2016-07-15 | 2016-07-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 22000 | 22000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-08-15 | 2016-09-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 11 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.09 | CCS Diagnostic Cluster and Visualization | 0 | 0 | 0 | 22000 | 22000 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 4% |  | Procurement | [7 empty] | CCS Core (TEC) | [6 empty] | Shutter Engin/Dsn
FALSE |  | SR341161 | AVAIL: ASPIC Production (REB Batch 1) | LSST Forecast - B57 - B1 | 0 | 0 | 2016-07-15 | 2016-07-15 | 0 | 2016-07-15 | 2016-07-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2016-08-15 | 2016-08-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.01 | ASPIC | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Bill Wahl |  |  | Level 5 Milestone | [22 empty] | ASPICS |  | Science Raft System
FALSE |  | CR222760 | Procure Cold Raft Electronics enhancement Commercial Components - Vendor Lead Time | LSST Forecast - B57 - B1 | 20 | 0 | 2016-07-18 | 2016-12-20 | 0 | 2016-07-18 | 2016-12-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-08-01 | 2016-08-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 107 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Vincent Riot |  |  |  | Procurement
FALSE |  | CR222770 | RCV: Procure Cold Raft Electronics enhancement Commercial Components | LSST Forecast - B57 - B1 | 20 | 0 | 2016-07-18 | 2016-12-20 | 0 | 2016-07-18 | 2016-12-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 54299 | 54299 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-08-08 | 2016-09-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 107 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 54299 | 54299 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot |  |  |  | Procurement | [7 empty] | Corner Raft Tower Module (CRTM) (TEC)
FALSE |  | CCS109600 | Vendor Lead Time - Wall Mounted Displays - Diagnostic Cluster for I&T | LSST Forecast - B57 - B1 | 30 | 0 | 2016-08-01 | 2016-08-13 | 0 | 2016-08-01 | 2016-08-13 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-09-01 | 2016-10-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 10 | 10 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 10 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.09 | CCS Diagnostic Cluster and Visualization | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  |  | Procurement
FALSE |  | CR222670 | Procure and fabricate Cold Raft Electronics test stand holding cart/table - Support | LSST Forecast - B57 - B1 | 10 | 0 | 2016-08-01 | 2016-08-19 | 0 | 2016-08-01 | 2016-08-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-09-01 | 2016-09-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 5 | 5 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 14 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | [11 empty] | Corner Raft Tower Module (CRTM) (TEC)
FALSE |  | OP521800 | RCV: Readiness for Coating Report (MS2) - Filter Development Report and Witness Sample | LSST Forecast - B57 - B1 | 145 | 0 | 2016-08-02 | 2017-04-28 | 0 | 2016-08-02 | 2017-04-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-12-12 | 2019-12-12 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2016-08-01 | 2017-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 145 | 185 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 7% |  | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Filters (TEC)
FALSE |  | CCS109000 | RCV: Components - Diagnostic Cluster for I&T | LSST Forecast - B57 - B1 | 20 | 0 | 2016-08-11 | 2016-08-30 | 0 | 2016-08-11 | 2016-08-30 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 80000 | 80000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-11-11 | 2016-12-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 13 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.09 | CCS Diagnostic Cluster and Visualization | 0 | 0 | 0 | 80000 | 80000 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 4% |  | Procurement | [7 empty] | CCS Core (TEC) | [6 empty] | Shutter Engin/Dsn
FALSE |  | SR341165 | AVAIL: ASPIC Production (REB Batch 5) | LSST Forecast - B57 - B1 | 0 | 0 | 2016-08-15 | 2016-08-15 | 0 | 2016-08-15 | 2016-08-15 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2016-09-01 | 2016-09-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.01 | ASPIC | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Bill Wahl |  |  | Level 5 Milestone | Testing/Integration | [21 empty] | ASPICS |  | Science Raft System
FALSE |  | SR341163 | AVAIL: ASPIC Production (REB Batch 3) | LSST Forecast - B57 - B1 | 0 | 0 | 2016-08-15 | 2016-08-15 | 0 | 2016-08-15 | 2016-08-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2016-09-01 | 2016-09-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.01 | ASPIC | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Bill Wahl |  |  | Level 5 Milestone | [22 empty] | ASPICS |  | Science Raft System
FALSE |  | SR343744_2 | Issue PO for fabrication of (15) First Article REB5 "Raw" boards | LSST Forecast - B57 - B1 | 1 | 0 | 2016-08-15 | 2016-08-15 | 0 | 2016-08-15 | 2016-08-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-09-06 | 2016-09-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | [11 empty] | Science Raft Electronics (TEC) | [13 empty] | First Article REB-5 Build |  | Science Raft System
FALSE |  | CCS109700 | RCV: Components - Wall Mounted Displays - Diagnostic Cluster for I&T | LSST Forecast - B57 - B1 | 20 | 0 | 2016-08-16 | 2016-08-30 | 0 | 2016-08-16 | 2016-08-30 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 5000 | 5000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-09-16 | 2016-10-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 10 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.09 | CCS Diagnostic Cluster and Visualization | 0 | 0 | 0 | 5000 | 5000 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 4% |  | Procurement | [7 empty] | CCS Core (TEC) | [6 empty] | Shutter Engin/Dsn
FALSE |  | SR332685 | Prod. Testing - Sensors V2 (Sensors #29-32) | LSST Forecast - B57 - B1 | 10 | 0 | 2016-08-18 | 2016-08-31 | 0 | 2016-08-18 | 2016-08-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-09-01 | 2016-09-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 30 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 30 | 30 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Catalog Listing or Industrial Construction Databases | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [6 empty] | Science Sensors Acceptance | [6 empty] | Sensors Vendor 2 |  | Science Sensors
FALSE |  | CR222680 | Procure and fabricate Cold Raft Electronics test stand holding cart/table - Vendor Lead Time | LSST Forecast - B57 - B1 | 15 | 0 | 2016-08-22 | 2016-10-21 | 0 | 2016-08-22 | 2016-10-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-09-09 | 2016-09-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 10 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 43 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Vincent Riot
FALSE |  | CRYO35068 | Glycol System Mechanical Design/Analysis (Routing-Balancing-Coldplates) | LSST Forecast - B57 - B1 | 40 | 0 | 2016-08-25 | 2016-09-30 | 0 | 2016-08-25 | 2016-09-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-10-25 | 2017-01-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 25 |  | Complete | 100% | 32 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.05.02 | Utility Trunk Thermo-Mechanical and Assembly | 32 | 32 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Utility Trunk Thermo-Mechanical and Assembly (TEC) | [6 empty] | Utility Trunk
FALSE |  | CRYO35069 | UT prelim structure & heat exchanger vacuum chamber integration | LSST Forecast - B57 - B1 | 40 | 0 | 2016-08-25 | 2016-09-30 | 0 | 2016-08-25 | 2016-09-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2016-10-25 | 2017-01-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 30 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 25 |  | Complete | 100% | 19.2 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.05.02 | Utility Trunk Thermo-Mechanical and Assembly | 19.2 | 19.2 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Utility Trunk Thermo-Mechanical and Assembly (TEC) |  | ICD's for Phase 2 |  |  |  |  | Utility Trunk
FALSE |  | SR330745 | RCV: Production Lot 1 Sensor - V2 - Sensors #35,36 | LSST Forecast - B57 - B1 | 3 | 0 | 2016-09-01 | 2016-09-06 | 0 | 2016-09-01 | 2016-09-06 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 6640 | 6640 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-10-03 | 2016-10-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 3 | 2 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 6640 | 6640 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 14% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC) | Sensor Delivery |  |  |  |  | Sensor | Science Sensors Procurement | [6 empty] | Sensors Vendor 2
FALSE |  | SR561110 | Batch1B_Perform Final Correction of V-Posts at vendor (6 Rafts) | LSST Forecast - B57 - B1 | 23 | 0 | 2016-09-01 | 2016-09-29 | 0 | 2016-09-01 | 2016-09-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-10-03 | 2016-11-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 23 | 19 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.02 | Science Raft Sensor Assembly (SRSA) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Bill Wahl | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement | [21 empty] | Sensor Assembly |  | Science Raft System
FALSE |  | SR330750 | RCV: Production Lot 1 Sensor - V2 - Sensors #37,38 | LSST Forecast - B57 - B1 | 3 | 0 | 2016-09-07 | 2016-09-09 | 0 | 2016-09-07 | 2016-09-09 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 6640 | 6640 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-10-06 | 2016-10-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 3 | 2 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 6640 | 6640 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 14% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC) | [5 empty] | Sensor | Science Sensors Procurement | [6 empty] | Sensors Vendor 2
FALSE |  | CR241240 | PROC: WEB (PCB & components) | LSST Forecast - B57 - B1 | 27 | 0 | 2016-09-12 | 2017-09-21 | 0 | 2016-09-12 | 2017-09-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 50000 | 50000 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-07-28 | 2017-09-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 27 | 250 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.01 | Wavefront Electronics Board (WEB) | 0 | 0 | 0 | 50000 | 50000 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Procurement | [7 empty] | Corner Raft Electronics (TEC) | WEB
FALSE |  | SR330755 | RCV: Production Lot 1 Sensor - V2 - Sensors #39,40 | LSST Forecast - B57 - B1 | 3 | 0 | 2016-09-12 | 2016-12-20 | 0 | 2016-09-12 | 2016-12-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 6640 | 6640 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-10-11 | 2016-10-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 3 | 69 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 6640 | 6640 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 14% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC) | [5 empty] | Sensor | Science Sensors Procurement | [6 empty] | Sensors Vendor 2 |  | Science Sensors
FALSE |  | CR222690 | RCV: Procure and fabricate Cold Raft Electronics test stand holding cart/table | LSST Forecast - B57 - B1 | 15 | 0 | 2016-09-12 | 2016-11-30 | 0 | 2016-09-12 | 2016-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 20000 | 20000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-10-03 | 2016-10-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 55 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 20000 | 20000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | [11 empty] | Corner Raft Tower Module (CRTM) (TEC)
FALSE |  | SR330880 | Release RFP - Sensor Production Lot 2 + Option 1 for Lot 3 | LSST Forecast - B57 - B1 | 0 | 0 | 2016-09-15 | 2016-09-15 | 0 | 2016-09-15 | 2016-09-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2016-10-03 | 2016-10-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien |  |  |  | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 14% | Level 4 Milestone | Procurement | [13 empty] | Sensor | [5 empty] | CP - CAMM2130 (Award of Sensor Lot #2) |  | Lot 2 Primary Vendor
FALSE |  | CRYO11729 | RCV: All Parts - Assembly Mandrel - Cryostat Assembly | LSST Forecast - B57 - B1 | 36 | 0 | 2016-09-17 | 2016-10-31 | 0 | 2016-09-17 | 2016-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 15000 | 15000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-10-17 | 2016-12-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 36 | 30 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 15000 | 15000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 5% | Level 4 Milestone | Procurement | [7 empty] | Cryostat Housing & Assembly (TEC)
FALSE |  | CRYO11728 | Vendor Lead Time - All Parts - Assembly Mandrel - Cryostat Assembly | LSST Forecast - B57 - B1 | 24 | 0 | 2016-09-17 | 2016-10-31 | 0 | 2016-09-17 | 2016-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-10-03 | 2016-11-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 10 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 24 | 30 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 10% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor
FALSE |  | SR553030 | RTM (1-3) - Materials Lead Time | LSST Forecast - B57 - B1 | 38 | 0 | 2016-09-20 | 2017-01-10 | 0 | 2016-09-20 | 2017-01-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-10-19 | 2016-12-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 38 | 67 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Existing Lien |  |  |  | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 14% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [8 empty] | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Sensor | [5 empty] | CP - CAMM2130 (Award of Sensor Lot #2) |  | RTM Materials |  | Science Raft System
FALSE |  | ITC25680 | Early (Long Lead) Procurement - Vendor Lead Time - BOT | LSST Forecast - B57 - B1 | 20 | 0 | 2016-09-26 | 2017-03-03 | 0 | 2016-09-26 | 2017-03-03 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-10-03 | 2016-10-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 99 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.02.01 | Bench For Optical Testing (BOT) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc)
FALSE |  | CCS200170 | RCV: Components - Parts - Single Bay HCU | LSST Forecast - B57 - B1 | 15 | 0 | 2016-10-15 | 2016-10-30 | 0 | 2016-10-15 | 2016-10-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 4000 | 4000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-11-15 | 2016-12-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 10 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.08.01 | Single Bay HCU | 0 | 0 | 0 | 4000 | 4000 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 4% |  | Procurement | [7 empty] | CCS HCU (TEC) | [6 empty] | Shutter Engin/Dsn
FALSE |  | CR222860 | RCV: Parts for TS-7 Cart Assembly | LSST Forecast - B57 - B1 | 5 | 0 | 2016-10-17 | 2016-10-17 | 0 | 2016-10-17 | 2016-10-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 3000 | 3000 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-11-22 | 2016-11-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 3000 | 3000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Procurement | [7 empty] | Corner Raft Tower Module (CRTM) (TEC)
FALSE |  | CR223120 | RCV: bench top 48V supplies for REB power supply cards (x3) | LSST Forecast - B57 - B1 | 20 | 0 | 2016-10-28 | 2016-10-28 | 0 | 2016-10-28 | 2016-10-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 1500 | 1500 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-11-15 | 2016-12-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 1500 | 1500 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Procurement | [7 empty] | Corner Raft Tower Module (CRTM) (TEC)
FALSE |  | CR223090 | RCV: OTM power supplies (x3) | LSST Forecast - B57 - B1 | 20 | 0 | 2016-10-31 | 2016-10-31 | 0 | 2016-10-31 | 2016-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 1500 | 1500 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-11-01 | 2016-11-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 1500 | 1500 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Procurement | [7 empty] | Corner Raft Tower Module (CRTM) (TEC)
FALSE |  | CRYO35071 | UT Prelim to TMA Interface Design/Eng | LSST Forecast - B57 - B1 | 64 | 0 | 2016-11-01 | 2017-07-18 | 0 | 2016-11-01 | 2017-07-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-12-01 | 2017-03-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 64 | 168 |  | Complete | 100% | 224 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.05.02 | Utility Trunk Thermo-Mechanical and Assembly | 224 | 224 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Utility Trunk Thermo-Mechanical and Assembly (TEC) | [6 empty] | Utility Trunk
FALSE |  | CRYO53160 | Vendor Lead Time - All Parts - Refrigerant Tank Heater and Feed Back Control System | LSST Forecast - B57 - B1 | 60 | 0 | 2016-11-05 | 2016-11-15 | 0 | 2016-11-05 | 2016-11-15 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-12-15 | 2017-03-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 30 | 30 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 6 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc)
FALSE |  | CRYO53290 | Procurement Process - Flow Rate Test | LSST Forecast - B57 - B1 | 40 | 0 | 2016-11-10 | 2016-11-15 | 0 | 2016-11-10 | 2016-11-15 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-01-30 | 2017-03-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 20 | 20 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 3 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  |  | Procurement
FALSE |  | CRYO53170 | RCV: All Parts - Refrigerant Tank Heater and Feed Back Control System | LSST Forecast - B57 - B1 | 30 | 0 | 2016-11-15 | 2016-11-15 | 0 | 2016-11-15 | 2016-11-15 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 25000 | 25000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-02-13 | 2017-03-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 25000 | 25000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% | Level 4 Milestone | Procurement | [7 empty] | Refrigeration System (TEC)
FALSE |  | CRYO53300 | Vendor Lead Time - All Parts - Flow Rate Test | LSST Forecast - B57 - B1 | 30 | 0 | 2016-11-15 | 2016-11-25 | 0 | 2016-11-15 | 2016-11-25 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-02-28 | 2017-04-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 10 | 10 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 7 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc)
FALSE |  | CRYO53310 | RCV: All Parts - Flow Rate Test | LSST Forecast - B57 - B1 | 30 | 0 | 2016-11-25 | 2016-11-25 | 0 | 2016-11-25 | 2016-11-25 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 30000 | 30000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-03-14 | 2017-04-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 30000 | 30000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% | Level 4 Milestone | Procurement | [7 empty] | Refrigeration System (TEC)
FALSE |  | CRYO31050 | RCV: Feedthru Flange Subcomponents - Cryostat Back End | LSST Forecast - B57 - B1 | 20 | 0 | 2016-11-30 | 2016-11-30 | 0 | 2016-11-30 | 2016-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 55050 | 55050 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-02-13 | 2017-03-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.01 | Cryostat Back End | 0 | 0 | 0 | 55050 | 55050 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Procurement | [7 empty] | Cryostat Backend & Vacuum Systems (TEC) | [6 empty] | Cryostat Back End
FALSE |  | SR530130 | TS8 - practice test on engineering grade RTM | LSST Forecast - B57 - B1 | 20 | 0 | 2016-12-01 | 2016-12-30 | 0 | 2016-12-01 | 2016-12-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-01-03 | 2017-01-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 19 |  | Complete | 100% | 240 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.05 | RTM Electro-Optical Testing (TS8) | 240 | 240 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 8 - Assembly & Commissioning |  | Science Raft System
FALSE |  | CRYO11723 | RCV: All Parts - Faro Arm Stand - Cryostat Assembly | LSST Forecast - B57 - B1 | 16 | 0 | 2016-12-01 | 2016-12-16 | 0 | 2016-12-01 | 2016-12-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 5000 | 5000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-01-16 | 2017-02-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 16 | 11 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 5000 | 5000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 5% | Level 4 Milestone | Procurement | [7 empty] | Cryostat Housing & Assembly (TEC)
FALSE |  | CRYO11722 | Vendor Lead Time - All Parts - Faro Arm Stand - Cryostat Assembly | LSST Forecast - B57 - B1 | 24 | 0 | 2016-12-01 | 2016-12-16 | 0 | 2016-12-01 | 2016-12-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-01-02 | 2017-02-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 10 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 24 | 11 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 10% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor
FALSE |  | ITC17715 | COTS Procurement - Vendor Lead Time - SBMS | LSST Forecast - B57 - B1 | 20 | 0 | 2016-12-01 | 2016-12-30 | 0 | 2016-12-01 | 2016-12-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-01-03 | 2017-01-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 10 | 10 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 12 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.01.01 | Single Bay Metrology Tests | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc)
FALSE |  | CR222960 | RCV: Parts for Dark Box | LSST Forecast - B57 - B1 | 12 | 0 | 2016-12-05 | 2017-03-24 | 0 | 2016-12-05 | 2017-03-24 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 10000 | 10000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-01-03 | 2017-01-19 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 12 | 66 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 10000 | 10000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Procurement | [7 empty] | Corner Raft Tower Module (CRTM) (TEC)
FALSE |  | ITC17720 | RCV: COTS Procurement - SBMS | LSST Forecast - B57 - B1 | 10 | 0 | 2016-12-10 | 2017-03-07 | 0 | 2016-12-10 | 2017-03-07 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 73000 | 73000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-01-18 | 2017-01-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 4 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 48 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.01.01 | Single Bay Metrology Tests | 0 | 0 | 0 | 73000 | 73000 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC)
FALSE |  | ITC17730 | Outside Fabrication - Vendor Lead Time - SBMS | LSST Forecast - B57 - B1 | 30 | 0 | 2016-12-10 | 2016-12-16 | 0 | 2016-12-10 | 2016-12-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-01-03 | 2017-02-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 10 | 10 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 4 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.01.01 | Single Bay Metrology Tests | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc)
FALSE |  | ITC17735 | RCV: Outside Fabrication Procurement - SBMS | LSST Forecast - B57 - B1 | 20 | 0 | 2016-12-10 | 2016-12-16 | 0 | 2016-12-10 | 2016-12-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 10000 | 10000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-01-18 | 2017-02-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 4 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 4 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.01.01 | Single Bay Metrology Tests | 0 | 0 | 0 | 10000 | 10000 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC)
FALSE |  | SR551730 | Fabrication - SRTM Shipping Container (Prototype) | LSST Forecast - B57 - B1 | 10 | 0 | 2016-12-15 | 2016-12-30 | 0 | 2016-12-15 | 2016-12-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-01-10 | 2017-01-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.03 | Science Raft Shipping Container | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Raft Tower Module (SRTM) (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Science Raft Shipping Container |  | Science Raft System
FALSE |  | SR550330 | RTM #2 (1st Article) - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2016-12-27 | 2017-03-16 | 0 | 2016-12-27 | 2017-03-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-02-08 | 2017-03-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 54 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #2 |  | Science Raft System
Merge Hotspot
The total number of activities with a high number of predecessor links.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | Previous Start | Previous Finish | Percent Complete | Previous Remaining Duration | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | IsLevelOfEffort | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | Global_Basis of Estimate | Global_Cobra Cost Class | Cobra PMT (EV Method)_Global | Global_Color of Money | Global_Control Account Manager | Global_Design Maturity | Global_Judgement Factor | Global_Milestone Levels | Global_Project Phase | Global_Funding Source | Global_EDIA Survey | Global_MS Type | Phase | NSF Milestones | Loading Curve | Sensor Vendor | LSST_CA | Summary Schedule | ICD for NSF Input | LSST Camera Critical Paths | CD2 Budget Changes | DOE Reviews | Critical Path (CD Reviews) | LSST WP Summary | Critical Path (Camera Delivery) | AWARD / NEED Sub-System | Final Design Key Links | CP - CAMM2100 | CP - CAMM2130 | CP - CAMM2160 | BNL Work Org | Last ETC Update | BNL WBS | LSST Story List | Sum Sch 01 (Camera) | Sum Sch 02 (IT w/Needs) | Sum Sch 03 (Sensors_RTM_IT) | LSST Raft Particulate Mitigation | LSST RTM
FALSE |  | SR530770 | Prep for C_MRR-TS4 | LSST Forecast - B57 - B1 | 20 | 0 | 2016-01-01 | 2016-01-30 | 0 | 2016-01-01 | 2016-01-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-02-01 | 2016-02-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 4 | 1 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 19 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.01 | RSA Assembly (TS4) | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 4 - Reviews |  | Science Raft System
FALSE |  | SR332505 | FA Testing - Sensors V1 (1 Set, 5 sensors, 1-5) | LSST Forecast - B57 - B1 | 32 | 0 | 2016-01-04 | 2016-11-25 | 0 | 2016-01-04 | 2016-11-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-02-02 | 2016-03-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 4 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 32 | 228 |  | Complete | 100% | 210 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 210 | 210 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Catalog Listing or Industrial Construction Databases | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [6 empty] | Science Sensors Acceptance | [6 empty] | Sensors Vendor 1 |  | Science Sensors
FALSE |  | SR344320 | Integrate emulator w/JK software (BNL & UPenn) | LSST Forecast - B57 - B1 | 20 | 0 | 2016-01-16 | 2016-04-29 | 0 | 2016-01-16 | 2016-04-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-02-16 | 2016-03-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 1 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 72 |  | Complete | 100% | 200 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 200 | 200 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation | [7 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [6 empty] | REB4 Test Stand Development (TS-REB) |  | Science Raft System
FALSE |  | CCS119950 | Bug fixes from 2.5 release - Core 3.0 Release | LSST Forecast - B57 - B1 | 20 | 0 | 2016-01-25 | 2016-03-13 | 0 | 2016-01-25 | 2016-03-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-31 | 2019-05-31 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-04-01 | 2016-04-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 34 |  | Complete | 100% | 125 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.02.04 | CCS Core 3.0 Release (Support MCM) | 125 | 125 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering | [7 empty] | CCS Core (TEC)
FALSE |  | SR529740 | TS8a - Construct test platform using TS8 dewar | LSST Forecast - B57 - B1 | 7 | 0 | 2016-02-01 | 2016-02-28 | 0 | 2016-02-01 | 2016-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-04-21 | 2016-04-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 7 | 19 |  | Complete | 100% | 48 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.06 | RTM Electro-Optical Testing (TS8a) For SLAC | 48 | 48 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 8a - Testing |  | Science Raft System
FALSE |  | OP540660 | Prep for C_FDR/MRR--Optics - L3 Assembly | LSST Forecast - B57 - B1 | 19 | 0 | 2016-02-01 | 2016-07-07 | 0 | 2016-02-01 | 2016-07-07 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2016-06-10 | 2016-07-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 19 | 110 |  | Complete | 100% | 604 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 604 | 604 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 14% |  | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | L3 Assembly (TEC) | [6 empty] | L1-L2 Opto-Mechanics
FALSE |  | ITC17605 | Update Defining Documentation - SBMS | LSST Forecast - B57 - B1 | 10 | 0 | 2016-02-01 | 2016-05-27 | 0 | 2016-02-01 | 2016-05-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-04-12 | 2016-04-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 83 |  | Complete | 100% | 36 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.01.01 | Single Bay Metrology Tests | 36 | 36 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC)
FALSE |  | SR531100 | TS7 - acceptance test of fabrication/assy hardware | LSST Forecast - B57 - B1 | 10 | 0 | 2016-02-01 | 2016-02-15 | 0 | 2016-02-01 | 2016-02-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-02-01 | 2016-02-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 10 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.04 | RTM Cryostat Integration (TS7) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 7 - Procurement & Fabrication |  | Science Raft System
FALSE |  | SR529940 | TS8 - generate final measurement test script and software requirements | LSST Forecast - B57 - B1 | 23 | 0 | 2016-02-01 | 2016-11-30 | 0 | 2016-02-01 | 2016-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-02-01 | 2016-03-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 23 | 211 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.05 | RTM Electro-Optical Testing (TS8) | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 8 - Design |  | Science Raft System
FALSE |  | CR211700 | Prep for C_FDR - Corner Raft | LSST Forecast - B57 - B1 | 10 | 0 | 2016-02-08 | 2016-02-26 | 0 | 2016-02-08 | 2016-02-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-02-12 | 2016-02-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 4 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 13 |  | Complete | 100% | 48 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.01 | Corner Raft System Integration and Management | 48 | 48 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft System Integration and Management (TEC) | Management | [5 empty] | Corner Raft System Integration and Management
FALSE |  | CR230400 | Prep for C_FDR - Corner raft sensor assembly | LSST Forecast - B57 - B1 | 10 | 0 | 2016-02-08 | 2016-02-26 | 0 | 2016-02-08 | 2016-02-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-02-12 | 2016-02-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 13 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | DAQ360500 | COMP: Prototype - IMS/IMC | LSST Forecast - B57 - B1 | 0 | 0 | 2016-02-08 | 2016-02-08 | 0 | 2016-02-08 | 2016-02-08 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2016-04-05 | 2016-04-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.09.01 | Image Management/Server/Client Software | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer |  |  | Level 4 Milestone | Engineering Test/Validation
FALSE |  | ITC33306 | Update Defining Documentation - Gantry | LSST Forecast - B57 - B1 | 10 | 0 | 2016-02-08 | 2016-06-30 | 0 | 2016-02-08 | 2016-06-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2016-03-01 | 2016-03-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 101 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.01 | Integration Gantry | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat I&T (TEC)
FALSE |  | ITC33700 | Update Defining Documentation - Cryo-Equip | LSST Forecast - B57 - B1 | 5 | 0 | 2016-02-08 | 2016-10-18 | 0 | 2016-02-08 | 2016-10-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-24 | 2019-07-24 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-03-01 | 2016-03-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 177 |  | Complete | 100% | 18 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.02 | Cryostat Handling Equipment | 18 | 18 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat I&T (TEC)
FALSE |  | ITC19400 | Update Defining Documentation - Integration Stand | LSST Forecast - B57 - B1 | 10 | 0 | 2016-02-08 | 2017-10-24 | 0 | 2016-02-08 | 2017-10-24 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-03 | 2019-06-03 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-08-01 | 2016-08-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 424 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.01 | Camera Integration Stand | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Camera I&T (TEC)
FALSE |  | CR220620 | Prep for C_FDR - Corner raft tower, tooling, shipping container | LSST Forecast - B57 - B1 | 11 | 0 | 2016-02-11 | 2016-02-26 | 0 | 2016-02-11 | 2016-02-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-02-11 | 2016-02-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 11 | 10 |  | Complete | 100% | 60 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 60 | 60 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Tower Module (CRTM) (TEC) | CRTM Final Design | [5 empty] | Corner Raft Tower Module (CRTM)
FALSE |  | OP522320 | AWARD: Procure Filter Blank (5 blanks) | LSST Forecast - B57 - B1 | 1 | 0 | 2016-02-11 | 2016-02-11 | 0 | 2016-02-11 | 2016-02-11 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-28 | 2020-01-28 | 127725 | 127725 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-03-14 | 2016-03-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 127725 | 127725 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | B1 Procurement Commitment (C5.1) |  | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 18% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Filters (TEC) | Production Filters Blank | [5 empty] | Filter Optics
FALSE |  | DAQ360900 | Update Documentation - Pre-Production - IMS/IMC | LSST Forecast - B57 - B1 | 20 | 0 | 2016-02-12 | 2016-05-28 | 0 | 2016-02-12 | 2016-05-28 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-04-12 | 2016-05-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 75 |  | Complete | 100% | 20 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.09.01 | Image Management/Server/Client Software | 20 | 20 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Testing/Integration |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | DAQ Readout Systems (TEC)
FALSE |  | CR220820 | AVAIL: Prototype - corner raft test setup EM revision (sidewall, cooling bars, support rods) | LSST Forecast - B57 - B1 | 0 | 0 | 2016-02-25 | 2016-02-25 | 0 | 2016-02-25 | 2016-02-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2016-02-19 | 2016-02-19 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% | Level 5 Milestone | Engineering Test/Validation | [8 empty] | CRTM Prototype EM Revision
FALSE |  | SR343700 | Assemble at Vendor, Clean & Test (15) First Article REB4 boards (ETU 1 & 2) | LSST Forecast - B57 - B1 | 25 | 0 | 2016-02-26 | 2016-04-29 | 0 | 2016-02-26 | 2016-04-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-02-26 | 2016-03-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 45 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation | [7 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [6 empty] | Assembly at Vendor (ETU 1 & 2) |  | Science Raft System
FALSE |  | CR211720 | C_FDR - Comp. Final Design Review - Corner Raft | LSST Forecast - B57 - B1 | 1 | 0 | 2016-02-29 | 2016-03-01 | 0 | 2016-02-29 | 2016-03-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-02-29 | 2016-02-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 6 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 1 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.01 | Corner Raft System Integration and Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  |  | Design/Engineering | [8 empty] | Management
FALSE |  | CR240700 | C_FDR - Comp. Final Design Review - WEB | LSST Forecast - B57 - B1 | 1 | 0 | 2016-02-29 | 2016-03-01 | 0 | 2016-02-29 | 2016-03-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-02-29 | 2016-02-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 1 |  | Complete | 100% | 8 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.01 | Wavefront Electronics Board (WEB) | 8 | 8 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Design Reviews | [5 empty] | Corner Raft Electronics (TEC) | WEB EM
FALSE |  | CR242000 | C_FDR - Comp. Final Design Review - GEB | LSST Forecast - B57 - B1 | 1 | 0 | 2016-02-29 | 2016-03-01 | 0 | 2016-02-29 | 2016-03-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-02-29 | 2016-02-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 8 | 0 | 8 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 1 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.02 | Guider Electronics Board (GEB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  |  | Design/Engineering | [8 empty] | GEB EM
FALSE |  | DAQ900160 | Fabricate Prototype Hybrid RTM (8) | LSST Forecast - B57 - B1 | 15 | 0 | 2016-03-01 | 2016-07-30 | 0 | 2016-03-01 | 2016-07-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-04-01 | 2016-04-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 3 | 2 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 107 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.13.03 | DAQ Version 2.0 | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer |  |  |  | Engineering Test/Validation
FALSE |  | CRYO11720 | Final Design & Engineering - Faro Arm Stand - Cryostat Assembly | LSST Forecast - B57 - B1 | 40 | 0 | 2016-03-07 | 2016-06-26 | 0 | 2016-03-07 | 2016-06-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-04-07 | 2016-06-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 30 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 79 |  | Complete | 100% | 26 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 26 | 26 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Housing & Assembly (TEC)
FALSE |  | OP522085 | AWARD: Filter First Article fabrication (Phase 1) | LSST Forecast - B57 - B1 | 1 | 0 | 2016-03-21 | 2016-03-21 | 0 | 2016-03-21 | 2016-03-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-25 | 2019-07-25 | 250700 | 250700 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-04-01 | 2016-04-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 250700 | 250700 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | B1 Procurement Commitment (C5.1) |  | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 18% | Level 4 Milestone | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Filters (TEC) | First Article Substrate Finishing | [5 empty] | Filter Optics
FALSE |  | SR345900 | COMP: REB Test Board (RTB) - Production REB Testing | LSST Forecast - B57 - B1 | 0 | 0 | 2016-03-31 | 2016-03-31 | 0 | 2016-03-31 | 2016-03-31 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2016-05-20 | 2016-05-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.06 | Electronics Production Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% | Level 4 Milestone | Design/Engineering | [21 empty] | RTB - Testing |  | Science Raft System
FALSE |  | ITC12900 | Finalize Ops and Maint procedures for I&T Facility | LSST Forecast - B57 - B1 | 47 | 0 | 2016-04-04 | 2016-09-30 | 0 | 2016-04-04 | 2016-09-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-05-02 | 2016-07-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 47 | 126 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.03 | IR2 Facility and Operations | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) |  | Integration Test and Calibration |  |  |  | Camera I&T (TEC) | [6 empty] | I&T Facility
FALSE |  | CR230590 | Check & approve Drawings - Corner raft sensor assembly | LSST Forecast - B57 - B1 | 30 | 0 | 2016-04-04 | 2016-05-31 | 0 | 2016-04-04 | 2016-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-05-02 | 2016-06-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 40 |  | Complete | 100% | 20 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 20 | 20 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | OP521780 | AWARD: Contract - Filter Development and Witness Sample (Phase 1) | LSST Forecast - B57 - B1 | 1 | 0 | 2016-04-05 | 2016-04-05 | 0 | 2016-04-05 | 2016-04-05 | 0 | 2019-06-01 | 2019-06-01 | 2019-12-12 | 2019-12-12 | 971000 | 971000 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2016-05-02 | 2016-05-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 971000 | 971000 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | B1 Procurement Commitment (C5.1) |  | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 18% | Level 4 Milestone | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Filters (TEC) | Witness Sample | [5 empty] | Filter Optics
FALSE |  | SR530930 | TS5 - Revise scripting and software | LSST Forecast - B57 - B1 | 25 | 0 | 2016-04-11 | 2016-11-30 | 0 | 2016-04-11 | 2016-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-05-10 | 2016-06-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 162 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.02 | RSA & RTM Warm-Cold Metrology (TS5) | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 5 - Assembly & Commissioning |  | Science Raft System
FALSE |  | CRYO22870 | Vendor Lead Time - Final Machining (Step 1) | LSST Forecast - B57 - B1 | 56 | 0 | 2016-04-18 | 2016-11-18 | 0 | 2016-04-18 | 2016-11-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-05-18 | 2016-08-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 56 | 151 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.04 | Grid Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor | [11 empty] | Grid Assembly | [5 empty] | CP - CAMM2160 (Cryostat Assy Ready for Integration)
FALSE |  | CRYO60855 | Test - Polyimide Hose Compatibility Test - Hose | LSST Forecast - B57 - B1 | 20 | 0 | 2016-04-23 | 2016-04-30 | 0 | 2016-04-23 | 2016-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-05-23 | 2016-06-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 5 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 16% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 2 |  |  |  |  | Refrigeration System
FALSE |  | CRYO22100 | COMP: Final Design and Engineering Phase - Grid Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2016-04-27 | 2016-04-27 | 0 | 2016-04-27 | 2016-04-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2016-06-01 | 2016-06-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.04 | Grid Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Design/Engineering
FALSE |  | CRYO60870 | COMP: Hose and Fitting Test Stand | LSST Forecast - B57 - B1 | 0 | 0 | 2016-04-30 | 2016-04-30 | 0 | 2016-04-30 | 2016-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | FALSE | 2016-06-20 | 2016-06-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Engineering Test/Validation
FALSE |  | AE211110 | Design Pre-Production Cryostat HCU | LSST Forecast - B57 - B1 | 25 | 0 | 2016-05-01 | 2016-09-28 | 0 | 2016-05-01 | 2016-09-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-06-01 | 2016-07-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 104 |  | Complete | 100% | 20 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.02.11 | Cryostat HCU | 20 | 20 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Gunther Haller | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Aux Elec Components (TEC) | [6 empty] | Power Control Monitoring
FALSE |  | SR550040 | RTM ETU #1 - Assembly and Test | LSST Forecast - B57 - B1 | 50 | 0 | 2016-05-02 | 2016-12-30 | 0 | 2016-05-02 | 2016-12-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-06-22 | 2016-08-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 4 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 30 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 50 | 167 |  | Complete | 100% | 800 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 800 | 800 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM ETU #1 |  | Science Raft System
FALSE |  | OP540900 | L3 Assembly - Phase 3 (Flat Assy - Fine Grind) | LSST Forecast - B57 - B1 | 82 | 0 | 2016-05-02 | 2016-12-08 | 0 | 2016-05-02 | 2016-12-08 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-14 | 2019-05-14 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-06-01 | 2016-09-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 82 | 153 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor | [11 empty] | L1-L2 Opto-Mechanics
FALSE |  | SE223128 | Sub-system FDR camera thermal integrated analysis - Camera Body, Carousel, Autochanger & Purge | LSST Forecast - B57 - B1 | 33 | 0 | 2016-05-02 | 2016-10-28 | 0 | 2016-05-02 | 2016-10-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-09 | 2019-09-09 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-07-21 | 2016-09-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 2 | 2 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 33 | 126 |  | Complete | 100% | 100 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.03 | Thermal and contamination system analysis | 100 | 100 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | SR343740 | AVAIL: (15) REB4 fully tested boards ready for ETU Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2016-05-02 | 2016-05-02 | 0 | 2016-05-02 | 2016-05-02 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2016-06-01 | 2016-06-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% | Level 5 Milestone | Engineering Test/Validation | [7 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [6 empty] | Assembly at Vendor (ETU 1 & 2) |  | Science Raft System
FALSE |  | SR330165 | RCV: First Articles Sensor - V1 (1 Set, Batch 1b, 4 Sensors, 2-5) | LSST Forecast - B57 - B1 | 5 | 0 | 2016-05-10 | 2016-11-10 | 0 | 2016-05-10 | 2016-11-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 490000 | 490000 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-06-01 | 2016-06-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 129 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 490000 | 490000 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 20% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC) | [5 empty] | Sensor | [7 empty] | Sensors Vendor 1 |  | Science Sensors
FALSE |  | CCS207800 | Develop Simple Camera Command Simulator for Use by OCS - CCS/OCS | LSST Forecast - B57 - B1 | 15 | 0 | 2016-05-11 | 2016-05-29 | 0 | 2016-05-11 | 2016-05-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-17 | 2019-10-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-11-28 | 2016-12-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 13 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.04 | CCS/OCS Bridge | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Testing/Integration | [7 empty] | CCS Core (TEC)
FALSE |  | SR344395 | Ready: Test stand ready for use | LSST Forecast - B57 - B1 | 0 | 0 | 2016-05-13 | 2016-05-13 | 0 | 2016-05-13 | 2016-05-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2016-06-14 | 2016-06-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% | Level 4 Milestone | Engineering Test/Validation | [7 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [6 empty] | REB4 Test Stand Development (TS-REB) |  | Science Raft System
FALSE |  | CBM45500 | Develop Test/Equip Prelim Design (Shutter Proto) | LSST Forecast - B57 - B1 | 20 | 0 | 2016-05-15 | 2016-09-30 | 0 | 2016-05-15 | 2016-09-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-06 | 2019-08-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-06-01 | 2016-06-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 96 |  | Complete | 100% | 140.4 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.02.02 | Shutter Development | 140.4 | 140.4 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 5% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Shutter Development (TEC) | [6 empty] | Shutter Prototype
FALSE |  | CRYO53060 | COMP: Charge and Recovery for SLAC System (Link to FDR#2) | LSST Forecast - B57 - B1 | 0 | 0 | 2016-05-19 | 2016-05-19 | 0 | 2016-05-19 | 2016-05-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2016-06-01 | 2016-06-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Engineering Test/Validation
FALSE |  | DAQ361000 | COMP: Pre-Production - IMS/IMC | LSST Forecast - B57 - B1 | 0 | 0 | 2016-05-28 | 2016-05-28 | 0 | 2016-05-28 | 2016-05-28 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2016-06-28 | 2016-06-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.09.01 | Image Management/Server/Client Software | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer |  |  | Level 4 Milestone | Testing/Integration
FALSE |  | CR306611 | COMP: Corner Raft Assy Test Station | LSST Forecast - B57 - B1 | 0 | 0 | 2016-05-31 | 2016-05-31 | 0 | 2016-05-31 | 2016-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2016-06-29 | 2016-06-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.05 | Corner Raft Assembly and Test Station | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 4 Milestone | Testing/Integration | [8 empty] | CR Assy/Test Station Development
FALSE |  | CR230600 | Prep for Manufacturing Readiness Review - Corner raft sensor assembly | LSST Forecast - B57 - B1 | 33 | 0 | 2016-06-01 | 2016-07-18 | 0 | 2016-06-01 | 2016-07-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-07-01 | 2016-08-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 33 | 32 |  | Complete | 100% | 20 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 20 | 20 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Final Design | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | SR552159 | AWARD: RSA base plate (24 Production Units) | LSST Forecast - B57 - B1 | 10 | 0 | 2016-06-01 | 2016-06-14 | 0 | 2016-06-01 | 2016-06-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 573240 | 573240 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-07-01 | 2016-07-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.02 | Science Raft Sensor Assembly (SRSA) | 0 | 0 | 0 | 573240 | 573240 | 0 | PercentComplete | 6% | CP_Phys |  | B1 Procurement Commitment (C5.1) | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Raft Tower Module (SRTM) (TEC) | [13 empty] | Sensor Assembly |  | Science Raft System
FALSE |  | ITC31785 | Analysis Software - Early Hardware Procurements | LSST Forecast - B57 - B1 | 20 | 0 | 2016-06-06 | 2016-06-30 | 0 | 2016-06-06 | 2016-06-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 35000 | 35000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-07-01 | 2016-07-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 18 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.04 | Verification Software Development | 0 | 0 | 0 | 35000 | 35000 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Other (specify) | [5 empty] | Verification Test Systems (TEC)
FALSE |  | CR234390 | COMP: MRR - Wavefront Sensor | LSST Forecast - B57 - B1 | 0 | 0 | 2016-06-10 | 2016-06-10 | 0 | 2016-06-10 | 2016-06-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2016-09-08 | 2016-09-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.02 | Wavefront Sensor | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 4 Milestone | Design/Engineering
FALSE |  | CAMM6306 | AVAIL: Start testing of targeted components for refrigerator utilities | LSST Forecast - B57 - B1 | 0 | 0 | 2016-06-13 | 2016-06-13 | 0 | 2016-06-13 | 2016-06-13 | 0 | 2019-06-01 | 2019-06-01 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Start Milestone | FALSE | 2016-11-01 | 2016-11-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 0 | 6 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.03 | NSF Interface Milestone (NSF Needs) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration
FALSE |  | CR234400 | Prepare PO - Phase 2 Production 2Kx4K Wavefront Sensor (14 2kx4k sensors) | LSST Forecast - B57 - B1 | 10 | 0 | 2016-06-13 | 2016-06-17 | 0 | 2016-06-13 | 2016-06-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-09-09 | 2016-09-22 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 4 |  | Complete | 100% | 16 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.02 | Wavefront Sensor | 16 | 16 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 1% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | [6 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | SR561000 | Prepare C/C Material (24 Rafts) | LSST Forecast - B57 - B1 | 1 | 0 | 2016-06-15 | 2016-06-16 | 0 | 2016-06-15 | 2016-06-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-07-18 | 2016-07-18 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 1 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.02 | Science Raft Sensor Assembly (SRSA) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Bill Wahl | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement | [21 empty] | Sensor Assembly |  | Science Raft System
FALSE |  | ITC25640 | Test Definition Review - Prep - BOT | LSST Forecast - B57 - B1 | 10 | 0 | 2016-06-20 | 2016-07-19 | 0 | 2016-06-20 | 2016-07-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-08-24 | 2016-09-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 20 |  | Complete | 100% | 50 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.02.01 | Bench For Optical Testing (BOT) | 50 | 50 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC)
FALSE |  | SR343743_3 | Close MRR Action Items | LSST Forecast - B57 - B1 | 8 | 0 | 2016-06-27 | 2016-09-09 | 0 | 2016-06-27 | 2016-09-09 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-07-05 | 2016-07-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 0 | 0 | 0 | 6 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 8 | 52 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Bill Wahl | [25 empty] | First Article REB-5 Build |  | Science Raft System
FALSE |  | CBM44000 | Recv, Prep, Assemble, Test (Drive Train) | LSST Forecast - B57 - B1 | 60 | 0 | 2016-07-01 | 2017-04-15 | 0 | 2016-07-01 | 2017-04-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-06 | 2019-08-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-08-01 | 2016-10-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 4 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 189 |  | Complete | 100% | 432 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.02.02 | Shutter Development | 432 | 432 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 7% |  | Engineering Test/Validation |  | Commissioning and Testing | [5 empty] | Shutter Development (TEC) | [6 empty] | Drive Train Test Unit
FALSE |  | CCS200000 | Port TS8 to SLAC - Single Bay HCU | LSST Forecast - B57 - B1 | 30 | 0 | 2016-07-01 | 2016-12-15 | 0 | 2016-07-01 | 2016-12-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-08-01 | 2016-09-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 115 |  | Complete | 100% | 240 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.08.01 | Single Bay HCU | 240 | 240 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Expert Opinion (Engineering Allowance) | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 6% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | CCS HCU (TEC) | [6 empty] | Camera I&T Hardware Control Unit
FALSE |  | CR233050 | Prep for Manufacturing Readiness Review - Shipping/Storage Container | LSST Forecast - B57 - B1 | 11 | 0 | 2016-07-01 | 2016-07-18 | 0 | 2016-07-01 | 2016-07-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-08-01 | 2016-08-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 11 | 10 |  | Complete | 100% | 16 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 16 | 16 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Shipping Container Design/Prod | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | SR330705 | Sensors Production Lot 1 - V2- Backside Batch and Test (21-65) | LSST Forecast - B57 - B1 | 65 | 0 | 2016-07-01 | 2016-07-26 | 0 | 2016-07-01 | 2016-07-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 10 | FALSE | Normal | FALSE | 2016-08-01 | 2016-10-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 10 | 0 | 1 | 9 | 0 | 0 | 1 | 0 | 3 | 0 | 0 | 49 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 65 | 16 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien |  |  |  | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 14% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor | [10 empty] | Sensor | [7 empty] | Sensors Vendor 2
FALSE |  | OP540680 | C_FDR/MRR--L3 Assembly | LSST Forecast - B57 - B1 | 1 | 0 | 2016-07-07 | 2016-07-21 | 0 | 2016-07-07 | 2016-07-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-14 | 2019-05-14 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-09-01 | 2016-09-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 10 |  | Complete | 100% | 88 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 88 | 88 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 14% |  | Procurement | [7 empty] | L3 Assembly (TEC) |  |  | Critical Path #2 (L1_L2 Assembly) |  |  |  | L1-L2 Opto-Mechanics
FALSE |  | CR240780 | Prepare PROC - WEB EM (PCB & components) | LSST Forecast - B57 - B1 | 5 | 0 | 2016-07-11 | 2016-07-22 | 0 | 2016-07-11 | 2016-07-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2016-08-08 | 2016-08-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 9 |  | Complete | 100% | 15 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.01 | Wavefront Electronics Board (WEB) | 15 | 15 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Procurement | [7 empty] | Corner Raft Electronics (TEC) | WEB EM
FALSE |  | CR242220 | Additional custom software and engineering support for GEB EM testing | LSST Forecast - B57 - B1 | 30 | 0 | 2016-07-11 | 2017-03-17 | 0 | 2016-07-11 | 2017-03-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2016-08-29 | 2016-10-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 2 | 0 | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 163 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.02 | Guider Electronics Board (GEB) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Fabrication/Assembly | [7 empty] | Corner Raft Electronics (TEC) | GEB EM
FALSE |  | CR242240 | Functional Testing - GEB EM | LSST Forecast - B57 - B1 | 30 | 0 | 2016-07-11 | 2016-09-23 | 0 | 2016-07-11 | 2016-09-23 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-08-29 | 2016-10-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 2 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 53 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.02 | Guider Electronics Board (GEB) | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Testing/Integration | [7 empty] | Corner Raft Electronics (TEC) | GEB EM
FALSE |  | SR332675 | Prod. Testing - Sensors V2 (Sensors #21-24) | LSST Forecast - B57 - B1 | 4 | 0 | 2016-07-11 | 2016-07-15 | 0 | 2016-07-11 | 2016-07-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-10-10 | 2016-10-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 4 |  | Complete | 100% | 30 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 30 | 30 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Catalog Listing or Industrial Construction Databases | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [6 empty] | Science Sensors Acceptance | [6 empty] | Sensors Vendor 2 |  | Science Sensors
FALSE |  | OP522420 | Prepare procurement for Filter fabrication | LSST Forecast - B57 - B1 | 20 | 0 | 2016-07-12 | 2016-08-16 | 0 | 2016-07-12 | 2016-08-16 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-08-30 | 2016-09-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 25 |  | Complete | 100% | 56 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 56 | 56 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 18% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Filters (TEC) | Production Filters Polish and integration | [5 empty] | Filter Optics
FALSE |  | SR332680 | Prod. Testing - Sensors V2 (Sensors #25-28) | LSST Forecast - B57 - B1 | 7 | 0 | 2016-07-18 | 2016-07-22 | 0 | 2016-07-18 | 2016-07-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-10-14 | 2016-10-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 7 | 4 |  | Complete | 100% | 30 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 30 | 30 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Catalog Listing or Industrial Construction Databases | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [6 empty] | Science Sensors Acceptance | [6 empty] | Sensors Vendor 2 |  | Science Sensors
FALSE |  | CR233070 | COMP: MRR - Shipping/Storage Container | LSST Forecast - B57 - B1 | 0 | 0 | 2016-07-19 | 2016-07-19 | 0 | 2016-07-19 | 2016-07-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2016-08-16 | 2016-08-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 4 Milestone | Design/Engineering | [8 empty] | CRSA Shipping Container Design/Prod
FALSE |  | SR530070 | TS8 - fabrication/assy - CCS controller | LSST Forecast - B57 - B1 | 28 | 0 | 2016-07-28 | 2016-10-28 | 0 | 2016-07-28 | 2016-10-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-08-11 | 2016-09-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 2 | 0 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 28 | 65 |  | Complete | 100% | 16 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.05 | RTM Electro-Optical Testing (TS8) | 16 | 16 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 8 - Procurement & Fabrication |  | Science Raft System
FALSE |  | OP540700 | COMP: C_FDR/MRR-L3 Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2016-07-29 | 2016-07-29 | 0 | 2016-07-29 | 2016-07-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-14 | 2019-05-14 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2016-09-01 | 2016-09-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  | Level 4 Milestone | Procurement | [10 empty] | Critical Path #2 (L1_L2 Assembly)
FALSE |  | CRYO60770 | COMP: Subscale Test Stand (Final Details) | LSST Forecast - B57 - B1 | 0 | 0 | 2016-07-30 | 2016-07-30 | 0 | 2016-07-30 | 2016-07-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | FALSE | 2016-08-29 | 2016-08-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 2 | 0 | 0 | 2 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Engineering Test/Validation
FALSE |  | SR330950 | AWARD: Sensor Production Lot 2 | LSST Forecast - B57 - B1 | 1 | 0 | 2016-08-02 | 2016-08-02 | 0 | 2016-08-02 | 2016-08-02 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 427671 | 427671 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-10-03 | 2016-10-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 427671 | 427671 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien | B1 Procurement Commitment (C5.1) |  | TEC Non-ARRA | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 14% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Sensor | Science Sensors Procurement |  |  |  |  | CP - CAMM2130 (Award of Sensor Lot #2) |  | Lot 2 Primary Vendor
FALSE |  | SR332685 | Prod. Testing - Sensors V2 (Sensors #29-32) | LSST Forecast - B57 - B1 | 10 | 0 | 2016-08-18 | 2016-08-31 | 0 | 2016-08-18 | 2016-08-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-09-01 | 2016-09-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 30 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 30 | 30 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Catalog Listing or Industrial Construction Databases | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [6 empty] | Science Sensors Acceptance | [6 empty] | Sensors Vendor 2 |  | Science Sensors
FALSE |  | CR234475 | Vendor Effort - Phase 2 Production 2Kx4K Wavefront Sensor (Remaining 13 2kx4k sensors) - Delivery | LSST Forecast - B57 - B1 | 73 | 0 | 2016-08-19 | 2016-12-20 | 0 | 2016-08-19 | 2016-12-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-09-02 | 2016-12-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 73 | 83 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.02 | Wavefront Sensor | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  |  | Procurement
FALSE |  | SR550110 | RTM ETU #2 - Assembly and Test | LSST Forecast - B57 - B1 | 74 | 0 | 2016-08-22 | 2017-02-15 | 0 | 2016-08-22 | 2017-02-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-11-01 | 2017-02-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 74 | 120 |  | Complete | 100% | 680 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 680 | 680 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM ETU #2 |  | Science Raft System
FALSE |  | CR240820 | RCV: WEB EM (PCB & components) | LSST Forecast - B57 - B1 | 0 | 0 | 2016-08-26 | 2016-08-26 | 0 | 2016-08-26 | 2016-08-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2016-09-29 | 2016-09-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.01 | Wavefront Electronics Board (WEB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 4 Milestone | Procurement | [8 empty] | WEB EM
FALSE |  | CRYO31000 | Procurement Process - Feedthru Flange Rings/Pump Plate - Cryostat Back End | LSST Forecast - B57 - B1 | 20 | 0 | 2016-09-03 | 2016-09-30 | 0 | 2016-09-03 | 2016-09-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-10-03 | 2016-10-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 18 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.01 | Cryostat Back End | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  |  | Procurement
FALSE |  | CCS109900 | Install visualization system in IR-2- Diagnostic Cluster for CCS Suite 2 | LSST Forecast - B57 - B1 | 66 | 0 | 2016-09-03 | 2016-12-16 | 0 | 2016-09-03 | 2016-12-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-10-03 | 2017-01-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 66 | 71 |  | Complete | 100% | 350 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.09 | CCS Diagnostic Cluster and Visualization | 350 | 350 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 11% |  | Engineering Test/Validation | [7 empty] | CCS Core (TEC)
FALSE |  | CCS109905 | Install visualization system in IR-2- Diagnostic Cluster for I&T | LSST Forecast - B57 - B1 | 90 | 0 | 2016-09-03 | 2017-03-15 | 0 | 2016-09-03 | 2017-03-15 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-10-03 | 2017-02-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 2 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 90 | 121 |  | Complete | 100% | 350 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.09 | CCS Diagnostic Cluster and Visualization | 350 | 350 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 11% |  | Engineering Test/Validation | [7 empty] | CCS Core (TEC)
FALSE |  | CR242260 | Electrical performance validation - GEB EM | LSST Forecast - B57 - B1 | 60 | 0 | 2016-09-05 | 2017-03-17 | 0 | 2016-09-05 | 2017-03-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-10-03 | 2017-01-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 0 | 2 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 123 |  | Complete | 100% | 320 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.02 | Guider Electronics Board (GEB) | 320 | 320 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Testing/Integration | [7 empty] | Corner Raft Electronics (TEC) | GEB EM
FALSE |  | OP520980 | Assemble and test filter mass simulator | LSST Forecast - B57 - B1 | 60 | 0 | 2016-09-05 | 2016-12-05 | 0 | 2016-09-05 | 2016-12-05 | 0 | 2019-06-01 | 2019-06-01 | 2018-10-30 | 2018-10-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-10-20 | 2017-01-19 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 63 |  | Complete | 100% | 240 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 240 | 240 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 18% |  | Fabrication/Assembly |  | Commissioning and Testing | [5 empty] | Filters (TEC) | Prototype Filter Assemblies |  |  | Maybe |  |  | Filter Opto-Mechanics
FALSE |  | SR332690 | Prod. Testing - Sensors V2 (Sensors #33-36) | LSST Forecast - B57 - B1 | 13 | 0 | 2016-09-07 | 2016-09-23 | 0 | 2016-09-07 | 2016-09-23 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-10-03 | 2016-10-19 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 13 | 12 |  | Complete | 100% | 30 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 30 | 30 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Catalog Listing or Industrial Construction Databases | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [6 empty] | Science Sensors Acceptance | [6 empty] | Sensors Vendor 2 |  | Science Sensors
FALSE |  | CR233090 | AWARD: Contract - Misc Parts - Shipping/Storage Container | LSST Forecast - B57 - B1 | 1 | 0 | 2016-09-08 | 2016-09-08 | 0 | 2016-09-08 | 2016-09-08 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 4000 | 4000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-11-14 | 2016-11-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 0 | 0 | 0 | 4000 | 4000 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | B1 Procurement Commitment (C5.1) |  | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% | Level 4 Milestone | Procurement |  | Other (specify) | Subcontractor |  |  |  |  | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Shipping Container Design/Prod | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CBM45100 | Recv, Prep, Assemble, Test (Blade Proto) | LSST Forecast - B57 - B1 | 7 | 0 | 2016-09-12 | 2017-04-28 | 0 | 2016-09-12 | 2017-04-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-06 | 2019-08-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-10-03 | 2016-10-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 7 | 149 |  | Complete | 100% | 228 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.02.02 | Shutter Development | 228 | 228 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 9% |  | Engineering Test/Validation |  | Commissioning and Testing | [5 empty] | Shutter Development (TEC) | [6 empty] | Blade Prototype Test Unit
FALSE |  | DAQ900075 | COMP: DAQ V1.0 | LSST Forecast - B57 - B1 | 0 | 0 | 2016-09-15 | 2016-09-15 | 0 | 2016-09-15 | 2016-09-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 5 | FALSE | Finish Milestone | FALSE | 2017-01-04 | 2017-01-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.13.01 | DAQ Version 1.0 | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer |  |  | Level 4 Milestone | Engineering Test/Validation
FALSE |  | CBM25200 | Prep for C_FDR - Camera Body | LSST Forecast - B57 - B1 | 10 | 0 | 2016-09-16 | 2016-09-23 | 0 | 2016-09-16 | 2016-09-23 | 0 | 2019-06-01 | 2019-06-01 | 2018-09-07 | 2018-09-07 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-10-03 | 2016-10-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 9 | 0 | 8 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 5 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.01.02 | Camera Body Development | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 15% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Camera Body Development (TEC) | [6 empty] | Cam Body/Purge Test Units
FALSE |  | CCS124900 | AVAIL: Deliver CCS software for drive-train prototype | LSST Forecast - B57 - B1 | 0 | 0 | 2016-09-16 | 2016-09-16 | 0 | 2016-09-16 | 2016-09-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-06 | 2019-08-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2016-11-01 | 2016-11-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.06 | Shutter HCU | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | OPC Non-ARRA | Tony Johnson |  |  | Level 5 Milestone | Engineering Test/Validation
FALSE |  | CR240940 | Functional Testing - WEB EM | LSST Forecast - B57 - B1 | 30 | 0 | 2016-09-19 | 2016-10-28 | 0 | 2016-09-19 | 2016-10-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-10-03 | 2016-11-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 29 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.01 | Wavefront Electronics Board (WEB) | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Testing/Integration | [7 empty] | Corner Raft Electronics (TEC) | WEB EM
FALSE |  | CBM44020 | CCS drive train testing | LSST Forecast - B57 - B1 | 20 | 0 | 2016-10-01 | 2016-12-14 | 0 | 2016-10-01 | 2016-12-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-06 | 2019-08-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-11-16 | 2016-12-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 50 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.02.02 | Shutter Development | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Martin Nordby |  |  |  | Engineering Test/Validation
FALSE |  | CCS100700 | Management FY17 - CCS | LSST Forecast - B57 - B1 | 242 | 0 | 2016-10-01 | 2017-09-29 | 0 | 2016-10-01 | 2017-09-29 | 0 | 2019-06-01 | 2019-06-01 | 2021-11-15 | 2021-11-15 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-11-01 | 2017-10-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 242 | 241 |  | Complete | 100% | 580 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.01 | CCS Integration & Management | 580 | 580 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Drtn | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Management/Administration |  | Construction Management | [5 empty] | CCS Integration & Management (TEC) | [6 empty] | Camera Control System
FALSE |  | ITC33346 | Test Definition Review - Prep - Gantry | LSST Forecast - B57 - B1 | 17 | 0 | 2016-10-01 | 2016-10-27 | 0 | 2016-10-01 | 2016-10-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-11-01 | 2016-11-23 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 17 | 18 |  | Complete | 100% | 29 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.01 | Integration Gantry | 29 | 29 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat I&T (TEC)
FALSE |  | OP10785 | Optics Sub-System Travel - FY17 | LSST Forecast - B57 - B1 | 250 | 0 | 2016-10-03 | 2017-09-29 | 0 | 2016-10-03 | 2017-09-29 | 0 | 2019-06-01 | 2019-06-01 | 2021-07-29 | 2021-07-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-11-01 | 2017-10-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 250 | 249 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.01 | Optics Integration & Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Drtn | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 0% |  | Management/Administration |  | Construction Management | [5 empty] | Optics System Management (TEC) | [6 empty] | Optics System Management
FALSE |  | CR234490 | Inspect Procured Parts - Wavefront Sensor | LSST Forecast - B57 - B1 | 60 | 0 | 2016-10-03 | 2017-03-31 | 0 | 2016-10-03 | 2017-03-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2017-02-15 | 2017-05-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 114 |  | Complete | 100% | 48 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.02 | Wavefront Sensor | 48 | 48 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 1% |  | Fabrication/Assembly |  | Other (specify) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | [6 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CRYO53130 | COMP: System Flushing for SLAC System (Link to FDR#2) | LSST Forecast - B57 - B1 | 0 | 0 | 2016-10-15 | 2016-10-15 | 0 | 2016-10-15 | 2016-10-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-04-18 | 2017-04-18 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Engineering Test/Validation
FALSE |  | CR240980 | Electrical performance validation - WEB EM | LSST Forecast - B57 - B1 | 30 | 0 | 2016-10-24 | 2017-02-24 | 0 | 2016-10-24 | 2017-02-24 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-11-01 | 2016-12-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 74 |  | Complete | 100% | 320 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.01 | Wavefront Electronics Board (WEB) | 320 | 320 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Testing/Integration | [7 empty] | Corner Raft Electronics (TEC) | WEB EM
FALSE |  | SR550270 | RTM #1 (1st Article) - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 20 | 0 | 2016-10-25 | 2017-01-10 | 0 | 2016-10-25 | 2017-01-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2016-11-16 | 2016-12-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 4 | 0 | 0 | 3 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 36 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 50 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #1 (First Article) |  | Science Raft System
FALSE |  | CRYO11730 | COMP: Assembly Mandrel- Cryostat Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2016-10-31 | 2016-10-31 | 0 | 2016-10-31 | 2016-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | FALSE | 2016-12-15 | 2016-12-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Fabrication/Assembly
FALSE |  | CRYO60940 | Prep for C_PDR - Refrigeration System | LSST Forecast - B57 - B1 | 20 | 0 | 2016-11-01 | 2016-11-14 | 0 | 2016-11-01 | 2016-11-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-12-01 | 2017-01-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 14 | 0 | 14 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 9 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.01 | Refrigeration System - Pre IR2 (System Design & Integration) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment |  | TEC Non-ARRA | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Refrigeration System
FALSE |  | CRYO30150 | Generate Manufacturing Docs - Cryostat Back End | LSST Forecast - B57 - B1 | 8 | 0 | 2016-11-01 | 2016-11-30 | 0 | 2016-11-01 | 2016-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-01-20 | 2017-01-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 8 | 19 |  | Complete | 100% | 32 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.01 | Cryostat Back End | 32 | 32 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Backend & Vacuum Systems (TEC) | [6 empty] | Cryostat Back End
FALSE |  | CRYO31030 | Procurement Process - Feedthru Flange Subcomponents - Cryostat Back End | LSST Forecast - B57 - B1 | 20 | 0 | 2016-11-01 | 2016-11-10 | 0 | 2016-11-01 | 2016-11-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-12-01 | 2017-01-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 7 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.01 | Cryostat Back End | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  |  | Procurement
FALSE |  | CR240920 | Additional custom software and engineering support for WEB EM testing | LSST Forecast - B57 - B1 | 15 | 0 | 2016-11-01 | 2017-02-24 | 0 | 2016-11-01 | 2017-02-24 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-12-01 | 2017-01-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 68 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.01 | Wavefront Electronics Board (WEB) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Testing/Integration | [7 empty] | Corner Raft Electronics (TEC) | WEB EM
FALSE |  | CR222710 | Clean Cold Raft Electronics test stand machined parts | LSST Forecast - B57 - B1 | 5 | 0 | 2016-11-01 | 2017-03-24 | 0 | 2016-11-01 | 2017-03-24 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-12-01 | 2016-12-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 88 |  | Complete | 100% | 16 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 16 | 16 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | [11 empty] | Corner Raft Tower Module (CRTM) (TEC)
FALSE |  | CRYO35070 | Stressed skin cover panels / attachment to UT structure | LSST Forecast - B57 - B1 | 65 | 0 | 2016-11-01 | 2017-05-31 | 0 | 2016-11-01 | 2017-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2016-12-01 | 2017-03-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 65 | 135 |  | Complete | 100% | 128 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.05.02 | Utility Trunk Thermo-Mechanical and Assembly | 128 | 128 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Utility Trunk Thermo-Mechanical and Assembly (TEC) | [6 empty] | Utility Trunk
FALSE |  | CCS124050 | NEED: Raft Electronics Board (REB5) | LSST Forecast - B57 - B1 | 0 | 0 | 2016-11-03 | 2016-11-03 | 0 | 2016-11-03 | 2016-11-03 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-01-03 | 2017-01-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.01.01 | REB Driver | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  | Level 5 Milestone | Design/Engineering
FALSE |  | CR222910 | Assemble the I&T TS-7 Dewar | LSST Forecast - B57 - B1 | 15 | 0 | 2016-11-09 | 2017-04-28 | 0 | 2016-11-09 | 2017-04-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-01-09 | 2017-01-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 107 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Procurement | [7 empty] | Corner Raft Tower Module (CRTM) (TEC)
FALSE |  | CRYO60670 | COMP: Subscale Test Stand (Second CRYO) | LSST Forecast - B57 - B1 | 0 | 0 | 2016-11-15 | 2016-11-15 | 0 | 2016-11-15 | 2016-11-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Finish Milestone | FALSE | 2016-12-15 | 2016-12-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 8 | 0 | 4 | 0 | 0 | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06 | Refrigeration System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Engineering Test/Validation
FALSE |  | SR332695 | Prod. Testing - Sensors V2 (Sensors #37-40) | LSST Forecast - B57 - B1 | 20 | 0 | 2016-11-15 | 2016-12-30 | 0 | 2016-11-15 | 2016-12-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-01-17 | 2017-02-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 29 |  | Complete | 100% | 30 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 30 | 30 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Catalog Listing or Industrial Construction Databases | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [6 empty] | Science Sensors Acceptance | [6 empty] | Sensors Vendor 2 |  | Science Sensors
FALSE |  | CR221920 | Vendor Fab & Machine - Corner raft tower | LSST Forecast - B57 - B1 | 40 | 0 | 2016-11-27 | 2017-04-28 | 0 | 2016-11-27 | 2017-04-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 164360 | 164360 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-03-27 | 2017-05-19 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 96 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 164360 | 164360 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Fabrication/Assembly |  | Other (specify) | [5 empty] | Corner Raft Tower Module (CRTM) (TEC) | CRTM Fab CRT | [5 empty] | Corner Raft Tower Module (CRTM)
FALSE |  | SR530130 | TS8 - practice test on engineering grade RTM | LSST Forecast - B57 - B1 | 20 | 0 | 2016-12-01 | 2016-12-30 | 0 | 2016-12-01 | 2016-12-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-01-03 | 2017-01-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 19 |  | Complete | 100% | 240 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.05 | RTM Electro-Optical Testing (TS8) | 240 | 240 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 8 - Assembly & Commissioning |  | Science Raft System
FALSE |  | AE220530 | Assemble Cables - Science/Corner Raft Test Stands Power Supplies | LSST Forecast - B57 - B1 | 30 | 0 | 2016-12-01 | 2017-01-11 | 0 | 2016-12-01 | 2017-01-11 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-01-30 | 2017-03-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 18 |  | Complete | 100% | 48 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.02.02 | Custom Raft Supply Boards | 48 | 48 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Gunther Haller | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Fabrication/Assembly |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Aux Elec Components (TEC)
FALSE |  | CR222780 | Assemble Enhanced Components into Cold Raft Electronics test stand | LSST Forecast - B57 - B1 | 10 | 0 | 2016-12-05 | 2017-02-24 | 0 | 2016-12-05 | 2017-02-24 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-02-15 | 2017-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 46 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot |  |  |  | Fabrication/Assembly | [7 empty] | Corner Raft Tower Module (CRTM) (TEC)
FALSE |  | CAMF660050 | COMP: Final Design & Assembly Drawings - Auto Changer | LSST Forecast - B57 - B1 | 0 | 0 | 2016-12-15 | 2016-12-15 | 0 | 2016-12-15 | 2016-12-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-01-03 | 2017-01-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.01 | Auto Changer | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  | Level 4 Milestone | Design/Engineering
FALSE |  | CRYO11724 | COMP: Faro Arm Stand - Cryostat Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2016-12-16 | 2016-12-16 | 0 | 2016-12-16 | 2016-12-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2017-02-06 | 2017-02-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Fabrication/Assembly
FALSE |  | SR552690 | Install & Commission Test Stand 6 | LSST Forecast - B57 - B1 | 20 | 0 | 2016-12-20 | 2017-02-17 | 0 | 2016-12-20 | 2017-02-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-01-30 | 2017-02-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 39 |  | Complete | 100% | 320 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.07.01 | Cleanroom Development & Commissioning | 320 | 320 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Assembly and Test Facility (TEC) | Test Stand Effort | [5 empty] | Science Raft - Assembly and Test Facility | [6 empty] | Test Stand 6 - Assembly & Commissioning |  | Science Raft System
FALSE |  | SR530095 | NEED: CCS Controller - Production | LSST Forecast - B57 - B1 | 0 | 0 | 2016-12-30 | 2016-12-30 | 0 | 2016-12-30 | 2016-12-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-01-31 | 2017-01-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.05 | RTM Electro-Optical Testing (TS8) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% | Level 5 Milestone | Fabrication/Assembly | [14 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 8 - Assembly & Commissioning |  | Science Raft System
FALSE |  | SR531180 | AVAIL: TS8 Ready for commissioning | LSST Forecast - B57 - B1 | 0 | 0 | 2016-12-30 | 2016-12-30 | 0 | 2016-12-30 | 2016-12-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2017-02-15 | 2017-02-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 4 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.05 | RTM Electro-Optical Testing (TS8) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% | Level 5 Milestone | Testing/Integration | [14 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 8 - Assembly & Commissioning |  | Science Raft System

## 2017 Details
Fuse® Analyst Report
Workbook: Workbook1 - 8168 Activities
Schedule Quality
Created on: 8/5/2019
Created by: brackett
2017: Detailed View | 2017: Detailed View | 2017: Detailed View
Number of Lags
Total number of activities that have lags in their predecessors. This number should not exceed 5%.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | Previous Start | Previous Finish | Percent Complete | Previous Remaining Duration | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | IsLevelOfEffort | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | Global_Basis of Estimate | Global_Cobra Cost Class | Cobra PMT (EV Method)_Global | Global_Color of Money | Global_Control Account Manager | Global_Design Maturity | Global_Judgement Factor | Global_Milestone Levels | Global_Project Phase | Global_Funding Source | Global_EDIA Survey | Global_MS Type | Phase | NSF Milestones | Loading Curve | Sensor Vendor | LSST_CA | Summary Schedule | ICD for NSF Input | LSST Camera Critical Paths | CD2 Budget Changes | DOE Reviews | Critical Path (CD Reviews) | LSST WP Summary | Critical Path (Camera Delivery) | AWARD / NEED Sub-System | Final Design Key Links | CP - CAMM2100 | CP - CAMM2130 | CP - CAMM2160 | BNL Work Org | Last ETC Update | BNL WBS | LSST Story List | Sum Sch 01 (Camera) | Sum Sch 02 (IT w/Needs) | Sum Sch 03 (Sensors_RTM_IT) | LSST Raft Particulate Mitigation | LSST RTM
FALSE |  | CRYO11758 | Vendor Lead Time - All Parts - Purge Box - Cryostat Assembly | LSST Forecast - B57 - B1 | 47 | 0 | 2017-01-02 | 2017-02-18 | 0 | 2017-01-02 | 2017-02-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-03-01 | 2017-05-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 47 | 35 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 10% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor
FALSE |  | SR343860 | Package/Ship (between BNL/Vendor/SLAC) | LSST Forecast - B57 - B1 | 103 | 0 | 2017-01-03 | 2017-08-29 | 0 | 2017-01-03 | 2017-08-29 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-02-01 | 2017-06-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 103 | 166 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [6 empty] | Prodcution REB-5 Build |  | Science Raft System
FALSE |  | CRYO23400 | Vendor Lead Time - Other items - Grid Assembly | LSST Forecast - B57 - B1 | 19 | 0 | 2017-01-09 | 2017-03-31 | 0 | 2017-01-09 | 2017-03-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-04-03 | 2017-04-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 19 | 57 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.04 | Grid Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [12 empty] | Grid Assembly
FALSE |  | CRYO11747 | RCV: All Parts - Other Lift Devices/Equipment - Cryostat Assembly | LSST Forecast - B57 - B1 | 12 | 0 | 2017-01-16 | 2017-01-31 | 0 | 2017-01-16 | 2017-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 20000 | 20000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-03-03 | 2017-03-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 12 | 11 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 20000 | 20000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 5% | Level 4 Milestone | Procurement | [7 empty] | Cryostat Housing & Assembly (TEC)
FALSE |  | CRYO11734 | Vendor Lead Time - All Parts - Grid Handling Fixture - Cryostat Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2017-02-01 | 2017-02-17 | 0 | 2017-02-01 | 2017-02-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-03-01 | 2017-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 0 | 12 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 10% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor
FALSE |  | SR343920 | Assemble at Vendor, Clean & Test REB5 Batch 2 at vendor (10 units - RTM 4-6) | LSST Forecast - B57 - B1 | 28 | 0 | 2017-02-01 | 2017-03-07 | 0 | 2017-02-01 | 2017-03-07 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2017-02-01 | 2017-03-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 28 | 23 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation | [7 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [6 empty] | Prodcution REB-5 Build |  | Science Raft System
FALSE |  | SR550274 | RTM1_RTM Construction at TS6 | LSST Forecast - B57 - B1 | 19 | 0 | 2017-02-02 | 2017-03-06 | 0 | 2017-02-02 | 2017-03-06 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-03-07 | 2017-03-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 3 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 19 | 21 |  | Complete | 100% | 64 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 64 | 64 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #1 (First Article) |  | Science Raft System
FALSE |  | SR551760 | Design Update - Incorporate FDR changes | LSST Forecast - B57 - B1 | 10 | 0 | 2017-02-14 | 2017-02-28 | 0 | 2017-02-14 | 2017-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-02-14 | 2017-02-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 10 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.03 | Science Raft Shipping Container | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Science Raft Tower Module (SRTM) (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Science Raft Shipping Container |  | Science Raft System
FALSE |  | SR344120 | Assemble, Clean & Test REB5 Batch 4 at vendor (25 units RTM 10-17) | LSST Forecast - B57 - B1 | 35 | 0 | 2017-02-15 | 2017-04-21 | 0 | 2017-02-15 | 2017-04-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-23 | 2019-07-23 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2017-02-15 | 2017-04-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 10 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 35 | 46 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation | [7 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [6 empty] | Prodcution REB-5 Build |  | Science Raft System
FALSE |  | SR344220 | Assemble at Vendor, Clean & Test REB5 Batch 5 at vendor (25 units RTM 18-24) | LSST Forecast - B57 - B1 | 41 | 0 | 2017-02-22 | 2017-05-30 | 0 | 2017-02-22 | 2017-05-30 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-02-22 | 2017-04-19 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 41 | 68 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation | [7 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [6 empty] | Prodcution REB-5 Build |  | Science Raft System
FALSE |  | SR550450 | RTM #4 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2017-03-21 | 2017-05-16 | 0 | 2017-03-21 | 2017-05-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-06-01 | 2017-07-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 3 | 2 | 0 | 1 | 2 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 40 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #4 |  | Science Raft System
FALSE |  | SR550570 | RTM #6 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2017-03-21 | 2017-08-15 | 0 | 2017-03-21 | 2017-08-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2017-05-22 | 2017-06-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 1 | 0 | 2 | 3 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 103 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #6 |  | Science Raft System
FALSE |  | SR550630 | RTM #7 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2017-03-21 | 2017-08-11 | 0 | 2017-03-21 | 2017-08-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-07-10 | 2017-08-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 0 | 1 | 0 | 3 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 101 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #7 |  | Science Raft System
FALSE |  | SR550690 | RTM #8 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2017-03-21 | 2017-09-11 | 0 | 2017-03-21 | 2017-09-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-06-20 | 2017-07-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 0 | 1 | 0 | 3 | 2 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 121 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #8 |  | Science Raft System
FALSE |  | SR550750 | RTM #9 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2017-03-21 | 2017-10-13 | 0 | 2017-03-21 | 2017-10-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-09-13 | 2017-10-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 1 | 0 | 2 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 145 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #9 |  | Science Raft System
FALSE |  | SR550810 | RTM #10 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 7 | 2017-03-21 | 2017-10-31 | 0 | 2017-03-21 | 2017-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-23 | 2019-07-23 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-10-04 | 2017-11-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 157 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #10 |  | Science Raft System
FALSE |  | SR550870 | RTM #11 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2017-03-21 | 2017-11-30 | 0 | 2017-03-21 | 2017-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-23 | 2019-07-23 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-10-25 | 2017-11-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 1 | 0 | 2 | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 177 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #11 |  | Science Raft System
FALSE |  | SR550930 | RTM #12 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2017-03-21 | 2018-01-23 | 0 | 2017-03-21 | 2018-01-23 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-23 | 2019-07-23 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-12-15 | 2018-01-23 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 1 | 0 | 2 | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 212 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #12 |  | Science Raft System
FALSE |  | SR550990 | RTM #13 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2017-03-21 | 2018-02-13 | 0 | 2017-03-21 | 2018-02-13 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-12-13 | 2018-01-19 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 1 | 0 | 2 | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 227 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #13 |  | Science Raft System
FALSE |  | SR551170 | RTM #16 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2017-03-21 | 2018-05-31 | 0 | 2017-03-21 | 2018-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-04-06 | 2018-05-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 302 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #16 |  | Science Raft System
FALSE |  | SR551410 | RTM #20 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2017-03-21 | 2018-09-10 | 0 | 2017-03-21 | 2018-09-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-06-19 | 2018-07-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 372 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #20 |  | Science Raft System
FALSE |  | SR550080 | SHIPPING: Ship RTM ETU #1 to SLAC | LSST Forecast - B57 - B1 | 6 | 0 | 2017-03-24 | 2017-03-31 | 0 | 2017-03-24 | 2017-03-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-04-26 | 2017-05-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 0 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 6 | 5 |  | Complete | 100% | 8 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 8 | 8 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration |  | Other (specify) | [5 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM ETU #1 |  | Science Raft System
FALSE |  | CRYO61220 | C_FDR - Final Design Review - Refrigeration System - IR2 | LSST Forecast - B57 - B1 | 2 | 0 | 2017-05-22 | 2017-05-22 | 0 | 2017-05-22 | 2017-05-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2017-06-01 | 2017-06-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.01 | Refrigeration System - Pre IR2 (System Design & Integration) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Design Reviews | [5 empty] | Refrigeration System (TEC) | [6 empty] | Refrigeration System
FALSE |  | SR344132 | Perform Mech. Assy/Tcycling/burnin-Test/Vac-Prep/RGA/ Prep for Ship at SLAC (25) REB5 boards | LSST Forecast - B57 - B1 | 48 | 0 | 2017-05-23 | 2017-09-11 | 0 | 2017-05-23 | 2017-09-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-23 | 2019-07-23 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-06-01 | 2017-08-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 48 | 76 |  | Complete | 100% | 100 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 100 | 100 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | [11 empty] | Science Raft Electronics (TEC) | [13 empty] | Prodcution REB-5 Build |  | Science Raft System
FALSE |  | SR343950 | Test REB5 Batch 2 Shipment at BNL (10 Units - RTM 4-6) | LSST Forecast - B57 - B1 | 25 | 0 | 2017-05-27 | 2017-07-18 | 0 | 2017-05-27 | 2017-07-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-05-30 | 2017-07-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 34 |  | Complete | 100% | 20 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 20 | 20 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation | [7 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [6 empty] | Prodcution REB-5 Build |  | Science Raft System
FALSE |  | CRYO60395 | Procurement Process - Compressors Oil Reservoirs - Cryo - IR2 (6 Units) | LSST Forecast - B57 - B1 | 30 | 0 | 2017-06-01 | 2017-06-07 | 0 | 2017-06-01 | 2017-06-07 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-07-03 | 2017-08-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 4 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.02 | Refrigeration System - Pre IR2 (Compressor Cabinet) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Alice Callen |  |  |  | Procurement
FALSE |  | ITC33340 | Procurement - Vendor Lead Time - Test Raft | LSST Forecast - B57 - B1 | 42 | 0 | 2017-06-05 | 2017-09-15 | 0 | 2017-06-05 | 2017-09-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-07-03 | 2017-08-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 42 | 72 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.02.02 | Pathfinder / Test Raft Program | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc)
FALSE |  | SR339400 | AWARD: Sensor Production Lot 2 V1, Long Lead Option 1 | LSST Forecast - B57 - B1 | 1 | 0 | 2017-06-06 | 2017-06-06 | 0 | 2017-06-06 | 2017-06-06 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 1362723 | 1362723 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-09-01 | 2017-09-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 1362723 | 1362723 | 0 | PercentComplete | 4% | CP_Phys |  | B1 Procurement Commitment (C5.1) |  | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR340255 | Backside Processing (Batch 3) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 15 | 0 | 2017-06-26 | 2017-07-24 | 0 | 2017-06-26 | 2017-07-24 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-07-03 | 2017-07-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 19 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR550150 | SHIPPING: Ship RTM ETU #2 to SLAC | LSST Forecast - B57 - B1 | 4 | 0 | 2017-07-03 | 2017-07-07 | 0 | 2017-07-03 | 2017-07-07 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-08-01 | 2017-08-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 3 |  | Complete | 100% | 8 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 8 | 8 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration |  | Other (specify) | [5 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM ETU #2 |  | Science Raft System
FALSE |  | ITC30580 | Perform Engineering RTM Receiving Test #2 | LSST Forecast - B57 - B1 | 25 | 0 | 2017-07-10 | 2017-09-15 | 0 | 2017-07-10 | 2017-09-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-08-07 | 2017-09-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 4 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 48 |  | Complete | 100% | 330 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.03 | Raft Acceptance Testing | 330 | 330 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [6 empty] | Cryostat I&T
FALSE |  | CR242520 | PROC: GEB (PCB & components) | LSST Forecast - B57 - B1 | 30 | 0 | 2017-07-10 | 2017-09-22 | 0 | 2017-07-10 | 2017-09-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 80000 | 80000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-08-15 | 2017-09-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 53 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.02 | Guider Electronics Board (GEB) | 0 | 0 | 0 | 80000 | 80000 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Procurement | [7 empty] | Corner Raft Electronics (TEC) | GEB
FALSE |  | ITC92090 | Early Procurements - Com Cam | LSST Forecast - B57 - B1 | 59 | 0 | 2017-07-10 | 2018-04-02 | 0 | 2017-07-10 | 2018-04-02 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-31 | 2019-05-31 | 170000 | 170000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-08-01 | 2017-10-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 59 | 190 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.06.01 | Commissioning Camera Hardware | 0 | 0 | 0 | 170000 | 170000 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Kevin Reil | (1.00) Task/item is fully invoiced/completed | 0% |  | Engineering Test/Validation |  | R&D | [5 empty] | Commissioning Camera (TEC)
FALSE |  | ITC17770 | Final Documentation - SBMS | LSST Forecast - B57 - B1 | 10 | 0 | 2017-07-11 | 2017-09-15 | 0 | 2017-07-11 | 2017-09-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-08-01 | 2017-08-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 47 |  | Complete | 100% | 168 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.01.01 | Single Bay Metrology Tests | 168 | 168 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC)
FALSE |  | CRYO61305 | Procurement - Condensing Unit & HW - IR2 | LSST Forecast - B57 - B1 | 36 | 0 | 2017-07-17 | 2018-04-04 | 0 | 2017-07-17 | 2018-04-04 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 24000 | 24000 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-08-01 | 2017-09-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 36 | 171 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.02 | Refrigeration System - Pre IR2 (Compressor Cabinet) | 0 | 0 | 0 | 24000 | 24000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | SR343990 | Receive REB5 Batch 3 Shipment at BNL (10 Units - RTM 7-9) | LSST Forecast - B57 - B1 | 10 | 0 | 2017-08-01 | 2017-08-14 | 0 | 2017-08-01 | 2017-08-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-09-01 | 2017-09-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment |  | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation | [7 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [6 empty] | Prodcution REB-5 Build |  | Science Raft System
FALSE |  | SR340295 | Backside Processing (Batch 5) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 19 | 0 | 2017-08-01 | 2017-08-28 | 0 | 2017-08-01 | 2017-08-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-09-01 | 2017-09-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 19 | 19 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR340315 | Backside Processing (Batch 6) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 14 | 0 | 2017-08-01 | 2017-08-28 | 0 | 2017-08-01 | 2017-08-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-09-11 | 2017-09-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 14 | 19 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR340355 | Backside Processing (Batch 8) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 6 | 0 | 2017-08-01 | 2017-08-30 | 0 | 2017-08-01 | 2017-08-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-09-01 | 2017-09-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 4 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 6 | 21 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR340335 | Backside Processing (Batch 7) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 2 | 0 | 2017-08-01 | 2017-08-28 | 0 | 2017-08-01 | 2017-08-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-08-01 | 2017-08-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 19 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | CCS208400 | OCS-DM-CCS complete visit test - CCS/OCS | LSST Forecast - B57 - B1 | 86 | 0 | 2017-08-21 | 2017-10-13 | 0 | 2017-08-21 | 2017-10-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-17 | 2019-10-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2018-02-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 86 | 38 |  | Complete | 100% | 240 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.04 | CCS/OCS Bridge | 240 | 240 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Testing/Integration | [7 empty] | CCS Core (TEC)
FALSE |  | ITC94000 | START: ComCam Baseline Planning | LSST Forecast - B57 - B1 | 0 | 0 | 2017-08-28 | 2017-08-28 | 0 | 2017-08-28 | 2017-08-28 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 5 | FALSE | Finish Milestone | FALSE | 2017-09-01 | 2017-09-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.06.06 | Commissioning Baseline Planning | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment |  | TEC Non-ARRA | Kevin Reil | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% | Level 4 Milestone | Testing/Integration
FALSE |  | CRYO61000 | Detail Piece Parts & Assemblies - Valve & Filters/Desiccators - Refrigeration (Compressor Chassis HW Outside) | LSST Forecast - B57 - B1 | 9 | 0 | 2017-09-01 | 2017-12-22 | 0 | 2017-09-01 | 2017-12-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2017-10-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 9 | 73 |  | Complete | 100% | 88 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.02 | Refrigeration System - Pre IR2 (Compressor Cabinet) | 88 | 88 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) | [6 empty] | Refrigeration System
FALSE |  | CRYO61340 | Requisition - Heat Exchanger Can Vac Sys - Cryostat | LSST Forecast - B57 - B1 | 10 | 0 | 2017-09-01 | 2017-09-15 | 0 | 2017-09-01 | 2017-09-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2017-10-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.04 | Refrigeration System - Pre IR2 (HX) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  |  | Procurement
FALSE |  | SR340375 | Backside Processing (Batch 9) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 20 | 0 | 2017-09-01 | 2017-09-15 | 0 | 2017-09-01 | 2017-09-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-10-02 | 2017-10-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 4 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 9 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR340395 | Backside Processing (Batch 10) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 25 | 0 | 2017-09-01 | 2017-09-15 | 0 | 2017-09-01 | 2017-09-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-10-02 | 2017-11-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 9 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR340415 | Backside Processing (Batch 11) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 27 | 0 | 2017-09-01 | 2017-09-15 | 0 | 2017-09-01 | 2017-09-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-10-05 | 2017-11-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 27 | 9 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR340435 | Backside Processing (Batch 12) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 27 | 0 | 2017-09-01 | 2017-09-15 | 0 | 2017-09-01 | 2017-09-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-10-12 | 2017-11-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 27 | 9 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | CRYO61255 | B750 Move-out - Refrigeration System | LSST Forecast - B57 - B1 | 20 | 0 | 2017-09-01 | 2018-01-31 | 0 | 2017-09-01 | 2018-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2017-10-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 93 |  | Complete | 100% | 240 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.01 | Refrigeration System - Pre IR2 (System Design & Integration) | 240 | 240 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC)
FALSE |  | ITC93350 | DAQ Pathfinder - Travel (1-5) | LSST Forecast - B57 - B1 | 200 | 0 | 2017-09-01 | 2018-09-05 | 0 | 2017-09-01 | 2018-09-05 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 15000 | 15000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2018-07-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 200 | 244 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.06.05 | DAQ Pathfinder | 0 | 0 | 0 | 15000 | 15000 | 0 | PercentComplete | 4% | CP_Drtn | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Kevin Reil | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Construction Management | [5 empty] | Commissioning Camera (TEC)
FALSE |  | ITC93000 | CCS Pathfinder 1 | LSST Forecast - B57 - B1 | 40 | 0 | 2017-09-01 | 2017-10-02 | 0 | 2017-09-01 | 2017-10-02 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2017-11-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 20 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.06.04 | CCS Pathfinder | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Kevin Reil | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | R&D | [5 empty] | Commissioning Camera (TEC)
FALSE |  | ITC93050 | CCS Pathfinder - Travel (1-5) | LSST Forecast - B57 - B1 | 200 | 0 | 2017-09-01 | 2018-08-02 | 0 | 2017-09-01 | 2018-08-02 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 15000 | 15000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2018-07-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 200 | 221 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.06.04 | CCS Pathfinder | 0 | 0 | 0 | 15000 | 15000 | 0 | PercentComplete | 4% | CP_Drtn | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Kevin Reil | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Construction Management | [5 empty] | Commissioning Camera (TEC)
FALSE |  | ITC33310 | Procurement - Vendor Lead Time - Cryostat Mockup | LSST Forecast - B57 - B1 | 19 | 0 | 2017-09-02 | 2017-09-28 | 0 | 2017-09-02 | 2017-09-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2017-10-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 19 | 17 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.02.02 | Pathfinder / Test Raft Program | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc)
FALSE |  | CAMF660600 | Requisition - Other Items - Auto Changer | LSST Forecast - B57 - B1 | 5 | 0 | 2017-09-05 | 2018-07-02 | 0 | 2017-09-05 | 2018-07-02 | 0 | 2019-06-01 | 2019-06-01 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2017-10-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 198 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.01 | Auto Changer | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Procurement
FALSE |  | CAMF664400 | Requisition - Parts - Filter Loader | LSST Forecast - B57 - B1 | 5 | 0 | 2017-09-05 | 2018-01-08 | 0 | 2017-09-05 | 2018-01-08 | 0 | 2019-06-01 | 2019-06-01 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2017-10-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 76 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.02 | Filter Loader | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Procurement
FALSE |  | CRYO32300 | Prep for Prelim Design Review - Cryostat Vacuum Purge | LSST Forecast - B57 - B1 | 5 | 0 | 2017-09-05 | 2017-09-11 | 0 | 2017-09-05 | 2017-09-11 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2017-10-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 4 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.03 | Vacuum Processing and Ground Support | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Cryostat Utillities
FALSE |  | CRYO61345 | Detail Drawings - Solenoid Valve Assy - Cryo - IR2 | LSST Forecast - B57 - B1 | 16 | 0 | 2017-09-05 | 2017-09-26 | 0 | 2017-09-05 | 2017-09-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2017-10-23 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 16 | 15 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.02 | Refrigeration System - Pre IR2 (Compressor Cabinet) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | CRYO70260 | Procurement - SS Tubes (Long Lines, Liquid) - IR2 | LSST Forecast - B57 - B1 | 20 | 0 | 2017-09-05 | 2017-09-28 | 0 | 2017-09-05 | 2017-09-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 5500 | 5500 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2017-10-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 17 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.03 | Refrigeration System - Pre IR2 (Long Lines) | 0 | 0 | 0 | 5500 | 5500 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | ITC33530 | Outside Fabrication - Vendor Lead Time - Gantry | LSST Forecast - B57 - B1 | 28 | 0 | 2017-09-08 | 2018-03-16 | 0 | 2017-09-08 | 2018-03-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2017-11-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 10 | 10 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 28 | 120 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.01 | Integration Gantry | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment |  | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc)
FALSE |  | SR340455 | Backside Processing (Batch 13) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 21 | 0 | 2017-09-18 | 2017-10-30 | 0 | 2017-09-18 | 2017-10-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-10-30 | 2017-12-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 21 | 30 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | OP521810_1 | RCV: 2nd-band Sub-scale Sample Metrology and Coating Report/Samples (MS3.1) - Filter Coating | LSST Forecast - B57 - B1 | 1 | 0 | 2017-09-22 | 2017-09-22 | 0 | 2017-09-22 | 2017-09-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-12-12 | 2019-12-12 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2017-10-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | 0-100% Method | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 7% |  | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Filters (TEC)
FALSE |  | CRYO73025 | Procurement of Servicing Equipment and Materials | LSST Forecast - B57 - B1 | 36 | 0 | 2017-09-23 | 2017-11-28 | 0 | 2017-09-23 | 2017-11-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 50400 | 50400 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2017-11-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 36 | 44 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.05 | Refrigeration System - Pre IR2 (Equipment & Refrigeration) | 0 | 0 | 0 | 50400 | 50400 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | CRYO70240 | Procurement - Long Line Hoses (Cold & Cryo) - IR2 | LSST Forecast - B57 - B1 | 20 | 0 | 2017-09-25 | 2017-10-02 | 0 | 2017-09-25 | 2017-10-02 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 12000 | 12000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2017-10-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 5 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.03 | Refrigeration System - Pre IR2 (Long Lines) | 0 | 0 | 0 | 12000 | 12000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | CCS208200 | NEED: OCS Release V4 - CCS/OCS | LSST Forecast - B57 - B1 | 0 | 0 | 2017-09-29 | 2017-09-29 | 0 | 2017-09-29 | 2017-09-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-17 | 2019-10-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-07-02 | 2018-07-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.04 | CCS/OCS Bridge | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | CRYO61510 | Requisition - Compressor Module Control Boxes - IR2 Install | LSST Forecast - B57 - B1 | 10 | 0 | 2017-10-02 | 2017-10-13 | 0 | 2017-10-02 | 2017-10-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-11-01 | 2017-11-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.02 | Refrigeration System - Pre IR2 (Compressor Cabinet) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  |  | Procurement
FALSE |  | CCS402920 | Develop Control System for IR2 Refrigeration - Cryostat HCU | LSST Forecast - B57 - B1 | 30 | 0 | 2017-10-02 | 2017-12-12 | 0 | 2017-10-02 | 2017-12-12 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-07 | 2019-05-07 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-11-01 | 2017-12-14 |  |  |  |  | 1 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 49 |  | Complete | 100% | 240 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.03 | Cryostat HCU | 240 | 240 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | CCS HCU (TEC) | [6 empty] | Camera I&T Hardware Control Unit
FALSE |  | AE214170 | Design Production Protection PLC System | LSST Forecast - B57 - B1 | 60 | 0 | 2017-10-02 | 2017-10-14 | 0 | 2017-10-02 | 2017-10-14 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-11-01 | 2018-02-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 10 |  | Complete | 100% | 220 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.02.14 | Protection PLC System | 220 | 220 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Gunther Haller | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Aux Elec Components (TEC) | [6 empty] | Power Control Monitoring
FALSE |  | AE215170 | Design Production Protection HCU System | LSST Forecast - B57 - B1 | 120 | 0 | 2017-10-02 | 2017-10-06 | 0 | 2017-10-02 | 2017-10-06 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-11-01 | 2018-05-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 120 | 4 |  | Complete | 100% | 20 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.02.15 | Protection HCU System | 20 | 20 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Gunther Haller | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Aux Elec Components (TEC) | [6 empty] | Power Control Monitoring
FALSE |  | CAMF702400 | Requisition - Production Parts - Filter Blocks | LSST Forecast - B57 - B1 | 5 | 0 | 2017-10-02 | 2017-10-06 | 0 | 2017-10-02 | 2017-10-06 | 0 | 2019-06-01 | 2019-06-01 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-11-01 | 2017-11-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 4 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.02 | Filter Loader | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Procurement
FALSE |  | SR340475 | Backside Processing (Batch 14) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 21 | 0 | 2017-10-02 | 2017-10-30 | 0 | 2017-10-02 | 2017-10-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-11-01 | 2017-12-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 21 | 20 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR339470 | E2v "Letters of Credit" for SLIN 0001 & 0002 | LSST Forecast - B57 - B1 | 15 | 0 | 2017-10-02 | 2017-10-20 | 0 | 2017-10-02 | 2017-10-20 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 34509 | 34509 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-11-01 | 2017-11-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 14 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 34509 | 34509 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC)
FALSE |  | SR340495 | Backside Processing (Batch 15) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 25 | 0 | 2017-10-03 | 2017-10-20 | 0 | 2017-10-03 | 2017-10-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-11-01 | 2017-12-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 13 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR340535 | Backside Processing (Batch 17) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 25 | 0 | 2017-10-04 | 2017-11-17 | 0 | 2017-10-04 | 2017-11-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-11-01 | 2017-12-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 32 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR340515 | Backside Processing (Batch 16) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 25 | 0 | 2017-10-10 | 2017-10-20 | 0 | 2017-10-10 | 2017-10-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-11-01 | 2017-12-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 8 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | DAQ341700 | Update Documentation - Production - RDS/RDC | LSST Forecast - B57 - B1 | 40 | 0 | 2017-10-23 | 2017-10-31 | 0 | 2017-10-23 | 2017-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-12 | 2018-05-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 6 |  | Complete | 100% | 20 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.09.02 | Raft Data Server/Client Software (RDS/RDC) | 20 | 20 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Testing/Integration |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | DAQ Readout Systems (TEC) |  | ICD's for Phase 3 |  |  |  |  | DAQ Readout Systems
FALSE |  | DAQ361400 | Update Documentation - Production - IMS/IMC | LSST Forecast - B57 - B1 | 40 | 0 | 2017-10-23 | 2017-10-31 | 0 | 2017-10-23 | 2017-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-12 | 2018-05-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 6 |  | Complete | 100% | 20 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.09.01 | Image Management/Server/Client Software | 20 | 20 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Testing/Integration |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | DAQ Readout Systems (TEC)
FALSE |  | SR339475 | AWARD: Sensor Production Lot 3 V1, Option 2 | LSST Forecast - B57 - B1 | 1 | 0 | 2017-10-24 | 2017-10-24 | 0 | 2017-10-24 | 2017-10-24 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 2077489 | 2077489 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-11-01 | 2017-11-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 2077489 | 2077489 | 0 | PercentComplete | 4% | CP_Phys |  | B1 Procurement Commitment (C5.1) |  | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC)
FALSE |  | CBM25551 | RCV: Intermediate Material Payment - Back Flange | LSST Forecast - B57 - B1 | 1 | 0 | 2017-10-31 | 2017-10-31 | 0 | 2017-10-31 | 2017-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2018-09-07 | 2018-09-07 | 15000 | 15000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-12-04 | 2017-12-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.01.02 | Camera Body Development | 0 | 0 | 0 | 15000 | 15000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | 0-100% Method | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% | Level 4 Milestone | Procurement | [7 empty] | Camera Body Development (TEC)
FALSE |  | CRYO61420 | Make Electrical Connections to Hex Vac Sys - Cryostat | LSST Forecast - B57 - B1 | 4 | 0 | 2017-11-01 | 2017-11-30 | 0 | 2017-11-01 | 2017-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-05-21 | 2018-05-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 19 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.04 | Refrigeration System - Pre IR2 (HX) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Fabrication/Assembly |  | Other (specify) | [5 empty] | Refrigeration System (TEC) | [6 empty] | Refrigeration System
FALSE |  | CRYO25550 | Finalize Design - Sieve | LSST Forecast - B57 - B1 | 80 | 0 | 2017-11-01 | 2017-11-17 | 0 | 2017-11-01 | 2017-11-17 | 0 | 2019-06-01 | 2019-06-01 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2018-04-02 | 2018-07-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 80 | 12 |  | Complete | 100% | 58 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.02 | Getter Pumps | 58 | 58 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Backend & Vacuum Systems (TEC) | [6 empty] | Cryostat Getter Pumps
FALSE |  | CRYO25560 | Finalize Analysis - Sieve | LSST Forecast - B57 - B1 | 80 | 0 | 2017-11-01 | 2017-11-17 | 0 | 2017-11-01 | 2017-11-17 | 0 | 2019-06-01 | 2019-06-01 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2018-04-02 | 2018-07-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 80 | 12 |  | Complete | 100% | 52 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.02 | Getter Pumps | 52 | 52 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Backend & Vacuum Systems (TEC) | [6 empty] | Cryostat Getter Pumps
FALSE |  | CCS250035 | Develop scripting interface for BOT - BOT HCU | LSST Forecast - B57 - B1 | 23 | 0 | 2017-11-01 | 2018-03-15 | 0 | 2017-11-01 | 2018-03-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-12-01 | 2018-01-18 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 23 | 81 |  | Complete | 100% | 200 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.08.02 | BOT HCU | 200 | 200 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Expert Opinion (Engineering Allowance) | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 6% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | CCS HCU (TEC) | [6 empty] | Camera I&T Hardware Control Unit
FALSE |  | ITC25865 | NEED: CCOB Wide Beam Ready | LSST Forecast - B57 - B1 | 0 | 0 | 2017-11-01 | 2017-11-01 | 0 | 2017-11-01 | 2017-11-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-12-01 | 2017-12-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.02.01 | Bench For Optical Testing (BOT) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | CCS310700 | NEED: Integration Gantry Hardware from I&T | LSST Forecast - B57 - B1 | 0 | 0 | 2017-11-01 | 2017-11-01 | 0 | 2017-11-01 | 2017-11-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-12-01 | 2017-12-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.08.04 | Gantry HCU | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Tony Johnson |  |  | Level 5 Milestone | Design/Engineering
FALSE |  | SR340555 | Backside Processing (Batch 18) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 25 | 0 | 2017-11-01 | 2017-11-17 | 0 | 2017-11-01 | 2017-11-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-12-01 | 2018-01-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 12 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | CRYO60986 | RCV: Compressor Module - IR2 | LSST Forecast - B57 - B1 | 22 | 0 | 2017-11-01 | 2017-11-30 | 0 | 2017-11-01 | 2017-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-01-31 | 2018-03-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 22 | 19 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.02 | Refrigeration System - Pre IR2 (Compressor Cabinet) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 20% |  | Procurement | [7 empty] | Refrigeration System (TEC)
FALSE |  | CRYO61635 | Beta Test Software for 8 Systems - Cold/Cryo | LSST Forecast - B57 - B1 | 15 | 0 | 2017-11-01 | 2017-11-30 | 0 | 2017-11-01 | 2017-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-06-15 | 2018-07-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 19 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.02 | Refrigeration System - IR2 | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | CRYO56400 | Assemble - Hx and Capillaries - Cryo - IR2 | LSST Forecast - B57 - B1 | 50 | 0 | 2017-11-01 | 2017-11-30 | 0 | 2017-11-01 | 2017-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-02-09 | 2018-04-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 50 | 19 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.04 | Refrigeration System - Pre IR2 (HX) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | CRYO56200 | Procurement - Hx & HW - Cold - IR2 | LSST Forecast - B57 - B1 | 1 | 0 | 2017-11-01 | 2017-11-30 | 0 | 2017-11-01 | 2017-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-11-30 | 2017-11-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 20 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.04 | Refrigeration System - Pre IR2 (HX) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | SR310640 | Sub-system Scientist | LSST Forecast - B57 - B1 | 240 | 0 | 2017-11-01 | 2018-10-15 | 0 | 2017-11-01 | 2018-10-15 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-12-01 | 2018-11-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 240 | 239 |  | Complete | 100% | 880 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.01 | Science Raft System Integration & Management | 880 | 880 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Drtn |  | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 0% |  | Management/Administration |  | Construction Management | [5 empty] | Science Raft System (TEC) | [13 empty] | Management - LOE |  | Science Raft System
FALSE |  | SR310650 | Sub-system Deputy PM | LSST Forecast - B57 - B1 | 240 | 0 | 2017-11-01 | 2018-10-15 | 0 | 2017-11-01 | 2018-10-15 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-12-01 | 2018-11-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 240 | 239 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.01 | Science Raft System Integration & Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Drtn |  | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 0% |  | Management/Administration |  | Construction Management | [5 empty] | Science Raft System (TEC) | [13 empty] | Management - LOE |  | Science Raft System
FALSE |  | DAQ313310 | Switch Selection - COB Production Candidate | LSST Forecast - B57 - B1 | 10 | 0 | 2017-11-01 | 2017-11-14 | 0 | 2017-11-01 | 2017-11-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-31 | 2019-10-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-12-01 | 2017-12-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.02 | DAQ COB (Main ATCA DAQ Module) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | DAQ Readout Systems (TEC)
FALSE |  | CBM27800 | Vendor Efforts - Fixtures/Equip - Camera Body | LSST Forecast - B57 - B1 | 45 | 0 | 2017-11-06 | 2018-01-31 | 0 | 2017-11-06 | 2018-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-26 | 2019-08-26 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-12-01 | 2018-02-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 45 | 48 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.01.02 | Camera Body Development | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Martin Nordby |  |  |  | Procurement
FALSE |  | CRYO61182 | Prep for C_IRR - Integration Readiness Review - IR2 Configuration | LSST Forecast - B57 - B1 | 23 | 0 | 2017-11-13 | 2017-12-15 | 0 | 2017-11-13 | 2017-12-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-12-01 | 2018-01-18 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 23 | 22 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.02 | Refrigeration System - IR2 | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC)
FALSE |  | SR340875 | Backside Processing (Batch 20) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 31 | 0 | 2017-11-14 | 2017-11-27 | 0 | 2017-11-14 | 2017-11-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-12-01 | 2018-02-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 31 | 4 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR340895 | Backside Processing (Batch 21) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 31 | 0 | 2017-11-14 | 2017-11-27 | 0 | 2017-11-14 | 2017-11-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-12-01 | 2018-02-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 31 | 4 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | CCS121600 | Implement - Pre-Production - Configuration Database | LSST Forecast - B57 - B1 | 58 | 0 | 2017-11-15 | 2018-03-30 | 0 | 2017-11-15 | 2018-03-30 | 0 | 2019-06-01 | 2019-06-01 | 2020-02-18 | 2020-02-18 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-12-01 | 2018-03-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 58 | 82 |  | Complete | 100% | 420 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.06 | CCS Database | 420 | 420 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering | [7 empty] | CCS Core (TEC)
FALSE |  | CCS250015 | NEED: CCOB Narrow Beam light source (being delivered from France-- May 2016) | LSST Forecast - B57 - B1 | 0 | 0 | 2017-11-15 | 2017-11-15 | 0 | 2017-11-15 | 2017-11-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-12-15 | 2017-12-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.08.02 | BOT HCU | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  | Level 5 Milestone | Design/Engineering
FALSE |  | CRYO56190 | AWARD: P.O. - Heat Exchanger Cryo/Cold - Cryostat | LSST Forecast - B57 - B1 | 1 | 0 | 2017-11-17 | 2017-11-17 | 0 | 2017-11-17 | 2017-11-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 216504 | 216504 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-11-22 | 2017-11-22 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.04 | Refrigeration System - Pre IR2 (HX) | 0 | 0 | 0 | 216504 | 216504 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | B1 Procurement Commitment (C5.1) |  | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 20% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Refrigeration System (TEC)
FALSE |  | SR339325 | RCV: SLIN 3 Option 2 to Purchase 5 additional fall-out sensors from E2V for I&T | LSST Forecast - B57 - B1 | 10 | 0 | 2017-11-20 | 2017-11-30 | 0 | 2017-11-20 | 2017-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-14 | 2019-05-14 | 20000 | 20000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-12-01 | 2017-12-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 6 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 20000 | 20000 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC)
FALSE |  | CRYO25630 | Generate Manufacturing Docs - Sieve | LSST Forecast - B57 - B1 | 20 | 0 | 2017-11-22 | 2017-11-22 | 0 | 2017-11-22 | 2017-11-22 | 0 | 2019-06-01 | 2019-06-01 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-08-29 | 2018-09-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.02 | Getter Pumps | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  |  | Design/Engineering
FALSE |  | SR340915 | Backside Processing (Batch 22) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 30 | 0 | 2017-11-28 | 2017-12-15 | 0 | 2017-11-28 | 2017-12-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-12-01 | 2018-02-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 13 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | CRYO23850 | AVAIL: Ready for Integration - Grid Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2017-12-01 | 2017-12-01 | 0 | 2017-12-01 | 2017-12-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Finish Milestone | FALSE | 2018-01-12 | 2018-01-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.04 | Grid Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 5 Milestone | Fabrication/Assembly | [24 empty] | Clean Room at SLAC
FALSE |  | CRYO41250 | Check and Release Detail and Assembly Drawings Cryostat Vacuum Purge | LSST Forecast - B57 - B1 | 28 | 0 | 2017-12-01 | 2017-12-11 | 0 | 2017-12-01 | 2017-12-11 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-02-09 | 2018-03-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 28 | 6 |  | Complete | 100% | 76 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.03 | Vacuum Processing and Ground Support | 76 | 76 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Backend & Vacuum Systems (TEC) | [6 empty] | Vacuum Purge System
FALSE |  | CRYO41300 | Generate Manufacturing Docs | LSST Forecast - B57 - B1 | 21 | 0 | 2017-12-01 | 2017-12-11 | 0 | 2017-12-01 | 2017-12-11 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-05-16 | 2018-06-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 21 | 6 |  | Complete | 100% | 16 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.03 | Vacuum Processing and Ground Support | 16 | 16 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Backend & Vacuum Systems (TEC) | [6 empty] | Vacuum Purge System
FALSE |  | CRYO24900 | Finalize Analysis - Evaporable Getter Pumps | LSST Forecast - B57 - B1 | 80 | 0 | 2017-12-01 | 2018-01-31 | 0 | 2017-12-01 | 2018-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2018-01-02 | 2018-04-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 80 | 31 |  | Complete | 100% | 52 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.02 | Getter Pumps | 52 | 52 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Backend & Vacuum Systems (TEC) | [6 empty] | Cryostat Getter Pumps
FALSE |  | CRYO26700 | ETU Final Design, Document and Oversite - Sieve | LSST Forecast - B57 - B1 | 30 | 0 | 2017-12-01 | 2017-12-08 | 0 | 2017-12-01 | 2017-12-08 | 0 | 2019-06-01 | 2019-06-01 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-05-07 | 2018-06-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 5 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.02 | Getter Pumps | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Backend & Vacuum Systems (TEC) | [6 empty] | Cryostat Getter Pumps
FALSE |  | CRYO70140 | Procurement - Isolation Valve Assembly HW & Fixturing (IR2) - Cold and Cryo | LSST Forecast - B57 - B1 | 26 | 0 | 2017-12-01 | 2017-12-11 | 0 | 2017-12-01 | 2017-12-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 32000 | 32000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-01-02 | 2018-02-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 26 | 6 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.03 | Refrigeration System - Pre IR2 (Long Lines) | 0 | 0 | 0 | 32000 | 32000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | CRYO72020 | Detail Piece Parts & Assemblies - Valve & Filters/Desiccators - (Cmpr Cabinet Plumbing) - Chile System | LSST Forecast - B57 - B1 | 15 | 0 | 2017-12-01 | 2017-12-22 | 0 | 2017-12-01 | 2017-12-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-31 | 2019-10-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-01-02 | 2018-01-23 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 11 |  | Complete | 100% | 16 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.02 | Refrigeration System - Chile System (Compressor Cabinet) | 16 | 16 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC)
FALSE |  | ITC27030 | Installation - MF06 for Rafts | LSST Forecast - B57 - B1 | 16 | 0 | 2017-12-01 | 2017-12-22 | 0 | 2017-12-01 | 2017-12-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-01-02 | 2018-01-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 16 | 11 |  | Complete | 100% | 50 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.01.02 | Single Bay EO Tests | 50 | 50 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Verification Test Systems (TEC)
FALSE |  | SR344420 | Order electronics parts for populating - Replacement REB5 Boards | LSST Forecast - B57 - B1 | 20 | 0 | 2017-12-01 | 2017-12-25 | 0 | 2017-12-01 | 2017-12-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-01-02 | 2018-01-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 16 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly | [23 empty] | Science Raft System
FALSE |  | DAQ900535 | Kitting and Testing of DAQ System to support 2 rafts | LSST Forecast - B57 - B1 | 20 | 0 | 2017-12-01 | 2017-12-22 | 0 | 2017-12-01 | 2017-12-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-01-02 | 2018-01-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 11 |  | Complete | 100% | 8 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.13.03 | DAQ Version 2.0 | 8 | 8 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Testing/Integration | [7 empty] | DAQ Readout Systems (TEC)
FALSE |  | CRYO11195 | FY18 - Cryostat Lead Engineer - Cryostat | LSST Forecast - B57 - B1 | 200 | 0 | 2017-12-01 | 2018-09-28 | 0 | 2017-12-01 | 2018-09-28 | 0 | 2019-06-01 | 2019-06-01 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-01-02 | 2018-10-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 200 | 199 |  | Complete | 100% | 628 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.01 | Cryostat Integration & Management | 628 | 628 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Drtn |  | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Management/Administration |  | Construction Management | [5 empty] | Cryostat Integration & Management (TEC)
FALSE |  | CCS106500 | Sustaining engineering - CCS/OCS | LSST Forecast - B57 - B1 | 60 | 0 | 2017-12-01 | 2018-09-28 | 0 | 2017-12-01 | 2018-09-28 | 0 | 2019-06-01 | 2019-06-01 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-01-11 | 2018-04-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 199 |  | Complete | 100% | 452 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.04 | CCS/OCS Bridge | 452 | 452 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration | [7 empty] | CCS Core (TEC)
FALSE |  | CRYO70220 | Assemble & Test and Braze Hose Fittings - Cold and Cryo - IR2 | LSST Forecast - B57 - B1 | 38 | 0 | 2017-12-01 | 2018-01-26 | 0 | 2017-12-01 | 2018-01-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-12-01 | 2018-02-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 17 | 17 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 38 | 28 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.03 | Refrigeration System - Pre IR2 (Long Lines) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | SR340935 | Backside Processing (Batch 23) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 25 | 0 | 2017-12-04 | 2017-12-15 | 0 | 2017-12-04 | 2017-12-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-01-10 | 2018-02-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 9 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR340955 | Backside Processing (Batch 24) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 21 | 0 | 2017-12-04 | 2017-12-15 | 0 | 2017-12-04 | 2017-12-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-01-18 | 2018-02-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 21 | 9 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | CRYO26750 | ETU Procurement Preps and Fabrification - Sieve | LSST Forecast - B57 - B1 | 90 | 0 | 2017-12-11 | 2017-12-15 | 0 | 2017-12-11 | 2017-12-15 | 0 | 2019-06-01 | 2019-06-01 | 2020-10-29 | 2020-10-29 | 30950 | 30950 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-05-07 | 2018-09-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 90 | 4 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.02 | Getter Pumps | 0 | 0 | 0 | 30950 | 30950 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Engineering Test/Validation |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Cryostat Backend & Vacuum Systems (TEC) | [6 empty] | Cryostat Getter Pumps
FALSE |  | CRYO70105 | Design - Cold System Verification Test | LSST Forecast - B57 - B1 | 40 | 0 | 2017-12-11 | 2018-01-08 | 0 | 2017-12-11 | 2018-01-08 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-07 | 2019-05-07 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-01-02 | 2018-02-28 |  |  |  |  | 1 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 10 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 9 |  | Complete | 100% | 220 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.02 | Refrigeration System - IR2 | 220 | 220 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) | [6 empty] | Utility Trunk
FALSE |  | CRYO26800 | ETU Test and Validate - Sieve | LSST Forecast - B57 - B1 | 90 | 0 | 2017-12-18 | 2017-12-20 | 0 | 2017-12-18 | 2017-12-20 | 0 | 2019-06-01 | 2019-06-01 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-05-07 | 2018-09-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 90 | 2 |  | Complete | 100% | 396 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.02 | Getter Pumps | 396 | 396 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Engineering Test/Validation |  | Commissioning and Testing | [5 empty] | Cryostat Backend & Vacuum Systems (TEC) | [6 empty] | Cryostat Getter Pumps
FALSE |  | SR333320 | Fallout Sensors (ITL Phase A) | LSST Forecast - B57 - B1 | 20 | 0 | 2017-12-20 | 2017-12-30 | 0 | 2017-12-20 | 2017-12-30 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-01-02 | 2018-01-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 7 |  | Complete | 100% | 26 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 26 | 26 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Catalog Listing or Industrial Construction Databases | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [6 empty] | Science Sensors Acceptance | [6 empty] | Lot 3 Primary Vendor |  | Science Sensors
Merge Hotspot
The total number of activities with a high number of predecessor links.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | Previous Start | Previous Finish | Percent Complete | Previous Remaining Duration | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | IsLevelOfEffort | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | Global_Basis of Estimate | Global_Cobra Cost Class | Cobra PMT (EV Method)_Global | Global_Color of Money | Global_Control Account Manager | Global_Design Maturity | Global_Judgement Factor | Global_Milestone Levels | Global_Project Phase | Global_Funding Source | Global_EDIA Survey | Global_MS Type | Phase | NSF Milestones | Loading Curve | Sensor Vendor | LSST_CA | Summary Schedule | ICD for NSF Input | LSST Camera Critical Paths | CD2 Budget Changes | DOE Reviews | Critical Path (CD Reviews) | LSST WP Summary | Critical Path (Camera Delivery) | AWARD / NEED Sub-System | Final Design Key Links | CP - CAMM2100 | CP - CAMM2130 | CP - CAMM2160 | BNL Work Org | Last ETC Update | BNL WBS | LSST Story List | Sum Sch 01 (Camera) | Sum Sch 02 (IT w/Needs) | Sum Sch 03 (Sensors_RTM_IT) | LSST Raft Particulate Mitigation | LSST RTM
FALSE |  | OP522475 | Five Remaining Filters Complete and Ready to Ship (MS5) - Filter Fabrication | LSST Forecast - B57 - B1 | 444 | 92 | 2017-01-02 | 2019-10-10 | 163 | 2017-01-02 |  | 0 | 2019-06-03 | 2019-10-10 | 2020-01-28 | 2020-06-05 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-03-01 | 2018-11-30 |  |  |  |  | 0.73 | 0 | FALSE | FALSE | None |  | None |  | 2019-10-10 |  |  |  |  | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 444 | 607 |  | InProgress | 73% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  |  | Procurement
FALSE |  | SR333395 | Batch Sensor Testing (RTM #2) | LSST Forecast - B57 - B1 | 5 | 0 | 2017-01-03 | 2017-03-15 | 0 | 2017-01-03 | 2017-03-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-02-08 | 2017-02-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 0 | 0 | 0 | 5 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 49 |  | Complete | 100% | 156 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 156 | 156 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | CR241000 | Performance validation with single CCD - WEB EM | LSST Forecast - B57 - B1 | 30 | 0 | 2017-01-09 | 2017-02-24 | 0 | 2017-01-09 | 2017-02-24 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-02-27 | 2017-04-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 2 | 0 | 0 | 2 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 32 |  | Complete | 100% | 320 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.01 | Wavefront Electronics Board (WEB) | 320 | 320 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Testing/Integration | [7 empty] | Corner Raft Electronics (TEC) | WEB EM
FALSE |  | SR330170 | RCV: First Article Sensors - V1 (Sensor #6) | LSST Forecast - B57 - B1 | 17 | 0 | 2017-01-09 | 2017-01-27 | 0 | 2017-01-09 | 2017-01-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 122500 | 122500 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-02-01 | 2017-02-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 17 | 13 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 122500 | 122500 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 14% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC) | [5 empty] | Sensor | Science Sensors Procurement | [6 empty] | Sensors Vendor 1 |  | Science Sensors
FALSE |  | SR552560 | COMP: Design and Engineering Phase | LSST Forecast - B57 - B1 | 0 | 0 | 2017-01-10 | 2017-01-10 | 0 | 2017-01-10 | 2017-01-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2017-02-08 | 2017-02-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 9 | 0 | 9 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.02.01 | Science Raft Tower Module (SRTM) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Bill Wahl |  |  | Level 4 Milestone | Design/Engineering | [14 empty] | Science Raft - Test Stands | [6 empty] | Tower Module |  | Science Raft System
FALSE |  | SR529835 | AVAIL: TS8a for SLAC I&T | LSST Forecast - B57 - B1 | 0 | 0 | 2017-01-13 | 2017-01-13 | 0 | 2017-01-13 | 2017-01-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-02-13 | 2017-02-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 8 | 0 | 8 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.06 | RTM Electro-Optical Testing (TS8a) For SLAC | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% | Level 5 Milestone | Fabrication/Assembly | [14 empty] | Science Raft - Test Stands |  | Science Raft System |  |  |  |  | Test Stand 8a - Assembly & Commissioning |  | Science Raft System
FALSE |  | CRYO11706 | COMP: Station 1 Assy - Cryostat Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2017-01-17 | 2017-01-17 | 0 | 2017-01-17 | 2017-01-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | FALSE | 2017-03-01 | 2017-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Fabrication/Assembly
FALSE |  | CRYO11712 | COMP: Station 2 Assy - Cryostat Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2017-01-17 | 2017-01-17 | 0 | 2017-01-17 | 2017-01-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | FALSE | 2017-03-01 | 2017-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Fabrication/Assembly
FALSE |  | SR530460 | TS6 - Revise eTraveler | LSST Forecast - B57 - B1 | 14 | 0 | 2017-01-26 | 2017-01-31 | 0 | 2017-01-26 | 2017-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-03-01 | 2017-03-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 14 | 3 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.03 | RTM Assembly (TS6) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 6 - Procurement & Fabrication |  | Science Raft System
FALSE |  | CRYO117471 | COMP: Other Lift Devices/Equipment - Cryostat Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2017-01-31 | 2017-01-31 | 0 | 2017-01-31 | 2017-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2017-03-01 | 2017-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Fabrication/Assembly
FALSE |  | SR530950 | Prep for C_MRR-TS5 | LSST Forecast - B57 - B1 | 11 | 0 | 2017-02-01 | 2017-02-15 | 0 | 2017-02-01 | 2017-02-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-03-01 | 2017-03-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 4 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 11 | 10 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.02 | RSA & RTM Warm-Cold Metrology (TS5) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 5 - Assembly & Commissioning |  | Science Raft System
FALSE |  | SR529775 | Prep for C_MRR-TS8a | LSST Forecast - B57 - B1 | 11 | 0 | 2017-02-01 | 2017-02-15 | 0 | 2017-02-01 | 2017-02-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-03-01 | 2017-03-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 11 | 10 |  | Complete | 100% | 12 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.06 | RTM Electro-Optical Testing (TS8a) For SLAC | 12 | 12 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 8a - Reviews |  | Science Raft System
FALSE |  | SR330280 | RCV: Production Lot 1 Sensors - V1 (Sensor #21) | LSST Forecast - B57 - B1 | 5 | 0 | 2017-02-01 | 2017-03-31 | 0 | 2017-02-01 | 2017-03-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 97200 | 97200 | 0 | 0 | 0 | 5 | FALSE | Normal | FALSE | 2017-03-08 | 2017-03-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 1 | 0 | 0 | 5 | 0 | 2 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 41 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 97200 | 97200 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.00) Task/item is fully invoiced/completed | 14% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC) | [5 empty] | Sensor | Science Sensors Procurement | [6 empty] | Sensors Vendor 1 |  | Science Sensors
FALSE |  | CRYO11766 | Generate Assembly Drawings - Cryostat Assembly | LSST Forecast - B57 - B1 | 54 | 0 | 2017-02-01 | 2017-05-31 | 0 | 2017-02-01 | 2017-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-03-01 | 2017-05-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 54 | 85 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package |  | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 10% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Cryostat Housing & Assembly (TEC)
FALSE |  | SR531140 | Prep for C_MRR-TS7 | LSST Forecast - B57 - B1 | 11 | 0 | 2017-02-01 | 2017-02-15 | 0 | 2017-02-01 | 2017-02-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-02-01 | 2017-02-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 11 | 11 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.04 | RTM Cryostat Integration (TS7) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 7 - Assembly & Commissioning |  | Science Raft System
FALSE |  | SR550274 | RTM1_RTM Construction at TS6 | LSST Forecast - B57 - B1 | 19 | 0 | 2017-02-02 | 2017-03-06 | 0 | 2017-02-02 | 2017-03-06 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-03-07 | 2017-03-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 3 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 19 | 21 |  | Complete | 100% | 64 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 64 | 64 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #1 (First Article) |  | Science Raft System
FALSE |  | SR330840 | AWARD: Sensor Production Lot 2 (V1, 30 Sensors) | LSST Forecast - B57 - B1 | 1 | 0 | 2017-02-10 | 2017-02-10 | 0 | 2017-02-10 | 2017-02-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 3680056 | 3680056 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2017-03-01 | 2017-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 3680056 | 3680056 | 0 | PercentComplete | 4% | CP_Phys |  | B1 Procurement Commitment (C5.1) |  | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR515050 | C_MRR--TS4-8 | LSST Forecast - B57 - B1 | 2 | 0 | 2017-02-14 | 2017-02-15 | 0 | 2017-02-14 | 2017-02-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-03-14 | 2017-03-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 6 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 2 |  | Complete | 100% | 96 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05 | Science Raft Test Stands (Dev & Commissioning) | 96 | 96 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering | [7 empty] | Science Raft - Test Stands (TEC) | Test Stand Effort | [5 empty] | Science Raft - Test Stands | [6 empty] | Test Stands - Review |  | Science Raft System
FALSE |  | SR552810 | C_MRR--Assembly & Test Facility | LSST Forecast - B57 - B1 | 2 | 0 | 2017-02-14 | 2017-02-15 | 0 | 2017-02-14 | 2017-02-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-02-14 | 2017-02-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 2 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.07.01 | Cleanroom Development & Commissioning | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Assembly and Test Facility (TEC) | Test Stand Effort | [5 empty] | Science Raft - Assembly and Test Facility | [6 empty] | Test Stand - Reviews |  | Science Raft System
FALSE |  | SR343870 | Assemble at Vendor, Clean & Test REB5 Batch 1 at vendor (10 units - RTM 1-3) | LSST Forecast - B57 - B1 | 14 | 0 | 2017-02-14 | 2017-03-06 | 0 | 2017-02-14 | 2017-03-06 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2017-02-14 | 2017-03-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 4 | 0 | 0 | 1 | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 8 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 14 | 13 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation | [7 empty] | Science Raft Electronics (TEC) | [6 empty] | Science Raft Electronics | [6 empty] | Prodcution REB-5 Build |  | Science Raft System
FALSE |  | SR529990 | COMP: C_TRR - Test Stand 8 | LSST Forecast - B57 - B1 | 0 | 0 | 2017-02-15 | 2017-02-15 | 0 | 2017-02-15 | 2017-02-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-03-15 | 2017-03-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.05 | RTM Electro-Optical Testing (TS8) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% | Level 4 Milestone | Design/Engineering | [14 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 8 - Reviews |  | Science Raft System
FALSE |  | CCS200200 | AVAIL: CCS Suite 1 (+HCU) Available for I&T | LSST Forecast - B57 - B1 | 0 | 0 | 2017-02-16 | 2017-02-16 | 0 | 2017-02-16 | 2017-02-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2017-03-16 | 2017-03-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.08.01 | Single Bay HCU | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  | Level 5 Milestone | Design/Engineering
FALSE |  | SR531090 | AVAIL: Test Stand 6 - Ready for Production | LSST Forecast - B57 - B1 | 0 | 0 | 2017-02-17 | 2017-02-17 | 0 | 2017-02-17 | 2017-02-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2017-03-17 | 2017-03-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.03 | RTM Assembly (TS6) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% | Level 5 Milestone | Testing/Integration | [14 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 6 - Assembly & Commissioning |  | Science Raft System
FALSE |  | SR340055 | Cold Probe Wafers at ITL (Lot A) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 10 | 0 | 2017-02-20 | 2017-04-12 | 0 | 2017-02-20 | 2017-04-12 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-04-07 | 2017-04-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 36 |  | Complete | 100% | 768 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 768 | 768 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR550390 | RTM #3 (1st Article) - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 46 | 0 | 2017-02-21 | 2017-04-17 | 0 | 2017-02-21 | 2017-04-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-02-21 | 2017-04-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 3 | 1 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 20 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 46 | 39 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [5 empty] | Critical Path to CD-2 | Science Raft - Test Stands | [6 empty] | RTM #3 |  | Science Raft System
FALSE |  | SR552680 | NEED: Test Stand 6 Ready for Test Facility Installation | LSST Forecast - B57 - B1 | 0 | 0 | 2017-02-28 | 2017-02-28 | 0 | 2017-02-28 | 2017-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-03-27 | 2017-03-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.07.01 | Cleanroom Development & Commissioning | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% | Level 5 Milestone | Testing/Integration | [8 empty] | Test Stand Effort | [5 empty] | Science Raft - Assembly and Test Facility | [6 empty] | Test Stand 6 - Assembly & Commissioning |  | Science Raft System
FALSE |  | CRYO11718 | COMP: Off-Load Frame - Cryostat Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2017-02-28 | 2017-02-28 | 0 | 2017-02-28 | 2017-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2017-03-01 | 2017-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 4 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Fabrication/Assembly
FALSE |  | CRYO11736 | COMP: Grid Handling Fixture - Cryostat Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2017-02-28 | 2017-02-28 | 0 | 2017-02-28 | 2017-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2017-03-01 | 2017-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Fabrication/Assembly
FALSE |  | CRYO11742 | COMP: Test Fixtures - Cryostat Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2017-02-28 | 2017-02-28 | 0 | 2017-02-28 | 2017-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2017-03-01 | 2017-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Fabrication/Assembly
FALSE |  | CRYO11762 | COMP: Purge Box - Cryostat Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2017-02-28 | 2017-02-28 | 0 | 2017-02-28 | 2017-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2017-03-01 | 2017-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.02 | Cryostat Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Fabrication/Assembly
FALSE |  | CCS103800 | Sustained Engineering - Code management | LSST Forecast - B57 - B1 | 240 | 0 | 2017-03-01 | 2018-03-28 | 0 | 2017-03-01 | 2018-03-28 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-04-03 | 2018-03-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 240 | 262 |  | Complete | 100% | 60 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.01 | CCS Developer Tools | 60 | 60 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering | [7 empty] | CCS Core (TEC)
FALSE |  | SR531000 | Incorporate TS5 -MRR changes | LSST Forecast - B57 - B1 | 14 | 0 | 2017-03-01 | 2017-03-20 | 0 | 2017-03-01 | 2017-03-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-18 | 2019-09-18 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-04-03 | 2017-04-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 14 | 13 |  | Complete | 100% | 8 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.05.02 | RSA & RTM Warm-Cold Metrology (TS5) | 8 | 8 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft - Test Stands (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | Test Stand 5 - Assembly & Commissioning |  | Science Raft System
FALSE |  | CR241020 | WEB EM prototype to WEB workshop | LSST Forecast - B57 - B1 | 5 | 0 | 2017-03-06 | 2017-03-20 | 0 | 2017-03-06 | 2017-03-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2017-04-03 | 2017-04-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 10 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.01 | Wavefront Electronics Board (WEB) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Testing/Integration | [7 empty] | Corner Raft Electronics (TEC) | WEB
FALSE |  | SR340215 | Backside Processing (Batch 1) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 35 | 0 | 2017-03-06 | 2017-04-27 | 0 | 2017-03-06 | 2017-04-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-05-02 | 2017-06-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 0 | 4 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 35 | 38 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | OP531110 | L2 Initial TWE Test Complete - L1-L2 Assembly - Phase 4b | LSST Forecast - B57 - B1 | 22 | 0 | 2017-03-10 | 2017-03-31 | 0 | 2017-03-10 | 2017-03-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-03 | 2019-09-03 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-04-03 | 2017-05-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 22 | 15 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Scott Winters | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor | [5 empty] | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly) |  |  |  | L1-L2 Opto-Mechanics
FALSE |  | CRYO19800 | AWARD: P.O. - Off the Shelf Items - Cryo & Cold Plate | LSST Forecast - B57 - B1 | 0 | 0 | 2017-03-13 | 2017-03-13 | 0 | 2017-03-13 | 2017-03-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 243100 | 243100 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2017-04-17 | 2017-04-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.03 | Cryo and Cold Plates | 0 | 0 | 0 | 243100 | 243100 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | B1 Procurement Commitment (C5.1) |  | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 3% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Cryo and Cold Plates (TEC) | [6 empty] | Cryo and Cold Plates
FALSE |  | CR223160 | Perform Initial Verification of TS-8 with CCS and DAQ | LSST Forecast - B57 - B1 | 15 | 0 | 2017-03-13 | 2017-06-09 | 0 | 2017-03-13 | 2017-06-09 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-04-13 | 2017-05-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 6 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 63 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Procurement | [7 empty] | Corner Raft Tower Module (CRTM) (TEC)
FALSE |  | AE210160 | Fabricate Prototype brackets, enclosures, filters | LSST Forecast - B57 - B1 | 40 | 0 | 2017-03-14 | 2017-07-11 | 0 | 2017-03-14 | 2017-07-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-04-10 | 2017-06-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 83 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.02.01 | AC and DC Power Distribution | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Gunther Haller | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Engineering Test/Validation |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Aux Elec Components (TEC) | [6 empty] | Power Control Monitoring
FALSE |  | CCS123600 | AVAIL: Diagnostic Cluster for I&T | LSST Forecast - B57 - B1 | 0 | 0 | 2017-03-15 | 2017-03-15 | 0 | 2017-03-15 | 2017-03-15 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2017-04-11 | 2017-04-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 4 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.09 | CCS Diagnostic Cluster and Visualization | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  | Level 5 Milestone | Design/Engineering
FALSE |  | CR234485 | COMP: Production 2Kx4K Wavefront Sensor (Phase 2) | LSST Forecast - B57 - B1 | 0 | 0 | 2017-03-17 | 2017-03-17 | 0 | 2017-03-17 | 2017-03-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2017-05-03 | 2017-05-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.02 | Wavefront Sensor | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 4 Milestone | Design/Engineering
FALSE |  | CR242300 | GEB EM prototype to GEB workshop | LSST Forecast - B57 - B1 | 5 | 0 | 2017-03-20 | 2017-03-31 | 0 | 2017-03-20 | 2017-03-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2017-04-20 | 2017-04-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 9 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.02 | Guider Electronics Board (GEB) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Testing/Integration | [7 empty] | Corner Raft Electronics (TEC) | GEB
FALSE |  | SR550450 | RTM #4 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2017-03-21 | 2017-05-16 | 0 | 2017-03-21 | 2017-05-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-06-01 | 2017-07-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 3 | 2 | 0 | 1 | 2 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 40 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #4 |  | Science Raft System
FALSE |  | SR550510 | RTM #5 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2017-03-21 | 2017-07-07 | 0 | 2017-03-21 | 2017-07-07 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-04-26 | 2017-05-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 76 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #5 |  | Science Raft System
FALSE |  | SR550570 | RTM #6 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2017-03-21 | 2017-08-15 | 0 | 2017-03-21 | 2017-08-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2017-05-22 | 2017-06-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 1 | 0 | 2 | 3 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 103 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #6 |  | Science Raft System
FALSE |  | SR550630 | RTM #7 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2017-03-21 | 2017-08-11 | 0 | 2017-03-21 | 2017-08-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-07-10 | 2017-08-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 0 | 1 | 0 | 3 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 101 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #7 |  | Science Raft System
FALSE |  | SR550690 | RTM #8 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2017-03-21 | 2017-09-11 | 0 | 2017-03-21 | 2017-09-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-06-20 | 2017-07-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 0 | 1 | 0 | 3 | 2 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 121 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #8 |  | Science Raft System
FALSE |  | SR550750 | RTM #9 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2017-03-21 | 2017-10-13 | 0 | 2017-03-21 | 2017-10-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-09-13 | 2017-10-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 1 | 0 | 2 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 145 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #9 |  | Science Raft System
FALSE |  | SR550870 | RTM #11 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2017-03-21 | 2017-11-30 | 0 | 2017-03-21 | 2017-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-23 | 2019-07-23 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-10-25 | 2017-11-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 1 | 0 | 2 | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 177 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #11 |  | Science Raft System
FALSE |  | SR550930 | RTM #12 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2017-03-21 | 2018-01-23 | 0 | 2017-03-21 | 2018-01-23 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-23 | 2019-07-23 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-12-15 | 2018-01-23 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 1 | 0 | 2 | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 212 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #12 |  | Science Raft System
FALSE |  | SR550990 | RTM #13 - Parts Receive, Inspect, Clean, Document, Store & Kit | LSST Forecast - B57 - B1 | 25 | 0 | 2017-03-21 | 2018-02-13 | 0 | 2017-03-21 | 2018-02-13 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-12-13 | 2018-01-19 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 1 | 0 | 2 | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 227 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #13 |  | Science Raft System
FALSE |  | CRYO61075 | System Level Test - Cryo - B750 | LSST Forecast - B57 - B1 | 45 | 0 | 2017-03-24 | 2017-10-25 | 0 | 2017-03-24 | 2017-10-25 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-06-28 | 2017-08-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 45 | 150 |  | Complete | 100% | 200 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.01 | Refrigeration System - Pre IR2 (System Design & Integration) | 200 | 200 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | SR333405 | Batch Sensor Testing (RTM #3) | LSST Forecast - B57 - B1 | 15 | 0 | 2017-03-28 | 2017-04-14 | 0 | 2017-03-28 | 2017-04-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-04-28 | 2017-05-18 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 9 | 0 | 0 | 0 | 0 | 9 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 13 |  | Complete | 100% | 306 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 306 | 306 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | SR333415 | Batch Sensor Testing (RTM #4) | LSST Forecast - B57 - B1 | 5 | 0 | 2017-03-28 | 2017-04-20 | 0 | 2017-03-28 | 2017-04-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-04-28 | 2017-05-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 9 | 0 | 0 | 0 | 0 | 9 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 17 |  | Complete | 100% | 103 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 103 | 103 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | SR333425 | Batch Sensor Testing (RTM #5) | LSST Forecast - B57 - B1 | 5 | 0 | 2017-03-28 | 2017-04-25 | 0 | 2017-03-28 | 2017-04-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-04-18 | 2017-04-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 9 | 0 | 0 | 0 | 0 | 9 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 20 |  | Complete | 100% | 103 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 103 | 103 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | CR234520 | AVAIL: Wavefront Sensors | LSST Forecast - B57 - B1 | 0 | 0 | 2017-03-31 | 2017-03-31 | 0 | 2017-03-31 | 2017-03-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2017-05-31 | 2017-05-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.02 | Wavefront Sensor | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 5 Milestone | Fabrication/Assembly
FALSE |  | CBM47500 | Finalize Design - Shutter | LSST Forecast - B57 - B1 | 30 | 0 | 2017-04-01 | 2017-05-31 | 0 | 2017-04-01 | 2017-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-06 | 2019-08-06 | 0 | 0 | 0 | 0 | 0 | 6 | FALSE | Normal | FALSE | 2017-05-01 | 2017-06-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 0 | 0 | 1 | 6 | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 41 |  | Complete | 100% | 190 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.02.02 | Shutter Development | 190 | 190 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Shutter Development (TEC) | [6 empty] | Shutter Prod Sprt |  |  | Final Design Link
FALSE |  | DAQ900140 | Integrate DAQ V2.0 (TDS, PGP) | LSST Forecast - B57 - B1 | 5 | 0 | 2017-04-03 | 2017-04-21 | 0 | 2017-04-03 | 2017-04-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-07-03 | 2017-07-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 5 | 1 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 14 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.13.03 | DAQ Version 2.0 | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Engineering Test/Validation | [7 empty] | DAQ Readout Systems (TEC)
FALSE |  | SR550274_1 | RTM1_RTM Qualification at TS8 | LSST Forecast - B57 - B1 | 17 | 0 | 2017-04-03 | 2017-04-25 | 0 | 2017-04-03 | 2017-04-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-05-01 | 2017-05-23 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 17 | 16 |  | Complete | 100% | 139 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 139 | 139 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #1 (First Article) |  | Science Raft System
FALSE |  | SR343932 | Perform Mech. Assy/Tcycling/burnin-Test/Vac-Prep/RGA/ Prep for Ship at SLAC (10) REB5 boards | LSST Forecast - B57 - B1 | 35 | 0 | 2017-04-03 | 2017-04-28 | 0 | 2017-04-03 | 2017-04-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-05-01 | 2017-06-19 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 35 | 19 |  | Complete | 100% | 50 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 50 | 50 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | [11 empty] | Science Raft Electronics (TEC) | [13 empty] | Prodcution REB-5 Build |  | Science Raft System
FALSE |  | CRYO61088 | Install & Test Hx - Cold - B750 | LSST Forecast - B57 - B1 | 15 | 0 | 2017-04-03 | 2017-04-14 | 0 | 2017-04-03 | 2017-04-14 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-05-01 | 2017-05-19 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 9 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.01 | Refrigeration System - Pre IR2 (System Design & Integration) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | SR550334 | RTM2_RTM Construction at TS6 | LSST Forecast - B57 - B1 | 11 | 0 | 2017-04-06 | 2017-04-20 | 0 | 2017-04-06 | 2017-04-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-05-04 | 2017-05-18 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 11 | 10 |  | Complete | 100% | 64 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 64 | 64 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #2 |  | Science Raft System
FALSE |  | CRYO20550 | Inspect Parts - Cryo & Cold Plate | LSST Forecast - B57 - B1 | 20 | 0 | 2017-04-10 | 2017-07-28 | 0 | 2017-04-10 | 2017-07-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-07-05 | 2017-08-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 77 |  | Complete | 100% | 172 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.03 | Cryo and Cold Plates | 172 | 172 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 11% |  | Fabrication/Assembly |  | Other (specify) | [5 empty] | Cryo and Cold Plates (TEC) | [5 empty] | Critical Path to CD-2 | Cryo and Cold Plates
FALSE |  | CRYO23500 | Inspect Grid Assembly | LSST Forecast - B57 - B1 | 20 | 0 | 2017-04-10 | 2017-05-31 | 0 | 2017-04-10 | 2017-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-05-01 | 2017-05-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 10 | 0 | 10 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 36 |  | Complete | 100% | 179 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.04 | Grid Assembly | 179 | 179 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Fabrication/Assembly |  | Other (specify) | [5 empty] | Grid Assembly (TEC) | [6 empty] | Grid Assembly | [5 empty] | CP - CAMM2160 (Cryostat Assy Ready for Integration)
FALSE |  | ITC33440 | Verification Planning - Gantry | LSST Forecast - B57 - B1 | 10 | 0 | 2017-04-10 | 2017-10-26 | 0 | 2017-04-10 | 2017-10-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-05-30 | 2017-06-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 140 |  | Complete | 100% | 116 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.01 | Integration Gantry | 116 | 116 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2
FALSE |  | CRYO61210 | Prep for C_FDR - Refrigeration System - IR2 | LSST Forecast - B57 - B1 | 10 | 0 | 2017-04-14 | 2017-05-19 | 0 | 2017-04-14 | 2017-05-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-06-06 | 2017-06-19 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 7 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 5 | 5 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 25 |  | Complete | 100% | 320 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.01 | Refrigeration System - Pre IR2 (System Design & Integration) | 320 | 320 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) | [6 empty] | Refrigeration System
FALSE |  | ITC17760 | Preliminary Testing - SBMS | LSST Forecast - B57 - B1 | 20 | 0 | 2017-04-24 | 2017-06-16 | 0 | 2017-04-24 | 2017-06-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-05-22 | 2017-06-19 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 4 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 38 |  | Complete | 100% | 328 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.01.01 | Single Bay Metrology Tests | 328 | 328 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC)
FALSE |  | CRYO13950 | Prep for Manufacturing Readiness Review - Cryostat Housing | LSST Forecast - B57 - B1 | 10 | 0 | 2017-05-01 | 2017-05-04 | 0 | 2017-05-01 | 2017-05-04 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-06-01 | 2017-06-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 10 | 0 | 10 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 3 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.01 | Cryostat Housing | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  |  | Design/Engineering
FALSE |  | CRYO31380 | Procurement Process - Other items - Cryostat Back End | LSST Forecast - B57 - B1 | 20 | 0 | 2017-05-01 | 2017-05-12 | 0 | 2017-05-01 | 2017-05-12 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-06-01 | 2017-06-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 9 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.01 | Cryostat Back End | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  |  | Procurement
FALSE |  | DAQ341400 | Design - Production - RDS/RDC | LSST Forecast - B57 - B1 | 100 | 0 | 2017-05-01 | 2017-06-09 | 0 | 2017-05-01 | 2017-06-09 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-08-30 | 2018-02-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 100 | 28 |  | Complete | 100% | 96 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.09.02 | Raft Data Server/Client Software (RDS/RDC) | 96 | 96 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | DAQ Readout Systems (TEC) |  | ICD's for Phase 3 |  |  |  |  | DAQ Readout Systems
FALSE |  | CCS125000 | Develop use-case and specification for shutter prototype | LSST Forecast - B57 - B1 | 20 | 0 | 2017-05-01 | 2017-06-28 | 0 | 2017-05-01 | 2017-06-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-06 | 2019-08-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-06-01 | 2017-06-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 41 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.06 | Shutter HCU | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 11% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | CCS HCU (TEC) | [6 empty] | Camera I&T Hardware Control Unit
FALSE |  | OP540940 | L3 Assembly - Phase 3 (Flat Assy - Assembly) | LSST Forecast - B57 - B1 | 34 | 0 | 2017-05-01 | 2017-12-12 | 0 | 2017-05-01 | 2017-12-12 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-14 | 2019-05-14 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-06-01 | 2017-07-19 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 34 | 156 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor | [11 empty] | L1-L2 Opto-Mechanics
FALSE |  | CR222740 | Integrated EO testing with cold raft electronics with single CCD cold | LSST Forecast - B57 - B1 | 31 | 0 | 2017-05-01 | 2017-06-16 | 0 | 2017-05-01 | 2017-06-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-07-03 | 2017-08-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 31 | 33 |  | Complete | 100% | 160 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 160 | 160 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | [11 empty] | Corner Raft Tower Module (CRTM) (TEC)
FALSE |  | ITC33335 | Procurement Prep - Test Raft | LSST Forecast - B57 - B1 | 22 | 0 | 2017-05-01 | 2017-05-30 | 0 | 2017-05-01 | 2017-05-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-06-01 | 2017-06-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 10 | 10 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 22 | 20 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.02.02 | Pathfinder / Test Raft Program | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC)
FALSE |  | OP521805 | Sub-scale Sample Metrology and Coating Report (MS3) - Filter Development and Witness Sample | LSST Forecast - B57 - B1 | 42 | 0 | 2017-05-01 | 2017-08-18 | 0 | 2017-05-01 | 2017-08-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-12-12 | 2019-12-12 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-06-01 | 2017-07-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 42 | 77 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  |  | Procurement
FALSE |  | CRYO35236 | NEED: Camera subsystems HCU architecture/design/hardware designation - Cryo UT | LSST Forecast - B57 - B1 | 0 | 0 | 2017-05-03 | 2017-05-03 | 0 | 2017-05-03 | 2017-05-03 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-06-01 | 2017-06-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.05.02 | Utility Trunk Thermo-Mechanical and Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 5 Milestone | Design/Engineering
FALSE |  | CAMM6265 | AVAIL: Preliminary glycol budget | LSST Forecast - B57 - B1 | 0 | 0 | 2017-05-03 | 2017-05-03 | 0 | 2017-05-03 | 2017-05-03 | 0 | 2019-06-01 | 2019-06-01 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-06-01 | 2017-06-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.03 | NSF Interface Milestone (NSF Needs) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration
FALSE |  | CR223190 | Commission TS-8 at SLAC with ETU | LSST Forecast - B57 - B1 | 10 | 0 | 2017-05-15 | 2017-06-09 | 0 | 2017-05-15 | 2017-06-09 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-06-08 | 2017-06-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 18 |  | Complete | 100% | 340 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 340 | 340 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Procurement | [7 empty] | Corner Raft Tower Module (CRTM) (TEC)
FALSE |  | CBM47800 | Prep for C_FDR - Shutter | LSST Forecast - B57 - B1 | 10 | 0 | 2017-05-22 | 2017-06-19 | 0 | 2017-05-22 | 2017-06-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-06 | 2019-08-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-07-28 | 2017-08-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 5 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 19 |  | Complete | 100% | 100 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.02.02 | Shutter Development | 100 | 100 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Shutter Development (TEC) | [6 empty] | Shutter Prod Sprt
FALSE |  | CRYO61220 | C_FDR - Final Design Review - Refrigeration System - IR2 | LSST Forecast - B57 - B1 | 2 | 0 | 2017-05-22 | 2017-05-22 | 0 | 2017-05-22 | 2017-05-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2017-06-01 | 2017-06-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.01 | Refrigeration System - Pre IR2 (System Design & Integration) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Design Reviews | [5 empty] | Refrigeration System (TEC) | [6 empty] | Refrigeration System
FALSE |  | CRYO31500 | Integrate & Test Hardware - Cryostat Back End | LSST Forecast - B57 - B1 | 40 | 0 | 2017-05-22 | 2017-07-28 | 0 | 2017-05-22 | 2017-07-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-07-26 | 2017-09-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 47 |  | Complete | 100% | 748 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.01 | Cryostat Back End | 748 | 748 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly |  | Other (specify) | [5 empty] | Cryostat Backend & Vacuum Systems (TEC) | [6 empty] | Cryostat Back End
FALSE |  | SR333435 | Batch Sensor Testing (RTM #6) | LSST Forecast - B57 - B1 | 5 | 0 | 2017-05-22 | 2017-06-26 | 0 | 2017-05-22 | 2017-06-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-06-15 | 2017-06-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 9 | 0 | 2 | 0 | 0 | 7 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 24 |  | Complete | 100% | 103 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 103 | 103 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | SR344132 | Perform Mech. Assy/Tcycling/burnin-Test/Vac-Prep/RGA/ Prep for Ship at SLAC (25) REB5 boards | LSST Forecast - B57 - B1 | 48 | 0 | 2017-05-23 | 2017-09-11 | 0 | 2017-05-23 | 2017-09-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-23 | 2019-07-23 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-06-01 | 2017-08-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 48 | 76 |  | Complete | 100% | 100 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.03.03 | Raft Electronics Board (REB) | 100 | 100 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | [11 empty] | Science Raft Electronics (TEC) | [13 empty] | Prodcution REB-5 Build |  | Science Raft System
FALSE |  | CRYO31060 | Procurement Process - Pump Plate Vac Sys Subcomponents - Cryostat Back End | LSST Forecast - B57 - B1 | 15 | 0 | 2017-06-01 | 2017-06-09 | 0 | 2017-06-01 | 2017-06-09 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-07-17 | 2017-08-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 6 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.01 | Cryostat Back End | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  |  | Procurement
FALSE |  | CRYO84000 | Finalize Design - Cryostat Utility Trunk | LSST Forecast - B57 - B1 | 52 | 0 | 2017-06-01 | 2017-11-13 | 0 | 2017-06-01 | 2017-11-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-07-03 | 2017-09-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 13 | 0 | 13 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 52 | 115 |  | Complete | 100% | 533 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.05.02 | Utility Trunk Thermo-Mechanical and Assembly | 533 | 533 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Utility Trunk Thermo-Mechanical and Assembly (TEC) |  | ICD's for Phase 3 |  |  |  |  | Utility Trunk
FALSE |  | CCS126940 | COMP: CCS Core 4.5 Release | LSST Forecast - B57 - B1 | 0 | 0 | 2017-06-06 | 2017-06-06 | 0 | 2017-06-06 | 2017-06-06 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-31 | 2019-05-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-07-07 | 2017-07-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.02.06 | CCS Core 5.0 Release (Support Lock Manager) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  | Level 4 Milestone | Design/Engineering
FALSE |  | DAQ900525 | COMP: DAQ V2.0 | LSST Forecast - B57 - B1 | 0 | 0 | 2017-06-09 | 2017-06-09 | 0 | 2017-06-09 | 2017-06-09 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | FALSE | 2017-08-09 | 2017-08-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.13.03 | DAQ Version 2.0 | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer |  |  | Level 4 Milestone | Testing/Integration
FALSE |  | CRYO53270 | COMP: Oil Reservoirs to Compressors (6 Units) - B750 | LSST Forecast - B57 - B1 | 0 | 0 | 2017-06-16 | 2017-06-16 | 0 | 2017-06-16 | 2017-06-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-07-03 | 2017-07-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 3 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.01 | Refrigeration System - Pre IR2 (System Design & Integration) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Engineering Test/Validation
FALSE |  | ITC13010 | AVAIL: I&T Facility Equipment Ready for Clean Room | LSST Forecast - B57 - B1 | 0 | 0 | 2017-06-23 | 2017-06-23 | 0 | 2017-06-23 | 2017-06-23 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2017-07-21 | 2017-07-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.03 | IR2 Facility and Operations | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | CAMF660200 | MRR - Manufacturing Readiness Review - Auto Changer | LSST Forecast - B57 - B1 | 3 | 0 | 2017-06-27 | 2017-06-29 | 0 | 2017-06-27 | 2017-06-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-07-25 | 2017-07-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 3 | 2 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.01 | Auto Changer | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Design/Engineering
FALSE |  | CAMF664000 | MRR - Manufacturing Readiness Review - Filter Loader | LSST Forecast - B57 - B1 | 3 | 0 | 2017-06-27 | 2017-06-29 | 0 | 2017-06-27 | 2017-06-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-07-25 | 2017-07-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 3 | 2 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.02 | Filter Loader | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Design/Engineering
FALSE |  | CAMF667650 | COMP: Final Design & Assembly Drawings - Carousel | LSST Forecast - B57 - B1 | 0 | 0 | 2017-07-03 | 2017-07-03 | 0 | 2017-07-03 | 2017-07-03 | 0 | 2019-06-01 | 2019-06-01 | 2018-10-16 | 2018-10-16 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-08-01 | 2017-08-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  | Level 4 Milestone | Design/Engineering
FALSE |  | CRYO15300 | Assemble Cryostat Housing | LSST Forecast - B57 - B1 | 78 | 0 | 2017-07-03 | 2017-12-11 | 0 | 2017-07-03 | 2017-12-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-08-01 | 2017-11-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 78 | 111 |  | Complete | 100% | 60 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.01 | Cryostat Housing | 60 | 60 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Fabrication/Assembly |  | Other (specify) | [5 empty] | Cryostat Housing & Assembly (TEC) | [6 empty] | Cryostat Housing
FALSE |  | SR550150 | SHIPPING: Ship RTM ETU #2 to SLAC | LSST Forecast - B57 - B1 | 4 | 0 | 2017-07-03 | 2017-07-07 | 0 | 2017-07-03 | 2017-07-07 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-08-01 | 2017-08-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 3 |  | Complete | 100% | 8 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 8 | 8 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration |  | Other (specify) | [5 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM ETU #2 |  | Science Raft System
FALSE |  | SR550274_2 | RTM1_RTM Qualification at TS5 | LSST Forecast - B57 - B1 | 19 | 0 | 2017-07-03 | 2017-07-28 | 0 | 2017-07-03 | 2017-07-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-18 | 2019-09-18 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-08-01 | 2017-08-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 19 | 18 |  | Complete | 100% | 45 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 45 | 45 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #1 (First Article) |  | Science Raft System
FALSE |  | ITC30580 | Perform Engineering RTM Receiving Test #2 | LSST Forecast - B57 - B1 | 25 | 0 | 2017-07-10 | 2017-09-15 | 0 | 2017-07-10 | 2017-09-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-08-07 | 2017-09-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 4 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 48 |  | Complete | 100% | 330 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.03 | Raft Acceptance Testing | 330 | 330 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [6 empty] | Cryostat I&T
FALSE |  | SR330840_5 | Vendor Lead Time - Backthinning Completion - V1 Prod Lot 2 (30 Sensors) | LSST Forecast - B57 - B1 | 107 | 0 | 2017-07-10 | 2017-11-10 | 0 | 2017-07-10 | 2017-11-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 10 | FALSE | Normal | FALSE | 2017-08-01 | 2018-01-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 4 | 1 | 0 | 0 | 10 | 0 | 1 | 8 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 107 | 88 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  |  | Procurement | [23 empty] | Science Sensors
FALSE |  | CBM46400 | Recv, Prep, Assemble (Shutter Proto) | LSST Forecast - B57 - B1 | 40 | 0 | 2017-07-14 | 2018-07-31 | 0 | 2017-07-14 | 2018-07-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-06 | 2019-08-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-09-18 | 2017-11-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 254 |  | Complete | 100% | 641 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.02.02 | Shutter Development | 641 | 641 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 5% |  | Engineering Test/Validation |  | Commissioning and Testing | [5 empty] | Shutter Development (TEC) | [6 empty] | Shutter Prototype
FALSE |  | CRYO35075 | COMP: Preliminary Design/Analysis - Cryostat Utility Trunk | LSST Forecast - B57 - B1 | 0 | 0 | 2017-07-18 | 2017-07-18 | 0 | 2017-07-18 | 2017-07-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-08-01 | 2017-08-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 4 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.05.02 | Utility Trunk Thermo-Mechanical and Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Design/Engineering
FALSE |  | SR333445 | Batch Sensor Testing (RTM #7) | LSST Forecast - B57 - B1 | 5 | 0 | 2017-07-25 | 2017-07-31 | 0 | 2017-07-25 | 2017-07-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-08-28 | 2017-09-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 9 | 0 | 9 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 4 |  | Complete | 100% | 83 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 83 | 83 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | SR333455 | Batch Sensor Testing (RTM #8) | LSST Forecast - B57 - B1 | 5 | 0 | 2017-07-28 | 2017-08-18 | 0 | 2017-07-28 | 2017-08-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-08-28 | 2017-09-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 15 |  | Complete | 100% | 103 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 103 | 103 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | SR550574 | RTM6_RTM Construction at TS6 | LSST Forecast - B57 - B1 | 15 | 0 | 2017-08-01 | 2017-08-21 | 0 | 2017-08-01 | 2017-08-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-09-01 | 2017-09-22 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 14 |  | Complete | 100% | 64 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 64 | 64 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #6 |  | Science Raft System
FALSE |  | CR222930 | Assemble the ComCam TS-7 Dewar | LSST Forecast - B57 - B1 | 15 | 0 | 2017-08-08 | 2017-08-25 | 0 | 2017-08-08 | 2017-08-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-16 | 2019-05-16 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-09-01 | 2017-09-22 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 3 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 13 |  | Complete | 100% | 100 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 100 | 100 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Procurement | [7 empty] | Corner Raft Tower Module (CRTM) (TEC)
FALSE |  | CR230900 | CRSA warm-cold metrology - practice CRSA metrology with fixtures | LSST Forecast - B57 - B1 | 15 | 0 | 2017-08-14 | 2017-12-15 | 0 | 2017-08-14 | 2017-12-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-09-18 | 2017-10-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 7 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 86 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.45) Task/item is a conceptual design and/or advances the state of the art | 0% |  | Testing/Integration |  | Other (specify) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Integration (Baseplate, thermal straps) | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CR223025 | AVAIL: Corner Raft TS-7 for I&T | LSST Forecast - B57 - B1 | 0 | 0 | 2017-08-18 | 2017-08-18 | 0 | 2017-08-18 | 2017-08-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-09-21 | 2017-09-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | SR330845_2 | RCV: 2nd Set Sensor Delivery - V1 Prod Lot 2 (Sensor 72) | LSST Forecast - B57 - B1 | 21 | 0 | 2017-08-21 | 2017-10-13 | 0 | 2017-08-21 | 2017-10-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 61335.6 | 61335.6 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2017-09-01 | 2017-10-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 0 | 7 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 21 | 38 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 61335.6 | 61335.6 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR333465 | Batch Sensor Testing (RTM #9) | LSST Forecast - B57 - B1 | 5 | 0 | 2017-08-21 | 2017-08-31 | 0 | 2017-08-21 | 2017-08-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2017-10-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 8 | 0 | 8 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 8 |  | Complete | 100% | 83 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 83 | 83 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | CRYO71120 | Prep for C_FDR - Chile System | LSST Forecast - B57 - B1 | 28 | 0 | 2017-08-21 | 2017-10-31 | 0 | 2017-08-21 | 2017-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-17 | 2019-06-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2017-11-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 3 | 3 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 28 | 50 |  | Complete | 100% | 140 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.01 | Refrigeration System - Chile System (System Design & Integration) | 140 | 140 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC)
FALSE |  | SR340395 | Backside Processing (Batch 10) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 25 | 0 | 2017-09-01 | 2017-09-15 | 0 | 2017-09-01 | 2017-09-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-10-02 | 2017-11-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 9 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR340415 | Backside Processing (Batch 11) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 27 | 0 | 2017-09-01 | 2017-09-15 | 0 | 2017-09-01 | 2017-09-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-10-05 | 2017-11-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 27 | 9 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | DAQ342900 | Update Documentation - Pre-Production - FES | LSST Forecast - B57 - B1 | 15 | 0 | 2017-09-04 | 2017-09-29 | 0 | 2017-09-04 | 2017-09-29 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2017-10-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 18 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.11 | FPA Emulation Server Software (FES) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Testing/Integration |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | DAQ Readout Systems (TEC) |  | ICD's for Phase 3 |  |  |  |  | DAQ Readout Systems
FALSE |  | CAMF660600 | Requisition - Other Items - Auto Changer | LSST Forecast - B57 - B1 | 5 | 0 | 2017-09-05 | 2018-07-02 | 0 | 2017-09-05 | 2018-07-02 | 0 | 2019-06-01 | 2019-06-01 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2017-10-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 198 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.01 | Auto Changer | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Procurement
FALSE |  | CRYO32300 | Prep for Prelim Design Review - Cryostat Vacuum Purge | LSST Forecast - B57 - B1 | 5 | 0 | 2017-09-05 | 2017-09-11 | 0 | 2017-09-05 | 2017-09-11 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-02 | 2017-10-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 4 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.03 | Vacuum Processing and Ground Support | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Cryostat Utillities
FALSE |  | CR241300 | WEB Assembly of PCB Boards (8 Units) | LSST Forecast - B57 - B1 | 25 | 0 | 2017-09-11 | 2017-12-20 | 0 | 2017-09-11 | 2017-12-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-10-02 | 2017-11-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 68 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.01 | Wavefront Electronics Board (WEB) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Fabrication/Assembly | [7 empty] | Corner Raft Electronics (TEC) | WEB
FALSE |  | CR241320 | Additional custom software and engineering support for WEB screening | LSST Forecast - B57 - B1 | 40 | 0 | 2017-09-11 | 2018-01-19 | 0 | 2017-09-11 | 2018-01-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-11-06 | 2018-01-18 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 2 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 80 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.01 | Wavefront Electronics Board (WEB) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Testing/Integration | [7 empty] | Corner Raft Electronics (TEC) | WEB
FALSE |  | CR242580 | GEB Assembly of PCB Boards (8 Units) | LSST Forecast - B57 - B1 | 20 | 0 | 2017-09-11 | 2017-12-22 | 0 | 2017-09-11 | 2017-12-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-10-30 | 2017-11-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 68 |  | Complete | 100% | 125 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.02 | Guider Electronics Board (GEB) | 125 | 125 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Fabrication/Assembly | [7 empty] | Corner Raft Electronics (TEC) | GEB
FALSE |  | SR550515 | RTM5_RTM Qualification at TS8 | LSST Forecast - B57 - B1 | 15 | 0 | 2017-09-11 | 2017-10-06 | 0 | 2017-09-11 | 2017-10-06 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-10-02 | 2017-10-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 19 |  | Complete | 100% | 139 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 139 | 139 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [5 empty] | Critical Path to CD-2 | Science Raft - Test Stands | [6 empty] | RTM #5 |  | Science Raft System
FALSE |  | ITC30612 | C_IRR- Raft Acceptance Testing | LSST Forecast - B57 - B1 | 1 | 0 | 2017-09-18 | 2017-09-18 | 0 | 2017-09-18 | 2017-09-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-10-16 | 2017-10-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 64 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.03 | Raft Acceptance Testing | 64 | 64 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Other (specify) | [5 empty] | Cryostat I&T (TEC)
FALSE |  | SR340455 | Backside Processing (Batch 13) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 21 | 0 | 2017-09-18 | 2017-10-30 | 0 | 2017-09-18 | 2017-10-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-10-30 | 2017-12-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 21 | 30 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR554120 | Testing of all Flex Cables | LSST Forecast - B57 - B1 | 15 | 0 | 2017-09-25 | 2018-04-25 | 0 | 2017-09-25 | 2018-04-25 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-11-10 | 2017-12-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 137 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Existing Lien | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.00) Task/item is fully invoiced/completed | 14% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | DAQ330000 | COMP: Prototype - SSD-RTM | LSST Forecast - B57 - B1 | 0 | 0 | 2017-09-29 | 2017-09-29 | 0 | 2017-09-29 | 2017-09-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-25 | 2019-07-25 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-12-08 | 2017-12-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.05 | SSD-RTM (Rear Transistion Module, incl Drives) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer |  |  | Level 4 Milestone | Engineering Test/Validation | [9 empty] | ICD's for Phase 3
FALSE |  | CR221420 | COMP: Corner raft tower tooling | LSST Forecast - B57 - B1 | 0 | 0 | 2017-09-29 | 2017-09-29 | 0 | 2017-09-29 | 2017-09-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-10-04 | 2017-10-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% | Level 4 Milestone | Fabrication/Assembly | [8 empty] | CRTM Fab/assy Tooling/shipping
FALSE |  | DAQ338460 | COMP: Production - Timing Distribution System | LSST Forecast - B57 - B1 | 0 | 0 | 2017-09-29 | 2017-09-29 | 0 | 2017-09-29 | 2017-09-29 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-10-31 | 2017-10-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 6 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.10 | Timing Distribution Server Hardware&Software (TDS) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer |  |  | Level 4 Milestone | Testing/Integration
FALSE |  | CRYO32550 | Prep for C_FDR - Cryostat Vacuum Purge | LSST Forecast - B57 - B1 | 5 | 0 | 2017-10-02 | 2017-10-13 | 0 | 2017-10-02 | 2017-10-13 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-11-01 | 2017-11-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 9 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.03 | Vacuum Processing and Ground Support | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Cryostat Utillities
FALSE |  | OP522180 | Prepare procurement for Filter First Article coating option | LSST Forecast - B57 - B1 | 20 | 0 | 2017-10-02 | 2017-10-11 | 0 | 2017-10-02 | 2017-10-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-25 | 2019-07-25 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-29 | 2018-04-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 7 |  | Complete | 100% | 56 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 56 | 56 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 18% |  | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Filters (TEC) | First Article Coating | [5 empty] | Filter Optics
FALSE |  | SR333475 | Batch Sensor Testing (RTM #10) | LSST Forecast - B57 - B1 | 10 | 0 | 2017-10-02 | 2017-10-13 | 0 | 2017-10-02 | 2017-10-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-11-01 | 2017-11-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 83 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 83 | 83 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | DAQ342400 | Generate Documentation - Prototype - FES | LSST Forecast - B57 - B1 | 10 | 0 | 2017-10-03 | 2017-10-13 | 0 | 2017-10-03 | 2017-10-13 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-11-01 | 2017-11-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 8 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.11 | FPA Emulation Server Software (FES) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | DAQ Readout Systems (TEC) |  | ICD's for Phase 3 |  |  |  |  | DAQ Readout Systems
FALSE |  | SR550516 | RTM5_RTM Qualification at TS5 | LSST Forecast - B57 - B1 | 5 | 0 | 2017-10-09 | 2017-10-16 | 0 | 2017-10-09 | 2017-10-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-11-08 | 2017-11-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 5 |  | Complete | 100% | 45 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 45 | 45 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #5 |  | Science Raft System
FALSE |  | ITC25840 | RCV: Outside Fabrication Procurement - BOT | LSST Forecast - B57 - B1 | 4 | 0 | 2017-10-10 | 2017-10-13 | 0 | 2017-10-10 | 2017-10-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 12097 | 12097 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-11-01 | 2017-11-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 3 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.02.01 | Bench For Optical Testing (BOT) | 0 | 0 | 0 | 12097 | 12097 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC)
FALSE |  | SR333485 | Batch Sensor Testing (RTM #11) | LSST Forecast - B57 - B1 | 10 | 0 | 2017-10-16 | 2017-11-30 | 0 | 2017-10-16 | 2017-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-11-01 | 2017-11-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 31 |  | Complete | 100% | 83 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 83 | 83 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | SR333605 | Batch Sensor Testing (CRRTM) | LSST Forecast - B57 - B1 | 20 | 0 | 2017-10-16 | 2017-10-31 | 0 | 2017-10-16 | 2017-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-11-01 | 2017-11-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 9 | 0 | 9 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 11 |  | Complete | 100% | 204 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 204 | 204 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | ITC25870 | Initial Integration - BOT | LSST Forecast - B57 - B1 | 2 | 0 | 2017-10-17 | 2017-12-15 | 0 | 2017-10-17 | 2017-12-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-11-21 | 2017-11-22 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 5 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 41 |  | Complete | 100% | 912 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.02.01 | Bench For Optical Testing (BOT) | 912 | 912 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC)
FALSE |  | DAQ341700 | Update Documentation - Production - RDS/RDC | LSST Forecast - B57 - B1 | 40 | 0 | 2017-10-23 | 2017-10-31 | 0 | 2017-10-23 | 2017-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-12 | 2018-05-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 6 |  | Complete | 100% | 20 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.09.02 | Raft Data Server/Client Software (RDS/RDC) | 20 | 20 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Testing/Integration |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | DAQ Readout Systems (TEC) |  | ICD's for Phase 3 |  |  |  |  | DAQ Readout Systems
FALSE |  | DAQ361400 | Update Documentation - Production - IMS/IMC | LSST Forecast - B57 - B1 | 40 | 0 | 2017-10-23 | 2017-10-31 | 0 | 2017-10-23 | 2017-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-12 | 2018-05-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 6 |  | Complete | 100% | 20 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.09.01 | Image Management/Server/Client Software | 20 | 20 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Testing/Integration |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | DAQ Readout Systems (TEC)
FALSE |  | CAMF668450 | RCV: other items - Carousel | LSST Forecast - B57 - B1 | 99 | 0 | 2017-10-23 | 2019-05-20 | 0 | 2017-10-23 | 2019-05-20 | 0 | 2019-06-01 | 2019-06-01 | 2018-10-16 | 2018-10-16 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-10-23 | 2018-03-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 99 | 378 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Procurement
FALSE |  | ITC25880 | Preliminary Testing - BOT | LSST Forecast - B57 - B1 | 42 | 0 | 2017-10-25 | 2017-12-15 | 0 | 2017-10-25 | 2017-12-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2017-11-27 | 2018-02-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 4 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 42 | 35 |  | Complete | 100% | 352 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.02.01 | Bench For Optical Testing (BOT) | 352 | 352 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC)
FALSE |  | CBM26200 | Prep for Manufacturing Readiness Review - Camera Body | LSST Forecast - B57 - B1 | 11 | 0 | 2017-11-01 | 2017-11-16 | 0 | 2017-11-01 | 2017-11-16 | 0 | 2019-06-01 | 2019-06-01 | 2018-09-07 | 2018-09-07 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-12-01 | 2017-12-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 11 | 11 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.01.02 | Camera Body Development | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 15% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Camera Body Development (TEC) | [6 empty] | Cam Body/Purge Prod Sprt
FALSE |  | CCS310800 | Test Integration Gantry Proof of Concept Subsystem - Gantry HCU | LSST Forecast - B57 - B1 | 4 | 0 | 2017-11-01 | 2017-11-06 | 0 | 2017-11-01 | 2017-11-06 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-12-01 | 2017-12-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 3 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.08.04 | Gantry HCU | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Design Support (i.e, soil testing, vibration testing, seismic analysis, etc needed for design) | [5 empty] | CCS HCU (TEC) | [5 empty] | Critical Path to CD-2
FALSE |  | SR340555 | Backside Processing (Batch 18) - Sensor Prod Lot 2 - V2 Phase A | LSST Forecast - B57 - B1 | 25 | 0 | 2017-11-01 | 2017-11-17 | 0 | 2017-11-01 | 2017-11-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-12-01 | 2018-01-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 12 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | CRYO71160 | COMP: C_FDR - Chile System | LSST Forecast - B57 - B1 | 0 | 0 | 2017-11-03 | 2017-11-03 | 0 | 2017-11-03 | 2017-11-03 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-17 | 2019-06-17 | 0 | 0 | 0 | 0 | 0 | 16 | FALSE | Finish Milestone | FALSE | 2017-12-04 | 2017-12-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 16 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 17 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.01 | Refrigeration System - Chile System (System Design & Integration) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Alice Callen |  |  | Level 4 Milestone | Design/Engineering
FALSE |  | CRYO84250 | COMP: Final Design/Analysis - Cryostat Utility Trunk | LSST Forecast - B57 - B1 | 0 | 0 | 2017-11-13 | 2017-11-13 | 0 | 2017-11-13 | 2017-11-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-12-13 | 2017-12-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.05.02 | Utility Trunk Thermo-Mechanical and Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Design/Engineering
FALSE |  | CRYO84600 | Incorporate C_FDR - Changes - Cryostat Utilities Trunk | LSST Forecast - B57 - B1 | 20 | 0 | 2017-11-15 | 2017-12-15 | 0 | 2017-11-15 | 2017-12-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2018-02-21 | 2018-03-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 20 |  | Complete | 100% | 94 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.05.02 | Utility Trunk Thermo-Mechanical and Assembly | 94 | 94 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Utility Trunk Thermo-Mechanical and Assembly (TEC) | [6 empty] | Utility Trunk
FALSE |  | SR333495 | Batch Sensor Testing (RTM #12) | LSST Forecast - B57 - B1 | 20 | 0 | 2017-11-15 | 2017-12-11 | 0 | 2017-11-15 | 2017-12-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-12-01 | 2017-12-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 16 |  | Complete | 100% | 83 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 83 | 83 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | ITC30640 | Perform Science RTM Receiving Test #1 | LSST Forecast - B57 - B1 | 13 | 0 | 2017-11-17 | 2018-01-12 | 0 | 2017-11-17 | 2018-01-12 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2017-12-01 | 2018-01-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 13 | 27 |  | Complete | 100% | 165 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.03 | Raft Acceptance Testing | 165 | 165 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | Raft Delivery to SLAC
FALSE |  | SR340735 | COMP: Production Lot 2 Phase A Complete | LSST Forecast - B57 - B1 | 0 | 0 | 2017-11-17 | 2017-11-17 | 0 | 2017-11-17 | 2017-11-17 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2017-12-01 | 2017-12-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 12 | 0 | 12 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% | Level 4 Milestone | Procurement |  |  | Subcontractor | [20 empty] | Science Sensors
FALSE |  | CRYO56190 | AWARD: P.O. - Heat Exchanger Cryo/Cold - Cryostat | LSST Forecast - B57 - B1 | 1 | 0 | 2017-11-17 | 2017-11-17 | 0 | 2017-11-17 | 2017-11-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 216504 | 216504 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2017-11-22 | 2017-11-22 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.04 | Refrigeration System - Pre IR2 (HX) | 0 | 0 | 0 | 216504 | 216504 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | B1 Procurement Commitment (C5.1) |  | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 20% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Refrigeration System (TEC)
FALSE |  | CRYO25630 | Generate Manufacturing Docs - Sieve | LSST Forecast - B57 - B1 | 20 | 0 | 2017-11-22 | 2017-11-22 | 0 | 2017-11-22 | 2017-11-22 | 0 | 2019-06-01 | 2019-06-01 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-08-29 | 2018-09-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.02 | Getter Pumps | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  |  | Design/Engineering
FALSE |  | CRYO23850 | AVAIL: Ready for Integration - Grid Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2017-12-01 | 2017-12-01 | 0 | 2017-12-01 | 2017-12-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Finish Milestone | FALSE | 2018-01-12 | 2018-01-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.04 | Grid Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 5 Milestone | Fabrication/Assembly | [24 empty] | Clean Room at SLAC
FALSE |  | CRYO33850 | Requisition - Rough and Purge Sys - Cryostat Vacuum Purge | LSST Forecast - B57 - B1 | 20 | 0 | 2017-12-01 | 2017-12-01 | 0 | 2017-12-01 | 2017-12-01 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-01-02 | 2018-01-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.03 | Vacuum Processing and Ground Support | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  |  | Procurement
FALSE |  | DAQ307500 | Procurement Process - Production Parts OTM and Cabling | LSST Forecast - B57 - B1 | 5 | 0 | 2017-12-01 | 2018-01-26 | 0 | 2017-12-01 | 2018-01-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-01-02 | 2018-01-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 28 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.01 | Optical Transition Module (OTM) and Cabling | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [7 empty] | ICD's for Phase 3 |  |  |  |  | DAQ Readout Systems
FALSE |  | ITC33580 | Preliminary Testing - Gantry | LSST Forecast - B57 - B1 | 11 | 0 | 2017-12-01 | 2018-03-16 | 0 | 2017-12-01 | 2018-03-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2018-02-13 | 2018-02-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 2 | 0 | 0 | 2 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 4 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 11 | 62 |  | Complete | 100% | 176 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.01 | Integration Gantry | 176 | 176 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2
FALSE |  | DAQ900535 | Kitting and Testing of DAQ System to support 2 rafts | LSST Forecast - B57 - B1 | 20 | 0 | 2017-12-01 | 2017-12-22 | 0 | 2017-12-01 | 2017-12-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-01-02 | 2018-01-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 11 |  | Complete | 100% | 8 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.13.03 | DAQ Version 2.0 | 8 | 8 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Testing/Integration | [7 empty] | DAQ Readout Systems (TEC)
FALSE |  | SR340935 | Backside Processing (Batch 23) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 25 | 0 | 2017-12-04 | 2017-12-15 | 0 | 2017-12-04 | 2017-12-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-01-10 | 2018-02-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 9 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | CRYO25660 | COMP: Design and Documentation - Sieve | LSST Forecast - B57 - B1 | 0 | 0 | 2017-12-20 | 2017-12-20 | 0 | 2017-12-20 | 2017-12-20 | 0 | 2019-06-01 | 2019-06-01 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2018-01-02 | 2018-01-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.02 | Getter Pumps | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Design/Engineering

## 2018 Details
Fuse® Analyst Report
Workbook: Workbook1 - 8168 Activities
Schedule Quality
Created on: 8/5/2019
Created by: brackett
2018: Detailed View | 2018: Detailed View | 2018: Detailed View | 2018: Detailed View
Critical
Number of critical activities
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | Previous Start | Previous Finish | Percent Complete | Previous Remaining Duration | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | IsLevelOfEffort | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | Global_Basis of Estimate | Global_Cobra Cost Class | Cobra PMT (EV Method)_Global | Global_Color of Money | Global_Control Account Manager | Global_Design Maturity | Global_Judgement Factor | Global_Milestone Levels | Global_Project Phase | Global_Funding Source | Global_EDIA Survey | Global_MS Type | Phase | NSF Milestones | Loading Curve | Sensor Vendor | LSST_CA | Summary Schedule | ICD for NSF Input | LSST Camera Critical Paths | CD2 Budget Changes | DOE Reviews | Critical Path (CD Reviews) | LSST WP Summary | Critical Path (Camera Delivery) | AWARD / NEED Sub-System | Final Design Key Links | CP - CAMM2100 | CP - CAMM2130 | CP - CAMM2160 | BNL Work Org | Last ETC Update | BNL WBS | LSST Story List | Sum Sch 01 (Camera) | Sum Sch 02 (IT w/Needs) | Sum Sch 03 (Sensors_RTM_IT) | LSST Raft Particulate Mitigation | LSST RTM
FALSE |  | CRYO70165 | Final Assy & Test - Cold System Verification Test | LSST Forecast - B57 - B1 | 40 | 5 | 2018-05-01 | 2019-06-07 | -18 | 2018-05-01 |  | 0 | 2019-06-03 | 2019-06-07 | 2019-05-07 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | TRUE | 2018-06-01 | 2018-07-27 |  |  |  |  | 0.8 | 0 | FALSE | TRUE | None |  | None |  | 2019-06-07 |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 266 |  | InProgress | 80% | 260 | 0 | 260 | 260 | LSST Forecast - B57 - B1.3.06.04.06.02 | Refrigeration System - IR2 | 208 | 260 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) | [6 empty] | Utility Trunk | CP #01 (Cryostat/Camera Integration)
Number of Lags
Total number of activities that have lags in their predecessors. This number should not exceed 5%.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | Previous Start | Previous Finish | Percent Complete | Previous Remaining Duration | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | IsLevelOfEffort | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | Global_Basis of Estimate | Global_Cobra Cost Class | Cobra PMT (EV Method)_Global | Global_Color of Money | Global_Control Account Manager | Global_Design Maturity | Global_Judgement Factor | Global_Milestone Levels | Global_Project Phase | Global_Funding Source | Global_EDIA Survey | Global_MS Type | Phase | NSF Milestones | Loading Curve | Sensor Vendor | LSST_CA | Summary Schedule | ICD for NSF Input | LSST Camera Critical Paths | CD2 Budget Changes | DOE Reviews | Critical Path (CD Reviews) | LSST WP Summary | Critical Path (Camera Delivery) | AWARD / NEED Sub-System | Final Design Key Links | CP - CAMM2100 | CP - CAMM2130 | CP - CAMM2160 | BNL Work Org | Last ETC Update | BNL WBS | LSST Story List | Sum Sch 01 (Camera) | Sum Sch 02 (IT w/Needs) | Sum Sch 03 (Sensors_RTM_IT) | LSST Raft Particulate Mitigation | LSST RTM
FALSE |  | ITC22250 | I&T Vacuum Qualification Test | LSST Forecast - B57 - B1 | 69 | 0 | 2018-01-02 | 2018-02-02 | 0 | 2018-01-02 | 2018-02-02 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-02-01 | 2018-05-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 6 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 69 | 22 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.01.03 | Vacuum Qualification Tests | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC)
FALSE |  | OP531235 | Shipping Container Design Update - L1-L2 | LSST Forecast - B57 - B1 | 60 | 0 | 2018-01-02 | 2018-02-28 | 0 | 2018-01-02 | 2018-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-05 | 2019-09-05 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-02-01 | 2018-04-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 39 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | L1-L2 Assembly (TEC)
FALSE |  | CRYO24850 | Finalize Design - Evaporable Getter Pumps | LSST Forecast - B57 - B1 | 21 | 0 | 2018-01-02 | 2018-01-31 | 0 | 2018-01-02 | 2018-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2018-01-02 | 2018-01-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 21 | 20 |  | Complete | 100% | 58 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.02 | Getter Pumps | 58 | 58 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Backend & Vacuum Systems (TEC) | [6 empty] | Cryostat Getter Pumps
FALSE |  | SR340975 | Backside Processing (Batch 25) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 20 | 0 | 2018-01-08 | 2018-01-19 | 0 | 2018-01-08 | 2018-01-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-02-01 | 2018-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 8 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | DAQ910010 | Design & Architecture - GDS | LSST Forecast - B57 - B1 | 40 | 0 | 2018-01-08 | 2018-01-26 | 0 | 2018-01-08 | 2018-01-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-12-09 | 2019-12-09 | 0 | 0 | 0 | 0 | 0 | 5 | FALSE | Normal | FALSE | 2018-02-01 | 2018-03-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 13 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.15 | Guiding Data System (GDS) | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | DAQ Readout Systems (TEC)
FALSE |  | CRYO70125 | Procurement Prep - Cold System Verification Test | LSST Forecast - B57 - B1 | 10 | 0 | 2018-01-09 | 2018-01-23 | 0 | 2018-01-09 | 2018-01-23 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-07 | 2019-05-07 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-02-01 | 2018-02-14 |  |  |  |  | 1 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.02 | Refrigeration System - IR2 | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  | Percent Complete on Work Package |  | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc)
FALSE |  | CRYO15250 | Clean Cryostat Housing | LSST Forecast - B57 - B1 | 22 | 0 | 2018-01-10 | 2018-01-29 | 0 | 2018-01-10 | 2018-01-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-02-01 | 2018-03-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 22 | 12 |  | Complete | 100% | 64 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.01 | Cryostat Housing | 64 | 64 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Fabrication/Assembly |  | Other (specify) | [5 empty] | Cryostat Housing & Assembly (TEC) | [6 empty] | Cryostat Housing
FALSE |  | CRYO70300 | Assemble IR2 Hoses with Fittings - Cold and Cryo | LSST Forecast - B57 - B1 | 31 | 0 | 2018-01-10 | 2018-01-26 | 0 | 2018-01-10 | 2018-01-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-02-01 | 2018-03-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 10 | 10 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 31 | 11 |  | Complete | 100% | 24 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.03 | Refrigeration System - Pre IR2 (Long Lines) | 24 | 24 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | CRYO70320 | Pre-Clean IR2 Hoses (linked to RQD Hose Fitting Installed) | LSST Forecast - B57 - B1 | 12 | 0 | 2018-01-10 | 2018-01-26 | 0 | 2018-01-10 | 2018-01-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-01-10 | 2018-01-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 12 | 12 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.03 | Refrigeration System - Pre IR2 (Long Lines) | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | CCS300005 | Plan for deployment of full focal plane software | LSST Forecast - B57 - B1 | 50 | 0 | 2018-01-11 | 2018-03-23 | 0 | 2018-01-11 | 2018-03-23 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-02-01 | 2018-04-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 50 | 49 |  | Complete | 100% | 360 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.08.03 | CCOB HCU | 360 | 360 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | CCS HCU (TEC)
FALSE |  | CCS120205 | Plan configuration database & telemetry support for ComCam/Full Camera | LSST Forecast - B57 - B1 | 40 | 0 | 2018-01-11 | 2018-06-29 | 0 | 2018-01-11 | 2018-06-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-31 | 2019-05-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-02-01 | 2018-03-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 118 |  | Complete | 100% | 220 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.02.07 | CCS Core 6.0 Release (Comcam Ship) | 220 | 220 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering | [7 empty] | CCS Core (TEC)
FALSE |  | SR340995 | Backside Processing (Batch 26) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 20 | 0 | 2018-01-16 | 2018-01-26 | 0 | 2018-01-16 | 2018-01-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-02-01 | 2018-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 8 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | CRYO72260 | Procurement of Compressor - Chile System | LSST Forecast - B57 - B1 | 60 | 0 | 2018-01-16 | 2018-04-27 | 0 | 2018-01-16 | 2018-04-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-31 | 2019-10-31 | 3300 | 3300 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-02-01 | 2018-04-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 72 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.02 | Refrigeration System - Chile System (Compressor Cabinet) | 0 | 0 | 0 | 3300 | 3300 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | OP521810_2 | RCV: 3rd-band Sub-scale Sample Metrology and Coating Report/Samples (MS3.2) - Filter Coating | LSST Forecast - B57 - B1 | 1 | 0 | 2018-01-26 | 2018-01-26 | 0 | 2018-01-26 | 2018-01-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-12-12 | 2019-12-12 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-02-01 | 2018-02-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | 0-100% Method | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 7% |  | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Filters (TEC)
FALSE |  | SR341015 | Backside Processing (Batch 27) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 20 | 0 | 2018-01-29 | 2018-02-20 | 0 | 2018-01-29 | 2018-02-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-02-01 | 2018-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 15 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | CRYO60976 | Procurement - Pressure Transducers | LSST Forecast - B57 - B1 | 10 | 0 | 2018-02-01 | 2018-02-14 | 0 | 2018-02-01 | 2018-02-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 2300 | 2300 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-01 | 2018-03-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.02 | Refrigeration System - Pre IR2 (Compressor Cabinet) | 0 | 0 | 0 | 2300 | 2300 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | CRYO73045 | Procurement - Refrigerant - IR2 | LSST Forecast - B57 - B1 | 25 | 0 | 2018-02-01 | 2018-10-01 | 0 | 2018-02-01 | 2018-10-01 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-02 | 2020-06-02 | 84000 | 84000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-01 | 2018-04-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 168 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.05 | Refrigeration System - Pre IR2 (Equipment & Refrigeration) | 0 | 0 | 0 | 84000 | 84000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | CRYO71200 | Detail Piece Parts & Assemblies - Cryo/UT Integration - Chile System | LSST Forecast - B57 - B1 | 15 | 0 | 2018-02-01 | 2018-02-26 | 0 | 2018-02-01 | 2018-02-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-31 | 2019-10-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-14 | 2018-04-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 16 |  | Complete | 100% | 114 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.01 | Refrigeration System - Chile System (System Design & Integration) | 114 | 114 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC)
FALSE |  | CAMF2450 | Outstanding Performance Annual Bonus FY18 | LSST Forecast - B57 - B1 | 19 | 0 | 2018-02-01 | 2018-02-28 | 0 | 2018-02-01 | 2018-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-01 | 2018-03-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 19 | 18 |  | Complete | 100% | 308 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01.01.01 | Project Office | 308 | 308 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Drtn | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 0% |  | Management/Administration |  | Project Management (cost estimating, scheduling, project controls, Risk assessment) | [5 empty] | Project Management (TEC)
FALSE |  | ITC93310 | DAQ Pathfinder 2 | LSST Forecast - B57 - B1 | 10 | 0 | 2018-02-01 | 2018-02-09 | 0 | 2018-02-01 | 2018-02-09 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-01 | 2018-03-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 6 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.06.05 | DAQ Pathfinder | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Kevin Reil | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | R&D | [5 empty] | Commissioning Camera (TEC)
FALSE |  | SR341035 | Backside Processing (Batch 28) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 20 | 0 | 2018-02-05 | 2018-02-27 | 0 | 2018-02-05 | 2018-02-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-03-01 | 2018-03-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 15 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | CRYO73160 | Detailed Drawings Hx - Chile System Configuration - Cryo | LSST Forecast - B57 - B1 | 9 | 0 | 2018-02-05 | 2018-03-20 | 0 | 2018-02-05 | 2018-03-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-17 | 2019-06-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-01 | 2018-03-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 9 | 30 |  | Complete | 100% | 30 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.04 | Refrigeration System - Chile System (HX) | 30 | 30 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | CRYO70345 | Procure refrigerant fixtures and Hardware for IR2 | LSST Forecast - B57 - B1 | 11 | 0 | 2018-02-08 | 2018-02-23 | 0 | 2018-02-08 | 2018-02-23 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 4000 | 4000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-01 | 2018-03-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 11 | 10 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.03 | Refrigeration System - Pre IR2 (Long Lines) | 0 | 0 | 0 | 4000 | 4000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | AE210330 | Design Support - UT AC/DC components | LSST Forecast - B57 - B1 | 40 | 0 | 2018-02-12 | 2018-04-30 | 0 | 2018-02-12 | 2018-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2018-03-01 | 2018-04-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 54 |  | Complete | 100% | 176 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.02.01 | AC and DC Power Distribution | 176 | 176 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Gunther Haller | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Aux Elec Components (TEC)
FALSE |  | AE212330 | Design Support - Production Heater Ex, UT Cooling HCU Components | LSST Forecast - B57 - B1 | 40 | 0 | 2018-02-12 | 2018-04-30 | 0 | 2018-02-12 | 2018-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-03-01 | 2018-04-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 54 |  | Complete | 100% | 176 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.02.12 | Heater Ex, UT Cooling HCU | 176 | 176 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Gunther Haller | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Aux Elec Components (TEC)
FALSE |  | AE213170 | Design Support - Production Cables/Networking | LSST Forecast - B57 - B1 | 40 | 0 | 2018-02-12 | 2018-04-30 | 0 | 2018-02-12 | 2018-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-03-01 | 2018-04-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 54 |  | Complete | 100% | 176 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.02.13 | Cables/Networking | 176 | 176 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Gunther Haller | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Aux Elec Components (TEC)
FALSE |  | AE214240 | Design Support - Production Protection PLC System | LSST Forecast - B57 - B1 | 40 | 0 | 2018-02-12 | 2018-04-30 | 0 | 2018-02-12 | 2018-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-03-01 | 2018-04-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 54 |  | Complete | 100% | 176 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.02.14 | Protection PLC System | 176 | 176 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Gunther Haller | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Aux Elec Components (TEC)
FALSE |  | AE211270 | Ion Pump Main Control Board Design, Fabricate and Test | LSST Forecast - B57 - B1 | 40 | 0 | 2018-02-12 | 2018-04-25 | 0 | 2018-02-12 | 2018-04-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 3100 | 3100 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-01 | 2018-04-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 51 |  | Complete | 100% | 148 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.02.11 | Cryostat HCU | 148 | 148 | 0 | 3100 | 3100 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Gunther Haller | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Aux Elec Components (TEC)
FALSE |  | AE211280 | Front-end Control Board Design, Fabricate and Test | LSST Forecast - B57 - B1 | 40 | 0 | 2018-02-12 | 2018-04-25 | 0 | 2018-02-12 | 2018-04-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 4000 | 4000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-01 | 2018-04-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 51 |  | Complete | 100% | 108 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.02.11 | Cryostat HCU | 108 | 108 | 0 | 4000 | 4000 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Gunther Haller | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Aux Elec Components (TEC)
FALSE |  | CRYO72060 | Procurement - Filter Dryer & Hardware Parts - Chile System | LSST Forecast - B57 - B1 | 40 | 0 | 2018-02-13 | 2018-04-10 | 0 | 2018-02-13 | 2018-04-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-31 | 2019-10-31 | 26000 | 26000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-01 | 2018-04-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 39 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.02 | Refrigeration System - Chile System (Compressor Cabinet) | 0 | 0 | 0 | 26000 | 26000 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | CRYO26300 | ETU Preliminary Design Analysis and Documentation - Evaporable Getter Pumps | LSST Forecast - B57 - B1 | 14 | 0 | 2018-02-15 | 2018-02-26 | 0 | 2018-02-15 | 2018-02-26 | 0 | 2019-06-01 | 2019-06-01 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2018-03-01 | 2018-03-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 14 | 7 |  | Complete | 100% | 16 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.02 | Getter Pumps | 16 | 16 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat Backend & Vacuum Systems (TEC) | [6 empty] | Cryostat Getter Pumps
FALSE |  | CRYO73420 | Requisition - Hx Can Vac Sys Cryostat - Chile System | LSST Forecast - B57 - B1 | 5 | 0 | 2018-02-22 | 2018-02-28 | 0 | 2018-02-22 | 2018-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-15 | 2019-10-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-01 | 2018-03-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 4 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.04 | Refrigeration System - Chile System (HX) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Alice Callen |  |  |  | Procurement
FALSE |  | SR341055 | Backside Processing (Batch 29) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 26 | 0 | 2018-02-28 | 2018-03-15 | 0 | 2018-02-28 | 2018-03-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-03-01 | 2018-04-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 26 | 11 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | CCS125920 | Vendor Lead Time - Parts - Camera Body HCU | LSST Forecast - B57 - B1 | 20 | 0 | 2018-03-01 | 2018-03-28 | 0 | 2018-03-01 | 2018-03-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-19 | 2019-07-19 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-04-02 | 2018-04-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 10 | 10 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 19 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.07 | Camera Body HCU | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  |  | Engineering Test/Validation
FALSE |  | ITC33540 | RCV: Outside Fabrication Procurement - Gantry | LSST Forecast - B57 - B1 | 12 | 0 | 2018-03-01 | 2018-03-16 | 0 | 2018-03-01 | 2018-03-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 32500 | 32500 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-04-02 | 2018-04-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 4 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 12 | 11 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.01 | Integration Gantry | 0 | 0 | 0 | 32500 | 32500 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat I&T (TEC)
FALSE |  | SR341075 | Backside Processing (Batch 30) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 25 | 0 | 2018-03-01 | 2018-03-23 | 0 | 2018-03-01 | 2018-03-23 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-04-02 | 2018-05-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 16 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR341095 | Backside Processing (Batch 31) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 25 | 0 | 2018-03-01 | 2018-03-23 | 0 | 2018-03-01 | 2018-03-23 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-04-09 | 2018-05-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 16 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR341115 | Backside Processing (Batch 32) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 35 | 0 | 2018-03-01 | 2018-03-23 | 0 | 2018-03-01 | 2018-03-23 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-04-16 | 2018-06-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 35 | 16 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | ITC25895 | Augmented Risk Reduction Testing - BOT | LSST Forecast - B57 - B1 | 49 | 0 | 2018-03-01 | 2018-05-08 | 0 | 2018-03-01 | 2018-05-08 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-04-02 | 2018-06-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 5 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 49 | 48 |  | Complete | 100% | 240 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.02.01 | Bench For Optical Testing (BOT) | 240 | 240 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC)
FALSE |  | CRYO91290 | Aux Elec mechanical layout and hardware design | LSST Forecast - B57 - B1 | 20 | 0 | 2018-03-01 | 2018-08-24 | 0 | 2018-03-01 | 2018-08-24 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-04-02 | 2018-04-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 124 |  | Complete | 100% | 160 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.05.02 | Utility Trunk Thermo-Mechanical and Assembly | 160 | 160 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Utility Trunk Thermo-Mechanical and Assembly (TEC)
FALSE |  | ITC92520 | Commissioning Camera - CCS Filter Changer | LSST Forecast - B57 - B1 | 80 | 0 | 2018-03-05 | 2019-03-29 | 0 | 2018-03-05 | 2019-03-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-31 | 2019-05-31 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-04-02 | 2018-07-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 80 | 262 |  | Complete | 100% | 320 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.06.02 | CCS Commissioning Camera Tucson Hardware | 320 | 320 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Kevin Reil | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | R&D | [5 empty] | Commissioning Camera (TEC)
FALSE |  | CRYO73042 | Prep for Manufacturing Readiness Review - Hx Chile | LSST Forecast - B57 - B1 | 20 | 0 | 2018-03-12 | 2018-04-25 | 0 | 2018-03-12 | 2018-04-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-17 | 2019-06-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-04-11 | 2018-05-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 32 |  | Complete | 100% | 236 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.04 | Refrigeration System - Chile System (HX) | 236 | 236 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  | Percent Complete on Work Package |  | Brian J. Langton |  |  |  | Design/Engineering | [7 empty] | Refrigeration System (TEC)
FALSE |  | CCS125930 | RCV: Components - Parts - Camera Body HCU | LSST Forecast - B57 - B1 | 10 | 0 | 2018-03-15 | 2018-03-28 | 0 | 2018-03-15 | 2018-03-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-19 | 2019-07-19 | 4000 | 4000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-04-16 | 2018-04-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.07 | Camera Body HCU | 0 | 0 | 0 | 4000 | 4000 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Engineering Test/Validation | [7 empty] | CCS HCU (TEC) | [6 empty] | Shutter Engin/Dsn
FALSE |  | ITC33595 | Augmented Risk Reduction Testing - Gantry | LSST Forecast - B57 - B1 | 11 | 0 | 2018-03-19 | 2018-04-25 | 0 | 2018-03-19 | 2018-04-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-04-02 | 2018-04-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 5 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 11 | 27 |  | Complete | 100% | 280 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.01 | Integration Gantry | 280 | 280 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat I&T (TEC)
FALSE |  | ITC33375 | Refurbishment of 3 REB boards - ETU#1 REB Upgrade | LSST Forecast - B57 - B1 | 5 | 0 | 2018-03-19 | 2018-03-23 | 0 | 2018-03-19 | 2018-03-23 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-04-02 | 2018-04-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 4 |  | Complete | 100% | 72 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.02.02 | Pathfinder / Test Raft Program | 72 | 72 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration | [7 empty] | Verification Test Systems (TEC)
FALSE |  | SR341135 | Backside Processing (Batch 33) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 35 | 0 | 2018-03-23 | 2018-04-30 | 0 | 2018-03-23 | 2018-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-04-23 | 2018-06-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 35 | 26 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR341155 | Backside Processing (Batch 34) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 35 | 0 | 2018-04-02 | 2018-04-30 | 0 | 2018-04-02 | 2018-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-05-01 | 2018-06-19 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 35 | 20 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | SR341195 | Backside Processing (Batch 36) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 35 | 0 | 2018-04-02 | 2018-04-30 | 0 | 2018-04-02 | 2018-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-05-01 | 2018-06-19 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 35 | 20 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | CRYO71240 | Detail Piece Parts & Assemblies - Observatory Op Integration (TMA) - Chile System | LSST Forecast - B57 - B1 | 30 | 0 | 2018-04-02 | 2018-05-11 | 0 | 2018-04-02 | 2018-05-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-31 | 2019-10-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-05-01 | 2018-06-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 29 |  | Complete | 100% | 168 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.01 | Refrigeration System - Chile System (System Design & Integration) | 168 | 168 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC)
FALSE |  | CRYO71280 | Detail Piece Parts & Assemblies - Chile Systems | LSST Forecast - B57 - B1 | 30 | 0 | 2018-04-02 | 2018-05-11 | 0 | 2018-04-02 | 2018-05-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-31 | 2019-10-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-05-01 | 2018-06-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 29 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.01 | Refrigeration System - Chile System (System Design & Integration) | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC)
FALSE |  | ITC14020 | Procurement Prep - IR2 Services Upgrades | LSST Forecast - B57 - B1 | 10 | 0 | 2018-04-02 | 2018-04-13 | 0 | 2018-04-02 | 2018-04-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-14 | 2019-05-14 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2018-05-01 | 2018-05-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 4 | 0 | 1 | 3 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.03 | IR2 Facility and Operations | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor
FALSE |  | SR341175 | Backside Processing (Batch 35) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 35 | 0 | 2018-04-09 | 2018-04-30 | 0 | 2018-04-09 | 2018-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-05-08 | 2018-06-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 35 | 15 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | CR231060 | CRSA#1 Guide Sensor #1 - pin locating fixture installation | LSST Forecast - B57 - B1 | 0 | 0 | 2018-04-13 | 2018-04-13 | 0 | 2018-04-13 | 2018-04-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-04-13 | 2018-04-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 8 | 0 | 8 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 0 | 1 |  | Complete | 100% | 4 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 4 | 4 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.45) Task/item is a conceptual design and/or advances the state of the art | 0% |  | Testing/Integration |  | Other (specify) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Integration (Guide/Wavefront Sensors) | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | OP541700 | Support L3 Coating | LSST Forecast - B57 - B1 | 104 | 0 | 2018-04-18 | 2018-09-28 | 0 | 2018-04-18 | 2018-09-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-05-01 | 2018-09-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 104 | 114 |  | Complete | 100% | 320 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 320 | 320 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Drtn | Engineering Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Scott Winters | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 15% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | L3 Assembly (TEC) | L1_L2 Summary | [5 empty] | L1-L2 Optics
FALSE |  | OP521810_3 | RCV: 4th-band Sub-scale Sample Metrology and Coating Report/Samples (MS3.3) - Filter Coating | LSST Forecast - B57 - B1 | 1 | 0 | 2018-04-27 | 2018-04-27 | 0 | 2018-04-27 | 2018-04-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-12-12 | 2019-12-12 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-05-21 | 2018-05-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | 0-100% Method | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 7% |  | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Filters (TEC)
FALSE |  | CCS106800 | Test/Validate Lock Manager Release 1 with Core and Console - Lock Manager | LSST Forecast - B57 - B1 | 30 | 0 | 2018-05-01 | 2019-02-28 | 0 | 2018-05-01 | 2019-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2020-03-30 | 2020-03-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-06-01 | 2018-07-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 200 |  | Complete | 100% | 400 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.05 | CCS Lock Manager | 400 | 400 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering | [7 empty] | CCS Core (TEC)
FALSE |  | ITC19885 | Early (Long Lead) Procurement - Vendor Lead Time - Handling Equipment | LSST Forecast - B57 - B1 | 30 | 0 | 2018-05-01 | 2018-05-31 | 0 | 2018-05-01 | 2018-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-07-26 | 2018-09-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 10 | 10 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 21 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.02 | Camera Handling Equipment | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc)
FALSE |  | ITC19895 | RCV: Early (Long Lead) Procurement - Handling Equipment | LSST Forecast - B57 - B1 | 20 | 0 | 2018-05-01 | 2018-05-31 | 0 | 2018-05-01 | 2018-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-08-09 | 2018-09-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 4 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 21 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.02 | Camera Handling Equipment | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Camera I&T (TEC)
FALSE |  | ITC19995 | COTS Procurement - Vendor Lead Time - Handling Equipment | LSST Forecast - B57 - B1 | 30 | 0 | 2018-05-01 | 2018-05-31 | 0 | 2018-05-01 | 2018-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-10-15 | 2018-11-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 10 | 10 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 21 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.02 | Camera Handling Equipment | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc)
FALSE |  | ITC20005 | RCV: COTS Procurement - Handling Equipment | LSST Forecast - B57 - B1 | 20 | 0 | 2018-05-01 | 2018-05-31 | 0 | 2018-05-01 | 2018-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-10-29 | 2018-11-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 4 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 21 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.02 | Camera Handling Equipment | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Camera I&T (TEC)
FALSE |  | ITC20026 | Outside Fabrication - Vendor Lead Time - Handling Equipment | LSST Forecast - B57 - B1 | 30 | 0 | 2018-05-01 | 2018-05-31 | 0 | 2018-05-01 | 2018-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-10-15 | 2018-11-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 10 | 10 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 21 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.02 | Camera Handling Equipment | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc)
FALSE |  | ITC20035 | RCV: Outside Fabrication Procurement - Handling Equipment | LSST Forecast - B57 - B1 | 20 | 0 | 2018-05-01 | 2018-05-31 | 0 | 2018-05-01 | 2018-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-10-29 | 2018-11-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 4 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 21 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.02 | Camera Handling Equipment | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Camera I&T (TEC)
FALSE |  | ITC94060 | Document Update - Commissioning Phase | LSST Forecast - B57 - B1 | 54 | 0 | 2018-05-01 | 2018-08-01 | 0 | 2018-05-01 | 2018-08-01 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-06-01 | 2018-08-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 54 | 64 |  | Complete | 100% | 50 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.06.06 | Commissioning Baseline Planning | 50 | 50 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Kevin Reil | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Project Management (cost estimating, scheduling, project controls, Risk assessment) | [5 empty] | Commissioning Camera (TEC)
FALSE |  | ITC22450 | Procurement Prep - TS7 HW | LSST Forecast - B57 - B1 | 10 | 0 | 2018-05-01 | 2018-05-04 | 0 | 2018-05-01 | 2018-05-04 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-06-01 | 2018-06-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 3 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.01.03 | Vacuum Qualification Tests | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor
FALSE |  | ITC32670 | Procurement Prep - IR2 Facility and Operations | LSST Forecast - B57 - B1 | 10 | 0 | 2018-05-01 | 2018-05-14 | 0 | 2018-05-01 | 2018-05-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-06-01 | 2018-06-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment |  | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor
FALSE |  | AE210340 | Installation Support - Auxiliary Electronics Power Distribution | LSST Forecast - B57 - B1 | 22 | 0 | 2018-05-01 | 2018-09-28 | 0 | 2018-05-01 | 2018-09-28 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-06-01 | 2018-07-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 22 | 105 |  | Complete | 100% | 176 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.02.01 | AC and DC Power Distribution | 176 | 176 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Gunther Haller | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Fabrication/Assembly |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Aux Elec Components (TEC)
FALSE |  | AE212340 | Installation Support - Auxiliary Electronics Heater Exchange and UT Cooling | LSST Forecast - B57 - B1 | 22 | 0 | 2018-05-01 | 2018-09-21 | 0 | 2018-05-01 | 2018-09-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-12-12 | 2019-12-12 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-06-01 | 2018-07-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 22 | 100 |  | Complete | 100% | 176 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.02.12 | Heater Ex, UT Cooling HCU | 176 | 176 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Gunther Haller | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Fabrication/Assembly |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Aux Elec Components (TEC)
FALSE |  | AE213180 | Installation Support - Auxiliary Electronics Cabling | LSST Forecast - B57 - B1 | 22 | 0 | 2018-05-01 | 2018-09-28 | 0 | 2018-05-01 | 2018-09-28 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-06-01 | 2018-07-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 22 | 105 |  | Complete | 100% | 176 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.02.13 | Cables/Networking | 176 | 176 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Gunther Haller | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Fabrication/Assembly |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Aux Elec Components (TEC)
FALSE |  | AE214250 | Programming Installation Support - Auxiliary Electronics Protection PLC System | LSST Forecast - B57 - B1 | 22 | 0 | 2018-05-01 | 2018-09-28 | 0 | 2018-05-01 | 2018-09-28 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-06-01 | 2018-07-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 22 | 105 |  | Complete | 100% | 176 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.02.14 | Protection PLC System | 176 | 176 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Gunther Haller | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Fabrication/Assembly |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Aux Elec Components (TEC)
FALSE |  | SR333535 | Batch Sensor Testing (RTM #16) | LSST Forecast - B57 - B1 | 15 | 0 | 2018-05-19 | 2018-05-31 | 0 | 2018-05-19 | 2018-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-06-21 | 2018-07-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 10 | 0 | 9 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 3 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 7 |  | Complete | 100% | 83 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 83 | 83 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | OP531240 | Procure L1 Coating | LSST Forecast - B57 - B1 | 40 | 0 | 2018-05-21 | 2018-11-21 | 0 | 2018-05-21 | 2018-11-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-03 | 2019-09-03 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-07-17 | 2018-09-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 5 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 129 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment |  | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 0% |  | Procurement | [7 empty] | L1-L2 Assembly (TEC) | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly) |  |  |  | L1-L2 Optics
FALSE |  | SR551171 | RTM16_RSA Construction at TS4 | LSST Forecast - B57 - B1 | 8 | 0 | 2018-06-01 | 2018-06-12 | 0 | 2018-06-01 | 2018-06-12 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-07-02 | 2018-07-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 8 | 7 |  | Complete | 100% | 44 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 44 | 44 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #16 |  | Science Raft System
FALSE |  | CRYO73055 | AWARD: P.O. - Heat Exchanger Cryo/Cold - Cryostat | LSST Forecast - B57 - B1 | 1 | 0 | 2018-06-01 | 2018-06-01 | 0 | 2018-06-01 | 2018-06-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-17 | 2019-06-17 | 188357 | 188357 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-07-02 | 2018-07-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.04 | Refrigeration System - Chile System (HX) | 0 | 0 | 0 | 188357 | 188357 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | B1 Procurement Commitment (C5.1) |  | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 20% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Refrigeration System (TEC)
FALSE |  | CRYO25250 | Generate Manufacturing Docs - Evaporable Getter Pump | LSST Forecast - B57 - B1 | 20 | 0 | 2018-06-04 | 2018-06-08 | 0 | 2018-06-04 | 2018-06-08 | 0 | 2019-06-01 | 2019-06-01 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-09-27 | 2018-10-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 4 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.02 | Getter Pumps | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  |  | Design/Engineering
FALSE |  | OP521810_4 | RCV: 5th-band Sub-scale Sample Metrology and Coating Report/Samples (MS3.4) - Filter Coating | LSST Forecast - B57 - B1 | 1 | 0 | 2018-06-14 | 2018-06-14 | 0 | 2018-06-14 | 2018-06-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-12-12 | 2019-12-12 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-07-09 | 2018-07-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | 0-100% Method | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 7% |  | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Filters (TEC)
FALSE |  | SR333545 | Batch Sensor Testing (RTM #17) | LSST Forecast - B57 - B1 | 10 | 0 | 2018-06-20 | 2018-07-06 | 0 | 2018-06-20 | 2018-07-06 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-07-03 | 2018-07-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 10 | 0 | 3 | 6 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 11 |  | Complete | 100% | 83 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 83 | 83 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | CRYO61405 | NEED: Cryostat Assembly Ready for Hx Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2018-06-28 | 2018-06-28 | 0 | 2018-06-28 | 2018-06-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-07-11 | 2018-07-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.04 | Refrigeration System - Pre IR2 (HX) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 5 Milestone | Fabrication/Assembly | [16 empty] | Cryostat
FALSE |  | CRYO61610 | Requisition - Compressor Module Control Boxes - Chile Hardware | LSST Forecast - B57 - B1 | 19 | 0 | 2018-07-02 | 2018-07-06 | 0 | 2018-07-02 | 2018-07-06 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-03 | 2019-10-03 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-08-01 | 2018-08-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 3 | 3 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 19 | 3 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.02 | Refrigeration System - Chile System (Compressor Cabinet) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  |  | Procurement
FALSE |  | ITC14090 | Procurement Prep - Raft Storage HW | LSST Forecast - B57 - B1 | 12 | 0 | 2018-07-02 | 2018-07-18 | 0 | 2018-07-02 | 2018-07-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-09 | 2019-09-09 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-08-01 | 2018-08-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 12 | 11 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.03 | IR2 Facility and Operations | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor
FALSE |  | CRYO61620 | Procurement Process - Compressor Module Control Boxes - Chile Hardware | LSST Forecast - B57 - B1 | 20 | 0 | 2018-07-06 | 2018-07-16 | 0 | 2018-07-06 | 2018-07-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-03 | 2019-10-03 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-08-06 | 2018-08-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 6 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.02 | Refrigeration System - Chile System (Compressor Cabinet) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  |  | Procurement
FALSE |  | SR333565 | Batch Sensor Testing (RTM #19) | LSST Forecast - B57 - B1 | 10 | 0 | 2018-07-12 | 2018-07-25 | 0 | 2018-07-12 | 2018-07-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-08-10 | 2018-08-23 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 103 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 103 | 103 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | CBM48900 | Engineering and Design Support for Fab/Assy/Test - Shutter | LSST Forecast - B57 - B1 | 195 | 15 | 2018-08-01 | 2019-06-21 | 116 | 2018-08-01 |  | 0 | 2019-06-03 | 2019-06-21 | 2019-11-14 | 2019-12-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-09-04 | 2019-06-24 |  |  |  |  | 0.65 | 0 | FALSE | FALSE | None |  | None |  | 2019-05-21 |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 195 | 202 |  | InProgress | 65% | 612 | 0 | 612 | 612 | LSST Forecast - B57 - B1.3.06.02.02 | Shutter Development | 397.8 | 561.7846 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 5% |  | Fabrication/Assembly |  | Construction Management | [5 empty] | Shutter Development (TEC) | [6 empty] | Shutter Prod Sprt
FALSE |  | SE221645 | Model Validation & I&T Test Support (LOE) | LSST Forecast - B57 - B1 | 340 | 84 | 2018-08-01 | 2019-09-30 | 273 | 2018-08-01 |  | 0 | 2019-06-03 | 2019-09-30 | 2020-07-14 | 2020-11-09 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-09-04 | 2020-02-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None |  | 2019-09-30 |  |  |  |  | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 340 | 202 |  | InProgress | 75.29% | 486 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.01 | Structural System Analysis | 365.9294 | 255.8647 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Drtn | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | ITC19805 | Update Defining Documentation - Handling Equipment | LSST Forecast - B57 - B1 | 24 | 0 | 2018-08-01 | 2018-08-10 | 0 | 2018-08-01 | 2018-08-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-16 | 2019-09-16 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-09-04 | 2018-10-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 24 | 7 |  | Complete | 100% | 9 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.02 | Camera Handling Equipment | 9 | 9 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Camera I&T (TEC)
FALSE |  | ITC98090 | I&T Physicist Support - IR2 Clean Room | LSST Forecast - B57 - B1 | 118 | 0 | 2018-08-01 | 2019-01-31 | 0 | 2018-08-01 | 2019-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-09-04 | 2019-03-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 118 | 117 |  | Complete | 100% | 1040 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.01 | I&T Integration & Management | 1040 | 1040 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Drtn | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Construction Management | [5 empty] | Integration & Testing (TEC)
FALSE |  | CRYO31505 | Procurement Prep - Material - Power Feedthrough | LSST Forecast - B57 - B1 | 10 | 0 | 2018-08-01 | 2018-08-14 | 0 | 2018-08-01 | 2018-08-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-09-04 | 2018-09-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.01 | Cryostat Back End | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Procurement
FALSE |  | CRYO31515 | Procurement Prep - Assy/Test Equipment - Power Feedthrough | LSST Forecast - B57 - B1 | 10 | 0 | 2018-08-01 | 2018-08-14 | 0 | 2018-08-01 | 2018-08-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-09-04 | 2018-09-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.01 | Cryostat Back End | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Procurement
FALSE |  | CAMM6390 | AVAIL: Camera Software for Auxiliary Telescope | LSST Forecast - B57 - B1 | 0 | 0 | 2018-08-01 | 2018-08-01 | 0 | 2018-08-01 | 2018-08-01 | 0 | 2019-06-01 | 2019-06-01 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-08-01 | 2018-08-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | FinishOnOrBefore | 2018-09-28 | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.03 | NSF Interface Milestone (NSF Needs) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration
FALSE |  | CAMF661550 | In-House Assembly - Auto Changer | LSST Forecast - B57 - B1 | 56 | 0 | 2018-08-02 | 2019-01-07 | 0 | 2018-08-02 | 2019-01-07 | 0 | 2019-06-01 | 2019-06-01 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-09-04 | 2018-11-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 56 | 99 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.01 | Auto Changer | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Fabrication/Assembly
FALSE |  | DAQ334600 | Procurement Process - Production Parts - ATCA Shelves | LSST Forecast - B57 - B1 | 10 | 0 | 2018-08-20 | 2018-08-27 | 0 | 2018-08-20 | 2018-08-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-24 | 2019-05-24 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-09-04 | 2018-09-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 5 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.06 | ATCA Shelves | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [7 empty] | ICD's for Phase 3 |  |  |  |  | DAQ Readout Systems
FALSE |  | DAQ920000 | START: Design and R & D (Firmware) | LSST Forecast - B57 - B1 | 0 | 0 | 2018-08-20 | 2018-08-20 | 0 | 2018-08-20 | 2018-08-20 | 0 | 2019-06-01 | 2019-06-01 | 2020-08-26 | 2020-08-26 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-09-18 | 2018-09-18 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.16 | Remote FPGA Reprogramming | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% | Level 5 Milestone | Design/Engineering
FALSE |  | DAQ313400 | START: (V2) of the New COB | LSST Forecast - B57 - B1 | 0 | 0 | 2018-08-28 | 2018-08-28 | 0 | 2018-08-28 | 2018-08-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-24 | 2019-05-24 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2018-09-04 | 2018-09-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.02 | DAQ COB (Main ATCA DAQ Module) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Michael Huffer |  |  | Level 5 Milestone
FALSE |  | ITC22320 | Develop Camera Shipping Plan | LSST Forecast - B57 - B1 | 20 | 0 | 2018-09-03 | 2018-09-21 | 0 | 2018-09-03 | 2018-09-21 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-10-01 | 2018-10-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 13 |  | Complete | 100% | 50 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.05 | Transportation & Storage Equipment | 50 | 50 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Kevin Reil | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Transportation & Storage Equipment (TEC)
FALSE |  | DAQ920030 | START: Design and R & D (Software) | LSST Forecast - B57 - B1 | 0 | 0 | 2018-09-04 | 2018-09-04 | 0 | 2018-09-04 | 2018-09-04 | 0 | 2019-06-01 | 2019-06-01 | 2020-07-16 | 2020-07-16 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-10-15 | 2018-10-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.16 | Remote FPGA Reprogramming | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment |  | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% | Level 5 Milestone | Design/Engineering
FALSE |  | CRYO31700 | Write Test and Verification Reports Cryostat Backend | LSST Forecast - B57 - B1 | 6 | 0 | 2018-09-17 | 2018-10-08 | 0 | 2018-09-17 | 2018-10-08 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2018-10-01 | 2018-10-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 6 | 15 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.01 | Cryostat Back End | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Brian J. Langton |  |  |  | Fabrication/Assembly
FALSE |  | ITC34090 | RCV: COTS Procurement - Cryo-Equip | LSST Forecast - B57 - B1 | 29 | 0 | 2018-09-21 | 2018-09-25 | 0 | 2018-09-21 | 2018-09-25 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 8000 | 8000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-10-15 | 2018-11-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 4 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 29 | 2 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.02 | Cryostat Handling Equipment | 0 | 0 | 0 | 8000 | 8000 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat I&T (TEC)
FALSE |  | CR231930 | CRSA#4 in cryostat cool down | LSST Forecast - B57 - B1 | 1 | 0 | 2018-09-24 | 2018-09-24 | 0 | 2018-09-24 | 2018-09-24 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-05 | 2019-06-05 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-09-24 | 2018-09-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 1 |  | Complete | 100% | 8 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 8 | 8 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Testing/Integration |  | Other (specify) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Integration (Guide/Wavefront Sensors) | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CRYO61040 | Detail Piece Parts & Assemblies - Evacuate, Purge & Charge HW - Chile System | LSST Forecast - B57 - B1 | 15 | 1 | 2018-10-01 | 2019-06-03 | 245 | 2018-10-01 |  | 0 | 2019-06-03 | 2019-06-03 | 2020-06-02 | 2020-06-03 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-11-01 | 2018-11-21 |  |  |  |  | 0.1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 160 |  | InProgress | 10% | 106 | 0 | 106 | 106 | LSST Forecast - B57 - B1.3.06.04.06.03.05 | Refrigeration System - Chile System (Equipment & Refrigeration) | 10.6 | 106 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) | [6 empty] | Refrigeration System
FALSE |  | CRYO72200 | Fab and Assembly - Compressors Oil Reservoirs - Cryo - Chile System (6 Unts) | LSST Forecast - B57 - B1 | 25 | 0 | 2018-10-01 | 2019-01-31 | 0 | 2018-10-01 | 2019-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-31 | 2019-10-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-11-01 | 2018-12-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 75 |  | Complete | 100% | 84 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.02 | Refrigeration System - Chile System (Compressor Cabinet) | 84 | 84 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.00) Task/item is fully invoiced/completed | 0% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC)
FALSE |  | DAQ900342 | Procure COB - FPGAs | LSST Forecast - B57 - B1 | 10 | 0 | 2018-10-01 | 2018-12-31 | 0 | 2018-10-01 | 2018-12-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 128000 | 128000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-02-01 | 2019-02-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 5 | 5 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 58 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.02 | DAQ COB (Main ATCA DAQ Module) | 0 | 0 | 0 | 128000 | 128000 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Fabrication/Assembly | [7 empty] | DAQ Readout Systems (TEC)
FALSE |  | CRYO61335 | Replace Condensing Unit - IR2 | LSST Forecast - B57 - B1 | 5 | 0 | 2018-10-08 | 2018-10-12 | 0 | 2018-10-08 | 2018-10-12 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-11-01 | 2018-11-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 4 |  | Complete | 100% | 16 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.02 | Refrigeration System - Pre IR2 (Compressor Cabinet) | 16 | 16 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | OP521810_5 | RCV: 6th-band Sub-scale Sample Metrology and Coating Report/Samples (MS3.5) - Filter Coating | LSST Forecast - B57 - B1 | 1 | 0 | 2018-10-29 | 2018-10-29 | 0 | 2018-10-29 | 2018-10-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-12-12 | 2019-12-12 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-11-01 | 2018-11-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | 0-100% Method | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 7% |  | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Filters (TEC)
FALSE |  | OP522105 | RCV: Filter First Article TWF testing data received (MS2) | LSST Forecast - B57 - B1 | 1 | 0 | 2018-10-31 | 2018-10-31 | 0 | 2018-10-31 | 2018-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-25 | 2019-07-25 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-11-12 | 2018-11-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | 0-100% Method | TEC Non-ARRA | Scott Winters |  |  | Level 4 Milestone | Procurement | [7 empty] | Filters (TEC)
FALSE |  | SE221370 | Prep camera FEA model for export to Obs; deliver and run verification checks | LSST Forecast - B57 - B1 | 40 | 0 | 2018-11-01 | 2018-11-30 | 0 | 2018-11-01 | 2018-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-13 | 2019-06-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-12-03 | 2019-02-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 19 |  | Complete | 100% | 20 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.01 | Structural System Analysis | 20 | 20 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | ITC31727 | NEED: All DAQ OTM's | LSST Forecast - B57 - B1 | 0 | 0 | 2018-11-02 | 2018-11-02 | 0 | 2018-11-02 | 2018-11-02 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-12-03 | 2018-12-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Auxiliary Electronics
FALSE |  | CRYO72340 | RCV: Compressor Module - Chile System | LSST Forecast - B57 - B1 | 40 | 0 | 2018-11-05 | 2019-01-18 | 0 | 2018-11-05 | 2019-01-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-31 | 2019-10-31 | 203981 | 203981 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-01-29 | 2019-03-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 42 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.02 | Refrigeration System - Chile System (Compressor Cabinet) | 0 | 0 | 0 | 203981 | 203981 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 20% |  | Procurement | [7 empty] | Refrigeration System (TEC)
FALSE |  | CBM50200 | Vendor Lead Time - Components - Shutter | LSST Forecast - B57 - B1 | 35 | 0 | 2018-12-03 | 2019-04-30 | 0 | 2018-12-03 | 2019-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-21 | 2019-08-21 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-01-07 | 2019-02-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 35 | 94 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.02.02 | Shutter Development | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Martin Nordby |  |  |  | Procurement
FALSE |  | OP541640 | Procure L3 Lens Coating | LSST Forecast - B57 - B1 | 59 | 0 | 2018-12-03 | 2019-02-22 | 0 | 2018-12-03 | 2019-02-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-01-02 | 2019-03-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 59 | 54 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement | [8 empty] | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly) |  |  |  | L1-L2 Optics
Merge Hotspot
The total number of activities with a high number of predecessor links.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | Previous Start | Previous Finish | Percent Complete | Previous Remaining Duration | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | IsLevelOfEffort | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | Global_Basis of Estimate | Global_Cobra Cost Class | Cobra PMT (EV Method)_Global | Global_Color of Money | Global_Control Account Manager | Global_Design Maturity | Global_Judgement Factor | Global_Milestone Levels | Global_Project Phase | Global_Funding Source | Global_EDIA Survey | Global_MS Type | Phase | NSF Milestones | Loading Curve | Sensor Vendor | LSST_CA | Summary Schedule | ICD for NSF Input | LSST Camera Critical Paths | CD2 Budget Changes | DOE Reviews | Critical Path (CD Reviews) | LSST WP Summary | Critical Path (Camera Delivery) | AWARD / NEED Sub-System | Final Design Key Links | CP - CAMM2100 | CP - CAMM2130 | CP - CAMM2160 | BNL Work Org | Last ETC Update | BNL WBS | LSST Story List | Sum Sch 01 (Camera) | Sum Sch 02 (IT w/Needs) | Sum Sch 03 (Sensors_RTM_IT) | LSST Raft Particulate Mitigation | LSST RTM
FALSE |  | CR230960 | CRSA baseplate lot 1 - Metrology (height/flatness/hole location) on test station 5 | LSST Forecast - B57 - B1 | 10 | 0 | 2018-01-02 | 2018-01-16 | 0 | 2018-01-02 | 2018-01-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-02-01 | 2018-02-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.45) Task/item is a conceptual design and/or advances the state of the art | 0% |  | Testing/Integration |  | Other (specify) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Integration (Baseplate, thermal straps) | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | ITC22250 | I&T Vacuum Qualification Test | LSST Forecast - B57 - B1 | 69 | 0 | 2018-01-02 | 2018-02-02 | 0 | 2018-01-02 | 2018-02-02 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-02-01 | 2018-05-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 6 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 69 | 22 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.01.03 | Vacuum Qualification Tests | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC)
FALSE |  | SR333505 | Batch Sensor Testing (RTM #13) | LSST Forecast - B57 - B1 | 9 | 0 | 2018-01-02 | 2018-01-12 | 0 | 2018-01-02 | 2018-01-12 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-02-01 | 2018-02-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 9 | 8 |  | Complete | 100% | 83 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 83 | 83 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | CRYO20750 | Test and Verify Cryo & Cold Plate | LSST Forecast - B57 - B1 | 20 | 0 | 2018-01-08 | 2018-01-31 | 0 | 2018-01-08 | 2018-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-02-02 | 2018-03-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 16 |  | Complete | 100% | 350 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.03 | Cryo and Cold Plates | 350 | 350 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 11% |  | Fabrication/Assembly |  | Other (specify) | [5 empty] | Cryo and Cold Plates (TEC) | [5 empty] | Critical Path to CD-2 | Cryo and Cold Plates
FALSE |  | CRYO24950 | Prep for C_FDR - Evaporable Getter Pumps | LSST Forecast - B57 - B1 | 5 | 0 | 2018-01-08 | 2018-01-30 | 0 | 2018-01-08 | 2018-01-30 | 0 | 2019-06-01 | 2019-06-01 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-04-11 | 2018-04-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 15 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.02 | Getter Pumps | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Brian J. Langton | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [12 empty] | Cryostat Getter Pumps
FALSE |  | SR550540 | SHIPPING: Ship RTM #5 to SLAC | LSST Forecast - B57 - B1 | 4 | 0 | 2018-01-09 | 2018-01-12 | 0 | 2018-01-09 | 2018-01-12 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-02-08 | 2018-02-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 3 |  | Complete | 100% | 8 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 8 | 8 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration |  | Other (specify) | [5 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #5 |  | Science Raft System
FALSE |  | CRYO15250 | Clean Cryostat Housing | LSST Forecast - B57 - B1 | 22 | 0 | 2018-01-10 | 2018-01-29 | 0 | 2018-01-10 | 2018-01-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-02-01 | 2018-03-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 22 | 12 |  | Complete | 100% | 64 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.02.01 | Cryostat Housing | 64 | 64 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Fabrication/Assembly |  | Other (specify) | [5 empty] | Cryostat Housing & Assembly (TEC) | [6 empty] | Cryostat Housing
FALSE |  | SR330845_3 | RCV: 3rd Set Sensor Delivery - V1 Prod Lot 2 (Sensor 78) | LSST Forecast - B57 - B1 | 21 | 0 | 2018-01-10 | 2018-03-02 | 0 | 2018-01-10 | 2018-03-02 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 61335.6 | 61335.6 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-01 | 2018-03-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 7 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 21 | 35 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 61335.6 | 61335.6 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | ITC92140 | Equipment Procurement Review - Prep - Com Cam | LSST Forecast - B57 - B1 | 2 | 0 | 2018-01-10 | 2018-01-12 | 0 | 2018-01-10 | 2018-01-12 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-16 | 2019-05-16 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-02-22 | 2018-02-23 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 2 |  | Complete | 100% | 14 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.06.01 | Commissioning Camera Hardware | 14 | 14 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Kevin Reil | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | R&D | [5 empty] | Commissioning Camera (TEC)
FALSE |  | CRYO70320 | Pre-Clean IR2 Hoses (linked to RQD Hose Fitting Installed) | LSST Forecast - B57 - B1 | 12 | 0 | 2018-01-10 | 2018-01-26 | 0 | 2018-01-10 | 2018-01-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-01-10 | 2018-01-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 12 | 12 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.03 | Refrigeration System - Pre IR2 (Long Lines) | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | CCS120205 | Plan configuration database & telemetry support for ComCam/Full Camera | LSST Forecast - B57 - B1 | 40 | 0 | 2018-01-11 | 2018-06-29 | 0 | 2018-01-11 | 2018-06-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-31 | 2019-05-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-02-01 | 2018-03-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 118 |  | Complete | 100% | 220 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.02.07 | CCS Core 6.0 Release (Comcam Ship) | 220 | 220 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering | [7 empty] | CCS Core (TEC)
FALSE |  | CRYO84700 | Generate Detail and Assembly Drawings Cryostat Utility Trunk | LSST Forecast - B57 - B1 | 80 | 20 | 2018-01-12 | 2019-06-28 | 27 | 2018-01-12 |  | 0 | 2019-06-03 | 2019-06-28 | 2019-07-11 | 2019-08-07 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-02-01 | 2018-05-24 |  |  |  |  | 0.9 | 0 | FALSE | FALSE | None |  | None |  | 2019-06-28 |  |  |  |  | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 80 | 341 |  | InProgress | 90% | 819 | 0 | 819 | 819 | LSST Forecast - B57 - B1.3.06.05.02 | Utility Trunk Thermo-Mechanical and Assembly | 737.1 | 819 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Utility Trunk Thermo-Mechanical and Assembly (TEC) | [6 empty] | Utility Trunk
FALSE |  | ITC25890 | Final Testing - BOT | LSST Forecast - B57 - B1 | 28 | 0 | 2018-01-15 | 2018-04-10 | 0 | 2018-01-15 | 2018-04-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-04-02 | 2018-05-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 1 | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 4 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 28 | 59 |  | Complete | 100% | 416 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.02.01 | Bench For Optical Testing (BOT) | 416 | 416 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC)
FALSE |  | SR340995 | Backside Processing (Batch 26) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 20 | 0 | 2018-01-16 | 2018-01-26 | 0 | 2018-01-16 | 2018-01-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-02-01 | 2018-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 8 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | CR231000 | AVAIL: Pre-Assembled CRSA - 4 production units, 4 I&T units | LSST Forecast - B57 - B1 | 0 | 0 | 2018-01-17 | 2018-01-17 | 0 | 2018-01-17 | 2018-01-17 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2018-03-01 | 2018-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 5 Milestone | Testing/Integration | [8 empty] | CRSA Integration (Baseplate, thermal straps)
FALSE |  | DAQ328200 | Procurement Process - Production Parts - FPA-RTM | LSST Forecast - B57 - B1 | 10 | 0 | 2018-01-29 | 2018-02-14 | 0 | 2018-01-29 | 2018-02-14 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2018-01-29 | 2018-02-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 12 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.04 | DAQ FPA-RTM (Rear Transistion Module) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [7 empty] | ICD's for Phase 3 |  |  |  |  | DAQ Readout Systems
FALSE |  | CAMF665250 | Inspect Procured Parts - Filter Loader | LSST Forecast - B57 - B1 | 5 | 0 | 2018-02-01 | 2018-07-18 | 0 | 2018-02-01 | 2018-07-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-28 | 2018-04-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 1 | 1 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 116 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.02 | Filter Loader | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Fabrication/Assembly
FALSE |  | ITC22440 | AVAIL: Vacuum Qualification Test Ready for Cryostat Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2018-02-02 | 2018-02-02 | 0 | 2018-02-02 | 2018-02-02 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-04-10 | 2018-04-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.01.03 | Vacuum Qualification Tests | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration | [16 empty] | Integration and Test
FALSE |  | CRYO73160 | Detailed Drawings Hx - Chile System Configuration - Cryo | LSST Forecast - B57 - B1 | 9 | 0 | 2018-02-05 | 2018-03-20 | 0 | 2018-02-05 | 2018-03-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-17 | 2019-06-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-01 | 2018-03-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 9 | 30 |  | Complete | 100% | 30 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.04 | Refrigeration System - Chile System (HX) | 30 | 30 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | SR550600 | SHIPPING: Ship RTM #6 to SLAC | LSST Forecast - B57 - B1 | 4 | 0 | 2018-02-12 | 2018-02-15 | 0 | 2018-02-12 | 2018-02-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-03-12 | 2018-03-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 3 |  | Complete | 100% | 8 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 8 | 8 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration |  | Other (specify) | [5 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #6 |  | Science Raft System
FALSE |  | OP541620 | AWARD: Phase 3 BBAR Coating of L3 (Option 2) | LSST Forecast - B57 - B1 | 1 | 0 | 2018-02-12 | 2018-02-12 | 0 | 2018-02-12 | 2018-02-12 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 81000 | 81000 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-04-24 | 2018-04-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 8 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 0 | 0 | 0 | 81000 | 81000 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | B1 Procurement Commitment (C5.1) |  | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 14% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | L3 Assembly (TEC) | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly) |  |  |  | L1-L2 Optics
FALSE |  | CR235190 | Guide Sensor Readout Study - CCD First Article | LSST Forecast - B57 - B1 | 5 | 10 | 2018-02-20 | 2019-10-01 | 510 | 2018-02-20 |  | 0 | 2019-09-18 | 2019-10-01 | 2021-10-18 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-05-22 | 2018-05-29 |  |  |  |  | 0.2917 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 4 | 0 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 316 |  | InProgress | 29.17% | 200 | 0 | 200 | 200 | LSST Forecast - B57 - B1.3.04.02.03.03 | Guide Sensors | 58.34 | 200 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Engineering Test/Validation |  | Other (specify) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | Guide Sensor study & testbed | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | DAQ313360 | Fabricate & Load 2 prototype boards - COB Production Candidate | LSST Forecast - B57 - B1 | 19 | 0 | 2018-02-20 | 2018-03-23 | 0 | 2018-02-20 | 2018-03-23 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-31 | 2019-10-31 | 30000 | 30000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-14 | 2018-04-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 19 | 23 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.02 | DAQ COB (Main ATCA DAQ Module) | 0 | 0 | 0 | 30000 | 30000 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | DAQ Readout Systems (TEC)
FALSE |  | CRYO73420 | Requisition - Hx Can Vac Sys Cryostat - Chile System | LSST Forecast - B57 - B1 | 5 | 0 | 2018-02-22 | 2018-02-28 | 0 | 2018-02-22 | 2018-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-15 | 2019-10-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-03-01 | 2018-03-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 4 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.04 | Refrigeration System - Chile System (HX) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Alice Callen |  |  |  | Procurement
FALSE |  | CBM49800 | AWARD: Contract - Shutter Blades | LSST Forecast - B57 - B1 | 1 | 0 | 2018-02-27 | 2018-02-27 | 0 | 2018-02-27 | 2018-02-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-22 | 2019-08-22 | 261854 | 261854 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-04-26 | 2018-04-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.02.02 | Shutter Development | 0 | 0 | 0 | 261854 | 261854 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | B1 Procurement Commitment (C5.1) |  | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 5% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Shutter Development (TEC) | [6 empty] | Shutter Prod Sprt
FALSE |  | SR333330 | COMP: Fallout sensor testing | LSST Forecast - B57 - B1 | 0 | 0 | 2018-02-28 | 2018-02-28 | 0 | 2018-02-28 | 2018-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-07-05 | 2018-07-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Catalog Listing or Industrial Construction Databases |  |  |  | Bill Wahl |  |  | Level 4 Milestone | Testing/Integration | [6 empty] | e2v | Science Sensors Acceptance (TEC) | [6 empty] | Science Sensors Acceptance | [6 empty] | Lot 3 Primary Vendor |  | Science Sensors
FALSE |  | SR341055 | Backside Processing (Batch 29) - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 26 | 0 | 2018-02-28 | 2018-03-15 | 0 | 2018-02-28 | 2018-03-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-03-01 | 2018-04-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 26 | 11 |  | Complete | 100% | 211 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 211 | 211 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | CRYO73042 | Prep for Manufacturing Readiness Review - Hx Chile | LSST Forecast - B57 - B1 | 20 | 0 | 2018-03-12 | 2018-04-25 | 0 | 2018-03-12 | 2018-04-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-17 | 2019-06-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-04-11 | 2018-05-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 32 |  | Complete | 100% | 236 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.04 | Refrigeration System - Chile System (HX) | 236 | 236 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  | Percent Complete on Work Package |  | Brian J. Langton |  |  |  | Design/Engineering | [7 empty] | Refrigeration System (TEC)
FALSE |  | CCS250040 | Test complete BOT system under eTraveler control - BOT HCU | LSST Forecast - B57 - B1 | 12 | 0 | 2018-03-16 | 2018-06-15 | 0 | 2018-03-16 | 2018-06-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-04-17 | 2018-05-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 12 | 64 |  | Complete | 100% | 300 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.08.02 | BOT HCU | 300 | 300 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Expert Opinion (Engineering Allowance) | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 6% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | CCS HCU (TEC) | [6 empty] | Camera I&T Hardware Control Unit
FALSE |  | ITC33590 | Final Testing - Gantry | LSST Forecast - B57 - B1 | 11 | 0 | 2018-03-19 | 2018-04-25 | 0 | 2018-03-19 | 2018-04-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-05-02 | 2018-05-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 8 | 0 | 8 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 4 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 11 | 27 |  | Complete | 100% | 248 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.01 | Integration Gantry | 248 | 248 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat I&T (TEC)
FALSE |  | OP531260 | Procure L2 Coating | LSST Forecast - B57 - B1 | 25 | 0 | 2018-03-27 | 2018-06-15 | 0 | 2018-03-27 | 2018-06-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-03 | 2019-09-03 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2018-04-02 | 2018-05-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 4 | 0 | 0 | 1 | 3 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 57 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment |  | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 0% |  | Procurement | [7 empty] | L1-L2 Assembly (TEC) | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly) |  |  |  | L1-L2 Optics
FALSE |  | CBM46500 | Test Shutter Proto--Mech, Light, Env, Life (Shutter Proto) | LSST Forecast - B57 - B1 | 8 | 0 | 2018-03-28 | 2018-10-15 | 0 | 2018-03-28 | 2018-10-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-06 | 2019-08-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-04-27 | 2018-05-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 4 | 2 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 8 | 140 |  | Complete | 100% | 360 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.02.02 | Shutter Development | 360 | 360 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 5% |  | Engineering Test/Validation |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Shutter Development (TEC) | [6 empty] | Shutter Prototype
FALSE |  | CR241360 | AVAIL: WEB Ready for Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2018-03-30 | 2018-03-30 | 0 | 2018-03-30 | 2018-03-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2018-04-02 | 2018-04-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.01 | Wavefront Electronics Board (WEB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 5 Milestone | Testing/Integration | [8 empty] | WEB
FALSE |  | CR242640 | AVAIL: GEB Ready for Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2018-03-30 | 2018-03-30 | 0 | 2018-03-30 | 2018-03-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2018-04-02 | 2018-04-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.04.02 | Guider Electronics Board (GEB) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 5 Milestone | Testing/Integration | [8 empty] | GEB
FALSE |  | ITC25860 | NEED: CCS Suite 10 (+HCU) | LSST Forecast - B57 - B1 | 0 | 0 | 2018-03-30 | 2018-03-30 | 0 | 2018-03-30 | 2018-03-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-12-03 | 2018-12-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.02.01 | Bench For Optical Testing (BOT) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | DAQ345280 | COMP: SATA Firmware | LSST Forecast - B57 - B1 | 0 | 0 | 2018-03-30 | 2018-03-30 | 0 | 2018-03-30 | 2018-03-30 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2018-04-02 | 2018-04-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.12 | Storage Array Software (SAS/SAC) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer |  |  | Level 4 Milestone | Testing/Integration
FALSE |  | CRYO25400 | COMP: Design and Documentation - Evaporable Getter Pump | LSST Forecast - B57 - B1 | 0 | 0 | 2018-04-02 | 2018-04-02 | 0 | 2018-04-02 | 2018-04-02 | 0 | 2019-06-01 | 2019-06-01 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-06-06 | 2018-06-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.02 | Getter Pumps | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Design/Engineering
FALSE |  | DAQ900260 | Fabricate Prototype flash (100) | LSST Forecast - B57 - B1 | 30 | 0 | 2018-04-02 | 2018-05-15 | 0 | 2018-04-02 | 2018-05-15 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-05-01 | 2018-06-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 31 |  | Complete | 100% | 8 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.13.09 | DAQ Assembled Hardware | 8 | 8 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Engineering Test/Validation | [7 empty] | DAQ Readout Systems (TEC)
FALSE |  | SR550991 | RTM13_RSA Construction at TS4 | LSST Forecast - B57 - B1 | 6 | 0 | 2018-04-02 | 2018-04-09 | 0 | 2018-04-02 | 2018-04-09 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-05-01 | 2018-05-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 6 | 5 |  | Complete | 100% | 44 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 44 | 44 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #13 |  | Science Raft System
FALSE |  | SR330845_4 | RCV: 4th Set Sensor Delivery - V1 Prod Lot 2 (Sensor 84) | LSST Forecast - B57 - B1 | 23 | 0 | 2018-04-02 | 2018-04-30 | 0 | 2018-04-02 | 2018-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 61335.6 | 61335.6 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2018-05-01 | 2018-06-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 7 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 23 | 20 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 61335.6 | 61335.6 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | CCS300012 | CCS Testing with External Power Supplies | LSST Forecast - B57 - B1 | 20 | 0 | 2018-04-02 | 2018-06-26 | 0 | 2018-04-02 | 2018-06-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-05-01 | 2018-05-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 60 |  | Complete | 100% | 180 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.08.03 | CCOB HCU | 180 | 180 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | CCS HCU (TEC)
FALSE |  | SR333515 | Batch Sensor Testing (RTM #14) | LSST Forecast - B57 - B1 | 18 | 0 | 2018-04-10 | 2018-05-09 | 0 | 2018-04-10 | 2018-05-09 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2018-05-01 | 2018-05-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 3 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 8 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 18 | 21 |  | Complete | 100% | 83 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 83 | 83 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | CR231060 | CRSA#1 Guide Sensor #1 - pin locating fixture installation | LSST Forecast - B57 - B1 | 0 | 0 | 2018-04-13 | 2018-04-13 | 0 | 2018-04-13 | 2018-04-13 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-04-13 | 2018-04-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 8 | 0 | 8 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 0 | 1 |  | Complete | 100% | 4 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.03.01 | Corner Raft Sensor Assembly (CRSA) | 4 | 4 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.45) Task/item is a conceptual design and/or advances the state of the art | 0% |  | Testing/Integration |  | Other (specify) | [5 empty] | Corner Raft Sensor Assembly (CRSA) (TEC) | CRSA Integration (Guide/Wavefront Sensors) | [5 empty] | Corner Raft Sensor Assembly (CRSA)
FALSE |  | CR222040 | CRTM#1 - In-House Assembly - Corner raft tower | LSST Forecast - B57 - B1 | 10 | 0 | 2018-04-23 | 2018-05-16 | 0 | 2018-04-23 | 2018-05-16 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-05-22 | 2018-06-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 7 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 17 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.45) Task/item is a conceptual design and/or advances the state of the art | 0% |  | Testing/Integration |  | Other (specify) | [5 empty] | Corner Raft Tower Module (CRTM) (TEC) | CRTM Assy CRT | [5 empty] | Corner Raft Tower Module (CRTM)
FALSE |  | SR554200 | COMP: ITL Flex Cables | LSST Forecast - B57 - B1 | 0 | 0 | 2018-04-25 | 2018-04-25 | 0 | 2018-04-25 | 2018-04-25 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-05-01 | 2018-05-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% | Level 4 Milestone | Procurement |  |  | Subcontractor | [20 empty] | Science Sensors
FALSE |  | DAQ900560 | Integrate DAQ V3.0 (SAS, FPA/SSD-RTM) | LSST Forecast - B57 - B1 | 10 | 0 | 2018-05-01 | 2018-05-01 | 0 | 2018-05-01 | 2018-05-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-25 | 2019-07-25 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Normal | FALSE | 2018-12-07 | 2018-12-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 0 |  | Complete | 100% | 72 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.13.05 | DAQ Version 3.0 | 72 | 72 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Testing/Integration | [7 empty] | DAQ Readout Systems (TEC)
FALSE |  | DAQ900580 | Integrate DAQ V4.0 (SAS, FPA/SSD-RTM) | LSST Forecast - B57 - B1 | 20 | 0 | 2018-05-01 | 2018-05-01 | 0 | 2018-05-01 | 2018-05-01 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-05-01 | 2019-05-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.13.06 | DAQ Version 4.0 | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Testing/Integration | [7 empty] | DAQ Readout Systems (TEC)
FALSE |  | DAQ900680 | Integrate & Test DAQ V5.0 | LSST Forecast - B57 - B1 | 55 | 0 | 2018-05-01 | 2018-05-01 | 0 | 2018-05-01 | 2018-05-01 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-13 | 2019-08-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 55 | 0 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.13.07 | DAQ Version 5.0 | 80 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Testing/Integration | [7 empty] | DAQ Readout Systems (TEC)
FALSE |  | ITC20055 | Initial Integration - Handling Equipment | LSST Forecast - B57 - B1 | 40 | 0 | 2018-05-01 | 2018-05-31 | 0 | 2018-05-01 | 2018-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-11-28 | 2019-02-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 21 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.02 | Camera Handling Equipment | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Camera I&T (TEC)
FALSE |  | ITC20085 | Test Readiness Review - Prep - Handling Equipment | LSST Forecast - B57 - B1 | 10 | 0 | 2018-05-01 | 2018-05-31 | 0 | 2018-05-01 | 2018-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-03-08 | 2019-03-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 21 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.02 | Camera Handling Equipment | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Camera I&T (TEC)
FALSE |  | SR550871 | RTM11_RSA Construction at TS4 | LSST Forecast - B57 - B1 | 6 | 0 | 2018-05-01 | 2018-05-08 | 0 | 2018-05-01 | 2018-05-08 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-06-01 | 2018-06-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 6 | 5 |  | Complete | 100% | 44 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 44 | 44 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #11 |  | Science Raft System
FALSE |  | SR330845_5 | RCV: 5th Set Sensor Delivery - V1 Prod Lot 2 (Sensor 90) | LSST Forecast - B57 - B1 | 21 | 0 | 2018-05-04 | 2018-06-04 | 0 | 2018-05-04 | 2018-06-04 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 30667.8 | 30667.8 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-06-04 | 2018-07-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 3 | 3 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 21 | 20 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 30667.8 | 30667.8 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC) | [15 empty] | Science Sensors
FALSE |  | ITC25910 | Test Readiness Review - Prep - BOT | LSST Forecast - B57 - B1 | 10 | 0 | 2018-05-09 | 2018-06-06 | 0 | 2018-05-09 | 2018-06-06 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-06-11 | 2018-06-22 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 19 |  | Complete | 100% | 50 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.02.01 | Bench For Optical Testing (BOT) | 50 | 50 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Verification Test Systems (TEC)
FALSE |  | SR550720 | SHIPPING: Ship RTM #8 to SLAC | LSST Forecast - B57 - B1 | 2 | 0 | 2018-05-10 | 2018-05-11 | 0 | 2018-05-10 | 2018-05-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-19 | 2019-07-19 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-06-12 | 2018-06-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 1 |  | Complete | 100% | 8 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 8 | 8 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration |  | Other (specify) | [5 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #8 |  | Science Raft System
FALSE |  | SR333525 | Batch Sensor Testing (RTM #15) | LSST Forecast - B57 - B1 | 17 | 0 | 2018-05-10 | 2018-05-18 | 0 | 2018-05-10 | 2018-05-18 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-07-02 | 2018-07-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 7 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 17 | 6 |  | Complete | 100% | 83 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 83 | 83 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | CBM28320 | Pack Back Flange - Camera Body | LSST Forecast - B57 - B1 | 5 | 0 | 2018-05-17 | 2018-06-22 | 0 | 2018-05-17 | 2018-06-22 | 0 | 2019-06-01 | 2019-06-01 | 2018-09-07 | 2018-09-07 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-06-19 | 2018-06-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 25 |  | Complete | 100% | 68 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.01.02 | Camera Body Development | 68 | 68 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly |  | Other (specify) | [5 empty] | Camera Body Development (TEC)
FALSE |  | SR333535 | Batch Sensor Testing (RTM #16) | LSST Forecast - B57 - B1 | 15 | 0 | 2018-05-19 | 2018-05-31 | 0 | 2018-05-19 | 2018-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-06-21 | 2018-07-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 10 | 0 | 9 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 3 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 7 |  | Complete | 100% | 83 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 83 | 83 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | OP531240 | Procure L1 Coating | LSST Forecast - B57 - B1 | 40 | 0 | 2018-05-21 | 2018-11-21 | 0 | 2018-05-21 | 2018-11-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-03 | 2019-09-03 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-07-17 | 2018-09-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 5 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 129 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment |  | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 0% |  | Procurement | [7 empty] | L1-L2 Assembly (TEC) | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly) |  |  |  | L1-L2 Optics
FALSE |  | CR222080 | CRTM#1 - Test - CRTM Performance test and optimization | LSST Forecast - B57 - B1 | 20 | 0 | 2018-05-25 | 2019-04-29 | 0 | 2018-05-25 | 2019-04-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 5 | FALSE | Normal | FALSE | 2018-07-24 | 2018-08-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 5 | 0 | 2 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 224 |  | Complete | 100% | 240 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 240 | 240 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.45) Task/item is a conceptual design and/or advances the state of the art | 0% |  | Testing/Integration |  | Other (specify) | [5 empty] | Corner Raft Tower Module (CRTM) (TEC) | CRTM Assy CRT |  |  |  |  | Critical Path to CD-2 | Corner Raft Tower Module (CRTM)
FALSE |  | ITC14080 | COMP: IR2 Services Upgrades | LSST Forecast - B57 - B1 | 0 | 0 | 2018-05-29 | 2018-05-29 | 0 | 2018-05-29 | 2018-05-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-14 | 2019-05-14 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-06-28 | 2018-06-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.03 | IR2 Facility and Operations | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Procurement |  |  | Subcontractor
FALSE |  | CRYO20900 | AVAIL: Ready for Integration - Cryo & Cold Plate | LSST Forecast - B57 - B1 | 0 | 0 | 2018-05-31 | 2018-05-31 | 0 | 2018-05-31 | 2018-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | FALSE | 2018-06-13 | 2018-06-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.03 | Cryo and Cold Plates | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 5 Milestone | Fabrication/Assembly
FALSE |  | SR550274_3 | RTM1_Prepare for Shipment | LSST Forecast - B57 - B1 | 15 | 0 | 2018-05-31 | 2018-06-19 | 0 | 2018-05-31 | 2018-06-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-18 | 2019-09-18 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-06-01 | 2018-06-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 13 |  | Complete | 100% | 45 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 45 | 45 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #1 (First Article) |  | Science Raft System
FALSE |  | DAQ331400 | Procurement Process - Production Parts - SSD-RTM | LSST Forecast - B57 - B1 | 10 | 0 | 2018-06-01 | 2018-06-08 | 0 | 2018-06-01 | 2018-06-08 | 0 | 2019-06-01 | 2019-06-01 | 2020-05-26 | 2020-05-26 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-07-02 | 2018-07-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 5 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.05 | SSD-RTM (Rear Transistion Module, incl Drives) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [7 empty] | ICD's for Phase 3 |  |  |  |  | DAQ Readout Systems
FALSE |  | SR551051 | RTM14_RSA Construction at TS4 | LSST Forecast - B57 - B1 | 5 | 0 | 2018-06-01 | 2018-06-07 | 0 | 2018-06-01 | 2018-06-07 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-07-02 | 2018-07-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 4 |  | Complete | 100% | 44 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 44 | 44 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #14 |  | Science Raft System
FALSE |  | SR341125 | COMP: Batch 32 - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 0 | 0 | 2018-06-01 | 2018-06-01 | 0 | 2018-06-01 | 2018-06-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-07-02 | 2018-07-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% | Level 4 Milestone | Procurement |  |  | Subcontractor | [20 empty] | Science Sensors
FALSE |  | SR341205 | COMP: Batch 36 - Sensor Prod Lot 2 - V2 Phase B | LSST Forecast - B57 - B1 | 0 | 0 | 2018-06-01 | 2018-06-01 | 0 | 2018-06-01 | 2018-06-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2018-07-02 | 2018-07-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% | Level 4 Milestone | Procurement |  |  | Subcontractor | [20 empty] | Science Sensors
FALSE |  | CRYO73055 | AWARD: P.O. - Heat Exchanger Cryo/Cold - Cryostat | LSST Forecast - B57 - B1 | 1 | 0 | 2018-06-01 | 2018-06-01 | 0 | 2018-06-01 | 2018-06-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-17 | 2019-06-17 | 188357 | 188357 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-07-02 | 2018-07-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.04 | Refrigeration System - Chile System (HX) | 0 | 0 | 0 | 188357 | 188357 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | B1 Procurement Commitment (C5.1) |  | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 20% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Refrigeration System (TEC)
FALSE |  | CRYO25250 | Generate Manufacturing Docs - Evaporable Getter Pump | LSST Forecast - B57 - B1 | 20 | 0 | 2018-06-04 | 2018-06-08 | 0 | 2018-06-04 | 2018-06-08 | 0 | 2019-06-01 | 2019-06-01 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-09-27 | 2018-10-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 4 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.02 | Getter Pumps | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  |  | Design/Engineering
FALSE |  | CRYO71320 | COMP: Chile System - Design and Intergration | LSST Forecast - B57 - B1 | 0 | 0 | 2018-06-04 | 2018-06-04 | 0 | 2018-06-04 | 2018-06-04 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-31 | 2019-10-31 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2018-07-03 | 2018-07-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.01 | Refrigeration System - Chile System (System Design & Integration) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Alice Callen |  |  | Level 4 Milestone | Design/Engineering
FALSE |  | ITC31752 | C_IRR--Cryostat I&T | LSST Forecast - B57 - B1 | 1 | 0 | 2018-06-06 | 2018-06-07 | 0 | 2018-06-06 | 2018-06-07 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-07-09 | 2018-07-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 8 | 0 | 8 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 1 |  | Complete | 100% | 64 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 64 | 64 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Other (specify) |  | Fabrication and Assembly |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T
FALSE |  | ITC31754 | COMP: C_IRR--Cryostat I&T | LSST Forecast - B57 - B1 | 0 | 0 | 2018-06-07 | 2018-06-07 | 0 | 2018-06-07 | 2018-06-07 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2018-08-06 | 2018-08-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 7 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Testing/Integration |  |  |  | Fabrication and Assembly | [12 empty] | Integration and Test
FALSE |  | ITC33620 | C_TRR - Test Readiness Review - Gantry | LSST Forecast - B57 - B1 | 1 | 0 | 2018-06-07 | 2018-06-07 | 0 | 2018-06-07 | 2018-06-07 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-07-09 | 2018-07-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 8 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.01 | Integration Gantry | 8 | 8 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat I&T (TEC)
FALSE |  | ITC31645 | NEED: BOT Ready for Cryostat I&T | LSST Forecast - B57 - B1 | 0 | 0 | 2018-06-08 | 2018-06-08 | 0 | 2018-06-08 | 2018-06-08 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-08-06 | 2018-08-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | OP540980 | RCV: L3 Assembly - Phase 3 (Flat Assy) | LSST Forecast - B57 - B1 | 1 | 0 | 2018-06-14 | 2018-06-14 | 0 | 2018-06-14 | 2018-06-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-14 | 2019-05-14 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-07-02 | 2018-07-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | 0-100% Method | TEC Non-ARRA | Scott Winters | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% | Level 4 Milestone | Procurement | [7 empty] | L3 Assembly (TEC)
FALSE |  | CCS126100 | Stress test and validate Purge Unit - Camera Body HCU | LSST Forecast - B57 - B1 | 15 | 0 | 2018-06-18 | 2018-09-28 | 0 | 2018-06-18 | 2018-09-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-19 | 2019-07-19 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-07-18 | 2018-08-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 72 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.07 | Camera Body HCU | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | CCS HCU (TEC) | [6 empty] | Camera I&T Hardware Control Unit
FALSE |  | OP531270_1 | L1_L2 Lens - Coating Performance Verification - Phase 2 | LSST Forecast - B57 - B1 | 40 | 0 | 2018-06-19 | 2019-01-18 | 0 | 2018-06-19 | 2019-01-18 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-05 | 2019-09-05 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-10-12 | 2018-12-10 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 146 |  | Complete | 100% | 120 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 120 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | L1-L2 Assembly (TEC)
FALSE |  | SR333545 | Batch Sensor Testing (RTM #17) | LSST Forecast - B57 - B1 | 10 | 0 | 2018-06-20 | 2018-07-06 | 0 | 2018-06-20 | 2018-07-06 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-07-03 | 2018-07-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 10 | 0 | 3 | 6 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 11 |  | Complete | 100% | 83 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 83 | 83 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | CRYO72240 | COMP: Compressors Oil Reservoirs - Cryo - Chile System (6 Unts) | LSST Forecast - B57 - B1 | 0 | 0 | 2018-06-22 | 2018-06-22 | 0 | 2018-06-22 | 2018-06-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-31 | 2019-10-31 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | FALSE | 2018-11-07 | 2018-11-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.02 | Refrigeration System - Chile System (Compressor Cabinet) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Alice Callen |  |  | Level 4 Milestone | Engineering Test/Validation
FALSE |  | CRYO61406 | Move cryostat assembly to IR-2 clean room - Cryostat Assembly | LSST Forecast - B57 - B1 | 5 | 0 | 2018-06-27 | 2018-06-29 | 0 | 2018-06-27 | 2018-06-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2018-07-02 | 2018-07-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 2 | 0 | 0 | 2 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 2 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.04 | Refrigeration System - Pre IR2 (HX) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Fabrication/Assembly |  | Other (specify) | [5 empty] | Refrigeration System (TEC)
FALSE |  | ITC92300 | Final Testing (Pre-Raft) - Com Cam | LSST Forecast - B57 - B1 | 19 | 0 | 2018-06-28 | 2019-01-15 | 0 | 2018-06-28 | 2019-01-15 | 0 | 2019-06-03 | 2019-06-03 | 2019-05-31 | 2019-05-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-02-26 | 2019-03-22 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 3 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 19 | 129 |  | Complete | 100% | 304 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.06.01 | Commissioning Camera Hardware | 304 | 304 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Kevin Reil | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | R&D | [5 empty] | Commissioning Camera (TEC)
FALSE |  | CRYO61405 | NEED: Cryostat Assembly Ready for Hx Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2018-06-28 | 2018-06-28 | 0 | 2018-06-28 | 2018-06-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-07-11 | 2018-07-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.04 | Refrigeration System - Pre IR2 (HX) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 5 Milestone | Fabrication/Assembly | [16 empty] | Cryostat
FALSE |  | ITC31814 | Cryostat Prep (pre Quad Box) | LSST Forecast - B57 - B1 | 49 | 0 | 2018-07-02 | 2019-04-19 | 0 | 2018-07-02 | 2019-04-19 | 0 | 2019-06-07 | 2019-06-07 | 2019-05-14 | 2019-05-14 | 0 | 0 | 0 | 0 | 0 | 1 | TRUE | Normal | FALSE | 2018-08-01 | 2018-10-09 |  |  |  |  | 1 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 8 | 0 | 3 | 0 | 0 | 5 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 49 | 193 |  | Complete | 100% | 216 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 216 | 216 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T
FALSE |  | SR551111 | RTM15_RSA Construction at TS4 | LSST Forecast - B57 - B1 | 10 | 0 | 2018-07-02 | 2018-07-16 | 0 | 2018-07-02 | 2018-07-16 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-08-01 | 2018-08-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 44 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 44 | 44 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #15 |  | Science Raft System
FALSE |  | CAMF669235 | Integration and Test - Carousel | LSST Forecast - B57 - B1 | 75 | 55 | 2018-07-06 | 2019-08-19 | -176 | 2018-07-06 |  | 0 | 2019-06-03 | 2019-08-19 | 2018-09-07 | 2018-11-26 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-08-01 | 2018-11-14 |  |  |  |  | 0.8 | 0 | FALSE | FALSE | None |  | None |  | 2019-08-19 |  |  |  |  | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 75 | 220 |  | InProgress | 80% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Fabrication/Assembly | [15 empty] | CP #03 (Carousel/Camera Integration)
FALSE |  | SR333555 | Batch Sensor Testing (RTM #18) | LSST Forecast - B57 - B1 | 10 | 0 | 2018-07-09 | 2018-07-20 | 0 | 2018-07-09 | 2018-07-20 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-08-07 | 2018-08-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 83 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 83 | 83 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | CBM48575 | Detail Config Assy Drawings - Shutter | LSST Forecast - B57 - B1 | 17 | 0 | 2018-07-10 | 2018-09-28 | 0 | 2018-07-10 | 2018-09-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-06 | 2019-08-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-08-22 | 2018-09-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 17 | 57 |  | Complete | 100% | 112 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.02.02 | Shutter Development | 112 | 112 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Shutter Development (TEC) | [6 empty] | Shutter Prod Sprt
FALSE |  | SR339525 | RCV: 2nd Set Sensor Delivery - V1 Prod Lot 3 (Sensor 102) | LSST Forecast - B57 - B1 | 19 | 0 | 2018-07-10 | 2018-08-28 | 0 | 2018-07-10 | 2018-08-28 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 51937 | 51937 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-09-04 | 2018-09-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 1 | 0 | 0 | 5 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 19 | 35 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 51937 | 51937 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC)
FALSE |  | ITC31813 | START: Engineering Raft Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2018-07-11 | 2018-07-11 | 0 | 2018-07-11 | 2018-07-11 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-14 | 2019-05-14 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2018-08-01 | 2018-08-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Testing/Integration
FALSE |  | SR333565 | Batch Sensor Testing (RTM #19) | LSST Forecast - B57 - B1 | 10 | 0 | 2018-07-12 | 2018-07-25 | 0 | 2018-07-12 | 2018-07-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-08-10 | 2018-08-23 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 103 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 103 | 103 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | SR551231 | RTM17_RSA Construction at TS4 | LSST Forecast - B57 - B1 | 8 | 0 | 2018-08-01 | 2018-08-10 | 0 | 2018-08-01 | 2018-08-10 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-09-04 | 2018-09-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 8 | 7 |  | Complete | 100% | 44 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 44 | 44 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #17 |  | Science Raft System
FALSE |  | CAMM6900 | COMP: Utilities & Services ICD Phase 3 (LSE-64) | LSST Forecast - B57 - B1 | 0 | 0 | 2018-08-01 | 2018-08-01 | 0 | 2018-08-01 | 2018-08-01 | 0 | 2019-06-01 | 2019-06-01 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2018-08-01 | 2018-08-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 24 | 0 | 24 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.03 | NSF Interface Milestone (NSF Needs) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration | [9 empty] | ICD's for Phase 3
FALSE |  | CAMM6930 | COMP: Mechanical & Thermal ICD Phase 3 (LSE-80) | LSST Forecast - B57 - B1 | 0 | 0 | 2018-08-01 | 2018-08-01 | 0 | 2018-08-01 | 2018-08-01 | 0 | 2019-06-01 | 2019-06-01 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-08-01 | 2018-08-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 9 | 0 | 9 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.03 | NSF Interface Milestone (NSF Needs) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration | [9 empty] | ICD's for Phase 3
FALSE |  | CAMM6935 | COMP: Camera to Telescope Interface Drawing ICD Phase 3 (LSE-18) | LSST Forecast - B57 - B1 | 0 | 0 | 2018-08-01 | 2018-08-01 | 0 | 2018-08-01 | 2018-08-01 | 0 | 2019-06-01 | 2019-06-01 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-08-01 | 2018-08-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 9 | 0 | 9 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.03 | NSF Interface Milestone (NSF Needs) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration | [9 empty] | ICD's for Phase 3
FALSE |  | CAMM6345 | AVAIL: Finish testing of targeted components for refrigerator uttilities | LSST Forecast - B57 - B1 | 0 | 0 | 2018-08-01 | 2018-08-01 | 0 | 2018-08-01 | 2018-08-01 | 0 | 2019-06-01 | 2019-06-01 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-08-01 | 2018-08-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.03 | NSF Interface Milestone (NSF Needs) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration
FALSE |  | CAMM6335 | AVAIL: Finish large scale refrigeration prototype (Ops & Maint) | LSST Forecast - B57 - B1 | 0 | 0 | 2018-08-01 | 2018-08-01 | 0 | 2018-08-01 | 2018-08-01 | 0 | 2019-06-01 | 2019-06-01 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-08-01 | 2018-08-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.03 | NSF Interface Milestone (NSF Needs) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration
FALSE |  | CAMM6355 | AVAIL: Final on-telescope electrical power budget | LSST Forecast - B57 - B1 | 0 | 0 | 2018-08-01 | 2018-08-01 | 0 | 2018-08-01 | 2018-08-01 | 0 | 2019-06-01 | 2019-06-01 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-08-01 | 2018-08-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 8 | 0 | 8 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.03 | NSF Interface Milestone (NSF Needs) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration
FALSE |  | CAMM6365 | AVAIL: Final glycol budget | LSST Forecast - B57 - B1 | 0 | 0 | 2018-08-01 | 2018-08-01 | 0 | 2018-08-01 | 2018-08-01 | 0 | 2019-06-01 | 2019-06-01 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-08-01 | 2018-08-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.03 | NSF Interface Milestone (NSF Needs) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration
FALSE |  | SR339555 | RCV: 3rd Set Sensor Delivery - V1 Prod Lot 3 (Sensor 108) | LSST Forecast - B57 - B1 | 23 | 0 | 2018-08-03 | 2018-08-28 | 0 | 2018-08-03 | 2018-08-28 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 51937 | 51937 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-10-01 | 2018-10-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 23 | 17 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 51937 | 51937 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC)
FALSE |  | DAQ334600 | Procurement Process - Production Parts - ATCA Shelves | LSST Forecast - B57 - B1 | 10 | 0 | 2018-08-20 | 2018-08-27 | 0 | 2018-08-20 | 2018-08-27 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-24 | 2019-05-24 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-09-04 | 2018-09-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 5 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.06 | ATCA Shelves | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [7 empty] | ICD's for Phase 3 |  |  |  |  | DAQ Readout Systems
FALSE |  | CRYO61563 | Populate IR2 Compressor Cabinets | LSST Forecast - B57 - B1 | 15 | 0 | 2018-08-24 | 2019-03-29 | 0 | 2018-08-24 | 2019-03-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-09-27 | 2018-10-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 9 | 0 | 5 | 0 | 0 | 4 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 140 |  | Complete | 100% | 838 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.02 | Refrigeration System - Pre IR2 (Compressor Cabinet) | 838 | 838 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  | Percent Complete on Work Package |  | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | SR333575 | Batch Sensor Testing (RTM #20) | LSST Forecast - B57 - B1 | 15 | 0 | 2018-08-28 | 2018-09-24 | 0 | 2018-08-28 | 2018-09-24 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-09-04 | 2018-09-24 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 9 | 0 | 9 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 18 |  | Complete | 100% | 83 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 83 | 83 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | SR337410 | COMP: Sensor Production - Long Lead V2 for Phase C | LSST Forecast - B57 - B1 | 0 | 0 | 2018-08-31 | 2018-08-31 | 0 | 2018-08-31 | 2018-08-31 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-09-04 | 2018-09-04 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% | Level 4 Milestone | Procurement | [23 empty] | Science Sensors
FALSE |  | AE100480 | Prep for C_FDR - Auxiliary Electronics | LSST Forecast - B57 - B1 | 40 | 0 | 2018-09-03 | 2018-09-21 | 0 | 2018-09-03 | 2018-09-21 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-10-01 | 2018-11-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 13 |  | Complete | 100% | 20 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.01 | Aux Electronics Integration & Management | 20 | 20 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Gunther Haller | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Aux Elec Integration & Management (TEC) | Management | [5 empty] | Corner Raft System Integration and Management
FALSE |  | SR339615 | RCV: 5th Set Sensor Delivery - V1 Prod Lot 3 (Sensor 120) | LSST Forecast - B57 - B1 | 20 | 0 | 2018-09-03 | 2018-11-07 | 0 | 2018-09-03 | 2018-11-07 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 51937 | 51937 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-11-01 | 2018-11-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 13 | 0 | 8 | 5 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 46 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.02 | Science Sensors Procurement | 0 | 0 | 0 | 51937 | 51937 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 20% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Science Sensors Procurement (TEC)
FALSE |  | SR551351 | RTM19_RSA Construction at TS4 | LSST Forecast - B57 - B1 | 5 | 0 | 2018-09-04 | 2018-09-10 | 0 | 2018-09-04 | 2018-09-10 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-10-01 | 2018-10-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 4 |  | Complete | 100% | 44 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 44 | 44 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #19 |  | Science Raft System
FALSE |  | SR333585 | Batch Sensor Testing (RTM #21) | LSST Forecast - B57 - B1 | 17 | 0 | 2018-09-04 | 2018-09-26 | 0 | 2018-09-04 | 2018-09-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-10-01 | 2018-10-23 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 17 | 16 |  | Complete | 100% | 103 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 103 | 103 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | SR551080 | SHIPPING: Ship RTM #14 to SLAC | LSST Forecast - B57 - B1 | 2 | 0 | 2018-09-13 | 2018-09-14 | 0 | 2018-09-13 | 2018-09-14 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2018-10-10 | 2018-10-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 1 |  | Complete | 100% | 8 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 8 | 8 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration |  | Other (specify) | [5 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #14 |  | Science Raft System
FALSE |  | SR551200 | SHIPPING: Ship RTM #16 to SLAC | LSST Forecast - B57 - B1 | 2 | 0 | 2018-09-13 | 2018-09-14 | 0 | 2018-09-13 | 2018-09-14 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-10-10 | 2018-10-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 1 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 1 |  | Complete | 100% | 8 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 8 | 8 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration |  | Other (specify) | [5 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #16 |  | Science Raft System
FALSE |  | CCS300025 | AVAIL: Support for 2 rafts on focal plane in IR2 | LSST Forecast - B57 - B1 | 0 | 0 | 2018-09-14 | 2018-09-14 | 0 | 2018-09-14 | 2018-09-14 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2018-09-14 | 2018-09-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.08.03 | CCOB HCU | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  | Level 5 Milestone | Design/Engineering
FALSE |  | CRYO31700 | Write Test and Verification Reports Cryostat Backend | LSST Forecast - B57 - B1 | 6 | 0 | 2018-09-17 | 2018-10-08 | 0 | 2018-09-17 | 2018-10-08 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2018-10-01 | 2018-10-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 6 | 15 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.05.01 | Cryostat Back End | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Brian J. Langton |  |  |  | Fabrication/Assembly
FALSE |  | AE212320 | AVAIL: Populated Quad Box Assy from Aux Elec | LSST Forecast - B57 - B1 | 0 | 0 | 2018-09-21 | 2018-09-21 | 0 | 2018-09-21 | 2018-09-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-10-09 | 2018-10-09 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.02.12 | Heater Ex, UT Cooling HCU | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Auxiliary Electronics
FALSE |  | ITC19660 | Initial Integration - Integration Stand | LSST Forecast - B57 - B1 | 60 | 32 | 2018-09-24 | 2019-07-17 | 0 | 2018-09-24 |  | 0 | 2019-06-03 | 2019-07-17 | 2019-06-03 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-12-04 | 2019-03-13 |  |  |  |  | 0.8 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 165 |  | InProgress | 80% | 532 | 0 | 532 | 532 | LSST Forecast - B57 - B1.3.08.04.01 | Camera Integration Stand | 425.6 | 532 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Camera I&T (TEC) | [7 empty] | CP #04 (Integration Stand, Camera IRR/Assy)
FALSE |  | CBM46800 | COMP: Shutter Proto Testing Complete | LSST Forecast - B57 - B1 | 0 | 0 | 2018-09-28 | 2018-09-28 | 0 | 2018-09-28 | 2018-09-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-06 | 2019-08-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-10-01 | 2018-10-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.02.02 | Shutter Development | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Martin Nordby | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 5% | Level 4 Milestone | Engineering Test/Validation | [14 empty] | Cam Body/Purge Engin/Dsn
FALSE |  | AE210320 | AVAIL: Production UT AC/DC components | LSST Forecast - B57 - B1 | 0 | 0 | 2018-09-28 | 2018-09-28 | 0 | 2018-09-28 | 2018-09-28 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-11-28 | 2018-11-28 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 9 | 0 | 9 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.02.01 | AC and DC Power Distribution | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Gunther Haller |  |  | Level 5 Milestone | Fabrication/Assembly | [16 empty] | Auxiliary Electronics
FALSE |  | SR333595 | Batch Sensor Testing (RTM #22) | LSST Forecast - B57 - B1 | 19 | 0 | 2018-10-01 | 2018-10-25 | 0 | 2018-10-01 | 2018-10-25 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-11-01 | 2018-11-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 19 | 18 |  | Complete | 100% | 83 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03.02.03 | Science Sensors Acceptance | 83 | 83 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 6% |  | Testing/Integration |  | QA Inspection/Testing/Acceptance | [5 empty] | Science Sensors Acceptance (TEC) | [15 empty] | Science Sensors
FALSE |  | SR551140 | SHIPPING: Ship RTM #15 to SLAC | LSST Forecast - B57 - B1 | 2 | 0 | 2018-10-11 | 2018-10-12 | 0 | 2018-10-11 | 2018-10-12 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-11-13 | 2018-11-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 1 |  | Complete | 100% | 8 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 8 | 8 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration |  | Other (specify) | [5 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #15 |  | Science Raft System
FALSE |  | SR551320 | SHIPPING: Ship RTM #18 to SLAC | LSST Forecast - B57 - B1 | 2 | 0 | 2018-10-11 | 2018-10-12 | 0 | 2018-10-11 | 2018-10-12 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-11-13 | 2018-11-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 1 |  | Complete | 100% | 8 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 8 | 8 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration |  | Other (specify) | [5 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #18 |  | Science Raft System
FALSE |  | DAQ910060 | SCI Firmware (Finalize LAM Behavior) - GDS | LSST Forecast - B57 - B1 | 48 | 0 | 2018-10-14 | 2018-11-30 | 0 | 2018-10-14 | 2018-11-30 | 0 | 2019-06-03 | 2019-06-03 | 2020-03-30 | 2020-03-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-03-04 | 2019-05-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 48 | 32 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.15 | Guiding Data System (GDS) | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | DAQ Readout Systems (TEC)
FALSE |  | ITC31720 | NEED: UT Aux Electronics (pre-production) | LSST Forecast - B57 - B1 | 0 | 0 | 2018-10-15 | 2018-10-15 | 0 | 2018-10-15 | 2018-10-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-11-01 | 2018-11-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 11 | 0 | 11 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Auxiliary Electronics
FALSE |  | CRYO70350 | Install Long Lines, Run utilities/install mounting hardware in IR-2 | LSST Forecast - B57 - B1 | 12 | 0 | 2018-10-15 | 2018-10-30 | 0 | 2018-10-15 | 2018-10-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-11-01 | 2018-11-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 12 | 11 |  | Complete | 100% | 250 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.03 | Refrigeration System - Pre IR2 (Long Lines) | 250 | 250 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | SR551414 | RTM20_RTM Construction at TS6 | LSST Forecast - B57 - B1 | 2 | 0 | 2018-10-16 | 2018-10-31 | 0 | 2018-10-16 | 2018-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-11-09 | 2018-11-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 11 |  | Complete | 100% | 64 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 64 | 64 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #20 |  | Science Raft System
FALSE |  | CRYO61050 | Check Drawings - Evacuate, Purge & Charge HW - Refrigeration | LSST Forecast - B57 - B1 | 2 | 0 | 2018-10-22 | 2018-10-23 | 0 | 2018-10-22 | 2018-10-23 | 0 | 2019-06-03 | 2019-06-03 | 2020-06-02 | 2020-06-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-01-15 | 2019-01-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 1 |  | Complete | 100% | 53 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.05 | Refrigeration System - Chile System (Equipment & Refrigeration) | 53 | 53 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) |  | ICD's for Phase 3 |  |  |  |  | Refrigeration System
FALSE |  | OP521815 | Phase 1- r-band repeatability and Phase 1 deliverables (MS4) - Filter Coating | LSST Forecast - B57 - B1 | 10 | 0 | 2018-10-29 | 2019-02-26 | 0 | 2018-10-29 | 2019-02-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-12-12 | 2019-12-12 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-02-01 | 2019-02-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 2 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 79 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  |  | Procurement | [8 empty] | Witness Sample
FALSE |  | OP522105 | RCV: Filter First Article TWF testing data received (MS2) | LSST Forecast - B57 - B1 | 1 | 0 | 2018-10-31 | 2018-10-31 | 0 | 2018-10-31 | 2018-10-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-25 | 2019-07-25 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-11-12 | 2018-11-12 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | 0-100% Method | TEC Non-ARRA | Scott Winters |  |  | Level 4 Milestone | Procurement | [7 empty] | Filters (TEC)
FALSE |  | AE213160 | AVAIL: Production Cables/Networking | LSST Forecast - B57 - B1 | 0 | 0 | 2018-11-01 | 2018-11-01 | 0 | 2018-11-01 | 2018-11-01 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-12-03 | 2018-12-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.02.13 | Cables/Networking | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Gunther Haller |  |  | Level 5 Milestone | Fabrication/Assembly | [16 empty] | Auxiliary Electronics
FALSE |  | AE214230 | AVAIL: Production Protection PLC System Components | LSST Forecast - B57 - B1 | 0 | 0 | 2018-11-01 | 2018-11-01 | 0 | 2018-11-01 | 2018-11-01 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-12-03 | 2018-12-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.03.02.14 | Protection PLC System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Gunther Haller |  |  | Level 5 Milestone | Fabrication/Assembly | [16 empty] | Auxiliary Electronics
FALSE |  | SE221370 | Prep camera FEA model for export to Obs; deliver and run verification checks | LSST Forecast - B57 - B1 | 40 | 0 | 2018-11-01 | 2018-11-30 | 0 | 2018-11-01 | 2018-11-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-13 | 2019-06-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-12-03 | 2019-02-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 19 |  | Complete | 100% | 20 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.01 | Structural System Analysis | 20 | 20 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | CAMF703000 | Clean - Production Units - Filter Blocks | LSST Forecast - B57 - B1 | 29 | 0 | 2018-11-01 | 2018-12-13 | 0 | 2018-11-01 | 2018-12-13 | 0 | 2019-06-01 | 2019-06-01 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2018-12-03 | 2019-01-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 29 | 28 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.02 | Filter Loader | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Fabrication/Assembly
FALSE |  | ITC31727 | NEED: All DAQ OTM's | LSST Forecast - B57 - B1 | 0 | 0 | 2018-11-02 | 2018-11-02 | 0 | 2018-11-02 | 2018-11-02 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-12-03 | 2018-12-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Auxiliary Electronics
FALSE |  | CRYO61334 | Move Compressor Cabinets to IR2 | LSST Forecast - B57 - B1 | 5 | 0 | 2018-11-08 | 2019-03-29 | 0 | 2018-11-08 | 2019-03-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-01-07 | 2019-01-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 87 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.02 | Refrigeration System - IR2 | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  | Percent Complete on Work Package |  | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | SR300150 | COMP: Sensor Production Complete | LSST Forecast - B57 - B1 | 0 | 0 | 2018-11-16 | 2018-11-16 | 0 | 2018-11-16 | 2018-11-16 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2018-12-03 | 2018-12-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 18 | 0 | 18 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03 | Science Sensors | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Bill Wahl |  |  | Level 3 Milestone | Management/Administration | [21 empty] | Milestones |  | Science Sensors
FALSE |  | OP541640 | Procure L3 Lens Coating | LSST Forecast - B57 - B1 | 59 | 0 | 2018-12-03 | 2019-02-22 | 0 | 2018-12-03 | 2019-02-22 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-01-02 | 2019-03-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 59 | 54 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement | [8 empty] | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly) |  |  |  | L1-L2 Optics
FALSE |  | CRYO646030 | Assemble, Braze, Solder Ceramic Break Assemblies - 2 Cold | LSST Forecast - B57 - B1 | 0 | 0 | 2018-12-03 | 2018-12-21 | 0 | 2018-12-03 | 2018-12-21 | 0 | 2019-06-01 | 2019-06-01 | 2018-12-13 | 2018-12-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2019-01-07 | 2019-01-07 |  |  |  |  | 1 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 0 | 14 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.04.01 | 2 Cryo/2 Cold HeX Vacuum Vessel Intgr | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys
FALSE |  | OP531310 | Pre-Bonded L1 Lens TWE Test Complete - L1-L2 Assembly - Phase 4b | LSST Forecast - B57 - B1 | 20 | 0 | 2018-12-19 | 2018-12-19 | 0 | 2018-12-19 | 2018-12-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-03 | 2019-09-03 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-01-02 | 2019-01-30 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Scott Winters | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor | [5 empty] | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly) |  |  |  | L1-L2 Opto-Mechanics
FALSE |  | OP541140 | COMP: L3 Assembly - Lens Ready for Coating | LSST Forecast - B57 - B1 | 0 | 0 | 2018-12-21 | 2018-12-21 | 0 | 2018-12-21 | 2018-12-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-04-02 | 2019-04-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2019-01-02 | 2019-01-02 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  | Level 4 Milestone | Procurement
FALSE |  | OP522115 | RCV: All Phase 1 deliverables received (MS3) - Filter First Article fabrication | LSST Forecast - B57 - B1 | 1 | 0 | 2018-12-21 | 2018-12-21 | 0 | 2018-12-21 | 2018-12-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-25 | 2019-07-25 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2019-01-22 | 2019-01-22 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | 0-100% Method | TEC Non-ARRA | Scott Winters |  |  | Level 4 Milestone | Procurement | [7 empty] | Filters (TEC)

## 2019 Details
Fuse® Analyst Report
Workbook: Workbook1 - 8168 Activities
Schedule Quality
Created on: 8/5/2019
Created by: brackett
2019: Detailed View | 2019: Detailed View | 2019: Detailed View | 2019: Detailed View | 2019: Detailed View | 2019: Detailed View
Missing Logic
Total number of activities that are missing a predecessor, a successor, or both. This number should not exceed 5%.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | Previous Start | Previous Finish | Percent Complete | Previous Remaining Duration | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | IsLevelOfEffort | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | Global_Basis of Estimate | Global_Cobra Cost Class | Cobra PMT (EV Method)_Global | Global_Color of Money | Global_Control Account Manager | Global_Design Maturity | Global_Judgement Factor | Global_Milestone Levels | Global_Project Phase | Global_Funding Source | Global_EDIA Survey | Global_MS Type | Phase | NSF Milestones | Loading Curve | Sensor Vendor | LSST_CA | Summary Schedule | ICD for NSF Input | LSST Camera Critical Paths | CD2 Budget Changes | DOE Reviews | Critical Path (CD Reviews) | LSST WP Summary | Critical Path (Camera Delivery) | AWARD / NEED Sub-System | Final Design Key Links | CP - CAMM2100 | CP - CAMM2130 | CP - CAMM2160 | BNL Work Org | Last ETC Update | BNL WBS | LSST Story List | Sum Sch 01 (Camera) | Sum Sch 02 (IT w/Needs) | Sum Sch 03 (Sensors_RTM_IT) | LSST Raft Particulate Mitigation | LSST RTM
FALSE |  | CAMF669240 | Remove Carousel Proto & 1st Dummy Back Flange - Carousel | LSST Forecast - B57 - B1 | 5 | 0 | 2019-01-07 | 2019-01-14 | 0 | 2019-01-07 | 2019-01-14 | 0 | 2019-06-01 | 2019-06-01 | 2018-10-24 | 2018-10-24 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-02-07 | 2019-02-13 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 5 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Fabrication/Assembly
FALSE |  | CAMC8000 | COMP: Partial Camera Image data for Data Management | LSST Forecast - B57 - B1 | 0 | 0 | 2019-10-11 | 2019-10-11 | 595 |  |  | 343 | 2019-10-11 | 2019-10-11 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 0 | FALSE | Finish Milestone | FALSE | 2019-10-11 | 2019-10-11 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01 | Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 3 Milestone | Management/Administration |  |  |  |  | Partial Camera Image Data for DM
Critical
Number of critical activities
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | Previous Start | Previous Finish | Percent Complete | Previous Remaining Duration | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | IsLevelOfEffort | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | Global_Basis of Estimate | Global_Cobra Cost Class | Cobra PMT (EV Method)_Global | Global_Color of Money | Global_Control Account Manager | Global_Design Maturity | Global_Judgement Factor | Global_Milestone Levels | Global_Project Phase | Global_Funding Source | Global_EDIA Survey | Global_MS Type | Phase | NSF Milestones | Loading Curve | Sensor Vendor | LSST_CA | Summary Schedule | ICD for NSF Input | LSST Camera Critical Paths | CD2 Budget Changes | DOE Reviews | Critical Path (CD Reviews) | LSST WP Summary | Critical Path (Camera Delivery) | AWARD / NEED Sub-System | Final Design Key Links | CP - CAMM2100 | CP - CAMM2130 | CP - CAMM2160 | BNL Work Org | Last ETC Update | BNL WBS | LSST Story List | Sum Sch 01 (Camera) | Sum Sch 02 (IT w/Needs) | Sum Sch 03 (Sensors_RTM_IT) | LSST Raft Particulate Mitigation | LSST RTM
FALSE |  | CRYO70165 | Final Assy & Test - Cold System Verification Test | LSST Forecast - B57 - B1 | 40 | 5 | 2018-05-01 | 2019-06-07 | -18 | 2018-05-01 |  | 0 | 2019-06-03 | 2019-06-07 | 2019-05-07 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | TRUE | 2018-06-01 | 2018-07-27 |  |  |  |  | 0.8 | 0 | FALSE | TRUE | None |  | None |  | 2019-06-07 |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 266 |  | InProgress | 80% | 260 | 0 | 260 | 260 | LSST Forecast - B57 - B1.3.06.04.06.02 | Refrigeration System - IR2 | 208 | 260 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) | [6 empty] | Utility Trunk | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC31820 | ETU EO/BOT Testing | LSST Forecast - B57 - B1 | 10 | 5 | 2019-04-01 | 2019-06-07 | -18 | 2019-04-01 |  | 0 | 2019-06-03 | 2019-06-07 | 2019-05-07 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2019-05-01 | 2019-05-14 |  |  |  |  | 0.5 | 0 | FALSE | TRUE | None |  | None |  | 2019-06-07 |  |  |  |  | 2 | 0 | 1 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 44 |  | InProgress | 50% | 281 | 0 | 281 | 281 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 140.5 | 281 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | CRYO646240 | Test Individual Circuits - 4 Cryo (15 d) | LSST Forecast - B57 - B1 | 13 | 5 | 2019-05-12 | 2019-06-07 | -113 | 2019-05-12 |  | 0 | 2019-06-03 | 2019-06-07 | 2018-12-07 | 2018-12-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2019-06-03 | 2019-06-19 |  |  |  |  | 0.5 | 0 | FALSE | TRUE | None |  | None |  | 2019-06-07 |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 13 | 14 |  | InProgress | 50% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.04.03 | 4 Cryo Heat Ex | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | [24 empty] | CP #01 (Cryostat/Camera Integration)
FALSE |  | CRYO70185 | Analyze Data - Cold System Verification Test | LSST Forecast - B57 - B1 | 8 | 5 | 2019-05-20 | 2019-06-07 | -18 | 2019-05-20 |  | 0 | 2019-06-03 | 2019-06-07 | 2019-05-07 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-06-10 | 2019-06-19 |  |  |  |  | 0.5 | 0 | FALSE | TRUE | None |  | None |  | 2019-06-07 |  |  |  |  | 3 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 8 | 9 |  | InProgress | 50% | 40 | 0 | 40 | 40 | LSST Forecast - B57 - B1.3.06.04.06.02 | Refrigeration System - IR2 | 20 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) | [6 empty] | Utility Trunk
FALSE |  | CRYO02825 | COMP: Cryostat Chamber & I&T Refrigeration System Ready for Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-07 | 2019-06-07 | -113 |  |  | 0 | 2019-06-07 | 2019-06-07 | 2018-12-13 | 2018-12-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | TRUE | 2019-06-07 | 2019-06-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04 | Cryostat | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 3 Milestone | Management/Administration
FALSE |  | CRYO70205 | COMP: Cold System Verification Test | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-07 | 2019-06-07 | -18 |  |  | 0 | 2019-06-07 | 2019-06-07 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2019-06-07 | 2019-06-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.02 | Refrigeration System - IR2 | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% | Level 4 Milestone | Design/Engineering
FALSE |  | CRYO61685_1 | AVAIL: Cryostat Assembly with Refrigeration for Integration (4 Cryo) | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-07 | 2019-06-07 | -18 |  |  | 0 | 2019-06-07 | 2019-06-07 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2019-06-07 | 2019-06-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.02 | Refrigeration System - IR2 | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 5 Milestone | Fabrication/Assembly | [16 empty] | Cryostat
FALSE |  | ITC31835 | NEED: Completion of Run Single-Circuit Cryo/Cold System Tests (4 Cryo) | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-07 | 2019-06-07 | -18 |  |  | 0 | 2019-06-07 | 2019-06-07 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | TRUE | 2019-06-07 | 2019-06-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Fabrication and Assembly | [12 empty] | Integration and Test
FALSE |  | CRYO646250 | AVAIL: Cryostat Assembly with Refrigeration for Integration (4 Cryo) | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-07 | 2019-06-07 | -113 |  |  | 0 | 2019-06-07 | 2019-06-07 | 2018-12-13 | 2018-12-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | TRUE | 2019-06-07 | 2019-06-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.04.03 | 4 Cryo Heat Ex | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | [7 empty] | Level 5 Milestone
FALSE |  | ITC31820_1 | ETU De-integration | LSST Forecast - B57 - B1 | 12 | 12 | 2019-06-10 | 2019-06-25 | -18 |  |  | 0 | 2019-06-10 | 2019-06-25 | 2019-05-14 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2019-06-10 | 2019-06-25 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 12 | 0 |  | Planned | 0% | 238 | 0 | 238 | 238 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC00290 | START: Science Raft Tower Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-25 | 2019-06-25 | -18 |  |  | 0 | 2019-06-25 | 2019-06-25 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2019-06-25 | 2019-06-25 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration
FALSE |  | ITC31840 | START: Science Raft Tower Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-25 | 2019-06-25 | -18 |  |  | 0 | 2019-06-25 | 2019-06-25 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | TRUE | 2019-06-25 | 2019-06-25 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 10 | 0 | 10 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [11 empty] | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC31830 | AVAIL: Eng Raft Tower from I&T for ComCam | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-25 | 2019-06-25 | -18 |  |  | 0 | 2019-06-25 | 2019-06-25 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2019-06-25 | 2019-06-25 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Fabrication/Assembly |  |  |  | Engineering | [12 empty] | Integration and Test
FALSE |  | ITC31860 | Integrate Science Raft Tower #1 of 21 | LSST Forecast - B57 - B1 | 4 | 4 | 2019-06-26 | 2019-07-01 | -18 |  |  | 0 | 2019-06-26 | 2019-07-01 | 2019-05-31 | 2019-06-05 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-06-26 | 2019-07-01 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T
FALSE |  | ITC31860_R | Integrate Science Raft Tower #1 of 21 | LSST Forecast - B57 - B1 | 4 | 4 | 2019-06-26 | 2019-07-01 | -18 |  |  | 0 | 2019-06-26 | 2019-07-01 | 2019-05-31 | 2019-06-05 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-06-26 | 2019-07-01 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 4 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 103 | 0 | 103 | 103 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Commissioning and Testing | [5 empty] | Cryostat I&T (TEC) | [7 empty] | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC31880 | Integrate Science Raft Tower #2 of 21 | LSST Forecast - B57 - B1 | 4 | 4 | 2019-07-02 | 2019-07-08 | -18 |  |  | 0 | 2019-07-02 | 2019-07-08 | 2019-06-06 | 2019-06-11 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-07-02 | 2019-07-08 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 102 | 0 | 102 | 102 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC31920 | Integrate Science Raft Tower #3 of 21 | LSST Forecast - B57 - B1 | 4 | 4 | 2019-07-09 | 2019-07-12 | -18 |  |  | 0 | 2019-07-09 | 2019-07-12 | 2019-06-12 | 2019-06-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2019-07-09 | 2019-07-12 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 104 | 0 | 104 | 104 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC31940 | Integrate Science Raft Tower #4 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-07-15 | 2019-07-16 | -18 |  |  | 0 | 2019-07-15 | 2019-07-16 | 2019-06-18 | 2019-06-19 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-07-15 | 2019-07-16 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC31960 | Integrate Science Raft Tower #5 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-07-17 | 2019-07-18 | -18 |  |  | 0 | 2019-07-17 | 2019-07-18 | 2019-06-20 | 2019-06-21 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-07-17 | 2019-07-18 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC31980 | Integrate Science Raft Tower #6 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-07-19 | 2019-07-22 | -18 |  |  | 0 | 2019-07-19 | 2019-07-22 | 2019-06-24 | 2019-06-25 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2019-07-19 | 2019-07-22 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32225 | Integrate Corner Raft Tower #1 of 4 | LSST Forecast - B57 - B1 | 4 | 4 | 2019-07-23 | 2019-07-26 | -18 |  |  | 0 | 2019-07-23 | 2019-07-26 | 2019-06-26 | 2019-07-01 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-07-23 | 2019-07-26 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 119 | 0 | 119 | 119 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32230 | Integrate Corner Raft Tower #2 of 4 | LSST Forecast - B57 - B1 | 4 | 4 | 2019-07-29 | 2019-08-01 | -18 |  |  | 0 | 2019-07-29 | 2019-08-01 | 2019-07-02 | 2019-07-08 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-07-29 | 2019-08-01 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 119 | 0 | 119 | 119 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32290 | Integrate Corner Raft Tower #3 of 4 | LSST Forecast - B57 - B1 | 4 | 4 | 2019-08-02 | 2019-08-07 | -18 |  |  | 0 | 2019-08-02 | 2019-08-07 | 2019-07-09 | 2019-07-12 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-08-02 | 2019-08-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 118 | 0 | 118 | 118 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32410 | Integrate Corner Raft Tower #4 of 4 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-08-08 | 2019-08-09 | -18 |  |  | 0 | 2019-08-08 | 2019-08-09 | 2019-07-15 | 2019-07-16 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-08-08 | 2019-08-09 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 118 | 0 | 118 | 118 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32000 | Integrate Science Raft Tower #7 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-08-12 | 2019-08-13 | -18 |  |  | 0 | 2019-08-12 | 2019-08-13 | 2019-07-17 | 2019-07-18 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-08-12 | 2019-08-13 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32020 | Integrate Science Raft Tower #8 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-08-14 | 2019-08-15 | -18 |  |  | 0 | 2019-08-14 | 2019-08-15 | 2019-07-19 | 2019-07-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-08-14 | 2019-08-15 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32040 | Integrate Science Raft Tower #9 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-08-16 | 2019-08-19 | -18 |  |  | 0 | 2019-08-16 | 2019-08-19 | 2019-07-23 | 2019-07-24 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-08-16 | 2019-08-19 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32140 | BOT Testing with Raft Tower #1-9 | LSST Forecast - B57 - B1 | 38 | 38 | 2019-08-20 | 2019-10-11 | -18 |  |  | 0 | 2019-08-20 | 2019-10-11 | 2019-07-25 | 2019-09-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2019-08-20 | 2019-10-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 38 | 0 |  | Planned | 0% | 517 | 0 | 517 | 517 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | CAMM6190 | DECISION: Spares for L1, L2 | LSST Forecast - B57 - B1 | 0 | 0 | 2019-09-18 | 2019-09-18 | 252 |  |  | 0 | 2019-09-18 | 2019-09-18 | 2020-09-29 | 2020-09-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2019-09-18 | 2019-09-18 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 360 | 360 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.05 | Upscope/Descope Decision Points | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration
FALSE |  | ITC00300 | COMP: Integration of 9 SR into Cryostat | LSST Forecast - B57 - B1 | 0 | 0 | 2019-10-11 | 2019-10-11 | -18 |  |  | 0 | 2019-10-11 | 2019-10-11 | 2019-09-17 | 2019-09-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2019-10-11 | 2019-10-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration
FALSE |  | ITC32160 | COMP: Integration of 9 SR into Cryostat | LSST Forecast - B57 - B1 | 0 | 0 | 2019-10-11 | 2019-10-11 | -18 |  |  | 0 | 2019-10-11 | 2019-10-11 | 2019-09-17 | 2019-09-17 | 0 | 0 | 0 | 0 | 0 | 6 | FALSE | Finish Milestone | TRUE | 2019-10-11 | 2019-10-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Testing/Integration
FALSE |  | ITC32180 | Integrate Science Raft Tower #10 of 21 | LSST Forecast - B57 - B1 | 6 | 6 | 2019-10-14 | 2019-10-21 | -18 |  |  | 0 | 2019-10-14 | 2019-10-21 | 2019-09-18 | 2019-09-25 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-10-14 | 2019-10-21 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 6 | 0 |  | Planned | 0% | 147 | 0 | 147 | 147 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing | [5 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32200 | Integrate Science Raft Tower #11 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-10-22 | 2019-10-23 | -18 |  |  | 0 | 2019-10-22 | 2019-10-23 | 2019-09-26 | 2019-09-27 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-10-22 | 2019-10-23 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32220 | Integrate Science Raft Tower #12 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-10-24 | 2019-10-25 | -18 |  |  | 0 | 2019-10-24 | 2019-10-25 | 2019-09-30 | 2019-10-01 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-10-24 | 2019-10-25 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32240 | Integrate Science Raft Tower #13 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-10-28 | 2019-10-29 | -18 |  |  | 0 | 2019-10-28 | 2019-10-29 | 2019-10-02 | 2019-10-03 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-10-28 | 2019-10-29 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32260 | Integrate Science Raft Tower #14 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-10-30 | 2019-10-31 | -18 |  |  | 0 | 2019-10-30 | 2019-10-31 | 2019-10-04 | 2019-10-07 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-10-30 | 2019-10-31 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32280 | Integrate Science Raft Tower #15 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-11-01 | 2019-11-04 | -18 |  |  | 0 | 2019-11-01 | 2019-11-04 | 2019-10-08 | 2019-10-09 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-11-01 | 2019-11-04 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32300 | Integrate Science Raft Tower #16 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-11-05 | 2019-11-06 | -18 |  |  | 0 | 2019-11-05 | 2019-11-06 | 2019-10-10 | 2019-10-11 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-11-05 | 2019-11-06 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32320 | Integrate Science Raft Tower #17 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-11-07 | 2019-11-08 | -18 |  |  | 0 | 2019-11-07 | 2019-11-08 | 2019-10-14 | 2019-10-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-11-07 | 2019-11-08 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32340 | Integrate Science Raft Tower #18 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-11-11 | 2019-11-12 | -18 |  |  | 0 | 2019-11-11 | 2019-11-12 | 2019-10-16 | 2019-10-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-11-11 | 2019-11-12 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32360 | Integrate Science Raft Tower #19 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-11-13 | 2019-11-14 | -18 |  |  | 0 | 2019-11-13 | 2019-11-14 | 2019-10-18 | 2019-10-21 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-11-13 | 2019-11-14 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32380 | Integrate Science Raft Tower #20 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-11-15 | 2019-11-18 | -18 |  |  | 0 | 2019-11-15 | 2019-11-18 | 2019-10-22 | 2019-10-23 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-11-15 | 2019-11-18 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32400 | Integrate Science Raft Tower #21 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-11-19 | 2019-11-20 | -18 |  |  | 0 | 2019-11-19 | 2019-11-20 | 2019-10-24 | 2019-10-25 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-11-19 | 2019-11-20 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32420 | BOT Testing with Raft Tower #1-21+4CR | LSST Forecast - B57 - B1 | 38 | 38 | 2019-11-21 | 2020-01-30 | -18 |  |  | 0 | 2019-11-21 | 2020-01-30 | 2019-10-28 | 2019-12-20 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-11-21 | 2020-01-30 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 38 | 0 |  | Planned | 0% | 517 | 0 | 517 | 517 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC00330 | START: Integrated Cryostat Testing | LSST Forecast - B57 - B1 | 0 | 0 | 2019-11-21 | 2019-11-21 | -18 |  |  | 0 | 2019-11-21 | 2019-11-21 | 2019-10-25 | 2019-10-25 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | TRUE | 2019-11-21 | 2019-11-21 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration
FALSE |  | ITC32415 | START: Final Integrated Cryostat Testing | LSST Forecast - B57 - B1 | 0 | 0 | 2019-11-21 | 2019-11-21 | -18 |  |  | 0 | 2019-11-21 | 2019-11-21 | 2019-10-25 | 2019-10-25 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Start Milestone | TRUE | 2019-11-21 | 2019-11-21 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Management/Administration
FALSE |  | CAMM6220 | DECISION: Spares for filters (6) | LSST Forecast - B57 - B1 | 0 | 0 | 2019-12-13 | 2019-12-13 | 252 |  |  | 0 | 2019-12-13 | 2019-12-13 | 2021-01-07 | 2021-01-07 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2019-12-13 | 2019-12-13 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 300 | 300 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.05 | Upscope/Descope Decision Points | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration
Negative Float
Number of activities with total finish float less than 0 working days.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | Previous Start | Previous Finish | Percent Complete | Previous Remaining Duration | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | IsLevelOfEffort | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | Global_Basis of Estimate | Global_Cobra Cost Class | Cobra PMT (EV Method)_Global | Global_Color of Money | Global_Control Account Manager | Global_Design Maturity | Global_Judgement Factor | Global_Milestone Levels | Global_Project Phase | Global_Funding Source | Global_EDIA Survey | Global_MS Type | Phase | NSF Milestones | Loading Curve | Sensor Vendor | LSST_CA | Summary Schedule | ICD for NSF Input | LSST Camera Critical Paths | CD2 Budget Changes | DOE Reviews | Critical Path (CD Reviews) | LSST WP Summary | Critical Path (Camera Delivery) | AWARD / NEED Sub-System | Final Design Key Links | CP - CAMM2100 | CP - CAMM2130 | CP - CAMM2160 | BNL Work Org | Last ETC Update | BNL WBS | LSST Story List | Sum Sch 01 (Camera) | Sum Sch 02 (IT w/Needs) | Sum Sch 03 (Sensors_RTM_IT) | LSST Raft Particulate Mitigation | LSST RTM
FALSE |  | CAMF669050 | Inspect Procured Parts - Carousel | LSST Forecast - B57 - B1 | 100 | 5 | 2018-02-01 | 2019-06-07 | -149 | 2018-02-01 |  | 0 | 2019-06-03 | 2019-06-07 | 2018-10-16 | 2018-10-22 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-03-01 | 2018-07-20 |  |  |  |  | 0.95 | 0 | FALSE | FALSE | None |  | None |  | 2019-06-07 |  |  |  |  | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 100 | 328 |  | InProgress | 95% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Fabrication/Assembly
FALSE |  | ITC92200 | Procurements - Com Cam | LSST Forecast - B57 - B1 | 59 | 10 | 2018-02-05 | 2019-06-14 | -10 | 2018-02-05 |  | 0 | 2019-06-03 | 2019-06-14 | 2019-05-17 | 2019-05-31 | 201650 | 201650 | 0 | 201650 | 201650 | 2 | FALSE | Normal | FALSE | 2018-04-11 | 2018-07-02 |  |  |  |  | 0.95 | 0 | FALSE | FALSE | None |  | None |  | 2019-06-14 |  |  |  |  | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 59 | 345 |  | InProgress | 95% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.06.01 | Commissioning Camera Hardware | 0 | 0 | 0 | 191567.5 | 201650 | 201650 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Kevin Reil | (1.00) Task/item is fully invoiced/completed | 0% |  | Engineering Test/Validation |  | R&D | [5 empty] | Commissioning Camera (TEC)
FALSE |  | CAMF669100 | Clean - Carousel | LSST Forecast - B57 - B1 | 105 | 10 | 2018-04-02 | 2019-06-14 | -149 | 2018-04-02 |  | 0 | 2019-06-03 | 2019-06-14 | 2018-10-16 | 2018-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-05-01 | 2018-09-27 |  |  |  |  | 0.9 | 0 | FALSE | FALSE | None |  | None |  | 2019-06-14 |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 105 | 287 |  | InProgress | 90% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Fabrication/Assembly
FALSE |  | ITC92240 | UT Assembly - Com Cam | LSST Forecast - B57 - B1 | 40 | 10 | 2018-04-09 | 2019-06-14 | -10 | 2018-04-09 |  | 0 | 2019-06-03 | 2019-06-14 | 2019-05-16 | 2019-05-31 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2018-07-03 | 2018-08-28 |  |  |  |  | 0.95 | 0 | FALSE | FALSE | None |  | None |  | 2019-06-14 |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 282 |  | InProgress | 95% | 336 | 0 | 336 | 336 | LSST Forecast - B57 - B1.3.08.06.01 | Commissioning Camera Hardware | 319.2 | 336 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Kevin Reil | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | R&D | [5 empty] | Commissioning Camera (TEC)
FALSE |  | CRYO70165 | Final Assy & Test - Cold System Verification Test | LSST Forecast - B57 - B1 | 40 | 5 | 2018-05-01 | 2019-06-07 | -18 | 2018-05-01 |  | 0 | 2019-06-03 | 2019-06-07 | 2019-05-07 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | TRUE | 2018-06-01 | 2018-07-27 |  |  |  |  | 0.8 | 0 | FALSE | TRUE | None |  | None |  | 2019-06-07 |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 266 |  | InProgress | 80% | 260 | 0 | 260 | 260 | LSST Forecast - B57 - B1.3.06.04.06.02 | Refrigeration System - IR2 | 208 | 260 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) | [6 empty] | Utility Trunk | CP #01 (Cryostat/Camera Integration)
FALSE |  | CCS117425 | Refactoring of FCS code to increase code quality/maintainability | LSST Forecast - B57 - B1 | 121 | 54 | 2018-06-01 | 2019-08-16 | -175 | 2018-06-01 |  | 0 | 2019-06-03 | 2019-08-16 | 2018-09-10 | 2018-11-26 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-07-02 | 2018-12-21 |  |  |  |  | 0.9 | 0 | FALSE | FALSE | None |  | None |  | 2019-08-16 |  |  |  |  | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 121 | 244 |  | InProgress | 90% | 200 | 0 | 200 | 200 | LSST Forecast - B57 - B1.3.07.01.03.05 | Filter/Carousel HCU | 180 | 200 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering | [7 empty] | CCS HCU (TEC)
FALSE |  | CAMF669235 | Integration and Test - Carousel | LSST Forecast - B57 - B1 | 75 | 55 | 2018-07-06 | 2019-08-19 | -176 | 2018-07-06 |  | 0 | 2019-06-03 | 2019-08-19 | 2018-09-07 | 2018-11-26 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-08-01 | 2018-11-14 |  |  |  |  | 0.8 | 0 | FALSE | FALSE | None |  | None |  | 2019-08-19 |  |  |  |  | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 75 | 220 |  | InProgress | 80% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Fabrication/Assembly | [15 empty] | CP #03 (Carousel/Camera Integration)
FALSE |  | CCS117430 | Develop final documentation for FCS software | LSST Forecast - B57 - B1 | 79 | 54 | 2018-08-01 | 2019-08-16 | -175 | 2018-08-01 |  | 0 | 2019-06-03 | 2019-08-16 | 2018-09-10 | 2018-11-26 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-09-04 | 2019-01-08 |  |  |  |  | 0.9 | 0 | FALSE | FALSE | None |  | None |  | 2019-08-16 |  |  |  |  | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 79 | 202 |  | InProgress | 90% | 200 | 0 | 200 | 200 | LSST Forecast - B57 - B1.3.07.01.03.05 | Filter/Carousel HCU | 180 | 200 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering | [7 empty] | CCS HCU (TEC)
FALSE |  | CCS117440 | Produce version of FCS software adapted for use with ComCom | LSST Forecast - B57 - B1 | 79 | 54 | 2018-08-01 | 2019-08-16 | -175 | 2018-08-01 |  | 0 | 2019-06-03 | 2019-08-16 | 2018-09-10 | 2018-11-26 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-09-04 | 2019-01-08 |  |  |  |  | 0.9 | 0 | FALSE | FALSE | None |  | None |  | 2019-08-16 |  |  |  |  | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 79 | 202 |  | InProgress | 90% | 200 | 0 | 200 | 200 | LSST Forecast - B57 - B1.3.07.01.03.05 | Filter/Carousel HCU | 180 | 200 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering | [7 empty] | CCS HCU (TEC)
FALSE |  | CCS117445 | Extended stress testing of software with final hardware | LSST Forecast - B57 - B1 | 79 | 54 | 2018-08-01 | 2019-08-16 | -175 | 2018-08-01 |  | 0 | 2019-06-03 | 2019-08-16 | 2018-09-10 | 2018-11-26 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2018-09-04 | 2019-01-08 |  |  |  |  | 0.75 | 0 | FALSE | FALSE | None |  | None |  | 2019-08-16 |  |  |  |  | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 79 | 202 |  | InProgress | 75% | 200 | 0 | 200 | 200 | LSST Forecast - B57 - B1.3.07.01.03.05 | Filter/Carousel HCU | 150 | 200 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering | [7 empty] | CCS HCU (TEC)
FALSE |  | OP541200 | L3 Assembly - Phase 4 (Lens Assy - Integration & Test) | LSST Forecast - B57 - B1 | 60 | 10 | 2019-03-11 | 2019-06-14 | -42 | 2019-03-11 |  | 0 | 2019-06-03 | 2019-06-14 | 2019-04-02 | 2019-04-16 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2019-04-01 | 2019-06-24 |  |  |  |  | 0.6 | 0 | FALSE | FALSE | None |  | None |  | 2019-06-14 |  |  |  |  | 2 | 0 | 2 | 0 | 0 | 0 | 3 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 59 |  | InProgress | 60% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor | [11 empty] | L1-L2 Opto-Mechanics
FALSE |  | OP541385 | Procurement Support - Phase 4 (Lens Assembly) | LSST Forecast - B57 - B1 | 69 | 20 | 2019-03-11 | 2019-06-28 | -42 | 2019-03-11 |  | 0 | 2019-06-03 | 2019-06-28 | 2019-04-02 | 2019-04-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-04-01 | 2019-07-08 |  |  |  |  | 0.6 | 0 | FALSE | FALSE | None |  | None |  | 2019-06-28 |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 69 | 59 |  | InProgress | 60% | 908 | 0 | 908 | 908 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 544.8 | 579.0145 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | L3 Assembly (TEC) | [6 empty] | L1-L2 Opto-Mechanics
FALSE |  | ITC31820 | ETU EO/BOT Testing | LSST Forecast - B57 - B1 | 10 | 5 | 2019-04-01 | 2019-06-07 | -18 | 2019-04-01 |  | 0 | 2019-06-03 | 2019-06-07 | 2019-05-07 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2019-05-01 | 2019-05-14 |  |  |  |  | 0.5 | 0 | FALSE | TRUE | None |  | None |  | 2019-06-07 |  |  |  |  | 2 | 0 | 1 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 44 |  | InProgress | 50% | 281 | 0 | 281 | 281 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 140.5 | 281 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | CRYO646240 | Test Individual Circuits - 4 Cryo (15 d) | LSST Forecast - B57 - B1 | 13 | 5 | 2019-05-12 | 2019-06-07 | -113 | 2019-05-12 |  | 0 | 2019-06-03 | 2019-06-07 | 2018-12-07 | 2018-12-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2019-06-03 | 2019-06-19 |  |  |  |  | 0.5 | 0 | FALSE | TRUE | None |  | None |  | 2019-06-07 |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 13 | 14 |  | InProgress | 50% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.04.03 | 4 Cryo Heat Ex | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | [24 empty] | CP #01 (Cryostat/Camera Integration)
FALSE |  | CRYO70185 | Analyze Data - Cold System Verification Test | LSST Forecast - B57 - B1 | 8 | 5 | 2019-05-20 | 2019-06-07 | -18 | 2019-05-20 |  | 0 | 2019-06-03 | 2019-06-07 | 2019-05-07 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-06-10 | 2019-06-19 |  |  |  |  | 0.5 | 0 | FALSE | TRUE | None |  | None |  | 2019-06-07 |  |  |  |  | 3 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 8 | 9 |  | InProgress | 50% | 40 | 0 | 40 | 40 | LSST Forecast - B57 - B1.3.06.04.06.02 | Refrigeration System - IR2 | 20 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) | [6 empty] | Utility Trunk
FALSE |  | OP541360 | L3 Assembly - Review & Validate Vacuum Optical Performance | LSST Forecast - B57 - B1 | 20 | 20 | 2019-06-03 | 2019-06-28 | -42 |  |  | 0 | 2019-06-03 | 2019-06-28 | 2019-04-02 | 2019-04-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-06-03 | 2019-06-28 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 392 | 0 | 392 | 392 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 14% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | L3 Assembly (TEC) |  |  |  | Scope that can be reduced |  |  | L3 Optics
FALSE |  | ITC31725 | NEED: Final Quad Box Assy from CCS | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-03 | 2019-06-03 | -14 |  |  | 0 | 2019-06-03 | 2019-06-03 | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-06-03 | 2019-06-03 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Auxiliary Electronics
FALSE |  | ITC31726 | I&T Acceptance of Quad Box from CCS | LSST Forecast - B57 - B1 | 1 | 1 | 2019-06-03 | 2019-06-03 | -14 |  |  | 0 | 2019-06-03 | 2019-06-03 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-03 | 2019-06-03 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis |  | Percent Complete on Work Package |  | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Other (specify) |  | Fabrication and Assembly | [9 empty] | Critical Path to CD-2
FALSE |  | ITC31813_1 | START: Cryostat Vacuum Testing | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-03 | 2019-06-03 | -14 |  |  | 4 | 2019-06-03 | 2019-06-03 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-06-03 | 2019-06-03 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Testing/Integration
FALSE |  | CAMM2195 | COMP: Cryostat Chamber & I&T Refrigeration System Ready for Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-07 | 2019-06-07 | -113 |  |  | 378 | 2019-06-07 | 2019-06-07 | 2018-12-13 | 2018-12-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-06-07 | 2019-06-07 |  |  |  |  | 0 | 0 | FALSE | FALSE | FinishOnOrBefore | 2018-12-13 | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.01 | DOE Project Milestones | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 2 Milestone | Management/Administration
FALSE |  | CRYO02825 | COMP: Cryostat Chamber & I&T Refrigeration System Ready for Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-07 | 2019-06-07 | -113 |  |  | 0 | 2019-06-07 | 2019-06-07 | 2018-12-13 | 2018-12-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | TRUE | 2019-06-07 | 2019-06-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04 | Cryostat | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 3 Milestone | Management/Administration
FALSE |  | CRYO70205 | COMP: Cold System Verification Test | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-07 | 2019-06-07 | -18 |  |  | 0 | 2019-06-07 | 2019-06-07 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2019-06-07 | 2019-06-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.02 | Refrigeration System - IR2 | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% | Level 4 Milestone | Design/Engineering
FALSE |  | CRYO61685_1 | AVAIL: Cryostat Assembly with Refrigeration for Integration (4 Cryo) | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-07 | 2019-06-07 | -18 |  |  | 0 | 2019-06-07 | 2019-06-07 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2019-06-07 | 2019-06-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.02 | Refrigeration System - IR2 | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 5 Milestone | Fabrication/Assembly | [16 empty] | Cryostat
FALSE |  | ITC31835 | NEED: Completion of Run Single-Circuit Cryo/Cold System Tests (4 Cryo) | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-07 | 2019-06-07 | -18 |  |  | 0 | 2019-06-07 | 2019-06-07 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | TRUE | 2019-06-07 | 2019-06-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Fabrication and Assembly | [12 empty] | Integration and Test
FALSE |  | CRYO646250 | AVAIL: Cryostat Assembly with Refrigeration for Integration (4 Cryo) | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-07 | 2019-06-07 | -113 |  |  | 0 | 2019-06-07 | 2019-06-07 | 2018-12-13 | 2018-12-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | TRUE | 2019-06-07 | 2019-06-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.04.03 | 4 Cryo Heat Ex | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | [7 empty] | Level 5 Milestone
FALSE |  | CCS300035 | NEED: DAQ with support for 9 rafts in IR2 | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-10 | 2019-06-10 | -9 |  |  | 0 | 2019-06-10 | 2019-06-10 | 2019-05-24 | 2019-05-24 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-06-10 | 2019-06-10 |  |  |  |  | 0 | 0 | FALSE | FALSE | FinishOnOrAfter | 2019-06-10 | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.08.03 | CCOB HCU | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Tony Johnson |  |  | Level 5 Milestone | Design/Engineering | [15 empty] | CP #02 (CCS Focal Plane Software)
FALSE |  | CCS300040 | Second release of full focal plane software in IR2 with support for 9+ rafts | LSST Forecast - B57 - B1 | 41 | 41 | 2019-06-10 | 2019-08-06 | -9 |  |  | 0 | 2019-06-10 | 2019-08-06 | 2019-05-28 | 2019-07-24 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-06-10 | 2019-08-06 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 41 | 0 |  | Planned | 0% | 360 | 0 | 360 | 360 | LSST Forecast - B57 - B1.3.07.01.03.08.03 | CCOB HCU | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | CCS HCU (TEC) | [7 empty] | CP #02 (CCS Focal Plane Software)
FALSE |  | ITC31820_1 | ETU De-integration | LSST Forecast - B57 - B1 | 12 | 12 | 2019-06-10 | 2019-06-25 | -18 |  |  | 0 | 2019-06-10 | 2019-06-25 | 2019-05-14 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2019-06-10 | 2019-06-25 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 12 | 0 |  | Planned | 0% | 238 | 0 | 238 | 238 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | CAMM2230 | COMP: Commissioning Camera Ready to Ship for Testing | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-14 | 2019-06-14 | -10 |  |  | 373 | 2019-06-14 | 2019-06-14 | 2019-05-31 | 2019-05-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-06-14 | 2019-06-14 |  |  |  |  | 0 | 0 | FALSE | FALSE | FinishOnOrBefore | 2019-05-31 | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.01 | DOE Project Milestones | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 2 Milestone | Management/Administration
FALSE |  | ITC00550 | COMP: Commissioning Camera Shipped to Tucson | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-14 | 2019-06-14 | -10 |  |  | 0 | 2019-06-14 | 2019-06-14 | 2019-05-31 | 2019-05-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-06-14 | 2019-06-14 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration
FALSE |  | OP541220 | RCV: L3 Assembly - Phase 4 (Lens Assembly) | LSST Forecast - B57 - B1 | 10 | 10 | 2019-06-17 | 2019-06-28 | -42 |  |  | 0 | 2019-06-17 | 2019-06-28 | 2019-04-16 | 2019-04-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-06-17 | 2019-06-28 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | 0-100% Method | TEC Non-ARRA | Scott Winters | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 23% |  | Procurement |  | Other (specify) | [5 empty] | L3 Assembly (TEC)
FALSE |  | CAMF669245 | Combined Test Assembly (Carousel + Loader 1+ Auto Changer 1) | LSST Forecast - B57 - B1 | 4 | 4 | 2019-06-25 | 2019-06-28 | -159 |  |  | 0 | 2019-06-25 | 2019-06-28 | 2018-10-24 | 2018-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-25 | 2019-06-28 |  |  |  |  | 0 | 0 | FALSE | FALSE | StartOnOrAfter | 2019-06-25 | None | [6 empty] | 6 | 0 | 5 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Fabrication/Assembly
FALSE |  | ITC00290 | START: Science Raft Tower Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-25 | 2019-06-25 | -18 |  |  | 0 | 2019-06-25 | 2019-06-25 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2019-06-25 | 2019-06-25 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration
FALSE |  | ITC31840 | START: Science Raft Tower Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-25 | 2019-06-25 | -18 |  |  | 0 | 2019-06-25 | 2019-06-25 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | TRUE | 2019-06-25 | 2019-06-25 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 10 | 0 | 10 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [11 empty] | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC31830 | AVAIL: Eng Raft Tower from I&T for ComCam | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-25 | 2019-06-25 | -18 |  |  | 0 | 2019-06-25 | 2019-06-25 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2019-06-25 | 2019-06-25 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Fabrication/Assembly |  |  |  | Engineering | [12 empty] | Integration and Test
FALSE |  | ITC31860 | Integrate Science Raft Tower #1 of 21 | LSST Forecast - B57 - B1 | 4 | 4 | 2019-06-26 | 2019-07-01 | -18 |  |  | 0 | 2019-06-26 | 2019-07-01 | 2019-05-31 | 2019-06-05 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-06-26 | 2019-07-01 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T
FALSE |  | ITC31860_R | Integrate Science Raft Tower #1 of 21 | LSST Forecast - B57 - B1 | 4 | 4 | 2019-06-26 | 2019-07-01 | -18 |  |  | 0 | 2019-06-26 | 2019-07-01 | 2019-05-31 | 2019-06-05 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-06-26 | 2019-07-01 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 4 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 103 | 0 | 103 | 103 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Commissioning and Testing | [5 empty] | Cryostat I&T (TEC) | [7 empty] | CP #01 (Cryostat/Camera Integration)
FALSE |  | CAMM2200 | COMP: L3 Assembly Ready for Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-28 | 2019-06-28 | -42 |  |  | 363 | 2019-06-28 | 2019-06-28 | 2019-04-30 | 2019-04-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-06-28 | 2019-06-28 |  |  |  |  | 0 | 0 | FALSE | FALSE | FinishOnOrBefore | 2019-04-30 | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.01 | DOE Project Milestones | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 2 Milestone | Management/Administration
FALSE |  | OP00980 | COMP: Camera L3 Lenses Ready for I&T | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-28 | 2019-06-28 | -42 |  |  | 0 | 2019-06-28 | 2019-06-28 | 2019-04-30 | 2019-04-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2019-06-28 | 2019-06-28 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05 | Optics | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  | Level 3 Milestone | Management/Administration |  |  |  |  | Camera Lenses
FALSE |  | OP541380 | AVAIL: L3 Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-28 | 2019-06-28 | -42 |  |  | 0 | 2019-06-28 | 2019-06-28 | 2019-04-30 | 2019-04-30 | 0 | 0 | 0 | 0 | 0 | 6 | FALSE | Finish Milestone | FALSE | 2019-06-28 | 2019-06-28 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  | Level 5 Milestone | Procurement | [10 empty] | Critical Path #2 (L1_L2 Assembly) | [5 empty] | Optics
FALSE |  | CAMF669250 | Combined Functionality and Performance Tests (Carousel + Loader 1 + Auto Changer 1) | LSST Forecast - B57 - B1 | 18 | 18 | 2019-07-01 | 2019-07-25 | -159 |  |  | 0 | 2019-07-01 | 2019-07-25 | 2018-10-30 | 2018-11-26 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2019-07-01 | 2019-07-25 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 8 | 0 | 8 | 0 | 0 | 0 | 3 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 18 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Fabrication/Assembly
FALSE |  | CAMF650350 | START: Filter Exchange System Testing | LSST Forecast - B57 - B1 | 0 | 0 | 2019-07-01 | 2019-07-01 | -104 |  |  | 0 | 2019-07-01 | 2019-07-01 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 5 | FALSE | Finish Milestone | FALSE | 2019-07-01 | 2019-07-01 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 0 | 3 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03 | Exchange System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  | Level 3 Milestone | Management/Administration
FALSE |  | ITC31880 | Integrate Science Raft Tower #2 of 21 | LSST Forecast - B57 - B1 | 4 | 4 | 2019-07-02 | 2019-07-08 | -18 |  |  | 0 | 2019-07-02 | 2019-07-08 | 2019-06-06 | 2019-06-11 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-07-02 | 2019-07-08 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 102 | 0 | 102 | 102 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC31920 | Integrate Science Raft Tower #3 of 21 | LSST Forecast - B57 - B1 | 4 | 4 | 2019-07-09 | 2019-07-12 | -18 |  |  | 0 | 2019-07-09 | 2019-07-12 | 2019-06-12 | 2019-06-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2019-07-09 | 2019-07-12 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 104 | 0 | 104 | 104 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC31940 | Integrate Science Raft Tower #4 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-07-15 | 2019-07-16 | -18 |  |  | 0 | 2019-07-15 | 2019-07-16 | 2019-06-18 | 2019-06-19 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-07-15 | 2019-07-16 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC31960 | Integrate Science Raft Tower #5 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-07-17 | 2019-07-18 | -18 |  |  | 0 | 2019-07-17 | 2019-07-18 | 2019-06-20 | 2019-06-21 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-07-17 | 2019-07-18 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC31980 | Integrate Science Raft Tower #6 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-07-19 | 2019-07-22 | -18 |  |  | 0 | 2019-07-19 | 2019-07-22 | 2019-06-24 | 2019-06-25 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2019-07-19 | 2019-07-22 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32225 | Integrate Corner Raft Tower #1 of 4 | LSST Forecast - B57 - B1 | 4 | 4 | 2019-07-23 | 2019-07-26 | -18 |  |  | 0 | 2019-07-23 | 2019-07-26 | 2019-06-26 | 2019-07-01 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-07-23 | 2019-07-26 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 119 | 0 | 119 | 119 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32230 | Integrate Corner Raft Tower #2 of 4 | LSST Forecast - B57 - B1 | 4 | 4 | 2019-07-29 | 2019-08-01 | -18 |  |  | 0 | 2019-07-29 | 2019-08-01 | 2019-07-02 | 2019-07-08 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-07-29 | 2019-08-01 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 119 | 0 | 119 | 119 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32290 | Integrate Corner Raft Tower #3 of 4 | LSST Forecast - B57 - B1 | 4 | 4 | 2019-08-02 | 2019-08-07 | -18 |  |  | 0 | 2019-08-02 | 2019-08-07 | 2019-07-09 | 2019-07-12 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-08-02 | 2019-08-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 118 | 0 | 118 | 118 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | CCS300045 | AVAIL: Support for 9 rafts in full focal plane | LSST Forecast - B57 - B1 | 0 | 0 | 2019-08-06 | 2019-08-06 | -9 |  |  | 9 | 2019-08-06 | 2019-08-06 | 2019-07-24 | 2019-07-24 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-08-06 | 2019-08-06 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.08.03 | CCOB HCU | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  | Level 5 Milestone | Design/Engineering | [15 empty] | CP #02 (CCS Focal Plane Software)
FALSE |  | ITC32410 | Integrate Corner Raft Tower #4 of 4 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-08-08 | 2019-08-09 | -18 |  |  | 0 | 2019-08-08 | 2019-08-09 | 2019-07-15 | 2019-07-16 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-08-08 | 2019-08-09 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 118 | 0 | 118 | 118 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32000 | Integrate Science Raft Tower #7 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-08-12 | 2019-08-13 | -18 |  |  | 0 | 2019-08-12 | 2019-08-13 | 2019-07-17 | 2019-07-18 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-08-12 | 2019-08-13 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32020 | Integrate Science Raft Tower #8 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-08-14 | 2019-08-15 | -18 |  |  | 0 | 2019-08-14 | 2019-08-15 | 2019-07-19 | 2019-07-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-08-14 | 2019-08-15 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32040 | Integrate Science Raft Tower #9 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-08-16 | 2019-08-19 | -18 |  |  | 0 | 2019-08-16 | 2019-08-19 | 2019-07-23 | 2019-07-24 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-08-16 | 2019-08-19 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32140 | BOT Testing with Raft Tower #1-9 | LSST Forecast - B57 - B1 | 38 | 38 | 2019-08-20 | 2019-10-11 | -18 |  |  | 0 | 2019-08-20 | 2019-10-11 | 2019-07-25 | 2019-09-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2019-08-20 | 2019-10-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 38 | 0 |  | Planned | 0% | 517 | 0 | 517 | 517 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | CAMF669270 | Subsystem Packaging - Carousel | LSST Forecast - B57 - B1 | 4 | 4 | 2019-08-20 | 2019-08-23 | -176 |  |  | 0 | 2019-08-20 | 2019-08-23 | 2018-11-27 | 2018-11-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-08-20 | 2019-08-23 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 9 | 0 | 9 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Fabrication/Assembly | [15 empty] | CP #03 (Carousel/Camera Integration)
FALSE |  | CAMF669280 | Shipped to SLAC - Carousel | LSST Forecast - B57 - B1 | 24 | 24 | 2019-08-26 | 2019-09-27 | -176 |  |  | 0 | 2019-08-26 | 2019-09-27 | 2018-12-03 | 2019-01-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-08-26 | 2019-09-27 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 24 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment |  | TEC Non-ARRA | Kevin Reil | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Commissioning and Testing | [13 empty] | CP #03 (Carousel/Camera Integration)
FALSE |  | CAMF669290 | Processed through Customes - Carousel #1 | LSST Forecast - B57 - B1 | 9 | 9 | 2019-09-30 | 2019-10-10 | -176 |  |  | 0 | 2019-09-30 | 2019-10-10 | 2019-01-18 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2019-09-30 | 2019-10-10 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 9 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications |  |  |  | Kevin Reil | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Commissioning and Testing | [13 empty] | CP #03 (Carousel/Camera Integration)
FALSE |  | CAMF650900 | COMP: Exchange System Ready for Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2019-10-10 | 2019-10-10 | -176 |  |  | 0 | 2019-10-10 | 2019-10-10 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2019-10-10 | 2019-10-10 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03 | Exchange System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  | Level 3 Milestone | Management/Administration | [15 empty] | CP #03 (Carousel/Camera Integration)
FALSE |  | CAMF669300 | AVAIL: Ready for Integration - Carousel | LSST Forecast - B57 - B1 | 0 | 0 | 2019-10-10 | 2019-10-10 | -176 |  |  | 0 | 2019-10-10 | 2019-10-10 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 5 | FALSE | Finish Milestone | FALSE | 2019-10-10 | 2019-10-10 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  | Level 5 Milestone | Fabrication/Assembly | [16 empty] | Exchange System
FALSE |  | ITC19600 | NEED: Carousel (with back flange #1) | LSST Forecast - B57 - B1 | 0 | 0 | 2019-10-10 | 2019-10-10 | -8 |  |  | 0 | 2019-10-10 | 2019-10-10 | 2019-09-30 | 2019-09-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-10-10 | 2019-10-10 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Exchange System
FALSE |  | CAMM2210 | COMP: Filter Exchange System Ready for Integration (IN2P3) | LSST Forecast - B57 - B1 | 0 | 0 | 2019-10-10 | 2019-10-10 | -176 |  |  | 291 | 2019-10-10 | 2019-10-10 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-10-10 | 2019-10-10 |  |  |  |  | 0 | 0 | FALSE | FALSE | FinishOnOrBefore | 2019-01-31 | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.01 | DOE Project Milestones | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 2 Milestone | Management/Administration
FALSE |  | ITC19700 | Acceptance Testing of Back Flange with Carousel | LSST Forecast - B57 - B1 | 6 | 6 | 2019-10-11 | 2019-10-18 | -8 |  |  | 0 | 2019-10-11 | 2019-10-18 | 2019-10-01 | 2019-10-08 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-10-11 | 2019-10-18 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 6 | 0 |  | Planned | 0% | 124 | 0 | 124 | 124 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Commissioning and Testing | [5 empty] | Camera I&T (TEC) | [7 empty] | CP #03 (Carousel/Camera Integration)
FALSE |  | ITC00300 | COMP: Integration of 9 SR into Cryostat | LSST Forecast - B57 - B1 | 0 | 0 | 2019-10-11 | 2019-10-11 | -18 |  |  | 0 | 2019-10-11 | 2019-10-11 | 2019-09-17 | 2019-09-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2019-10-11 | 2019-10-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration
FALSE |  | ITC32160 | COMP: Integration of 9 SR into Cryostat | LSST Forecast - B57 - B1 | 0 | 0 | 2019-10-11 | 2019-10-11 | -18 |  |  | 0 | 2019-10-11 | 2019-10-11 | 2019-09-17 | 2019-09-17 | 0 | 0 | 0 | 0 | 0 | 6 | FALSE | Finish Milestone | TRUE | 2019-10-11 | 2019-10-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Testing/Integration
FALSE |  | ITC32180 | Integrate Science Raft Tower #10 of 21 | LSST Forecast - B57 - B1 | 6 | 6 | 2019-10-14 | 2019-10-21 | -18 |  |  | 0 | 2019-10-14 | 2019-10-21 | 2019-09-18 | 2019-09-25 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-10-14 | 2019-10-21 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 6 | 0 |  | Planned | 0% | 147 | 0 | 147 | 147 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing | [5 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC19715 | Mount and check camera housing to back flange | LSST Forecast - B57 - B1 | 11 | 11 | 2019-10-21 | 2019-11-04 | -8 |  |  | 0 | 2019-10-21 | 2019-11-04 | 2019-10-09 | 2019-10-23 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-10-21 | 2019-11-04 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 11 | 0 |  | Planned | 0% | 177 | 0 | 177 | 177 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Commissioning and Testing | [5 empty] | Camera I&T (TEC) | [7 empty] | CP #03 (Carousel/Camera Integration)
FALSE |  | ITC32200 | Integrate Science Raft Tower #11 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-10-22 | 2019-10-23 | -18 |  |  | 0 | 2019-10-22 | 2019-10-23 | 2019-09-26 | 2019-09-27 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-10-22 | 2019-10-23 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32220 | Integrate Science Raft Tower #12 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-10-24 | 2019-10-25 | -18 |  |  | 0 | 2019-10-24 | 2019-10-25 | 2019-09-30 | 2019-10-01 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-10-24 | 2019-10-25 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32240 | Integrate Science Raft Tower #13 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-10-28 | 2019-10-29 | -18 |  |  | 0 | 2019-10-28 | 2019-10-29 | 2019-10-02 | 2019-10-03 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-10-28 | 2019-10-29 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32260 | Integrate Science Raft Tower #14 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-10-30 | 2019-10-31 | -18 |  |  | 0 | 2019-10-30 | 2019-10-31 | 2019-10-04 | 2019-10-07 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-10-30 | 2019-10-31 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32280 | Integrate Science Raft Tower #15 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-11-01 | 2019-11-04 | -18 |  |  | 0 | 2019-11-01 | 2019-11-04 | 2019-10-08 | 2019-10-09 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-11-01 | 2019-11-04 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC19752 | NEED: Auto Changer | LSST Forecast - B57 - B1 | 0 | 0 | 2019-11-04 | 2019-11-04 | -8 |  |  | 0 | 2019-11-04 | 2019-11-04 | 2019-10-23 | 2019-10-23 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-11-04 | 2019-11-04 |  |  |  |  | 0 | 0 | FALSE | FALSE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | ITC19754 | Camera Assembly - Autochanger | LSST Forecast - B57 - B1 | 30 | 30 | 2019-11-05 | 2019-12-18 | -8 |  |  | 0 | 2019-11-05 | 2019-12-18 | 2019-10-24 | 2019-12-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-11-05 | 2019-12-18 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 0 |  | Planned | 0% | 783 | 0 | 783 | 783 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Camera I&T (TEC) | [6 empty] | Camera I&T | CP #03 (Carousel/Camera Integration)
FALSE |  | ITC32300 | Integrate Science Raft Tower #16 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-11-05 | 2019-11-06 | -18 |  |  | 0 | 2019-11-05 | 2019-11-06 | 2019-10-10 | 2019-10-11 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-11-05 | 2019-11-06 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32320 | Integrate Science Raft Tower #17 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-11-07 | 2019-11-08 | -18 |  |  | 0 | 2019-11-07 | 2019-11-08 | 2019-10-14 | 2019-10-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-11-07 | 2019-11-08 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32340 | Integrate Science Raft Tower #18 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-11-11 | 2019-11-12 | -18 |  |  | 0 | 2019-11-11 | 2019-11-12 | 2019-10-16 | 2019-10-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-11-11 | 2019-11-12 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32360 | Integrate Science Raft Tower #19 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-11-13 | 2019-11-14 | -18 |  |  | 0 | 2019-11-13 | 2019-11-14 | 2019-10-18 | 2019-10-21 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-11-13 | 2019-11-14 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32380 | Integrate Science Raft Tower #20 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-11-15 | 2019-11-18 | -18 |  |  | 0 | 2019-11-15 | 2019-11-18 | 2019-10-22 | 2019-10-23 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-11-15 | 2019-11-18 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32400 | Integrate Science Raft Tower #21 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-11-19 | 2019-11-20 | -18 |  |  | 0 | 2019-11-19 | 2019-11-20 | 2019-10-24 | 2019-10-25 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-11-19 | 2019-11-20 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC00330 | START: Integrated Cryostat Testing | LSST Forecast - B57 - B1 | 0 | 0 | 2019-11-21 | 2019-11-21 | -18 |  |  | 0 | 2019-11-21 | 2019-11-21 | 2019-10-25 | 2019-10-25 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | TRUE | 2019-11-21 | 2019-11-21 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration
FALSE |  | ITC32415 | START: Final Integrated Cryostat Testing | LSST Forecast - B57 - B1 | 0 | 0 | 2019-11-21 | 2019-11-21 | -18 |  |  | 0 | 2019-11-21 | 2019-11-21 | 2019-10-25 | 2019-10-25 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Start Milestone | TRUE | 2019-11-21 | 2019-11-21 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Management/Administration
FALSE |  | ITC19756 | NEED: Shutter | LSST Forecast - B57 - B1 | 0 | 0 | 2019-12-18 | 2019-12-18 | -8 |  |  | 0 | 2019-12-18 | 2019-12-18 | 2019-12-06 | 2019-12-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-12-18 | 2019-12-18 |  |  |  |  | 0 | 0 | FALSE | FALSE | AsLateAsPossible |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Camera Body & Shutter
FALSE |  | ITC19758 | NEED: Shutter CCS Software & HCU | LSST Forecast - B57 - B1 | 0 | 0 | 2019-12-18 | 2019-12-18 | -8 |  |  | 0 | 2019-12-18 | 2019-12-18 | 2019-12-06 | 2019-12-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-12-18 | 2019-12-18 |  |  |  |  | 0 | 0 | FALSE | FALSE | AsLateAsPossible |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Camera Body & Shutter
Number of Lags
Total number of activities that have lags in their predecessors. This number should not exceed 5%.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | Previous Start | Previous Finish | Percent Complete | Previous Remaining Duration | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | IsLevelOfEffort | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | Global_Basis of Estimate | Global_Cobra Cost Class | Cobra PMT (EV Method)_Global | Global_Color of Money | Global_Control Account Manager | Global_Design Maturity | Global_Judgement Factor | Global_Milestone Levels | Global_Project Phase | Global_Funding Source | Global_EDIA Survey | Global_MS Type | Phase | NSF Milestones | Loading Curve | Sensor Vendor | LSST_CA | Summary Schedule | ICD for NSF Input | LSST Camera Critical Paths | CD2 Budget Changes | DOE Reviews | Critical Path (CD Reviews) | LSST WP Summary | Critical Path (Camera Delivery) | AWARD / NEED Sub-System | Final Design Key Links | CP - CAMM2100 | CP - CAMM2130 | CP - CAMM2160 | BNL Work Org | Last ETC Update | BNL WBS | LSST Story List | Sum Sch 01 (Camera) | Sum Sch 02 (IT w/Needs) | Sum Sch 03 (Sensors_RTM_IT) | LSST Raft Particulate Mitigation | LSST RTM
FALSE |  | ITC31775 | CCOB Analysis Software | LSST Forecast - B57 - B1 | 80 | 0 | 2019-01-07 | 2019-02-21 | 0 | 2019-01-07 | 2019-02-21 | 0 | 2019-06-01 | 2019-06-01 | 2020-05-05 | 2020-05-05 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-02-07 | 2019-05-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 80 | 31 |  | Complete | 100% | 335 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.04 | Verification Software Development | 335 | 335 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Other (specify) | [5 empty] | Verification Test Systems (TEC)
FALSE |  | SR571110 | Modify REC Walls (Design Update & Batch A1) | LSST Forecast - B57 - B1 | 20 | 0 | 2019-01-07 | 2019-01-31 | 0 | 2019-01-07 | 2019-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-02-01 | 2019-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 17 |  | Complete | 100% | 32 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 32 | 32 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Science Raft Production Assembly and Test (TEC) | [15 empty] | Science Raft System
FALSE |  | SR571140 | Modify A-Frames (Design Update & Batch A1) | LSST Forecast - B57 - B1 | 20 | 0 | 2019-01-07 | 2019-01-31 | 0 | 2019-01-07 | 2019-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-02-01 | 2019-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 17 |  | Complete | 100% | 17 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 17 | 17 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Science Raft Production Assembly and Test (TEC) | [15 empty] | Science Raft System
FALSE |  | SR571170 | Modify MF08 (Design Update & Batch A1) | LSST Forecast - B57 - B1 | 20 | 0 | 2019-01-07 | 2019-01-31 | 0 | 2019-01-07 | 2019-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-02-01 | 2019-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 17 |  | Complete | 100% | 29 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 29 | 29 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Science Raft Production Assembly and Test (TEC) | [15 empty] | Science Raft System
FALSE |  | ITC36080 | Develop RSA Cleaning Process | LSST Forecast - B57 - B1 | 20 | 0 | 2019-01-07 | 2019-02-28 | 0 | 2019-01-07 | 2019-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 10000 | 10000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-02-01 | 2019-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 36 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.03 | Raft Acceptance Testing | 40 | 40 | 0 | 10000 | 10000 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC)
FALSE |  | ITC36090 | RTM Tools, Storage Rack, Aliveness Bench | LSST Forecast - B57 - B1 | 20 | 0 | 2019-01-07 | 2019-02-28 | 0 | 2019-01-07 | 2019-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 16000 | 16000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-02-01 | 2019-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 36 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.03 | Raft Acceptance Testing | 0 | 0 | 0 | 16000 | 16000 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC)
FALSE |  | ITC36100 | I&T eTraveler Development | LSST Forecast - B57 - B1 | 20 | 0 | 2019-01-07 | 2019-02-28 | 0 | 2019-01-07 | 2019-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-02-01 | 2019-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 36 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.03 | Raft Acceptance Testing | 80 | 80 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC)
FALSE |  | DAQ900350 | Assemble Production COBs | LSST Forecast - B57 - B1 | 24 | 0 | 2019-01-07 | 2019-04-15 | 0 | 2019-01-07 | 2019-04-15 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-01-07 | 2019-02-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 4 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 24 | 68 |  | Complete | 100% | 180 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.02 | DAQ COB (Main ATCA DAQ Module) | 180 | 180 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | [11 empty] | DAQ Readout Systems (TEC)
FALSE |  | SR310635 | Sub-system manager FY19 (Project Extension) | LSST Forecast - B57 - B1 | 124 | 54 | 2019-01-08 | 2019-08-15 | 683 | 2019-01-08 |  | 0 | 2019-06-03 | 2019-08-15 | 2022-01-13 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2019-02-01 | 2019-07-24 |  |  |  |  | 0.33 | 0 | FALSE | FALSE | None |  | None |  | 2019-08-15 |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 124 | 104 |  | InProgress | 56.45% | 264 | 0 | 264 | 264 | LSST Forecast - B57 - B1.3.04.01.01 | Science Raft System Integration & Management | 149.0323 | 183.0968 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Drtn |  | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Bill Wahl | (1.10) Task/item is a modification of an existing design | 0% |  | Management/Administration |  | Construction Management | [5 empty] | Science Raft System (TEC) | [13 empty] | Management - LOE |  | Science Raft System
FALSE |  | SR570870 | RTM19_Disassemble REC | LSST Forecast - B57 - B1 | 4 | 0 | 2019-01-25 | 2019-01-31 | 0 | 2019-01-25 | 2019-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-13 | 2019-06-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-02-14 | 2019-02-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 4 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [13 empty] | RTM #19 |  | Science Raft System
FALSE |  | CRYO61493 | AWARD: P.O. - Gas to calibrate chromatograph - Chile System | LSST Forecast - B57 - B1 | 1 | 0 | 2019-01-31 | 2019-01-31 | 0 | 2019-01-31 | 2019-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-02 | 2020-06-02 | 28000 | 28000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-02-01 | 2019-02-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.05 | Refrigeration System - Chile System (Equipment & Refrigeration) | 0 | 0 | 0 | 28000 | 28000 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | B1 Procurement Commitment (C5.1) |  | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 20% | Level 4 Milestone | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Refrigeration System (TEC)
FALSE |  | CRYO74040 | Procurement Process - Servicing Equipment & Materials - Chile System (240V, 50Hz) | LSST Forecast - B57 - B1 | 40 | 0 | 2019-01-31 | 2019-01-31 | 0 | 2019-01-31 | 2019-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-02 | 2020-06-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-02-01 | 2019-03-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.05 | Refrigeration System - Chile System (Equipment & Refrigeration) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Alice Callen |  |  |  | Procurement
FALSE |  | CBM50000 | RCV: Phase 2 Requirements - Shutter Blades | LSST Forecast - B57 - B1 | 1 | 0 | 2019-02-01 | 2019-02-01 | 0 | 2019-02-01 | 2019-02-01 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-22 | 2019-08-22 | 147369 | 147369 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-03-01 | 2019-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.02.02 | Shutter Development | 0 | 0 | 0 | 147369 | 147369 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | 0-100% Method | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 5% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Shutter Development (TEC) | [6 empty] | Shutter Prod Sprt
FALSE |  | CAMF2460 | Outstanding Performance Annual Bonus FY19 | LSST Forecast - B57 - B1 | 19 | 0 | 2019-02-01 | 2019-02-28 | 0 | 2019-02-01 | 2019-02-28 | 0 | 2019-06-01 | 2019-06-01 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-03-01 | 2019-03-27 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 19 | 18 |  | Complete | 100% | 295 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01.01.01 | Project Office | 295 | 295 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 0% |  | Management/Administration |  | Project Management (cost estimating, scheduling, project controls, Risk assessment) | [5 empty] | Project Management (TEC)
FALSE |  | ITC10892 | IT&C Travel--FY19 (UC Davis Support) | LSST Forecast - B57 - B1 | 160 | 76 | 2019-02-01 | 2019-09-18 | 612 | 2019-02-01 |  | 0 | 2019-06-03 | 2019-09-18 | 2021-11-24 | 2022-03-29 | 30000 | 30000 | 0 | 30000 | 30000 | 1 | FALSE | Normal | FALSE | 2019-03-01 | 2019-10-15 |  |  |  |  | 0.125 | 0 | FALSE | FALSE | None |  | None |  | 2019-09-18 |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 160 | 84 |  | InProgress | 52.5% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.01 | I&T Integration & Management | 0 | 0 | 0 | 15750 | 12187.5 | 30000 | PercentComplete | 4% | CP_Drtn | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Management/Administration |  | Construction Management | [5 empty] | Integration & Testing (TEC)
FALSE |  | OP521820 | RCV: r-band repeatability and Phase 1 deliverables (MS4) - Filter Coating | LSST Forecast - B57 - B1 | 2 | 0 | 2019-02-25 | 2019-02-26 | 0 | 2019-02-25 | 2019-02-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-12-12 | 2019-12-12 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-02-25 | 2019-02-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 2 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | 0-100% Method | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 23% |  | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Filters (TEC) | Witness Sample | [5 empty] | Filter Optics
FALSE |  | ITC31820 | ETU EO/BOT Testing | LSST Forecast - B57 - B1 | 10 | 5 | 2019-04-01 | 2019-06-07 | -18 | 2019-04-01 |  | 0 | 2019-06-03 | 2019-06-07 | 2019-05-07 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2019-05-01 | 2019-05-14 |  |  |  |  | 0.5 | 0 | FALSE | TRUE | None |  | None |  | 2019-06-07 |  |  |  |  | 2 | 0 | 1 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 44 |  | InProgress | 50% | 281 | 0 | 281 | 281 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 140.5 | 281 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | SR570280 | RTM06_Inspect, Clean & Test RSA | LSST Forecast - B57 - B1 | 6 | 0 | 2019-04-01 | 2019-04-08 | 0 | 2019-04-01 | 2019-04-08 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-20 | 2019-06-20 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-05-01 | 2019-05-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 6 | 5 |  | Complete | 100% | 70 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 70 | 70 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [13 empty] | RTM #6 |  | Science Raft System
FALSE |  | ITC36020 | Modify A-Frames (Batch B1) | LSST Forecast - B57 - B1 | 20 | 0 | 2019-04-01 | 2019-04-29 | 0 | 2019-04-01 | 2019-04-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-25 | 2019-10-25 | 600 | 600 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-05-01 | 2019-05-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 20 |  | Complete | 100% | 6 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.03 | Raft Acceptance Testing | 6 | 6 | 0 | 600 | 600 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC)
FALSE |  | ITC36050 | Modify MF08 (Batch B1) | LSST Forecast - B57 - B1 | 20 | 0 | 2019-04-01 | 2019-04-29 | 0 | 2019-04-01 | 2019-04-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-30 | 2019-08-30 | 1000 | 1000 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-05-01 | 2019-05-29 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 20 |  | Complete | 100% | 12 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.03 | Raft Acceptance Testing | 12 | 12 | 0 | 1000 | 1000 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC)
FALSE |  | CRYO73090 | Eden Change Orders (Line Item 2,3,4) - Hx & HW - Chile System | LSST Forecast - B57 - B1 | 20 | 0 | 2019-04-01 | 2019-04-30 | 0 | 2019-04-01 | 2019-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 38684 | 38684 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-05-03 | 2019-05-31 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 21 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.04 | Refrigeration System - Chile System (HX) | 0 | 0 | 0 | 38684 | 38684 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | ITC36150 | RTM1 r1_Disassemble REC | LSST Forecast - B57 - B1 | 5 | 0 | 2019-04-01 | 2019-04-05 | 0 | 2019-04-01 | 2019-04-05 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-21 | 2019-08-21 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-05-01 | 2019-05-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 4 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.03 | Raft Acceptance Testing | 40 | 40 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC)
FALSE |  | OP522490 | RCV: 2 of 6 Filter Complete and Ready to Ship (MS5) - Filter Fabrication | LSST Forecast - B57 - B1 | 1 | 0 | 2019-04-17 | 2019-04-17 | 0 | 2019-04-17 | 2019-04-17 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-06-03 | 2019-06-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | 0-100% Method | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Filters (TEC)
FALSE |  | OP522485 | COMP: 1st Production Filter Complete and Ready to Ship - Filter Fabrication | LSST Forecast - B57 - B1 | 0 | 0 | 2019-04-17 | 2019-04-17 | 0 | 2019-04-17 | 2019-04-17 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-06-03 | 2019-06-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters | (1.10) Task/item is a modification of an existing design | 7% | Level 4 Milestone | Procurement |  |  | Subcontractor
FALSE |  | SR570470 | RTM09_RTM Qualification at TS5 | LSST Forecast - B57 - B1 | 5 | 0 | 2019-04-17 | 2019-04-30 | 0 | 2019-04-17 | 2019-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-20 | 2019-06-20 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-05-02 | 2019-05-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 9 |  | Complete | 100% | 45 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 45 | 45 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [13 empty] | RTM #9 |  | Science Raft System
FALSE |  | CBM29000 | Perform Verification Testing - Purge Cabinets | LSST Forecast - B57 - B1 | 15 | 15 | 2019-04-21 | 2019-06-21 | 49 | 2019-04-21 |  | 0 | 2019-06-03 | 2019-06-21 | 2019-08-12 | 2019-08-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-05-01 | 2019-05-21 |  |  |  |  | 0.5 | 0 | FALSE | FALSE | None |  | None |  | 2019-06-21 |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 29 |  | InProgress | 50% | 168 | 0 | 168 | 168 | LSST Forecast - B57 - B1.3.06.01.02 | Camera Body Development | 84 | 168 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 15% |  | Testing/Integration |  | Other (specify) | [5 empty] | Camera Body Development (TEC) | [6 empty] | Camera Body and Purge Production
FALSE |  | CCS120310 | Procurement Process - Parts - CCS Computing Equipments for the Summit & Base | LSST Forecast - B57 - B1 | 20 | 10 | 2019-04-21 | 2019-06-14 | 26 | 2019-04-21 |  | 0 | 2019-06-03 | 2019-06-14 | 2019-07-10 | 2019-07-24 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-05-01 | 2019-05-29 |  |  |  |  | 0.8 | 0 | FALSE | FALSE | None |  | None |  | 2019-06-14 |  |  |  |  | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 29 |  | InProgress | 80% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.02.07 | CCS Core 6.0 Release (Comcam Ship) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment |  | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Design/Engineering
FALSE |  | CCS320100 | Modify OCS + CCS Bridge for Use with Camera Rotator - HCU | LSST Forecast - B57 - B1 | 20 | 14 | 2019-04-22 | 2019-06-20 | 8 | 2019-04-22 |  | 0 | 2019-06-03 | 2019-06-20 | 2019-06-13 | 2019-07-02 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-05-01 | 2019-05-29 |  |  |  |  | 0.5 | 0 | FALSE | FALSE | None |  | None |  | 2019-06-20 |  |  |  |  | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 29 |  | InProgress | 50% | 120 | 0 | 120 | 120 | LSST Forecast - B57 - B1.3.07.01.03.08.05 | Camera Rotator HCU | 60 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | CCS HCU (TEC)
FALSE |  | ITC36210 | RTM11 r1_Disassemble REC | LSST Forecast - B57 - B1 | 5 | 0 | 2019-05-01 | 2019-05-07 | 0 | 2019-05-01 | 2019-05-07 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-18 | 2019-06-18 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-03 | 2019-06-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 4 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.03 | Raft Acceptance Testing | 40 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration
FALSE |  | SR570230 | RTM05_Inspect, Clean & Test RSA | LSST Forecast - B57 - B1 | 4 | 0 | 2019-05-03 | 2019-05-06 | 0 | 2019-05-03 | 2019-05-06 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-30 | 2019-07-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-06-03 | 2019-06-06 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 1 |  | Complete | 100% | 70 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 70 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [13 empty] | RTM #5 |  | Science Raft System
FALSE |  | SR570130 | RTM03_Inspect, Clean & Test RSA | LSST Forecast - B57 - B1 | 3 | 0 | 2019-05-08 | 2019-05-10 | 0 | 2019-05-08 | 2019-05-10 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-10 | 2019-07-10 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-06-03 | 2019-06-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 3 | 2 |  | Complete | 100% | 70 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 70 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [13 empty] | RTM #3 |  | Science Raft System
FALSE |  | CCS126400 | Stress test and validate camera body HCU Purge Unit - Camera Body HCU | LSST Forecast - B57 - B1 | 5 | 0 | 2019-05-13 | 2019-05-31 | 0 | 2019-05-13 | 2019-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-19 | 2019-07-19 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-03 | 2019-06-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 13 |  | Complete | 100% | 40 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.07 | Camera Body HCU | 40 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | CCS HCU (TEC) | [6 empty] | Camera I&T Hardware Control Unit
FALSE |  | SR570360 | RTM07_Inspect, Clean & Test RSA | LSST Forecast - B57 - B1 | 3 | 0 | 2019-05-17 | 2019-05-21 | 0 | 2019-05-17 | 2019-05-21 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-30 | 2019-07-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-06-03 | 2019-06-05 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 3 | 2 |  | Complete | 100% | 70 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 70 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [13 empty] | RTM #7 |  | Science Raft System
FALSE |  | SR570650 | RTM12_Inspect, Clean & Test RSA | LSST Forecast - B57 - B1 | 2 | 0 | 2019-05-24 | 2019-05-28 | 0 | 2019-05-24 | 2019-05-28 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-07 | 2019-08-07 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-06-17 | 2019-06-18 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 5 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 1 |  | Complete | 100% | 70 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 70 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [13 empty] | RTM #12 |  | Science Raft System
FALSE |  | CRYO62080 | Requisition - Refrigerant - Chile Hardware | LSST Forecast - B57 - B1 | 20 | 20 | 2019-06-03 | 2019-06-28 | 103 |  |  | 0 | 2019-06-03 | 2019-06-28 | 2019-10-28 | 2019-11-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-03 | 2019-06-28 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.05 | Refrigeration System - Chile System (Equipment & Refrigeration) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  |  | Procurement
FALSE |  | ITC31780 | Camera Verification Analysis Software | LSST Forecast - B57 - B1 | 80 | 80 | 2019-06-03 | 2019-09-24 | 225 |  |  | 243 | 2019-06-03 | 2019-09-24 | 2020-05-05 | 2020-08-26 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-03 | 2019-09-24 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 80 | 0 |  | Planned | 0% | 1005 | 0 | 1005 | 1005 | LSST Forecast - B57 - B1.3.08.02.04 | Verification Software Development | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Other (specify) | [5 empty] | Verification Test Systems (TEC)
FALSE |  | ITC33890 | COTS Procurement - Vendor Lead Time - Cryo-Equip | LSST Forecast - B57 - B1 | 36 | 36 | 2019-06-03 | 2019-07-23 | 36 |  |  | 0 | 2019-06-03 | 2019-07-23 | 2019-07-24 | 2019-09-12 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-03 | 2019-07-23 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None |  | 2019-07-23 |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 36 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.02 | Cryostat Handling Equipment | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [13 empty] | CP #12 (Cryo Equip)
FALSE |  | ITC33920 | Outside Fabrication - Vendor Lead Time - Cryo-Equip | LSST Forecast - B57 - B1 | 36 | 36 | 2019-06-03 | 2019-07-23 | 36 |  |  | 0 | 2019-06-03 | 2019-07-23 | 2019-07-24 | 2019-09-12 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-03 | 2019-07-23 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None |  | 2019-07-23 |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 36 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.02 | Cryostat Handling Equipment | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [13 empty] | CP #12 (Cryo Equip)
FALSE |  | DAQ920050 | Server-Side Implementation & Test (Software) | LSST Forecast - B57 - B1 | 30 | 30 | 2019-06-03 | 2019-07-15 | 275 |  |  | 0 | 2019-06-03 | 2019-07-15 | 2020-07-16 | 2020-08-26 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-03 | 2019-07-15 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 0 |  | Planned | 0% | 40 | 0 | 40 | 40 | LSST Forecast - B57 - B1.3.07.02.02.16 | Remote FPGA Reprogramming | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Testing/Integration |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | DAQ Readout Systems (TEC)
FALSE |  | SR570700 | RTM13_Inspect, Clean & Test RSA | LSST Forecast - B57 - B1 | 1 | 1 | 2019-06-03 | 2019-06-03 | 51 |  |  | 0 | 2019-06-03 | 2019-06-03 | 2019-08-14 | 2019-08-14 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-06-03 | 2019-06-03 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None |  | 2019-05-28 |  |  |  |  | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Planned | 0% | 70 | 0 | 70 | 70 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [13 empty] | RTM #13 |  | Science Raft System
FALSE |  | ITC36110 | TS7-2 Modifiaction & Qualification | LSST Forecast - B57 - B1 | 22 | 22 | 2019-06-03 | 2019-07-02 | 573 |  |  | 361 | 2019-06-03 | 2019-07-02 | 2021-09-30 | 2021-10-29 | 6000 | 6000 | 0 | 6000 | 6000 | 1 | FALSE | Normal | FALSE | 2019-06-03 | 2019-07-02 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 22 | 0 |  | Planned | 0% | 40 | 0 | 40 | 40 | LSST Forecast - B57 - B1.3.08.03.03 | Raft Acceptance Testing | 0 | 0 | 0 | 0 | 0 | 6000 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC)
FALSE |  | ITC36120 | REB Re-Testing effort | LSST Forecast - B57 - B1 | 64 | 64 | 2019-06-03 | 2019-08-30 | 531 |  |  | 319 | 2019-06-03 | 2019-08-30 | 2021-08-02 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-03 | 2019-08-30 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 64 | 0 |  | Planned | 0% | 96 | 0 | 96 | 96 | LSST Forecast - B57 - B1.3.08.03.03 | Raft Acceptance Testing | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC)
FALSE |  | OP541386 | RCV: L3 Assembly - Phase 4 (L3 Clean Room Testing) | LSST Forecast - B57 - B1 | 20 | 20 | 2019-06-03 | 2019-06-28 | 121 |  |  | 146 | 2019-06-03 | 2019-06-28 | 2019-11-21 | 2019-12-20 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-03 | 2019-06-28 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement | [7 empty] | L3 Assembly (TEC)
FALSE |  | CCS300110 | Re Program CCS with Holding Pump Logic | LSST Forecast - B57 - B1 | 2 | 2 | 2019-06-06 | 2019-06-07 | 27 |  |  | 0 | 2019-06-06 | 2019-06-07 | 2019-07-16 | 2019-07-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-06 | 2019-06-07 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.08.03 | CCOB HCU | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Martin Nordby
FALSE |  | CCS300040 | Second release of full focal plane software in IR2 with support for 9+ rafts | LSST Forecast - B57 - B1 | 41 | 41 | 2019-06-10 | 2019-08-06 | -9 |  |  | 0 | 2019-06-10 | 2019-08-06 | 2019-05-28 | 2019-07-24 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-06-10 | 2019-08-06 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 41 | 0 |  | Planned | 0% | 360 | 0 | 360 | 360 | LSST Forecast - B57 - B1.3.07.01.03.08.03 | CCOB HCU | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | CCS HCU (TEC) | [7 empty] | CP #02 (CCS Focal Plane Software)
FALSE |  | OP522490_1 | RCV: 3 of 6 Filter Complete and Ready to Ship (MS5) - Filter Fabrication | LSST Forecast - B57 - B1 | 1 | 1 | 2019-06-14 | 2019-06-14 | 245 |  |  | 82 | 2019-06-14 | 2019-06-14 | 2020-06-05 | 2020-06-05 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-14 | 2019-06-14 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | 0-100% Method | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Filters (TEC)
FALSE |  | CAMF669245 | Combined Test Assembly (Carousel + Loader 1+ Auto Changer 1) | LSST Forecast - B57 - B1 | 4 | 4 | 2019-06-25 | 2019-06-28 | -159 |  |  | 0 | 2019-06-25 | 2019-06-28 | 2018-10-24 | 2018-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-25 | 2019-06-28 |  |  |  |  | 0 | 0 | FALSE | FALSE | StartOnOrAfter | 2019-06-25 | None | [6 empty] | 6 | 0 | 5 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Fabrication/Assembly
FALSE |  | CCS300050 | M/S - CCOB HCU | LSST Forecast - B57 - B1 | 20 | 20 | 2019-07-10 | 2019-08-06 | 69 |  |  | 0 | 2019-07-10 | 2019-08-06 | 2019-10-16 | 2019-11-13 | 4000 | 4000 | 0 | 4000 | 4000 | 1 | FALSE | Normal | FALSE | 2019-07-10 | 2019-08-06 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.08.03 | CCOB HCU | 0 | 0 | 0 | 0 | 0 | 4000 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 4% |  | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | CCS HCU (TEC) | [6 empty] | Camera I&T Hardware Control Unit
FALSE |  | OP522490_2 | RCV: 4 of 6 Filter Complete and Ready to Ship (MS5) - Filter Fabrication | LSST Forecast - B57 - B1 | 1 | 1 | 2019-07-23 | 2019-07-23 | 219 |  |  | 56 | 2019-07-23 | 2019-07-23 | 2020-06-05 | 2020-06-05 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-07-23 | 2019-07-23 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | 0-100% Method | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Filters (TEC)
FALSE |  | CCS107000 | Implement Release 2 - Lock Manager | LSST Forecast - B57 - B1 | 30 | 30 | 2019-07-30 | 2019-09-10 | 159 |  |  | 0 | 2019-07-30 | 2019-09-10 | 2020-03-30 | 2020-05-08 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-07-30 | 2019-09-10 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 0 |  | Planned | 0% | 400 | 0 | 400 | 400 | LSST Forecast - B57 - B1.3.07.01.02.05 | CCS Lock Manager | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Design/Engineering | [7 empty] | CCS Core (TEC)
FALSE |  | CRYO73280 | Assemble - Hx and Capillaries - Cryo - Chile System | LSST Forecast - B57 - B1 | 20 | 20 | 2019-08-05 | 2019-08-30 | 10 |  |  | 0 | 2019-08-05 | 2019-08-30 | 2019-08-19 | 2019-09-16 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-08-05 | 2019-08-30 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 16 | 0 | 16 | 16 | LSST Forecast - B57 - B1.3.06.04.06.03.04 | Refrigeration System - Chile System (HX) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC) | [7 empty] | CP #09 (Cryo Chile System for Ready for UT)
FALSE |  | CCS120360 | RCV: Parts - CCS Computing Equipments for the Summit & Base (Other) | LSST Forecast - B57 - B1 | 20 | 20 | 2019-08-19 | 2019-09-16 | 594 |  |  | 0 | 2019-08-19 | 2019-09-16 | 2022-02-01 | 2022-03-01 | 154000 | 154000 | 0 | 154000 | 154000 | 1 | FALSE | Normal | FALSE | 2019-08-19 | 2019-09-16 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.02.02.07 | CCS Core 6.0 Release (Comcam Ship) | 0 | 0 | 0 | 0 | 0 | 154000 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering | [7 empty] | CCS Core (TEC)
FALSE |  | DAQ338700 | Design Prototype (blocks, interfaces, coding, review prep) - Crosstalk Correction Firmware | LSST Forecast - B57 - B1 | 20 | 20 | 2019-09-03 | 2019-09-30 | 4 |  |  | 0 | 2019-09-03 | 2019-09-30 | 2019-09-09 | 2019-10-04 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-09-03 | 2019-09-30 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 160 | 0 | 160 | 160 | LSST Forecast - B57 - B1.3.07.02.02.08 | Crosstalk Correction Firmware | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Engineering Test/Validation |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | DAQ Readout Systems (TEC) |  | ICD's for Phase 3 |  |  |  |  | DAQ Readout Systems | CP #07 (DAQ Crosstalk Correction)
FALSE |  | OP522490_3 | RCV: 5 of 6 Filter Complete and Ready to Ship (MS5) - Filter Fabrication | LSST Forecast - B57 - B1 | 1 | 1 | 2019-09-09 | 2019-09-09 | 186 |  |  | 23 | 2019-09-09 | 2019-09-09 | 2020-06-05 | 2020-06-05 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-09-09 | 2019-09-09 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | 0-100% Method | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Filters (TEC)
FALSE |  | CR222420 | CRTM#5 - Test - CRTM Performance test and optimization | LSST Forecast - B57 - B1 | 10 | 10 | 2019-09-18 | 2019-10-01 | 510 |  |  | 0 | 2019-09-18 | 2019-10-01 | 2021-10-18 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-09-18 | 2019-10-01 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 0 |  | Planned | 0% | 120 | 0 | 120 | 120 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Testing/Integration |  | Other (specify) | [5 empty] | Corner Raft Tower Module (CRTM) (TEC) | CRTM Assy CRT | [5 empty] | Corner Raft Tower Module (CRTM)
FALSE |  | OP522490_4 | RCV: 6 of 6 Filter Complete and Ready to Ship (MS5) - Filter Fabrication | LSST Forecast - B57 - B1 | 1 | 1 | 2019-10-10 | 2019-10-10 | 163 |  |  | 0 | 2019-10-10 | 2019-10-10 | 2020-06-05 | 2020-06-05 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-10-10 | 2019-10-10 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | 0-100% Method | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor |  |  |  |  | Filters (TEC)
Merge Hotspot
The total number of activities with a high number of predecessor links.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | Previous Start | Previous Finish | Percent Complete | Previous Remaining Duration | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | IsLevelOfEffort | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | Global_Basis of Estimate | Global_Cobra Cost Class | Cobra PMT (EV Method)_Global | Global_Color of Money | Global_Control Account Manager | Global_Design Maturity | Global_Judgement Factor | Global_Milestone Levels | Global_Project Phase | Global_Funding Source | Global_EDIA Survey | Global_MS Type | Phase | NSF Milestones | Loading Curve | Sensor Vendor | LSST_CA | Summary Schedule | ICD for NSF Input | LSST Camera Critical Paths | CD2 Budget Changes | DOE Reviews | Critical Path (CD Reviews) | LSST WP Summary | Critical Path (Camera Delivery) | AWARD / NEED Sub-System | Final Design Key Links | CP - CAMM2100 | CP - CAMM2130 | CP - CAMM2160 | BNL Work Org | Last ETC Update | BNL WBS | LSST Story List | Sum Sch 01 (Camera) | Sum Sch 02 (IT w/Needs) | Sum Sch 03 (Sensors_RTM_IT) | LSST Raft Particulate Mitigation | LSST RTM
FALSE |  | SR551531 | RTM22_RSA Construction at TS4 | LSST Forecast - B57 - B1 | 10 | 0 | 2019-01-02 | 2019-01-15 | 0 | 2019-01-02 | 2019-01-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-06-06 | 2019-06-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-02-01 | 2019-02-14 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 9 |  | Complete | 100% | 44 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01.06 | Science Raft Production Assembly and Test | 44 | 44 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Bill Wahl | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Testing/Integration | [7 empty] | Science Raft Production Assembly and Test (TEC) | [6 empty] | Science Raft - Test Stands | [6 empty] | RTM #22 |  | Science Raft System
FALSE |  | CAMF665450 | Verification Testing - Filter Loader | LSST Forecast - B57 - B1 | 33 | 0 | 2019-01-07 | 2019-04-12 | 0 | 2019-01-07 | 2019-04-12 | 0 | 2019-06-01 | 2019-06-01 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2019-02-05 | 2019-03-22 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 33 | 67 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.02 | Filter Loader | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Fabrication/Assembly
FALSE |  | DAQ900350 | Assemble Production COBs | LSST Forecast - B57 - B1 | 24 | 0 | 2019-01-07 | 2019-04-15 | 0 | 2019-01-07 | 2019-04-15 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-01-07 | 2019-02-08 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 4 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 24 | 68 |  | Complete | 100% | 180 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.02 | DAQ COB (Main ATCA DAQ Module) | 180 | 180 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | [11 empty] | DAQ Readout Systems (TEC)
FALSE |  | CRYO61410 | Install Heat-X cans into cryostat and Leak Check - Cryostat Assembly | LSST Forecast - B57 - B1 | 5 | 0 | 2019-01-14 | 2019-04-15 | 0 | 2019-01-14 | 2019-04-15 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2019-02-11 | 2019-02-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 1 | 3 | 0 | 0 | 3 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 63 |  | Complete | 100% | 35 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.01.04 | Refrigeration System - Pre IR2 (HX) | 35 | 35 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Fabrication/Assembly |  | Other (specify) | [5 empty] | Refrigeration System (TEC)
FALSE |  | CRYO61337 | Install/Interconnect compressor cabinets with Power, Utility & Refrigeration Lines in IR-2 | LSST Forecast - B57 - B1 | 20 | 0 | 2019-01-14 | 2019-03-29 | 0 | 2019-01-14 | 2019-03-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-02-11 | 2019-03-11 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 52 |  | Complete | 100% | 200 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.02 | Refrigeration System - IR2 | 200 | 200 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | CBM28900 | Assemble and Inspect - Purge Cabinets | LSST Forecast - B57 - B1 | 20 | 0 | 2019-01-21 | 2019-03-29 | 0 | 2019-01-21 | 2019-03-29 | 0 | 2019-06-01 | 2019-06-01 | 2019-08-12 | 2019-08-12 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-02-01 | 2019-03-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 5 | 5 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 47 |  | Complete | 100% | 450 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.01.02 | Camera Body Development | 450 | 450 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 15% |  | Fabrication/Assembly |  | Other (specify) | [5 empty] | Camera Body Development (TEC) | [6 empty] | Camera Body and Purge Production
FALSE |  | SR300030 | COMP: Ready for CD-4 - Science Sensors | LSST Forecast - B57 - B1 | 0 | 0 | 2019-01-31 | 2019-01-31 | 0 | 2019-01-31 | 2019-01-31 | 0 | 2019-06-01 | 2019-06-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-04-26 | 2019-04-26 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.03 | Science Sensors | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Bill Wahl |  |  | Level 3 Milestone | Management/Administration | [21 empty] | Milestones |  | Science Sensors
FALSE |  | CRYO61635_1 | Pump Down Vacuums | LSST Forecast - B57 - B1 | 2 | 0 | 2019-02-01 | 2019-04-30 | 0 | 2019-02-01 | 2019-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2019-04-02 | 2019-04-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 2 | 0 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 61 |  | Complete | 100% | 114 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.02 | Refrigeration System - IR2 | 114 | 114 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | [11 empty] | Refrigeration System (TEC)
FALSE |  | CAMF661650 | Verification Testing - Auto Changer | LSST Forecast - B57 - B1 | 33 | 0 | 2019-02-01 | 2019-04-12 | 0 | 2019-02-01 | 2019-04-12 | 0 | 2019-06-01 | 2019-06-01 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2019-02-01 | 2019-03-20 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 33 | 49 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.01 | Auto Changer | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Fabrication/Assembly
FALSE |  | ITC31660 | NEED: Vacuum System (pre-production) | LSST Forecast - B57 - B1 | 0 | 0 | 2019-02-07 | 2019-02-07 | 0 | 2019-02-07 | 2019-02-07 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-02-07 | 2019-02-07 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Cryostat
FALSE |  | CBM28350 | Assemble and Inspect - Housing - Camera Body | LSST Forecast - B57 - B1 | 33 | 19 | 2019-02-13 | 2019-06-27 | 42 | 2019-02-13 |  | 0 | 2019-06-03 | 2019-06-27 | 2019-08-01 | 2019-08-27 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-03-13 | 2019-04-26 |  |  |  |  | 0.9 | 0 | FALSE | FALSE | None |  | None |  | 2019-05-28 |  |  |  |  | 5 | 0 | 4 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 33 | 76 |  | InProgress | 90% | 120 | 0 | 120 | 120 | LSST Forecast - B57 - B1.3.06.01.02 | Camera Body Development | 108 | 120 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly |  | Other (specify) | [5 empty] | Camera Body Development (TEC)
FALSE |  | ITC35010 | RTM01_Receive, Install in TS7 & Cool Down | LSST Forecast - B57 - B1 | 2 | 0 | 2019-02-22 | 2019-02-26 | 0 | 2019-02-22 | 2019-02-26 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-30 | 2019-05-30 | 1500 | 1500 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-02-22 | 2019-02-25 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 2 |  | Complete | 100% | 60 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.03 | Raft Acceptance Testing | 60 | 60 | 0 | 1500 | 1500 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC)
FALSE |  | DAQ900410 | Receive Production flash | LSST Forecast - B57 - B1 | 59 | 0 | 2019-03-04 | 2019-04-30 | 0 | 2019-03-04 | 2019-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 74700 | 74700 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-04-01 | 2019-06-21 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 59 | 41 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.13.09 | DAQ Assembled Hardware | 0 | 0 | 0 | 74700 | 55708.47 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Fabrication/Assembly | [7 empty] | DAQ Readout Systems (TEC)
FALSE |  | CBM50800 | Receive, Inspect, Clean, Prep Procured Parts - Shutter | LSST Forecast - B57 - B1 | 12 | 10 | 2019-03-18 | 2019-06-17 | 56 | 2019-03-18 |  | 0 | 2019-06-04 | 2019-06-17 | 2019-08-22 | 2019-09-05 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-05-30 | 2019-06-14 |  |  |  |  | 0.955 | 0 | FALSE | FALSE | None |  | None |  | 2019-06-14 |  |  |  |  | 4 | 0 | 1 | 1 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 12 | 54 |  | InProgress | 95.5% | 232 | 0 | 232 | 232 | LSST Forecast - B57 - B1.3.06.02.02 | Shutter Development | 221.56 | 38.6667 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly |  | Other (specify) | [5 empty] | Shutter Development (TEC) | [6 empty] | Shutter Production
FALSE |  | OP522215 | Phase 2 deliverables per the SOW completed and received (MS6) - First Article Filter Coat | LSST Forecast - B57 - B1 | 31 | 27 | 2019-03-18 | 2019-07-10 | 37 | 2019-03-18 |  | 0 | 2019-06-03 | 2019-07-10 | 2019-07-25 | 2019-08-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-04-01 | 2019-05-13 |  |  |  |  | 0.85 | 0 | FALSE | FALSE | None |  | None |  | 2019-07-10 |  |  |  |  | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 31 | 54 |  | InProgress | 85% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters | (1.10) Task/item is a modification of an existing design | 7% |  | Procurement |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc)
FALSE |  | CRYO646155 | AVAIL: Cryostat Assembly with Refrigeration for Integration (2 Cryo/2 Cold) | LSST Forecast - B57 - B1 | 0 | 0 | 2019-03-29 | 2019-03-29 | 0 | 2019-03-29 | 2019-03-29 | 0 | 2019-06-01 | 2019-06-01 | 2018-12-13 | 2018-12-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2019-04-22 | 2019-04-22 |  |  |  |  | 1 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.04.02 | 2 Cryo/2 Cold Heat Airside Assy | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | [7 empty] | Level 5 Milestone
FALSE |  | SE222452 | Finalize camera assy dwg's and BOM's for IRR (Camera I&T IRR) | LSST Forecast - B57 - B1 | 20 | 0 | 2019-04-01 | 2019-04-19 | 0 | 2019-04-01 | 2019-04-19 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-16 | 2019-09-16 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-05-20 | 2019-06-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | AsLateAsPossible |  | None | [6 empty] | 7 | 0 | 6 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 14 |  | Complete | 100% | 32 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.02 | Mechanical Integration | 32 | 14.4 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC)
FALSE |  | OP522485 | COMP: 1st Production Filter Complete and Ready to Ship - Filter Fabrication | LSST Forecast - B57 - B1 | 0 | 0 | 2019-04-17 | 2019-04-17 | 0 | 2019-04-17 | 2019-04-17 | 0 | 2019-06-01 | 2019-06-01 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-06-03 | 2019-06-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters | (1.10) Task/item is a modification of an existing design | 7% | Level 4 Milestone | Procurement |  |  | Subcontractor
FALSE |  | CBM29200 | Perform Full System Verif Testing - Camera Body | LSST Forecast - B57 - B1 | 10 | 22 | 2019-04-21 | 2019-07-02 | 42 | 2019-04-21 |  | 0 | 2019-06-03 | 2019-07-02 | 2019-08-01 | 2019-08-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-03 | 2019-06-14 |  |  |  |  | 0.5 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 29 |  | InProgress | 50% | 96 | 0 | 96 | 96 | LSST Forecast - B57 - B1.3.06.01.02 | Camera Body Development | 48 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 15% |  | Testing/Integration |  | Other (specify) | [5 empty] | Camera Body Development (TEC) | [6 empty] | Camera Body and Purge Production
FALSE |  | CRYO61685 | AVAIL: Cryostat Assembly with Refrigeration for Integration (2 Cryo/2 Cold) | LSST Forecast - B57 - B1 | 0 | 0 | 2019-04-30 | 2019-04-30 | 0 | 2019-04-30 | 2019-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | FALSE | 2019-05-15 | 2019-05-15 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 3 | 0 | 0 | 1 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.02 | Refrigeration System - IR2 | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 5 Milestone | Fabrication/Assembly | [16 empty] | Cryostat
FALSE |  | CRYO72560 | COMP: Compressor Cabinet Components Ready for Chile System | LSST Forecast - B57 - B1 | 0 | 0 | 2019-04-30 | 2019-04-30 | 0 | 2019-04-30 | 2019-04-30 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-31 | 2019-10-31 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | FALSE | 2019-05-01 | 2019-05-01 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 7 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.02 | Refrigeration System - Chile System (Compressor Cabinet) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Alice Callen |  |  | Level 4 Milestone
FALSE |  | OP521840 | Validation of Vendor Results - Witness Sample | LSST Forecast - B57 - B1 | 32 | 0 | 2019-05-01 | 2019-05-24 | 0 | 2019-05-01 | 2019-05-24 | 0 | 2019-06-01 | 2019-06-01 | 2019-12-12 | 2019-12-12 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-03 | 2019-07-17 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 9 | 0 | 9 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 32 | 17 |  | Complete | 100% | 80 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 80 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 18% |  | Procurement | [7 empty] | Filters (TEC) | Witness Sample
FALSE |  | CRYO70185 | Analyze Data - Cold System Verification Test | LSST Forecast - B57 - B1 | 8 | 5 | 2019-05-20 | 2019-06-07 | -18 | 2019-05-20 |  | 0 | 2019-06-03 | 2019-06-07 | 2019-05-07 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-06-10 | 2019-06-19 |  |  |  |  | 0.5 | 0 | FALSE | TRUE | None |  | None |  | 2019-06-07 |  |  |  |  | 3 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 8 | 9 |  | InProgress | 50% | 40 | 0 | 40 | 40 | LSST Forecast - B57 - B1.3.06.04.06.02 | Refrigeration System - IR2 | 20 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Refrigeration System (TEC) | [6 empty] | Utility Trunk
FALSE |  | OP531470 | TRR Complete - L1-L2 Assembly - Phase 5 | LSST Forecast - B57 - B1 | 10 | 2 | 2019-05-21 | 2019-06-04 | 64 | 2019-05-21 |  | 0 | 2019-06-03 | 2019-06-04 | 2019-09-03 | 2019-09-05 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-06-03 | 2019-06-14 |  |  |  |  | 0.2 | 0 | FALSE | FALSE | None |  | None |  | 2019-06-04 |  |  |  |  | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 8 |  | InProgress | 20% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Scott Winters | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor | [5 empty] | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly) |  |  |  | L1-L2 Opto-Mechanics
FALSE |  | OP531464 | COMP: L1-L2 Assembly Phase 4b | LSST Forecast - B57 - B1 | 0 | 0 | 2019-05-24 | 2019-05-24 | 0 | 2019-05-24 | 2019-05-24 | 0 | 2019-06-01 | 2019-06-01 | 2019-09-05 | 2019-09-05 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | FALSE | 2019-06-03 | 2019-06-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 8 | 0 | 8 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  | Level 4 Milestone | Procurement | [8 empty] | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly)
FALSE |  | ITC92360 | Prep for Pre Ship Review - Com Cam | LSST Forecast - B57 - B1 | 10 | 0 | 2019-05-27 | 2019-05-28 | 0 | 2019-05-27 | 2019-05-28 | 0 | 2019-06-03 | 2019-06-03 | 2019-05-31 | 2019-05-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-07-02 | 2019-07-16 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 11 | 0 | 11 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 0 |  | Complete | 100% | 48 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.06.01 | Commissioning Camera Hardware | 48 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Kevin Reil | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Construction Management | [5 empty] | Commissioning Camera (TEC)
FALSE |  | DAQ900600 | AVAIL: DAQ V3.0 for ComCam, Camera | LSST Forecast - B57 - B1 | 0 | 0 | 2019-05-31 | 2019-05-31 | 0 | 2019-05-31 | 2019-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-10-31 | 2019-10-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-06-03 | 2019-06-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.13.05 | DAQ Version 3.0 | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer |  |  | Level 5 Milestone
FALSE |  | DAQ900620 | AVAIL: DAQ V3.0 for DM Data Challenge | LSST Forecast - B57 - B1 | 0 | 0 | 2019-05-31 | 2019-05-31 | 0 | 2019-05-31 | 2019-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2019-06-03 | 2019-06-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.13.05 | DAQ Version 3.0 | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer |  |  | Level 5 Milestone
FALSE |  | DAQ900635 | COMP: DAQ V3.0 | LSST Forecast - B57 - B1 | 0 | 0 | 2019-05-31 | 2019-05-31 | 0 | 2019-05-31 | 2019-05-31 | 0 | 2019-06-01 | 2019-06-01 | 2019-07-25 | 2019-07-25 | 0 | 0 | 0 | 0 | 0 | 8 | FALSE | Finish Milestone | FALSE | 2019-06-03 | 2019-06-03 |  |  |  |  | 1 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Complete | 100% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.13.05 | DAQ Version 3.0 | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer |  |  | Level 4 Milestone
FALSE |  | CRYO62080 | Requisition - Refrigerant - Chile Hardware | LSST Forecast - B57 - B1 | 20 | 20 | 2019-06-03 | 2019-06-28 | 103 |  |  | 0 | 2019-06-03 | 2019-06-28 | 2019-10-28 | 2019-11-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-03 | 2019-06-28 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.05 | Refrigeration System - Chile System (Equipment & Refrigeration) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  |  | Procurement
FALSE |  | OP521100 | Assemble test stand and prep (Phase 2) | LSST Forecast - B57 - B1 | 30 | 30 | 2019-06-03 | 2019-07-15 | 166 |  |  | 0 | 2019-06-03 | 2019-07-15 | 2020-01-31 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-06-03 | 2019-07-15 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 0 |  | Planned | 0% | 128 | 0 | 128 | 128 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 18% |  | Fabrication/Assembly |  | Other (specify) | [5 empty] | Filters (TEC) | Production Filter Frames | [5 empty] | Filter Opto-Mechanics
FALSE |  | OP522650 | Support Filter coating | LSST Forecast - B57 - B1 | 140 | 140 | 2019-06-03 | 2019-12-19 | 136 |  |  | 29 | 2019-06-03 | 2019-12-19 | 2019-12-16 | 2020-07-07 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-03 | 2019-12-19 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 140 | 0 |  | Planned | 0% | 392 | 0 | 392 | 392 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 18% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | Filters (TEC) | Production Filters Coating | [5 empty] | Filter Optics
FALSE |  | DAQ900675 | COMP: DAQ V4.0 | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-03 | 2019-06-03 | 259 |  |  | 0 | 2019-06-03 | 2019-06-03 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2019-06-03 | 2019-06-03 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.13.06 | DAQ Version 4.0 | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer |  |  | Level 4 Milestone
FALSE |  | ITC31813_1 | START: Cryostat Vacuum Testing | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-03 | 2019-06-03 | -14 |  |  | 4 | 2019-06-03 | 2019-06-03 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-06-03 | 2019-06-03 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Testing/Integration
FALSE |  | OP531490 | Final Alignment/Integration Complete - L1-L2 Assembly - Phase 5 | LSST Forecast - B57 - B1 | 10 | 10 | 2019-06-05 | 2019-06-18 | 64 |  |  | 0 | 2019-06-05 | 2019-06-18 | 2019-09-05 | 2019-09-19 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-05 | 2019-06-18 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment |  | TEC Non-ARRA | Scott Winters | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | Subcontractor | [5 empty] | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly) |  |  |  | L1-L2 Opto-Mechanics
FALSE |  | ITC32730 | COMP: Prepare for Cryostat Vacuum bake-out and pum/vent | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-05 | 2019-06-05 | 98 |  |  | 116 | 2019-06-05 | 2019-06-05 | 2019-10-23 | 2019-10-23 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-06-05 | 2019-06-05 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Martin Nordby |  |  | Level 4 Milestone
FALSE |  | CRYO70205 | COMP: Cold System Verification Test | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-07 | 2019-06-07 | -18 |  |  | 0 | 2019-06-07 | 2019-06-07 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2019-06-07 | 2019-06-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.02 | Refrigeration System - IR2 | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Alice Callen | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% | Level 4 Milestone | Design/Engineering
FALSE |  | CRYO61685_1 | AVAIL: Cryostat Assembly with Refrigeration for Integration (4 Cryo) | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-07 | 2019-06-07 | -18 |  |  | 0 | 2019-06-07 | 2019-06-07 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2019-06-07 | 2019-06-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.02 | Refrigeration System - IR2 | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 5 Milestone | Fabrication/Assembly | [16 empty] | Cryostat
FALSE |  | ITC31835 | NEED: Completion of Run Single-Circuit Cryo/Cold System Tests (4 Cryo) | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-07 | 2019-06-07 | -18 |  |  | 0 | 2019-06-07 | 2019-06-07 | 2019-05-13 | 2019-05-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | TRUE | 2019-06-07 | 2019-06-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Fabrication and Assembly | [12 empty] | Integration and Test
FALSE |  | CCS300035 | NEED: DAQ with support for 9 rafts in IR2 | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-10 | 2019-06-10 | -9 |  |  | 0 | 2019-06-10 | 2019-06-10 | 2019-05-24 | 2019-05-24 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-06-10 | 2019-06-10 |  |  |  |  | 0 | 0 | FALSE | FALSE | FinishOnOrAfter | 2019-06-10 | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.08.03 | CCOB HCU | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Tony Johnson |  |  | Level 5 Milestone | Design/Engineering | [15 empty] | CP #02 (CCS Focal Plane Software)
FALSE |  | CCS300040 | Second release of full focal plane software in IR2 with support for 9+ rafts | LSST Forecast - B57 - B1 | 41 | 41 | 2019-06-10 | 2019-08-06 | -9 |  |  | 0 | 2019-06-10 | 2019-08-06 | 2019-05-28 | 2019-07-24 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-06-10 | 2019-08-06 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 41 | 0 |  | Planned | 0% | 360 | 0 | 360 | 360 | LSST Forecast - B57 - B1.3.07.01.03.08.03 | CCOB HCU | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | CCS HCU (TEC) | [7 empty] | CP #02 (CCS Focal Plane Software)
FALSE |  | ITC31820_1 | ETU De-integration | LSST Forecast - B57 - B1 | 12 | 12 | 2019-06-10 | 2019-06-25 | -18 |  |  | 0 | 2019-06-10 | 2019-06-25 | 2019-05-14 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2019-06-10 | 2019-06-25 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 12 | 0 |  | Planned | 0% | 238 | 0 | 238 | 238 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC00550 | COMP: Commissioning Camera Shipped to Tucson | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-14 | 2019-06-14 | -10 |  |  | 0 | 2019-06-14 | 2019-06-14 | 2019-05-31 | 2019-05-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-06-14 | 2019-06-14 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration
FALSE |  | ITC32170 | NEED: Corner Raft Tower/RCM #1 thru #4 | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-21 | 2019-06-21 | 2 |  |  | 20 | 2019-06-21 | 2019-06-21 | 2019-06-25 | 2019-06-25 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-06-21 | 2019-06-21 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 7 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration | [16 empty] | Corner Raft System
FALSE |  | SR000040 | COMP: Ready for CD-4 - Science Rafts | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-21 | 2019-06-21 | 593 |  |  | 375 | 2019-06-21 | 2019-06-21 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-06-21 | 2019-06-21 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 21 | 0 | 21 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01 | Science Raft System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Bill Wahl |  |  | Level 3 Milestone | Management/Administration | [21 empty] | Milestones |  | Science Raft System
FALSE |  | SR000950 | COMP: Last Production RTM (#21) Available for I&T | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-21 | 2019-06-21 | 181 |  |  | 0 | 2019-06-21 | 2019-06-21 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2019-06-21 | 2019-06-21 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 12 | 0 | 12 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.01 | Science Raft System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Bill Wahl |  |  | Level 3 Milestone | Management/Administration | [21 empty] | Milestones |  | Science Raft System
FALSE |  | CCS126740 | Finalize CCS Camera Body drivers, subsystem, gui - Camera Body HCU | LSST Forecast - B57 - B1 | 20 | 20 | 2019-06-25 | 2019-07-23 | 33 |  |  | 0 | 2019-06-25 | 2019-07-23 | 2019-08-12 | 2019-09-09 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-25 | 2019-07-23 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 120 | 0 | 120 | 120 | LSST Forecast - B57 - B1.3.07.01.03.07 | Camera Body HCU | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 5% |  | Testing/Integration | [7 empty] | CCS HCU (TEC) | [7 empty] | CP #11 (CCS, Camera Body HCU)
FALSE |  | OP530845 | Phase 4a Close-out | LSST Forecast - B57 - B1 | 5 | 5 | 2019-06-25 | 2019-07-01 | 85 |  |  | 0 | 2019-06-25 | 2019-07-01 | 2019-10-24 | 2019-10-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-25 | 2019-07-01 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 0 |  | Planned | 0% | 16 | 0 | 16 | 16 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 0% |  | Procurement |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | L1-L2 Assembly (TEC) | L1_L2 Summary | [5 empty] | L1-L2 Optics
FALSE |  | CAMF669245 | Combined Test Assembly (Carousel + Loader 1+ Auto Changer 1) | LSST Forecast - B57 - B1 | 4 | 4 | 2019-06-25 | 2019-06-28 | -159 |  |  | 0 | 2019-06-25 | 2019-06-28 | 2018-10-24 | 2018-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-06-25 | 2019-06-28 |  |  |  |  | 0 | 0 | FALSE | FALSE | StartOnOrAfter | 2019-06-25 | None | [6 empty] | 6 | 0 | 5 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Fabrication/Assembly
FALSE |  | ITC35870 | RTM19_Receive, Install in TS7 & Cool Down | LSST Forecast - B57 - B1 | 5 | 5 | 2019-06-25 | 2019-07-01 | 8 |  |  | 0 | 2019-06-25 | 2019-07-01 | 2019-07-08 | 2019-07-12 | 1500 | 1500 | 0 | 1500 | 1500 | 1 | FALSE | Normal | FALSE | 2019-06-25 | 2019-07-01 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 0 |  | Planned | 0% | 60 | 0 | 60 | 60 | LSST Forecast - B57 - B1.3.08.03.03 | Raft Acceptance Testing | 0 | 0 | 0 | 0 | 0 | 1500 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [7 empty] | CP #08 (I&T RTM Test)
FALSE |  | ITC31840 | START: Science Raft Tower Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-25 | 2019-06-25 | -18 |  |  | 0 | 2019-06-25 | 2019-06-25 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | TRUE | 2019-06-25 | 2019-06-25 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 10 | 0 | 10 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [11 empty] | CP #01 (Cryostat/Camera Integration)
FALSE |  | CRYO02900 | COMP: Cryostat Early Hardware & Software Ready for Summit | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-28 | 2019-06-28 | 86 |  |  | 60 | 2019-06-28 | 2019-06-28 | 2019-10-31 | 2019-10-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-06-28 | 2019-06-28 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04 | Cryostat | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 3 Milestone | Management/Administration
FALSE |  | OP541380 | AVAIL: L3 Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-28 | 2019-06-28 | -42 |  |  | 0 | 2019-06-28 | 2019-06-28 | 2019-04-30 | 2019-04-30 | 0 | 0 | 0 | 0 | 0 | 6 | FALSE | Finish Milestone | FALSE | 2019-06-28 | 2019-06-28 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.04 | L3 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  | Level 5 Milestone | Procurement | [10 empty] | Critical Path #2 (L1_L2 Assembly) | [5 empty] | Optics
FALSE |  | CRYO02875 | COMP: Chile Compressor System Ready for Pathfinder | LSST Forecast - B57 - B1 | 0 | 0 | 2019-06-28 | 2019-06-28 | 575 |  |  | 122 | 2019-06-28 | 2019-06-28 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-06-28 | 2019-06-28 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04 | Cryostat | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 3 Milestone | Management/Administration
FALSE |  | CAMF669250 | Combined Functionality and Performance Tests (Carousel + Loader 1 + Auto Changer 1) | LSST Forecast - B57 - B1 | 18 | 18 | 2019-07-01 | 2019-07-25 | -159 |  |  | 0 | 2019-07-01 | 2019-07-25 | 2018-10-30 | 2018-11-26 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2019-07-01 | 2019-07-25 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 8 | 0 | 8 | 0 | 0 | 0 | 3 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 18 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Fabrication/Assembly
FALSE |  | CAMF650350 | START: Filter Exchange System Testing | LSST Forecast - B57 - B1 | 0 | 0 | 2019-07-01 | 2019-07-01 | -104 |  |  | 0 | 2019-07-01 | 2019-07-01 | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 5 | FALSE | Finish Milestone | FALSE | 2019-07-01 | 2019-07-01 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 0 | 3 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03 | Exchange System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  | Level 3 Milestone | Management/Administration
FALSE |  | CCS320500 | Vendor Lead Time - Hardware - Camera Rotator HCU | LSST Forecast - B57 - B1 | 20 | 20 | 2019-07-01 | 2019-07-29 | 18 |  |  | 0 | 2019-07-01 | 2019-07-29 | 2019-07-26 | 2019-08-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-07-01 | 2019-07-29 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.01.03.08.05 | Camera Rotator HCU | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Tony Johnson |  |  |  | Procurement
FALSE |  | DAQ910040 | Client Readout Software - GDS | LSST Forecast - B57 - B1 | 44 | 44 | 2019-07-01 | 2019-08-30 | 135 |  |  | 4 | 2019-07-01 | 2019-08-30 | 2020-01-27 | 2020-03-27 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-07-01 | 2019-08-30 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 44 | 0 |  | Planned | 0% | 40 | 0 | 40 | 40 | LSST Forecast - B57 - B1.3.07.02.02.15 | Guiding Data System (GDS) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | DAQ Readout Systems (TEC)
FALSE |  | DAQ910050 | Client API Software - GDS | LSST Forecast - B57 - B1 | 48 | 48 | 2019-07-01 | 2019-09-06 | 131 |  |  | 0 | 2019-07-01 | 2019-09-06 | 2020-01-21 | 2020-03-27 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-07-01 | 2019-09-06 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 48 | 0 |  | Planned | 0% | 72 | 0 | 72 | 72 | LSST Forecast - B57 - B1.3.07.02.02.15 | Guiding Data System (GDS) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | DAQ Readout Systems (TEC)
FALSE |  | OP530850 | COMP: L1-L2 Assembly Phase 4a | LSST Forecast - B57 - B1 | 0 | 0 | 2019-07-01 | 2019-07-01 | 85 |  |  | 0 | 2019-07-01 | 2019-07-01 | 2019-10-31 | 2019-10-31 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2019-07-01 | 2019-07-01 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  | Level 4 Milestone | Procurement | [8 empty] | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly)
FALSE |  | ITC31880 | Integrate Science Raft Tower #2 of 21 | LSST Forecast - B57 - B1 | 4 | 4 | 2019-07-02 | 2019-07-08 | -18 |  |  | 0 | 2019-07-02 | 2019-07-08 | 2019-06-06 | 2019-06-11 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-07-02 | 2019-07-08 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 102 | 0 | 102 | 102 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | CBM29300 | Prepare for Pre-Ship Review - Camera Body | LSST Forecast - B57 - B1 | 10 | 10 | 2019-07-03 | 2019-07-17 | 37 |  |  | 4 | 2019-07-03 | 2019-07-17 | 2019-08-26 | 2019-09-09 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-07-03 | 2019-07-17 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 0 |  | Planned | 0% | 344 | 0 | 344 | 344 | LSST Forecast - B57 - B1.3.06.01.02 | Camera Body Development | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 15% |  | Testing/Integration |  | Other (specify) | [5 empty] | Camera Body Development (TEC) | [6 empty] | Camera Body and Purge Production
FALSE |  | CBM51500 | Assemble and Test Shutter Units - Shutter | LSST Forecast - B57 - B1 | 40 | 40 | 2019-07-03 | 2019-08-28 | 45 |  |  | 0 | 2019-07-03 | 2019-08-28 | 2019-09-06 | 2019-10-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-07-03 | 2019-08-28 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 0 |  | Planned | 0% | 448 | 0 | 448 | 448 | LSST Forecast - B57 - B1.3.06.02.02 | Shutter Development | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 0% |  | Testing/Integration |  | Other (specify) | [5 empty] | Shutter Development (TEC) | [6 empty] | Shutter Production | CP #13 (Shutter)
FALSE |  | OP522270 | Mount filters in frame - First Article | LSST Forecast - B57 - B1 | 45 | 45 | 2019-07-11 | 2019-09-12 | 124 |  |  | 0 | 2019-07-11 | 2019-09-12 | 2020-01-09 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-07-11 | 2019-09-12 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 45 | 0 |  | Planned | 0% | 116 | 0 | 116 | 116 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 18% |  | Testing/Integration |  | Other (specify) | [5 empty] | Filters (TEC) | Production Filters Polish and integration | [5 empty] | Filter Opto-Mechanics
FALSE |  | OP522550 | Production Readiness Confirmation (MS7) - Filter Coating | LSST Forecast - B57 - B1 | 20 | 20 | 2019-07-11 | 2019-08-07 | 107 |  |  | 0 | 2019-07-11 | 2019-08-07 | 2019-12-12 | 2020-01-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-07-11 | 2019-08-07 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  |  | Procurement
FALSE |  | ITC31940 | Integrate Science Raft Tower #4 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-07-15 | 2019-07-16 | -18 |  |  | 0 | 2019-07-15 | 2019-07-16 | 2019-06-18 | 2019-06-19 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-07-15 | 2019-07-16 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | CR221720 | COMP: Corner raft tower shipping container | LSST Forecast - B57 - B1 | 0 | 0 | 2019-07-15 | 2019-07-15 | 565 |  |  | 55 | 2019-07-15 | 2019-07-15 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-07-15 | 2019-07-15 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02.02 | Corner Raft Tower Module (CRTM) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 7% | Level 4 Milestone | Fabrication/Assembly | [8 empty] | CRTM Fab/assy Tooling/shipping
FALSE |  | DAQ920100 | COMP: Remote FPGA Reprogramming | LSST Forecast - B57 - B1 | 0 | 0 | 2019-07-15 | 2019-07-15 | 275 |  |  | 293 | 2019-07-15 | 2019-07-15 | 2020-08-26 | 2020-08-26 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-07-15 | 2019-07-15 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02.02.16 | Remote FPGA Reprogramming | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment |  | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% | Level 5 Milestone | Design/Engineering
FALSE |  | ITC32225 | Integrate Corner Raft Tower #1 of 4 | LSST Forecast - B57 - B1 | 4 | 4 | 2019-07-23 | 2019-07-26 | -18 |  |  | 0 | 2019-07-23 | 2019-07-26 | 2019-06-26 | 2019-07-01 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-07-23 | 2019-07-26 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 119 | 0 | 119 | 119 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | CBM29400 | PSR - Pre-Ship Review - Camera Body | LSST Forecast - B57 - B1 | 5 | 5 | 2019-07-24 | 2019-07-30 | 33 |  |  | 0 | 2019-07-24 | 2019-07-30 | 2019-09-10 | 2019-09-16 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2019-07-24 | 2019-07-30 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 0 |  | Planned | 0% | 100 | 0 | 100 | 100 | LSST Forecast - B57 - B1.3.06.01.02 | Camera Body Development | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Martin Nordby | (1.35) Task/item is a new design and/or requires some R&D (not beyond state of art) | 15% |  | Testing/Integration |  | Other (specify) | [5 empty] | Camera Body Development (TEC) | [6 empty] | Camera Body and Purge Production | CP #11 (CCS, Camera Body HCU)
FALSE |  | ITC33950 | Initial Integration - Cryo-Equip | LSST Forecast - B57 - B1 | 28 | 28 | 2019-07-24 | 2019-08-30 | 36 |  |  | 0 | 2019-07-24 | 2019-08-30 | 2019-09-13 | 2019-10-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-07-24 | 2019-08-30 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None |  | 2019-08-30 |  |  |  |  | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 28 | 0 |  | Planned | 0% | 280 | 0 | 280 | 280 | LSST Forecast - B57 - B1.3.08.03.02 | Cryostat Handling Equipment | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | Cryostat I&T (TEC) | [7 empty] | CP #12 (Cryo Equip)
FALSE |  | SE224070 | LCA-17 as-built allocation | LSST Forecast - B57 - B1 | 60 | 60 | 2019-07-25 | 2019-10-17 | 218 |  |  | 106 | 2019-07-25 | 2019-10-17 | 2020-06-17 | 2020-09-10 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2019-07-25 | 2019-10-17 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 0 |  | Planned | 0% | 110 | 0 | 110 | 110 | LSST Forecast - B57 - B1.3.02.02.04 | Optics system analysis | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | OP531590 | COMP: L1-L2 Assembly Phase 5 | LSST Forecast - B57 - B1 | 0 | 0 | 2019-07-31 | 2019-07-31 | 64 |  |  | 0 | 2019-07-31 | 2019-07-31 | 2019-10-31 | 2019-10-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-07-31 | 2019-07-31 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.03 | L1-L2 Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  | Level 4 Milestone | Procurement | [8 empty] | L1_L2 Summary |  | Critical Path #2 (L1_L2 Assembly)
FALSE |  | CRYO90050 | Inspect Cryostat Utility Trunk | LSST Forecast - B57 - B1 | 15 | 15 | 2019-08-06 | 2019-08-26 | 19 |  |  | 0 | 2019-08-06 | 2019-08-26 | 2019-09-03 | 2019-09-23 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-08-06 | 2019-08-26 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 1 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 0 |  | Planned | 0% | 141 | 0 | 141 | 141 | LSST Forecast - B57 - B1.3.06.05.02 | Utility Trunk Thermo-Mechanical and Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Fabrication/Assembly |  | Other (specify) | [5 empty] | Utility Trunk Thermo-Mechanical and Assembly (TEC) | [6 empty] | Utility Trunk | CP #10 (Utility Trunk)
FALSE |  | ITC32000 | Integrate Science Raft Tower #7 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-08-12 | 2019-08-13 | -18 |  |  | 0 | 2019-08-12 | 2019-08-13 | 2019-07-17 | 2019-07-18 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-08-12 | 2019-08-13 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32020 | Integrate Science Raft Tower #8 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-08-14 | 2019-08-15 | -18 |  |  | 0 | 2019-08-14 | 2019-08-15 | 2019-07-19 | 2019-07-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-08-14 | 2019-08-15 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32040 | Integrate Science Raft Tower #9 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-08-16 | 2019-08-19 | -18 |  |  | 0 | 2019-08-16 | 2019-08-19 | 2019-07-23 | 2019-07-24 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-08-16 | 2019-08-19 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | SE222432 | IRR Analyze Interfaces & Impacts - SEs (Camera I&T IRR) | LSST Forecast - B57 - B1 | 20 | 20 | 2019-08-16 | 2019-09-13 | 0 |  |  | 0 | 2019-08-16 | 2019-09-13 | 2019-08-16 | 2019-09-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-08-16 | 2019-09-13 |  |  |  |  | 0 | 0 | FALSE | FALSE | AsLateAsPossible |  | None | [6 empty] | 6 | 0 | 5 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 8 | 0 | 8 | 8 | LSST Forecast - B57 - B1.3.02.02.02 | Mechanical Integration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC)
FALSE |  | CCS117450 | Support deployment of FCS at SLAC | LSST Forecast - B57 - B1 | 100 | 100 | 2019-08-19 | 2020-01-23 | 35 |  |  | 53 | 2019-08-19 | 2020-01-23 | 2019-10-08 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-08-19 | 2020-01-23 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 7 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 100 | 0 |  | Planned | 0% | 200 | 0 | 200 | 200 | LSST Forecast - B57 - B1.3.07.01.03.05 | Filter/Carousel HCU | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Design/Engineering | [7 empty] | CCS HCU (TEC)
FALSE |  | ITC32140 | BOT Testing with Raft Tower #1-9 | LSST Forecast - B57 - B1 | 38 | 38 | 2019-08-20 | 2019-10-11 | -18 |  |  | 0 | 2019-08-20 | 2019-10-11 | 2019-07-25 | 2019-09-17 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2019-08-20 | 2019-10-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 38 | 0 |  | Planned | 0% | 517 | 0 | 517 | 517 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  |  |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | CAMF669270 | Subsystem Packaging - Carousel | LSST Forecast - B57 - B1 | 4 | 4 | 2019-08-20 | 2019-08-23 | -176 |  |  | 0 | 2019-08-20 | 2019-08-23 | 2018-11-27 | 2018-11-30 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-08-20 | 2019-08-23 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 9 | 0 | 9 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 4 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.03 | Carousel | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  |  | Fabrication/Assembly | [15 empty] | CP #03 (Carousel/Camera Integration)
FALSE |  | ITC21550 | Assemble and Test CCOB | LSST Forecast - B57 - B1 | 30 | 30 | 2019-08-27 | 2019-10-08 | 55 |  |  | 0 | 2019-08-27 | 2019-10-08 | 2019-11-13 | 2020-01-10 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-08-27 | 2019-10-08 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.02.03.02 | CCOB (France) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  | TEC Non-ARRA | Tim Bond |  |  |  | Testing/Integration |  |  |  | Fabrication and Assembly
FALSE |  | ITC35930 | RTM21_Receive, Install in TS7 & Cool Down | LSST Forecast - B57 - B1 | 3 | 3 | 2019-08-30 | 2019-09-04 | 8 |  |  | 0 | 2019-08-30 | 2019-09-04 | 2019-09-12 | 2019-09-16 | 1500 | 1500 | 0 | 1500 | 1500 | 2 | FALSE | Normal | FALSE | 2019-08-30 | 2019-09-04 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 3 | 0 |  | Planned | 0% | 60 | 0 | 60 | 60 | LSST Forecast - B57 - B1.3.08.03.03 | Raft Acceptance Testing | 0 | 0 | 0 | 0 | 0 | 1500 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [7 empty] | CP #08 (I&T RTM Test)
FALSE |  | ITC19395 | NEED: Rotator from Telescope | LSST Forecast - B57 - B1 | 0 | 0 | 2019-09-04 | 2019-09-04 | 2 |  |  | 2 | 2019-09-04 | 2019-09-04 | 2019-09-06 | 2019-09-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-09-04 | 2019-09-04 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  |  | Rotator fromTelescope
FALSE |  | ITC35600 | RTM13_Receive, Install in TS7 & Cool Down | LSST Forecast - B57 - B1 | 5 | 5 | 2019-09-05 | 2019-09-11 | 8 |  |  | 0 | 2019-09-05 | 2019-09-11 | 2019-09-17 | 2019-09-23 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-09-05 | 2019-09-11 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 0 |  | Planned | 0% | 60 | 0 | 60 | 60 | LSST Forecast - B57 - B1.3.08.03.03 | Raft Acceptance Testing | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) | [7 empty] | CP #08 (I&T RTM Test)
FALSE |  | ITC19415 | Prep for C_IRR - Camera I&T | LSST Forecast - B57 - B1 | 5 | 5 | 2019-09-09 | 2019-09-13 | 0 |  |  | 0 | 2019-09-09 | 2019-09-13 | 2019-09-09 | 2019-09-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-09-09 | 2019-09-13 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 11 | 0 | 11 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 0 |  | Planned | 0% | 140 | 0 | 140 | 140 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Commissioning and Testing | [5 empty] | Camera I&T (TEC) | [7 empty] | CP #04 (Integration Stand, Camera IRR/Assy)
FALSE |  | DAQ910070 | Integration & Test - GDS | LSST Forecast - B57 - B1 | 60 | 60 | 2019-09-09 | 2019-12-03 | 131 |  |  | 0 | 2019-09-09 | 2019-12-03 | 2020-03-30 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-09-09 | 2019-12-03 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 0 |  | Planned | 0% | 224 | 0 | 224 | 224 | LSST Forecast - B57 - B1.3.07.02.02.15 | Guiding Data System (GDS) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Michael Huffer | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 2% |  | Design/Engineering |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | DAQ Readout Systems (TEC)
FALSE |  | ITC19425 | C_IRR - Camera I&T | LSST Forecast - B57 - B1 | 1 | 1 | 2019-09-16 | 2019-09-16 | 0 |  |  | 0 | 2019-09-16 | 2019-09-16 | 2019-09-16 | 2019-09-16 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-09-16 | 2019-09-16 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 8 | 0 | 8 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 1 | 0 |  | Planned | 0% | 64 | 0 | 64 | 64 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Commissioning and Testing | [5 empty] | Camera I&T (TEC) | [7 empty] | CP #04 (Integration Stand, Camera IRR/Assy)
FALSE |  | ITC19445 | START: Camera I&T | LSST Forecast - B57 - B1 | 0 | 0 | 2019-09-16 | 2019-09-16 | 0 |  |  | 0 | 2019-09-16 | 2019-09-16 | 2019-09-16 | 2019-09-16 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2019-09-16 | 2019-09-16 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Testing/Integration |  |  |  | Fabrication and Assembly
FALSE |  | ITC19500 | Camera Assembly - Main Body Acceptance | LSST Forecast - B57 - B1 | 10 | 10 | 2019-09-17 | 2019-09-30 | 0 |  |  | 8 | 2019-09-17 | 2019-09-30 | 2019-09-17 | 2019-09-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-09-17 | 2019-09-30 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 0 |  | Planned | 0% | 40 | 0 | 40 | 40 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Camera I&T (TEC) | [6 empty] | Camera I&T | CP #04 (Integration Stand, Camera IRR/Assy)
FALSE |  | CCS120370 | Install OS/Software, Test Prior to Ship (Other) | LSST Forecast - B57 - B1 | 20 | 20 | 2019-09-17 | 2019-10-14 | 594 |  |  | 0 | 2019-09-17 | 2019-10-14 | 2022-03-02 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-09-17 | 2019-10-14 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 60 | 0 | 60 | 60 | LSST Forecast - B57 - B1.3.07.01.02.02.07 | CCS Core 6.0 Release (Comcam Ship) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tony Johnson | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 1% |  | Design/Engineering |  | Special Equipment (ie - microscopes, probes, instruments, detectors, etc) | [5 empty] | CCS Core (TEC)
FALSE |  | CAMM9230 | COMP: RTM22 acceptance package available in eTraveler | LSST Forecast - B57 - B1 | 0 | 0 | 2019-09-20 | 2019-09-20 | 610 |  |  | 305 | 2019-09-20 | 2019-09-20 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-09-20 | 2019-09-20 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.07 | NSF New Interface Milestones (Watch) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration
FALSE |  | CAMM2260 | COMP: Early Hardware & Software Ready for Summit | LSST Forecast - B57 - B1 | 0 | 0 | 2019-09-24 | 2019-09-24 | 26 |  |  | 303 | 2019-09-24 | 2019-09-24 | 2019-10-31 | 2019-10-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-09-24 | 2019-09-24 |  |  |  |  | 0 | 0 | FALSE | FALSE | FinishOnOrBefore | 2019-10-31 | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.01 | DOE Project Milestones | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 2 Milestone | Management/Administration
FALSE |  | CR010200 | COMP: Ready for CD-4 - Corner Raft | LSST Forecast - B57 - B1 | 0 | 0 | 2019-10-01 | 2019-10-01 | 510 |  |  | 298 | 2019-10-01 | 2019-10-01 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-10-01 | 2019-10-01 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 8 | 0 | 8 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.04.02 | Corner Raft System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 3 Milestone | Management/Administration
FALSE |  | OP522630 | Procure Filter coating (MS9) - Remaining Production Filters | LSST Forecast - B57 - B1 | 80 | 80 | 2019-10-08 | 2020-02-04 | 107 |  |  | 0 | 2019-10-08 | 2020-02-04 | 2020-03-16 | 2020-07-07 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-10-08 | 2020-02-04 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 3 | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 80 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  |  | Procurement | [8 empty] | Production Filters Coating
FALSE |  | CAMF650300 | COMP: Ready for CD-4 - Exchange System | LSST Forecast - B57 - B1 | 0 | 0 | 2019-10-10 | 2019-10-10 | 515 |  |  | 263 | 2019-10-10 | 2019-10-10 | 2021-11-16 | 2021-11-16 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-10-10 | 2019-10-10 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03 | Exchange System | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  | Level 3 Milestone | Management/Administration
FALSE |  | CAMF661700 | AVAIL: Ready for Integration - Auto Changer | LSST Forecast - B57 - B1 | 0 | 0 | 2019-10-10 | 2019-10-10 | 9 |  |  | 0 | 2019-10-10 | 2019-10-10 | 2019-10-23 | 2019-10-23 | 0 | 0 | 0 | 0 | 0 | 5 | FALSE | Finish Milestone | FALSE | 2019-10-10 | 2019-10-10 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 2 | 0 | 0 | 1 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.01 | Auto Changer | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  | Level 5 Milestone | Fabrication/Assembly | [16 empty] | Exchange System
FALSE |  | CAMF665500 | AVAIL: Ready for Integration - Filter Loader | LSST Forecast - B57 - B1 | 0 | 0 | 2019-10-10 | 2019-10-10 | 153 |  |  | 0 | 2019-10-10 | 2019-10-10 | 2020-06-02 | 2020-06-02 | 0 | 0 | 0 | 0 | 0 | 5 | FALSE | Finish Milestone | FALSE | 2019-10-10 | 2019-10-10 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.03.02 | Filter Loader | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Nadine Kurita |  |  | Level 5 Milestone | Fabrication/Assembly | [16 empty] | Exchange System
FALSE |  | CAMM7065 | COMP: Filter Exchange System | LSST Forecast - B57 - B1 | 0 | 0 | 2019-10-10 | 2019-10-10 | 596 |  |  | 291 | 2019-10-10 | 2019-10-10 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2019-10-10 | 2019-10-10 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.02 | NSF Watched Milestones | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration |  |  |  |  | Rotator fromTelescope
FALSE |  | OP522495 | All Phase 2 Deliverables Received (MS6) - Filter Fabrication | LSST Forecast - B57 - B1 | 20 | 20 | 2019-10-11 | 2019-11-07 | 163 |  |  | 0 | 2019-10-11 | 2019-11-07 | 2020-06-08 | 2020-07-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-10-11 | 2019-11-07 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 7 | 0 | 6 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  |  | Procurement | [8 empty] | Production Filters Polish and integration
FALSE |  | ITC32180 | Integrate Science Raft Tower #10 of 21 | LSST Forecast - B57 - B1 | 6 | 6 | 2019-10-14 | 2019-10-21 | -18 |  |  | 0 | 2019-10-14 | 2019-10-21 | 2019-09-18 | 2019-09-25 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-10-14 | 2019-10-21 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 6 | 0 |  | Planned | 0% | 147 | 0 | 147 | 147 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing | [5 empty] | Cryostat I&T (TEC) | [5 empty] | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | CRYO91100 | Test and Verify - Cryostat Utility Trunk | LSST Forecast - B57 - B1 | 20 | 20 | 2019-11-19 | 2019-12-18 | 10 |  |  | 0 | 2019-11-19 | 2019-12-18 | 2019-12-05 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-11-19 | 2019-12-18 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 532 | 0 | 532 | 532 | LSST Forecast - B57 - B1.3.06.05.02 | Utility Trunk Thermo-Mechanical and Assembly | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Alice Callen | (1.25) Task/item is a new design, not exotic, being estimated with no prior experience | 3% |  | Fabrication/Assembly |  | Other (specify) | [5 empty] | Utility Trunk Thermo-Mechanical and Assembly (TEC) | [6 empty] | Utility Trunk | CP #09 (Cryo Chile System for Ready for UT)
FALSE |  | ITC32400 | Integrate Science Raft Tower #21 of 21 | LSST Forecast - B57 - B1 | 2 | 2 | 2019-11-19 | 2019-11-20 | -18 |  |  | 0 | 2019-11-19 | 2019-11-20 | 2019-10-24 | 2019-10-25 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-11-19 | 2019-11-20 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 59 | 0 | 59 | 59 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | OP522700 | Mount filters in frame - 1 filter | LSST Forecast - B57 - B1 | 40 | 40 | 2019-11-19 | 2020-01-21 | 107 |  |  | 0 | 2019-11-19 | 2020-01-21 | 2020-04-27 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2019-11-19 | 2020-01-21 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 0 |  | Planned | 0% | 116 | 0 | 116 | 116 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 18% |  | Testing/Integration |  | Other (specify) | [5 empty] | Filters (TEC) | Production Filters Polish and integration | [5 empty] | Filter Opto-Mechanics
FALSE |  | ITC00330 | START: Integrated Cryostat Testing | LSST Forecast - B57 - B1 | 0 | 0 | 2019-11-21 | 2019-11-21 | -18 |  |  | 0 | 2019-11-21 | 2019-11-21 | 2019-10-25 | 2019-10-25 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | TRUE | 2019-11-21 | 2019-11-21 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration
FALSE |  | ITC19760 | Camera Assembly - Shutter | LSST Forecast - B57 - B1 | 27 | 27 | 2019-12-19 | 2020-02-10 | -8 |  |  | 0 | 2019-12-19 | 2020-02-10 | 2019-12-09 | 2020-01-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-12-19 | 2020-02-10 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 27 | 0 |  | Planned | 0% | 407 | 0 | 407 | 407 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Camera I&T (TEC) | [6 empty] | Camera I&T | CP #03 (Carousel/Camera Integration)

## 2020 Details
Fuse® Analyst Report
Workbook: Workbook1 - 8168 Activities
Schedule Quality
Created on: 8/5/2019
Created by: brackett
2020: Detailed View | 2020: Detailed View | 2020: Detailed View | 2020: Detailed View | 2020: Detailed View | 2020: Detailed View
Missing Logic
Total number of activities that are missing a predecessor, a successor, or both. This number should not exceed 5%.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | Previous Start | Previous Finish | Percent Complete | Previous Remaining Duration | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | IsLevelOfEffort | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | Global_Basis of Estimate | Global_Cobra Cost Class | Cobra PMT (EV Method)_Global | Global_Color of Money | Global_Control Account Manager | Global_Design Maturity | Global_Judgement Factor | Global_Milestone Levels | Global_Project Phase | Global_Funding Source | Global_EDIA Survey | Global_MS Type | Phase | NSF Milestones | Loading Curve | Sensor Vendor | LSST_CA | Summary Schedule | ICD for NSF Input | LSST Camera Critical Paths | CD2 Budget Changes | DOE Reviews | Critical Path (CD Reviews) | LSST WP Summary | Critical Path (Camera Delivery) | AWARD / NEED Sub-System | Final Design Key Links | CP - CAMM2100 | CP - CAMM2130 | CP - CAMM2160 | BNL Work Org | Last ETC Update | BNL WBS | LSST Story List | Sum Sch 01 (Camera) | Sum Sch 02 (IT w/Needs) | Sum Sch 03 (Sensors_RTM_IT) | LSST Raft Particulate Mitigation | LSST RTM
FALSE |  | CAMM6050 | APPROVED: CD-4 - Project Completion - Camera | LSST Forecast - B57 - B1 | 0 | 0 | 2020-12-17 | 2020-12-17 | 305 |  |  | 53 | 2020-12-17 | 2020-12-17 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 0 | FALSE | Finish Milestone | FALSE | 2020-12-17 | 2020-12-17 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 149 | 0 | 149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.02 | NSF Watched Milestones | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration |  |  |  |  | CD-4 Project Close
FALSE |  | CAMC8700 | COMP: Project Level of Effort Support | LSST Forecast - B57 - B1 | 0 | 0 | 2020-12-18 | 2020-12-18 | 304 |  |  | 52 | 2020-12-18 | 2020-12-18 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 0 | FALSE | Finish Milestone | FALSE | 2020-12-18 | 2020-12-18 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 151 | 0 | 151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01 | Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 3 Milestone | Management/Administration
Critical
Number of critical activities
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | Previous Start | Previous Finish | Percent Complete | Previous Remaining Duration | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | IsLevelOfEffort | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | Global_Basis of Estimate | Global_Cobra Cost Class | Cobra PMT (EV Method)_Global | Global_Color of Money | Global_Control Account Manager | Global_Design Maturity | Global_Judgement Factor | Global_Milestone Levels | Global_Project Phase | Global_Funding Source | Global_EDIA Survey | Global_MS Type | Phase | NSF Milestones | Loading Curve | Sensor Vendor | LSST_CA | Summary Schedule | ICD for NSF Input | LSST Camera Critical Paths | CD2 Budget Changes | DOE Reviews | Critical Path (CD Reviews) | LSST WP Summary | Critical Path (Camera Delivery) | AWARD / NEED Sub-System | Final Design Key Links | CP - CAMM2100 | CP - CAMM2130 | CP - CAMM2160 | BNL Work Org | Last ETC Update | BNL WBS | LSST Story List | Sum Sch 01 (Camera) | Sum Sch 02 (IT w/Needs) | Sum Sch 03 (Sensors_RTM_IT) | LSST Raft Particulate Mitigation | LSST RTM
FALSE |  | ITC32420 | BOT Testing with Raft Tower #1-21+4CR | LSST Forecast - B57 - B1 | 38 | 38 | 2019-11-21 | 2020-01-30 | -18 |  |  | 0 | 2019-11-21 | 2020-01-30 | 2019-10-28 | 2019-12-20 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-11-21 | 2020-01-30 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 38 | 0 |  | Planned | 0% | 517 | 0 | 517 | 517 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC00335 | COMP: I&T of Loaded Cryostat (21 SR+4 CR) | LSST Forecast - B57 - B1 | 0 | 0 | 2020-01-30 | 2020-01-30 | -18 |  |  | 0 | 2020-01-30 | 2020-01-30 | 2019-12-20 | 2019-12-20 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | TRUE | 2020-01-30 | 2020-01-30 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration
FALSE |  | ITC32460 | NEED: L3 Lens Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2020-01-30 | 2020-01-30 | -18 |  |  | 0 | 2020-01-30 | 2020-01-30 | 2019-12-20 | 2019-12-20 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | TRUE | 2020-01-30 | 2020-01-30 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Optics
FALSE |  | ITC32440 | COMP: I&T of Loaded Cryostat (21 SR+4 CR) | LSST Forecast - B57 - B1 | 0 | 0 | 2020-01-30 | 2020-01-30 | -18 |  |  | 0 | 2020-01-30 | 2020-01-30 | 2019-12-20 | 2019-12-20 | 0 | 0 | 0 | 0 | 0 | 6 | FALSE | Finish Milestone | TRUE | 2020-01-30 | 2020-01-30 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [6 empty] | Critical Path #1 (Sensor & Raft Tower Production) |  |  |  |  | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32480 | Mount L3 Lens Assembly | LSST Forecast - B57 - B1 | 8 | 8 | 2020-01-31 | 2020-02-11 | -18 |  |  | 0 | 2020-01-31 | 2020-02-11 | 2020-01-06 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-01-31 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 8 | 0 |  | Planned | 0% | 65 | 0 | 65 | 65 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32500 | NEED: Utility Trunk | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Cryostat
FALSE |  | ITC32520 | NEED: Camera purge unit | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Camera Body & Shutter
FALSE |  | ITC32540 | NEED: UT cooling system | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Utility Trunk
FALSE |  | ITC32580 | NEED: UT Aux Electronics | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 14 | 0 | 14 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Auxiliary Electronics
FALSE |  | ITC32565 | NEED: Diagnostic Cluster from CCS | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Auxiliary Electronics
FALSE |  | ITC32590 | NEED: Cryostat Lift Fixture for Cryostat I&T | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Cryostat
FALSE |  | ITC32510 | NEED: Vacuum Purge | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Cryostat
FALSE |  | ITC32530 | NEED: Cryostat Handling Equipment | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | ITC32570 | NEED: Controls for Utility Trunk | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | ITC32620 | Mount and Populate Utility Trunk | LSST Forecast - B57 - B1 | 40 | 40 | 2020-02-12 | 2020-04-08 | -18 |  |  | 0 | 2020-02-12 | 2020-04-08 | 2020-01-16 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-02-12 | 2020-04-08 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 13 | 0 | 13 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 0 |  | Planned | 0% | 767 | 0 | 767 | 767 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | CAMM6200 | DECISION: Spares for L3 | LSST Forecast - B57 - B1 | 0 | 0 | 2020-03-24 | 2020-03-24 | 252 |  |  | 0 | 2020-03-24 | 2020-03-24 | 2021-04-02 | 2021-04-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-03-24 | 2020-03-24 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 240 | 240 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.05 | Upscope/Descope Decision Points | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration
FALSE |  | ITC00340 | COMP: Cryostat and UT Assembled | LSST Forecast - B57 - B1 | 0 | 0 | 2020-04-08 | 2020-04-08 | -18 |  |  | 0 | 2020-04-08 | 2020-04-08 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-04-08 | 2020-04-08 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration |  |  |  |  | SR Rafts Installed and Cryostat Closed (min of 5 SR and 4 CR)
FALSE |  | ITC19850 | NEED: Loaded Cryostat | LSST Forecast - B57 - B1 | 0 | 0 | 2020-04-08 | 2020-04-08 | -18 |  |  | 0 | 2020-04-08 | 2020-04-08 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-04-08 | 2020-04-08 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Integration and Test
FALSE |  | ITC32660 | AVAIL: Loaded Cryostat Ready for Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2020-04-08 | 2020-04-08 | -18 |  |  | 0 | 2020-04-08 | 2020-04-08 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | TRUE | 2020-04-08 | 2020-04-08 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration | [16 empty] | Integration and Test
FALSE |  | ITC19852 | NEED: Camera Handling Equipment Ready for Camera I&T | LSST Forecast - B57 - B1 | 0 | 0 | 2020-04-08 | 2020-04-08 | -18 |  |  | 0 | 2020-04-08 | 2020-04-08 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-04-08 | 2020-04-08 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | ITC19900 | Camera / Cryostat Integration | LSST Forecast - B57 - B1 | 30 | 30 | 2020-04-09 | 2020-05-20 | -18 |  |  | 0 | 2020-04-09 | 2020-05-20 | 2020-03-16 | 2020-04-24 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2020-04-09 | 2020-05-20 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 7 | 0 | 7 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 0 |  | Planned | 0% | 518 | 0 | 518 | 518 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration | Stanford University | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Camera I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Camera I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC20000 | NEED: L1-L2 Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2020-05-20 | 2020-05-20 | -18 |  |  | 0 | 2020-05-20 | 2020-05-20 | 2020-04-24 | 2020-04-24 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-05-20 | 2020-05-20 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Optics
FALSE |  | ITC00450 | COMP: Cryostat Integrated Into Camera Body | LSST Forecast - B57 - B1 | 0 | 0 | 2020-05-20 | 2020-05-20 | -18 |  |  | 0 | 2020-05-20 | 2020-05-20 | 2020-04-24 | 2020-04-24 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-05-20 | 2020-05-20 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration
FALSE |  | ITC20025 | L1-L2 Integration | LSST Forecast - B57 - B1 | 25 | 25 | 2020-05-21 | 2020-06-25 | -18 |  |  | 0 | 2020-05-21 | 2020-06-25 | 2020-04-27 | 2020-06-01 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-05-21 | 2020-06-25 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 0 |  | Planned | 0% | 816 | 0 | 816 | 816 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration | Stanford University | Commissioning and Testing | [5 empty] | Camera I&T (TEC) | [5 empty] | Critical Path to CD-2 |  | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC20050 | Final Camera Assembly / Closeout | LSST Forecast - B57 - B1 | 15 | 15 | 2020-06-26 | 2020-07-17 | -18 |  |  | 0 | 2020-06-26 | 2020-07-17 | 2020-06-02 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-06-26 | 2020-07-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 0 |  | Planned | 0% | 270 | 0 | 270 | 270 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration | Stanford University | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Camera I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Camera I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC00475 | COMP: Camera Ready for Verification Testing | LSST Forecast - B57 - B1 | 0 | 0 | 2020-07-17 | 2020-07-17 | -18 |  |  | 0 | 2020-07-17 | 2020-07-17 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | TRUE | 2020-07-17 | 2020-07-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration
FALSE |  | ITC20070 | NEED: Filters (partial) | LSST Forecast - B57 - B1 | 0 | 0 | 2020-07-17 | 2020-07-17 | -18 |  |  | 0 | 2020-07-17 | 2020-07-17 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-07-17 | 2020-07-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration | [16 empty] | Optics
FALSE |  | ITC20060 | COMP: Camera Ready for Verification Testing | LSST Forecast - B57 - B1 | 0 | 0 | 2020-07-17 | 2020-07-17 | -18 |  |  | 0 | 2020-07-17 | 2020-07-17 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | TRUE | 2020-07-17 | 2020-07-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Testing/Integration | [10 empty] | Critical Path #1 (Sensor & Raft Tower Production)
FALSE |  | ITC20065 | NEED: OCS & CCS Ready for I&T Testing (CCS Suite #9) | LSST Forecast - B57 - B1 | 0 | 0 | 2020-07-17 | 2020-07-17 | -18 |  |  | 0 | 2020-07-17 | 2020-07-17 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-07-17 | 2020-07-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 11 | 0 | 11 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration | [16 empty] | Project Management
FALSE |  | ITC20076 | NEED: DAQ Production V5.0 | LSST Forecast - B57 - B1 | 0 | 0 | 2020-07-17 | 2020-07-17 | -18 |  |  | 0 | 2020-07-17 | 2020-07-17 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-07-17 | 2020-07-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 10 | 0 | 10 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | ITC20072 | NEED: Filter Loader | LSST Forecast - B57 - B1 | 0 | 0 | 2020-07-17 | 2020-07-17 | -18 |  |  | 0 | 2020-07-17 | 2020-07-17 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-07-17 | 2020-07-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | ITC20125 | Camera Functional Testing | LSST Forecast - B57 - B1 | 46 | 46 | 2020-07-20 | 2020-09-22 | -18 |  |  | 0 | 2020-07-20 | 2020-09-22 | 2020-06-23 | 2020-08-26 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2020-07-20 | 2020-09-22 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 46 | 0 |  | Planned | 0% | 1432 | 0 | 1432 | 1432 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration | Stanford University | Commissioning and Testing | [5 empty] | Camera I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Camera I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | CAMM6210 | DECISION: Spare filter blank | LSST Forecast - B57 - B1 | 0 | 0 | 2020-09-11 | 2020-09-11 | 252 |  |  | 0 | 2020-09-11 | 2020-09-11 | 2021-09-22 | 2021-09-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-09-11 | 2020-09-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 120 | 120 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.05 | Upscope/Descope Decision Points | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration
FALSE |  | CAMM6150 | DECISION: Postpone System-Level Verification Testing | LSST Forecast - B57 - B1 | 0 | 0 | 2020-09-22 | 2020-09-22 | -18 |  |  | 0 | 2020-09-22 | 2020-09-22 | 2020-08-26 | 2020-08-26 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-09-22 | 2020-09-22 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.05 | Upscope/Descope Decision Points | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration
FALSE |  | ITC20130 | NEED: CCOB Ready for Camera Verification Testing | LSST Forecast - B57 - B1 | 0 | 0 | 2020-09-22 | 2020-09-22 | -18 |  |  | 0 | 2020-09-22 | 2020-09-22 | 2020-08-26 | 2020-08-26 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-09-22 | 2020-09-22 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | ITC20150 | Camera Verification Testing | LSST Forecast - B57 - B1 | 45 | 45 | 2020-09-23 | 2020-11-24 | -18 |  |  | 0 | 2020-09-23 | 2020-11-24 | 2020-08-27 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | TRUE | 2020-09-23 | 2020-11-24 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 7 | 0 | 5 | 0 | 0 | 2 | 3 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 45 | 0 |  | Planned | 0% | 1468 | 0 | 1468 | 1468 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration | Stanford University | Commissioning and Testing | [5 empty] | Camera I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Camera I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | CAM112810 | CD-4/CRR Director's Team Pre Doc Review | LSST Forecast - B57 - B1 | 5 | 5 | 2020-11-06 | 2020-11-12 | 252 |  |  | 0 | 2020-11-06 | 2020-11-12 | 2021-11-17 | 2021-11-23 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-11-06 | 2020-11-12 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01.01.02 | Reviews & Collaboration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Vincent Riot | (1.10) Task/item is a modification of an existing design | 0% |  | Management/Administration |  | Project Management (cost estimating, scheduling, project controls, Risk assessment) | [10 empty] | CD-3b | Critical Path to CD-3b | Project Management
FALSE |  | CAM112820 | CD-4/CRR Directors Review | LSST Forecast - B57 - B1 | 3 | 3 | 2020-11-13 | 2020-11-17 | 252 |  |  | 0 | 2020-11-13 | 2020-11-17 | 2021-11-24 | 2021-11-30 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-11-13 | 2020-11-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 3 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01.01.02 | Reviews & Collaboration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Vincent Riot | (1.10) Task/item is a modification of an existing design | 0% |  | Management/Administration |  | Project Management (cost estimating, scheduling, project controls, Risk assessment) | [12 empty] | Project Management
FALSE |  | CAM112830 | CD-4/CRR Documentation Updates | LSST Forecast - B57 - B1 | 20 | 20 | 2020-11-18 | 2020-12-17 | 252 |  |  | 0 | 2020-11-18 | 2020-12-17 | 2021-12-01 | 2022-01-11 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-11-18 | 2020-12-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 20 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01.01.02 | Reviews & Collaboration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Vincent Riot | (1.10) Task/item is a modification of an existing design | 0% |  | Management/Administration | [14 empty] | Project Management
FALSE |  | ITC20160 | NEED: Filters Remaining | LSST Forecast - B57 - B1 | 0 | 0 | 2020-11-24 | 2020-11-24 | -18 |  |  | 0 | 2020-11-24 | 2020-11-24 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-11-24 | 2020-11-24 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration | [16 empty] | Optics
FALSE |  | ITC20170 | NEED: Cryostat Sieve (Getter Pumps) | LSST Forecast - B57 - B1 | 0 | 0 | 2020-11-24 | 2020-11-24 | -18 |  |  | 0 | 2020-11-24 | 2020-11-24 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-11-24 | 2020-11-24 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration | [16 empty] | Optics
FALSE |  | ITC20175 | NEED: Cryostat Evaporative Getter Pumps | LSST Forecast - B57 - B1 | 0 | 0 | 2020-11-24 | 2020-11-24 | -18 |  |  | 0 | 2020-11-24 | 2020-11-24 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-11-24 | 2020-11-24 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration | [16 empty] | Optics
FALSE |  | ITC20180 | Recover from tests, secure Camera for shipping | LSST Forecast - B57 - B1 | 7 | 7 | 2020-11-25 | 2020-12-07 | -18 |  |  | 0 | 2020-11-25 | 2020-12-07 | 2020-10-30 | 2020-11-09 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-11-25 | 2020-12-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 7 | 0 |  | Planned | 0% | 392 | 0 | 392 | 392 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration | Stanford University | Commissioning and Testing | [5 empty] | Camera I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Camera I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC00500 | COMP: Camera Ready - Integrated & Tested @ SLAC | LSST Forecast - B57 - B1 | 0 | 0 | 2020-12-07 | 2020-12-07 | -18 |  |  | 0 | 2020-12-07 | 2020-12-07 | 2020-11-09 | 2020-11-09 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-12-07 | 2020-12-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration
FALSE |  | ITC20200 | COMP: Camera Verification Tests Complete | LSST Forecast - B57 - B1 | 0 | 0 | 2020-12-07 | 2020-12-07 | -18 |  |  | 0 | 2020-12-07 | 2020-12-07 | 2020-11-09 | 2020-11-09 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | TRUE | 2020-12-07 | 2020-12-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Testing/Integration | [10 empty] | Critical Path #1 (Sensor & Raft Tower Production)
FALSE |  | ITC20349 | NEED: As-built documentation | LSST Forecast - B57 - B1 | 0 | 0 | 2020-12-07 | 2020-12-07 | -18 |  |  | 0 | 2020-12-07 | 2020-12-07 | 2020-11-09 | 2020-11-09 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | TRUE | 2020-12-07 | 2020-12-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration | [10 empty] | Critical Path #1 (Sensor & Raft Tower Production)
FALSE |  | ITC20350 | Prep for C_PSR/ORR--Camera | LSST Forecast - B57 - B1 | 6 | 6 | 2020-12-08 | 2020-12-15 | -18 |  |  | 0 | 2020-12-08 | 2020-12-15 | 2020-11-10 | 2020-11-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-12-08 | 2020-12-15 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 10 | 0 | 10 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 6 | 0 |  | Planned | 0% | 120 | 0 | 120 | 120 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration | Stanford University | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Camera I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Camera I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC20375 | Camera Pre-Ship/Operations Readiness Review | LSST Forecast - B57 - B1 | 2 | 2 | 2020-12-16 | 2020-12-17 | -18 |  |  | 0 | 2020-12-16 | 2020-12-17 | 2020-11-18 | 2020-11-19 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-12-16 | 2020-12-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 48 | 0 | 48 | 48 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration | Stanford University | Commissioning and Testing | [5 empty] | Camera I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 |  | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC00100 | COMP: Ready for CD-4 - I&T | LSST Forecast - B57 - B1 | 0 | 0 | 2020-12-17 | 2020-12-17 | 212 |  |  | 0 | 2020-12-17 | 2020-12-17 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-12-17 | 2020-12-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 31 | 0 | 31 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration
FALSE |  | ITC20400 | COMP: C_PSR/ORR--Camera Pre-Ship/Operations Readiness Review Complete | LSST Forecast - B57 - B1 | 0 | 0 | 2020-12-17 | 2020-12-17 | -18 |  |  | 0 | 2020-12-17 | 2020-12-17 | 2020-11-19 | 2020-11-19 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Finish Milestone | TRUE | 2020-12-17 | 2020-12-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration
FALSE |  | CAMC02750 | COMP: Ready for CD-4 Review - Camera | LSST Forecast - B57 - B1 | 0 | 0 | 2020-12-17 | 2020-12-17 | 212 |  |  | 0 | 2020-12-17 | 2020-12-17 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | TRUE | 2020-12-17 | 2020-12-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01 | Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 3 Milestone | Management/Administration
FALSE |  | CAM112800 | COMP: Project Ready for CD-4/CRR | LSST Forecast - B57 - B1 | 0 | 0 | 2020-12-17 | 2020-12-17 | 212 |  |  | 0 | 2020-12-17 | 2020-12-17 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-12-17 | 2020-12-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 13 | 0 | 13 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01.01.02 | Reviews & Collaboration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Vincent Riot | (1.10) Task/item is a modification of an existing design | 0% | Level 4 Milestone | Management/Administration | [12 empty] | CD-3b | Critical Path to CD-3b | Project Management
FALSE |  | CAM112840 | CD-4/CRR DOE/SC Team Pre Doc Review | LSST Forecast - B57 - B1 | 10 | 10 | 2020-12-18 | 2021-01-14 | 252 |  |  | 0 | 2020-12-18 | 2021-01-14 | 2022-01-12 | 2022-01-26 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-12-18 | 2021-01-14 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01.01.02 | Reviews & Collaboration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Vincent Riot | (1.10) Task/item is a modification of an existing design | 0% |  | Management/Administration | [14 empty] | Project Management
Negative Float
Number of activities with total finish float less than 0 working days.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | Previous Start | Previous Finish | Percent Complete | Previous Remaining Duration | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | IsLevelOfEffort | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | Global_Basis of Estimate | Global_Cobra Cost Class | Cobra PMT (EV Method)_Global | Global_Color of Money | Global_Control Account Manager | Global_Design Maturity | Global_Judgement Factor | Global_Milestone Levels | Global_Project Phase | Global_Funding Source | Global_EDIA Survey | Global_MS Type | Phase | NSF Milestones | Loading Curve | Sensor Vendor | LSST_CA | Summary Schedule | ICD for NSF Input | LSST Camera Critical Paths | CD2 Budget Changes | DOE Reviews | Critical Path (CD Reviews) | LSST WP Summary | Critical Path (Camera Delivery) | AWARD / NEED Sub-System | Final Design Key Links | CP - CAMM2100 | CP - CAMM2130 | CP - CAMM2160 | BNL Work Org | Last ETC Update | BNL WBS | LSST Story List | Sum Sch 01 (Camera) | Sum Sch 02 (IT w/Needs) | Sum Sch 03 (Sensors_RTM_IT) | LSST Raft Particulate Mitigation | LSST RTM
FALSE |  | ITC32420 | BOT Testing with Raft Tower #1-21+4CR | LSST Forecast - B57 - B1 | 38 | 38 | 2019-11-21 | 2020-01-30 | -18 |  |  | 0 | 2019-11-21 | 2020-01-30 | 2019-10-28 | 2019-12-20 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2019-11-21 | 2020-01-30 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 38 | 0 |  | Planned | 0% | 517 | 0 | 517 | 517 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration | [7 empty] | Cryostat I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC19760 | Camera Assembly - Shutter | LSST Forecast - B57 - B1 | 27 | 27 | 2019-12-19 | 2020-02-10 | -8 |  |  | 0 | 2019-12-19 | 2020-02-10 | 2019-12-09 | 2020-01-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2019-12-19 | 2020-02-10 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 27 | 0 |  | Planned | 0% | 407 | 0 | 407 | 407 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Camera I&T (TEC) | [6 empty] | Camera I&T | CP #03 (Carousel/Camera Integration)
FALSE |  | ITC00335 | COMP: I&T of Loaded Cryostat (21 SR+4 CR) | LSST Forecast - B57 - B1 | 0 | 0 | 2020-01-30 | 2020-01-30 | -18 |  |  | 0 | 2020-01-30 | 2020-01-30 | 2019-12-20 | 2019-12-20 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | TRUE | 2020-01-30 | 2020-01-30 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration
FALSE |  | ITC32460 | NEED: L3 Lens Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2020-01-30 | 2020-01-30 | -18 |  |  | 0 | 2020-01-30 | 2020-01-30 | 2019-12-20 | 2019-12-20 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | TRUE | 2020-01-30 | 2020-01-30 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Optics
FALSE |  | ITC32440 | COMP: I&T of Loaded Cryostat (21 SR+4 CR) | LSST Forecast - B57 - B1 | 0 | 0 | 2020-01-30 | 2020-01-30 | -18 |  |  | 0 | 2020-01-30 | 2020-01-30 | 2019-12-20 | 2019-12-20 | 0 | 0 | 0 | 0 | 0 | 6 | FALSE | Finish Milestone | TRUE | 2020-01-30 | 2020-01-30 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [6 empty] | Critical Path #1 (Sensor & Raft Tower Production) |  |  |  |  | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC32480 | Mount L3 Lens Assembly | LSST Forecast - B57 - B1 | 8 | 8 | 2020-01-31 | 2020-02-11 | -18 |  |  | 0 | 2020-01-31 | 2020-02-11 | 2020-01-06 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-01-31 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 8 | 0 |  | Planned | 0% | 65 | 0 | 65 | 65 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC00400 | COMP: Shutter Integrated Into Camera | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-10 | 2020-02-10 | -8 |  |  | 0 | 2020-02-10 | 2020-02-10 | 2020-01-29 | 2020-01-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2020-02-10 | 2020-02-10 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration | [15 empty] | CP #03 (Carousel/Camera Integration)
FALSE |  | ITC19772 | NEED: CCS Suite #8 (+HCU) (NEEDS LINK) | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-10 | 2020-02-10 | -8 |  |  | 0 | 2020-02-10 | 2020-02-10 | 2020-01-29 | 2020-01-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2020-02-10 | 2020-02-10 |  |  |  |  | 0 | 0 | FALSE | FALSE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | ITC19775 | Camera Assembly - Integrated Testing | LSST Forecast - B57 - B1 | 26 | 26 | 2020-02-11 | 2020-03-18 | -8 |  |  | 0 | 2020-02-11 | 2020-03-18 | 2020-01-30 | 2020-03-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2020-02-11 | 2020-03-18 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 26 | 0 |  | Planned | 0% | 555 | 0 | 555 | 555 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Commissioning and Testing | [5 empty] | Camera I&T (TEC) | [7 empty] | CP #03 (Carousel/Camera Integration)
FALSE |  | ITC32500 | NEED: Utility Trunk | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Cryostat
FALSE |  | ITC32520 | NEED: Camera purge unit | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Camera Body & Shutter
FALSE |  | ITC32540 | NEED: UT cooling system | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Utility Trunk
FALSE |  | ITC32580 | NEED: UT Aux Electronics | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 14 | 0 | 14 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Auxiliary Electronics
FALSE |  | ITC32565 | NEED: Diagnostic Cluster from CCS | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Auxiliary Electronics
FALSE |  | ITC32590 | NEED: Cryostat Lift Fixture for Cryostat I&T | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Cryostat
FALSE |  | ITC32510 | NEED: Vacuum Purge | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Cryostat
FALSE |  | ITC32530 | NEED: Cryostat Handling Equipment | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | ITC32570 | NEED: Controls for Utility Trunk | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | ITC32620 | Mount and Populate Utility Trunk | LSST Forecast - B57 - B1 | 40 | 40 | 2020-02-12 | 2020-04-08 | -18 |  |  | 0 | 2020-02-12 | 2020-04-08 | 2020-01-16 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-02-12 | 2020-04-08 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 13 | 0 | 13 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 0 |  | Planned | 0% | 767 | 0 | 767 | 767 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC00425 | COMP: Filter Systems Integrated Into Camera | LSST Forecast - B57 - B1 | 0 | 0 | 2020-03-18 | 2020-03-18 | -8 |  |  | 0 | 2020-03-18 | 2020-03-18 | 2020-03-06 | 2020-03-06 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2020-03-18 | 2020-03-18 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration | [15 empty] | CP #03 (Carousel/Camera Integration)
FALSE |  | ITC19800 | Camera Disassembly | LSST Forecast - B57 - B1 | 5 | 5 | 2020-03-19 | 2020-03-25 | -8 |  |  | 10 | 2020-03-19 | 2020-03-25 | 2020-03-09 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2020-03-19 | 2020-03-25 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 0 |  | Planned | 0% | 108 | 0 | 108 | 108 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Commissioning and Testing | [5 empty] | Camera I&T (TEC) | [7 empty] | CP #03 (Carousel/Camera Integration)
FALSE |  | ITC00340 | COMP: Cryostat and UT Assembled | LSST Forecast - B57 - B1 | 0 | 0 | 2020-04-08 | 2020-04-08 | -18 |  |  | 0 | 2020-04-08 | 2020-04-08 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-04-08 | 2020-04-08 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration |  |  |  |  | SR Rafts Installed and Cryostat Closed (min of 5 SR and 4 CR)
FALSE |  | ITC19850 | NEED: Loaded Cryostat | LSST Forecast - B57 - B1 | 0 | 0 | 2020-04-08 | 2020-04-08 | -18 |  |  | 0 | 2020-04-08 | 2020-04-08 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-04-08 | 2020-04-08 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Integration and Test
FALSE |  | ITC32660 | AVAIL: Loaded Cryostat Ready for Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2020-04-08 | 2020-04-08 | -18 |  |  | 0 | 2020-04-08 | 2020-04-08 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | TRUE | 2020-04-08 | 2020-04-08 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration | [16 empty] | Integration and Test
FALSE |  | ITC19852 | NEED: Camera Handling Equipment Ready for Camera I&T | LSST Forecast - B57 - B1 | 0 | 0 | 2020-04-08 | 2020-04-08 | -18 |  |  | 0 | 2020-04-08 | 2020-04-08 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-04-08 | 2020-04-08 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | ITC19900 | Camera / Cryostat Integration | LSST Forecast - B57 - B1 | 30 | 30 | 2020-04-09 | 2020-05-20 | -18 |  |  | 0 | 2020-04-09 | 2020-05-20 | 2020-03-16 | 2020-04-24 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2020-04-09 | 2020-05-20 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 7 | 0 | 7 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 0 |  | Planned | 0% | 518 | 0 | 518 | 518 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration | Stanford University | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Camera I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Camera I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC20000 | NEED: L1-L2 Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2020-05-20 | 2020-05-20 | -18 |  |  | 0 | 2020-05-20 | 2020-05-20 | 2020-04-24 | 2020-04-24 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-05-20 | 2020-05-20 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Optics
FALSE |  | ITC00450 | COMP: Cryostat Integrated Into Camera Body | LSST Forecast - B57 - B1 | 0 | 0 | 2020-05-20 | 2020-05-20 | -18 |  |  | 0 | 2020-05-20 | 2020-05-20 | 2020-04-24 | 2020-04-24 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-05-20 | 2020-05-20 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration
FALSE |  | ITC20025 | L1-L2 Integration | LSST Forecast - B57 - B1 | 25 | 25 | 2020-05-21 | 2020-06-25 | -18 |  |  | 0 | 2020-05-21 | 2020-06-25 | 2020-04-27 | 2020-06-01 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-05-21 | 2020-06-25 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 25 | 0 |  | Planned | 0% | 816 | 0 | 816 | 816 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration | Stanford University | Commissioning and Testing | [5 empty] | Camera I&T (TEC) | [5 empty] | Critical Path to CD-2 |  | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC20050 | Final Camera Assembly / Closeout | LSST Forecast - B57 - B1 | 15 | 15 | 2020-06-26 | 2020-07-17 | -18 |  |  | 0 | 2020-06-26 | 2020-07-17 | 2020-06-02 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-06-26 | 2020-07-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 15 | 0 |  | Planned | 0% | 270 | 0 | 270 | 270 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration | Stanford University | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Camera I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Camera I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC00475 | COMP: Camera Ready for Verification Testing | LSST Forecast - B57 - B1 | 0 | 0 | 2020-07-17 | 2020-07-17 | -18 |  |  | 0 | 2020-07-17 | 2020-07-17 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | TRUE | 2020-07-17 | 2020-07-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration
FALSE |  | ITC20070 | NEED: Filters (partial) | LSST Forecast - B57 - B1 | 0 | 0 | 2020-07-17 | 2020-07-17 | -18 |  |  | 0 | 2020-07-17 | 2020-07-17 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-07-17 | 2020-07-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration | [16 empty] | Optics
FALSE |  | ITC20060 | COMP: Camera Ready for Verification Testing | LSST Forecast - B57 - B1 | 0 | 0 | 2020-07-17 | 2020-07-17 | -18 |  |  | 0 | 2020-07-17 | 2020-07-17 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | TRUE | 2020-07-17 | 2020-07-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Testing/Integration | [10 empty] | Critical Path #1 (Sensor & Raft Tower Production)
FALSE |  | ITC20065 | NEED: OCS & CCS Ready for I&T Testing (CCS Suite #9) | LSST Forecast - B57 - B1 | 0 | 0 | 2020-07-17 | 2020-07-17 | -18 |  |  | 0 | 2020-07-17 | 2020-07-17 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-07-17 | 2020-07-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 11 | 0 | 11 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration | [16 empty] | Project Management
FALSE |  | ITC20076 | NEED: DAQ Production V5.0 | LSST Forecast - B57 - B1 | 0 | 0 | 2020-07-17 | 2020-07-17 | -18 |  |  | 0 | 2020-07-17 | 2020-07-17 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-07-17 | 2020-07-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 10 | 0 | 10 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | ITC20072 | NEED: Filter Loader | LSST Forecast - B57 - B1 | 0 | 0 | 2020-07-17 | 2020-07-17 | -18 |  |  | 0 | 2020-07-17 | 2020-07-17 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-07-17 | 2020-07-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | ITC20125 | Camera Functional Testing | LSST Forecast - B57 - B1 | 46 | 46 | 2020-07-20 | 2020-09-22 | -18 |  |  | 0 | 2020-07-20 | 2020-09-22 | 2020-06-23 | 2020-08-26 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2020-07-20 | 2020-09-22 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 46 | 0 |  | Planned | 0% | 1432 | 0 | 1432 | 1432 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration | Stanford University | Commissioning and Testing | [5 empty] | Camera I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Camera I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | CAMM6150 | DECISION: Postpone System-Level Verification Testing | LSST Forecast - B57 - B1 | 0 | 0 | 2020-09-22 | 2020-09-22 | -18 |  |  | 0 | 2020-09-22 | 2020-09-22 | 2020-08-26 | 2020-08-26 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-09-22 | 2020-09-22 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.05 | Upscope/Descope Decision Points | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration
FALSE |  | ITC20130 | NEED: CCOB Ready for Camera Verification Testing | LSST Forecast - B57 - B1 | 0 | 0 | 2020-09-22 | 2020-09-22 | -18 |  |  | 0 | 2020-09-22 | 2020-09-22 | 2020-08-26 | 2020-08-26 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-09-22 | 2020-09-22 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | ITC20150 | Camera Verification Testing | LSST Forecast - B57 - B1 | 45 | 45 | 2020-09-23 | 2020-11-24 | -18 |  |  | 0 | 2020-09-23 | 2020-11-24 | 2020-08-27 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | TRUE | 2020-09-23 | 2020-11-24 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 7 | 0 | 5 | 0 | 0 | 2 | 3 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 45 | 0 |  | Planned | 0% | 1468 | 0 | 1468 | 1468 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration | Stanford University | Commissioning and Testing | [5 empty] | Camera I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Camera I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC20160 | NEED: Filters Remaining | LSST Forecast - B57 - B1 | 0 | 0 | 2020-11-24 | 2020-11-24 | -18 |  |  | 0 | 2020-11-24 | 2020-11-24 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-11-24 | 2020-11-24 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration | [16 empty] | Optics
FALSE |  | ITC20170 | NEED: Cryostat Sieve (Getter Pumps) | LSST Forecast - B57 - B1 | 0 | 0 | 2020-11-24 | 2020-11-24 | -18 |  |  | 0 | 2020-11-24 | 2020-11-24 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-11-24 | 2020-11-24 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration | [16 empty] | Optics
FALSE |  | ITC20175 | NEED: Cryostat Evaporative Getter Pumps | LSST Forecast - B57 - B1 | 0 | 0 | 2020-11-24 | 2020-11-24 | -18 |  |  | 0 | 2020-11-24 | 2020-11-24 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-11-24 | 2020-11-24 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration | [16 empty] | Optics
FALSE |  | ITC20180 | Recover from tests, secure Camera for shipping | LSST Forecast - B57 - B1 | 7 | 7 | 2020-11-25 | 2020-12-07 | -18 |  |  | 0 | 2020-11-25 | 2020-12-07 | 2020-10-30 | 2020-11-09 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-11-25 | 2020-12-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 7 | 0 |  | Planned | 0% | 392 | 0 | 392 | 392 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration | Stanford University | Commissioning and Testing | [5 empty] | Camera I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Camera I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC00500 | COMP: Camera Ready - Integrated & Tested @ SLAC | LSST Forecast - B57 - B1 | 0 | 0 | 2020-12-07 | 2020-12-07 | -18 |  |  | 0 | 2020-12-07 | 2020-12-07 | 2020-11-09 | 2020-11-09 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-12-07 | 2020-12-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration
FALSE |  | ITC20200 | COMP: Camera Verification Tests Complete | LSST Forecast - B57 - B1 | 0 | 0 | 2020-12-07 | 2020-12-07 | -18 |  |  | 0 | 2020-12-07 | 2020-12-07 | 2020-11-09 | 2020-11-09 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | TRUE | 2020-12-07 | 2020-12-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Testing/Integration | [10 empty] | Critical Path #1 (Sensor & Raft Tower Production)
FALSE |  | ITC20349 | NEED: As-built documentation | LSST Forecast - B57 - B1 | 0 | 0 | 2020-12-07 | 2020-12-07 | -18 |  |  | 0 | 2020-12-07 | 2020-12-07 | 2020-11-09 | 2020-11-09 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | TRUE | 2020-12-07 | 2020-12-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration | [10 empty] | Critical Path #1 (Sensor & Raft Tower Production)
FALSE |  | ITC20350 | Prep for C_PSR/ORR--Camera | LSST Forecast - B57 - B1 | 6 | 6 | 2020-12-08 | 2020-12-15 | -18 |  |  | 0 | 2020-12-08 | 2020-12-15 | 2020-11-10 | 2020-11-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-12-08 | 2020-12-15 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 10 | 0 | 10 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 6 | 0 |  | Planned | 0% | 120 | 0 | 120 | 120 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration | Stanford University | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Camera I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Camera I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC20375 | Camera Pre-Ship/Operations Readiness Review | LSST Forecast - B57 - B1 | 2 | 2 | 2020-12-16 | 2020-12-17 | -18 |  |  | 0 | 2020-12-16 | 2020-12-17 | 2020-11-18 | 2020-11-19 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-12-16 | 2020-12-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 2 | 0 |  | Planned | 0% | 48 | 0 | 48 | 48 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration | Stanford University | Commissioning and Testing | [5 empty] | Camera I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 |  | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC00525 | COMP: C_PSR/ORR - Camera Pre-Ship/Operations Readiness Review Complete | LSST Forecast - B57 - B1 | 0 | 0 | 2020-12-17 | 2020-12-17 | -18 |  |  | 0 | 2020-12-17 | 2020-12-17 | 2020-11-19 | 2020-11-19 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2020-12-17 | 2020-12-17 |  |  |  |  | 0 | 0 | FALSE | FALSE | FinishOnOrBefore | 2020-11-19 | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration | [10 empty] | Critical Path #1 (Sensor & Raft Tower Production) |  |  |  |  | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC20400 | COMP: C_PSR/ORR--Camera Pre-Ship/Operations Readiness Review Complete | LSST Forecast - B57 - B1 | 0 | 0 | 2020-12-17 | 2020-12-17 | -18 |  |  | 0 | 2020-12-17 | 2020-12-17 | 2020-11-19 | 2020-11-19 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Finish Milestone | TRUE | 2020-12-17 | 2020-12-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 4 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration
Number of Lags
Total number of activities that have lags in their predecessors. This number should not exceed 5%.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | Previous Start | Previous Finish | Percent Complete | Previous Remaining Duration | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | IsLevelOfEffort | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | Global_Basis of Estimate | Global_Cobra Cost Class | Cobra PMT (EV Method)_Global | Global_Color of Money | Global_Control Account Manager | Global_Design Maturity | Global_Judgement Factor | Global_Milestone Levels | Global_Project Phase | Global_Funding Source | Global_EDIA Survey | Global_MS Type | Phase | NSF Milestones | Loading Curve | Sensor Vendor | LSST_CA | Summary Schedule | ICD for NSF Input | LSST Camera Critical Paths | CD2 Budget Changes | DOE Reviews | Critical Path (CD Reviews) | LSST WP Summary | Critical Path (Camera Delivery) | AWARD / NEED Sub-System | Final Design Key Links | CP - CAMM2100 | CP - CAMM2130 | CP - CAMM2160 | BNL Work Org | Last ETC Update | BNL WBS | LSST Story List | Sum Sch 01 (Camera) | Sum Sch 02 (IT w/Needs) | Sum Sch 03 (Sensors_RTM_IT) | LSST Raft Particulate Mitigation | LSST RTM
FALSE |  | OP522800 | Mount filters in frame - Remaining filter | LSST Forecast - B57 - B1 | 60 | 60 | 2020-01-08 | 2020-04-02 | 107 |  |  | 0 | 2020-01-08 | 2020-04-02 | 2020-06-10 | 2020-09-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2020-01-08 | 2020-04-02 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 0 |  | Planned | 0% | 346 | 0 | 346 | 346 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 18% |  | Testing/Integration |  | Other (specify) | [5 empty] | Filters (TEC) | Production Filters Polish and integration | [5 empty] | Filter Opto-Mechanics
FALSE |  | CAMF2470 | Outstanding Performance Annual Bonus FY20 | LSST Forecast - B57 - B1 | 19 | 19 | 2020-02-03 | 2020-02-28 | 509 |  |  | 205 | 2020-02-03 | 2020-02-28 | 2022-03-03 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2020-02-03 | 2020-02-28 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 19 | 0 |  | Planned | 0% | 287 | 0 | 287 | 287 | LSST Forecast - B57 - B1.3.01.01.01 | Project Office | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Vincent Riot | (1.10) Task/item is a modification of an existing design | 0% |  | Management/Administration |  | Project Management (cost estimating, scheduling, project controls, Risk assessment) | [5 empty] | Project Management (TEC)
FALSE |  | ITC98080 | I&T Sust Engineering - Project Extension | LSST Forecast - B57 - B1 | 86 | 86 | 2020-03-02 | 2020-06-30 | 423 |  |  | 119 | 2020-03-02 | 2020-06-30 | 2021-11-10 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2020-03-02 | 2020-06-30 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 86 | 0 |  | Planned | 0% | 242 | 0 | 242 | 242 | LSST Forecast - B57 - B1.3.08.01 | I&T Integration & Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Drtn | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Level of Effort | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Construction Management | [5 empty] | Integration & Testing (TEC)
Merge Hotspot
The total number of activities with a high number of predecessor links.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | Previous Start | Previous Finish | Percent Complete | Previous Remaining Duration | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | IsLevelOfEffort | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | Global_Basis of Estimate | Global_Cobra Cost Class | Cobra PMT (EV Method)_Global | Global_Color of Money | Global_Control Account Manager | Global_Design Maturity | Global_Judgement Factor | Global_Milestone Levels | Global_Project Phase | Global_Funding Source | Global_EDIA Survey | Global_MS Type | Phase | NSF Milestones | Loading Curve | Sensor Vendor | LSST_CA | Summary Schedule | ICD for NSF Input | LSST Camera Critical Paths | CD2 Budget Changes | DOE Reviews | Critical Path (CD Reviews) | LSST WP Summary | Critical Path (Camera Delivery) | AWARD / NEED Sub-System | Final Design Key Links | CP - CAMM2100 | CP - CAMM2130 | CP - CAMM2160 | BNL Work Org | Last ETC Update | BNL WBS | LSST Story List | Sum Sch 01 (Camera) | Sum Sch 02 (IT w/Needs) | Sum Sch 03 (Sensors_RTM_IT) | LSST Raft Particulate Mitigation | LSST RTM
FALSE |  | CRYO00300 | COMP: Ready for CD-4- Cryostat | LSST Forecast - B57 - B1 | 0 | 0 | 2020-01-06 | 2020-01-06 | 474 |  |  | 248 | 2020-01-06 | 2020-01-06 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2020-01-06 | 2020-01-06 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 31 | 0 | 31 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04 | Cryostat | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 3 Milestone | Management/Administration
FALSE |  | CRYO62130 | COMP: CRYO Equipment & Refigeration - Chile System Ready for Summit | LSST Forecast - B57 - B1 | 0 | 0 | 2020-01-06 | 2020-01-06 | 103 |  |  | 0 | 2020-01-06 | 2020-01-06 | 2020-06-02 | 2020-06-02 | 0 | 0 | 0 | 0 | 0 | 4 | FALSE | Finish Milestone | FALSE | 2020-01-06 | 2020-01-06 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.06.04.06.03.05 | Refrigeration System - Chile System (Equipment & Refrigeration) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Brian J. Langton |  |  | Level 4 Milestone | Fabrication/Assembly
FALSE |  | SE223250 | System engineering contamination as-built design inputs for optics throughput | LSST Forecast - B57 - B1 | 60 | 60 | 2020-01-07 | 2020-04-01 | 103 |  |  | 0 | 2020-01-07 | 2020-04-01 | 2020-06-03 | 2020-08-26 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2020-01-07 | 2020-04-01 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 11 | 0 | 11 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 0 |  | Planned | 0% | 20 | 0 | 20 | 20 | LSST Forecast - B57 - B1.3.02.02.03 | Thermal and contamination system analysis | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | OP522800 | Mount filters in frame - Remaining filter | LSST Forecast - B57 - B1 | 60 | 60 | 2020-01-08 | 2020-04-02 | 107 |  |  | 0 | 2020-01-08 | 2020-04-02 | 2020-06-10 | 2020-09-02 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2020-01-08 | 2020-04-02 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 60 | 0 |  | Planned | 0% | 346 | 0 | 346 | 346 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Scott Winters | (1.10) Task/item is a modification of an existing design | 18% |  | Testing/Integration |  | Other (specify) | [5 empty] | Filters (TEC) | Production Filters Polish and integration | [5 empty] | Filter Opto-Mechanics
FALSE |  | ITC32460 | NEED: L3 Lens Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2020-01-30 | 2020-01-30 | -18 |  |  | 0 | 2020-01-30 | 2020-01-30 | 2019-12-20 | 2019-12-20 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | TRUE | 2020-01-30 | 2020-01-30 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Optics
FALSE |  | ITC32480 | Mount L3 Lens Assembly | LSST Forecast - B57 - B1 | 8 | 8 | 2020-01-31 | 2020-02-11 | -18 |  |  | 0 | 2020-01-31 | 2020-02-11 | 2020-01-06 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-01-31 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 8 | 0 |  | Planned | 0% | 65 | 0 | 65 | 65 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | SE224080 | LCA-18 as-built allocation | LSST Forecast - B57 - B1 | 40 | 40 | 2020-02-06 | 2020-04-02 | 112 |  |  | 0 | 2020-02-06 | 2020-04-02 | 2020-07-16 | 2020-09-10 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | FALSE | 2020-02-06 | 2020-04-02 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 0 |  | Planned | 0% | 50 | 0 | 50 | 50 | LSST Forecast - B57 - B1.3.02.02.04 | Optics system analysis | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | ITC19775 | Camera Assembly - Integrated Testing | LSST Forecast - B57 - B1 | 26 | 26 | 2020-02-11 | 2020-03-18 | -8 |  |  | 0 | 2020-02-11 | 2020-03-18 | 2020-01-30 | 2020-03-06 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2020-02-11 | 2020-03-18 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 26 | 0 |  | Planned | 0% | 555 | 0 | 555 | 555 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Commissioning and Testing | [5 empty] | Camera I&T (TEC) | [7 empty] | CP #03 (Carousel/Camera Integration)
FALSE |  | ITC32580 | NEED: UT Aux Electronics | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 14 | 0 | 14 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Auxiliary Electronics
FALSE |  | ITC32570 | NEED: Controls for Utility Trunk | LSST Forecast - B57 - B1 | 0 | 0 | 2020-02-11 | 2020-02-11 | -18 |  |  | 0 | 2020-02-11 | 2020-02-11 | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-02-11 | 2020-02-11 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | ITC32620 | Mount and Populate Utility Trunk | LSST Forecast - B57 - B1 | 40 | 40 | 2020-02-12 | 2020-04-08 | -18 |  |  | 0 | 2020-02-12 | 2020-04-08 | 2020-01-16 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-02-12 | 2020-04-08 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 13 | 0 | 13 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 0 |  | Planned | 0% | 767 | 0 | 767 | 767 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Analysis | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 25% |  | Testing/Integration |  | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Cryostat I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Cryostat I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC19800 | Camera Disassembly | LSST Forecast - B57 - B1 | 5 | 5 | 2020-03-19 | 2020-03-25 | -8 |  |  | 10 | 2020-03-19 | 2020-03-25 | 2020-03-09 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2020-03-19 | 2020-03-25 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 5 | 0 |  | Planned | 0% | 108 | 0 | 108 | 108 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Documented Vendor Estimate Based on Drawings/Sketches and Specifications | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 0% |  | Testing/Integration |  | Commissioning and Testing | [5 empty] | Camera I&T (TEC) | [7 empty] | CP #03 (Carousel/Camera Integration)
FALSE |  | SE224085 | COMP: Optics System Analysis | LSST Forecast - B57 - B1 | 0 | 0 | 2020-04-02 | 2020-04-02 | 392 |  |  | 114 | 2020-04-02 | 2020-04-02 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2020-04-02 | 2020-04-02 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.04 | Optics system analysis | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% | Level 4 Milestone | Design/Engineering
FALSE |  | ITC32660 | AVAIL: Loaded Cryostat Ready for Integration | LSST Forecast - B57 - B1 | 0 | 0 | 2020-04-08 | 2020-04-08 | -18 |  |  | 0 | 2020-04-08 | 2020-04-08 | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | TRUE | 2020-04-08 | 2020-04-08 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.03.04 | Cryostat Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration | [16 empty] | Integration and Test
FALSE |  | ITC19900 | Camera / Cryostat Integration | LSST Forecast - B57 - B1 | 30 | 30 | 2020-04-09 | 2020-05-20 | -18 |  |  | 0 | 2020-04-09 | 2020-05-20 | 2020-03-16 | 2020-04-24 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2020-04-09 | 2020-05-20 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 7 | 0 | 7 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 30 | 0 |  | Planned | 0% | 518 | 0 | 518 | 518 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration | Stanford University | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Camera I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Camera I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | SE221650 | Generate End Item Data Package materials and charts for PSR | LSST Forecast - B57 - B1 | 42 | 42 | 2020-04-16 | 2020-06-15 | 103 |  |  | 63 | 2020-04-16 | 2020-06-15 | 2020-09-11 | 2020-11-09 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | FALSE | 2020-04-16 | 2020-06-15 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 13 | 0 | 13 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 42 | 0 |  | Planned | 0% | 60 | 0 | 60 | 60 | LSST Forecast - B57 - B1.3.02.02.01 | Structural System Analysis | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | ITC20000 | NEED: L1-L2 Assembly | LSST Forecast - B57 - B1 | 0 | 0 | 2020-05-20 | 2020-05-20 | -18 |  |  | 0 | 2020-05-20 | 2020-05-20 | 2020-04-24 | 2020-04-24 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-05-20 | 2020-05-20 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration |  |  |  | Integration Test and Calibration | [12 empty] | Optics
FALSE |  | OP00160 | COMP: Ready for CD-4 - Optics | LSST Forecast - B57 - B1 | 0 | 0 | 2020-05-29 | 2020-05-29 | 358 |  |  | 140 | 2020-05-29 | 2020-05-29 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2020-05-29 | 2020-05-29 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05 | Optics | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  | Level 3 Milestone | Management/Administration
FALSE |  | OP522840 | AVAIL: Remaining Filters | LSST Forecast - B57 - B1 | 0 | 0 | 2020-05-29 | 2020-05-29 | 107 |  |  | 0 | 2020-05-29 | 2020-05-29 | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Finish Milestone | FALSE | 2020-05-29 | 2020-05-29 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.05.02 | Filter Assemblies | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Scott Winters |  |  | Level 5 Milestone | Testing/Integration | [8 empty] | Production Filters Polish and integration | [7 empty] | Optics
FALSE |  | DAQ100130 | COMP: Ready for CD-4 - DAQ | LSST Forecast - B57 - B1 | 0 | 0 | 2020-06-16 | 2020-06-16 | 340 |  |  | 128 | 2020-06-16 | 2020-06-16 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2020-06-16 | 2020-06-16 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 19 | 0 | 19 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.07.02 | Data Acquisition System (DAQ) | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Michael Huffer |  |  | Level 3 Milestone | Management/Administration
FALSE |  | ITC20065 | NEED: OCS & CCS Ready for I&T Testing (CCS Suite #9) | LSST Forecast - B57 - B1 | 0 | 0 | 2020-07-17 | 2020-07-17 | -18 |  |  | 0 | 2020-07-17 | 2020-07-17 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-07-17 | 2020-07-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 11 | 0 | 11 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration | [16 empty] | Project Management
FALSE |  | ITC20076 | NEED: DAQ Production V5.0 | LSST Forecast - B57 - B1 | 0 | 0 | 2020-07-17 | 2020-07-17 | -18 |  |  | 0 | 2020-07-17 | 2020-07-17 | 2020-06-22 | 2020-06-22 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-07-17 | 2020-07-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 10 | 0 | 10 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Tim Bond |  |  | Level 5 Milestone | Testing/Integration
FALSE |  | ITC20125 | Camera Functional Testing | LSST Forecast - B57 - B1 | 46 | 46 | 2020-07-20 | 2020-09-22 | -18 |  |  | 0 | 2020-07-20 | 2020-09-22 | 2020-06-23 | 2020-08-26 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2020-07-20 | 2020-09-22 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 6 | 0 | 6 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 46 | 0 |  | Planned | 0% | 1432 | 0 | 1432 | 1432 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration | Stanford University | Commissioning and Testing | [5 empty] | Camera I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Camera I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | SE222640 | Generate charts for camera-level PSR, Status Director's and DOE Review | LSST Forecast - B57 - B1 | 40 | 40 | 2020-07-20 | 2020-09-14 | 40 |  |  | 0 | 2020-07-20 | 2020-09-14 | 2020-09-15 | 2020-11-09 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | FALSE | 2020-07-20 | 2020-09-14 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 5 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 0 |  | Planned | 0% | 40 | 0 | 40 | 40 | LSST Forecast - B57 - B1.3.02.02.02 | Mechanical Integration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Percent Complete on Work Package | TEC Non-ARRA | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% |  | Fabrication/Assembly |  | Engineering Design (A/E, tech specs, conceptual, preliminary, and final design, As-built drawings, etc) | [5 empty] | System Integration & Analysis (TEC) | [6 empty] | System Analysis
FALSE |  | SE01210 | COMP: Ready for CD-4 Review - SI | LSST Forecast - B57 - B1 | 0 | 0 | 2020-09-14 | 2020-09-14 | 278 |  |  | 66 | 2020-09-14 | 2020-09-14 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2020-09-14 | 2020-09-14 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 8 | 0 | 8 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02 | Systems Integration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 3 Milestone | Management/Administration
FALSE |  | SE222650 | AVAIL: As-built Documentation | LSST Forecast - B57 - B1 | 0 | 0 | 2020-09-14 | 2020-09-14 | 40 |  |  | 0 | 2020-09-14 | 2020-09-14 | 2020-11-09 | 2020-11-09 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Finish Milestone | FALSE | 2020-09-14 | 2020-09-14 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 8 | 0 | 8 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.02.02.02 | Mechanical Integration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Vincent Riot | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 9% | Level 5 Milestone | Design/Engineering
FALSE |  | ITC20150 | Camera Verification Testing | LSST Forecast - B57 - B1 | 45 | 45 | 2020-09-23 | 2020-11-24 | -18 |  |  | 0 | 2020-09-23 | 2020-11-24 | 2020-08-27 | 2020-10-29 | 0 | 0 | 0 | 0 | 0 | 3 | FALSE | Normal | TRUE | 2020-09-23 | 2020-11-24 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 7 | 0 | 5 | 0 | 0 | 2 | 3 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 45 | 0 |  | Planned | 0% | 1468 | 0 | 1468 | 1468 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration | Stanford University | Commissioning and Testing | [5 empty] | Camera I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Camera I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC20180 | Recover from tests, secure Camera for shipping | LSST Forecast - B57 - B1 | 7 | 7 | 2020-11-25 | 2020-12-07 | -18 |  |  | 0 | 2020-11-25 | 2020-12-07 | 2020-10-30 | 2020-11-09 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-11-25 | 2020-12-07 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 4 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 7 | 0 |  | Planned | 0% | 392 | 0 | 392 | 392 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration | Stanford University | Commissioning and Testing | [5 empty] | Camera I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Camera I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | ITC20350 | Prep for C_PSR/ORR--Camera | LSST Forecast - B57 - B1 | 6 | 6 | 2020-12-08 | 2020-12-15 | -18 |  |  | 0 | 2020-12-08 | 2020-12-15 | 2020-11-10 | 2020-11-17 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-12-08 | 2020-12-15 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 10 | 0 | 10 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 6 | 0 |  | Planned | 0% | 120 | 0 | 120 | 120 | LSST Forecast - B57 - B1.3.08.04.04 | Camera Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures | BCR Impact Assessment | Planning Package | TEC Non-ARRA | Tim Bond | (1.15) Task/item is a new design, not exotic, being estimated with no prior experience | 13% |  | Testing/Integration | Stanford University | Commissioning and Testing |  | Integration Test and Calibration |  |  |  | Camera I&T (TEC) |  |  | Critical Path #1 (Sensor & Raft Tower Production) |  |  | Critical Path to CD-2 | Camera I&T | CP #01 (Cryostat/Camera Integration)
FALSE |  | CAMM2300 | COMP: KPPs achieved (Camera Readiness Review, Ready for CD-4) | LSST Forecast - B57 - B1 | 0 | 0 | 2020-12-17 | 2020-12-17 | 212 |  |  | 53 | 2020-12-17 | 2020-12-17 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | FALSE | 2020-12-17 | 2020-12-17 |  |  |  |  | 0 | 0 | FALSE | FALSE | FinishOnOrBefore | 2021-10-29 | None | [6 empty] | 37 | 0 | 37 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.01 | DOE Project Milestones | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 2 Milestone | Management/Administration
FALSE |  | ITC00100 | COMP: Ready for CD-4 - I&T | LSST Forecast - B57 - B1 | 0 | 0 | 2020-12-17 | 2020-12-17 | 212 |  |  | 0 | 2020-12-17 | 2020-12-17 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-12-17 | 2020-12-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 31 | 0 | 31 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.08 | Integration and Test | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Kevin Reil |  |  | Level 3 Milestone | Management/Administration
FALSE |  | CAM112800 | COMP: Project Ready for CD-4/CRR | LSST Forecast - B57 - B1 | 0 | 0 | 2020-12-17 | 2020-12-17 | 212 |  |  | 0 | 2020-12-17 | 2020-12-17 | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2020-12-17 | 2020-12-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 13 | 0 | 13 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01.01.02 | Reviews & Collaboration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Vincent Riot | (1.10) Task/item is a modification of an existing design | 0% | Level 4 Milestone | Management/Administration | [12 empty] | CD-3b | Critical Path to CD-3b | Project Management
FALSE |  | CAMM6050 | APPROVED: CD-4 - Project Completion - Camera | LSST Forecast - B57 - B1 | 0 | 0 | 2020-12-17 | 2020-12-17 | 305 |  |  | 53 | 2020-12-17 | 2020-12-17 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 0 | FALSE | Finish Milestone | FALSE | 2020-12-17 | 2020-12-17 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 149 | 0 | 149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.02 | NSF Watched Milestones | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration |  |  |  |  | CD-4 Project Close
FALSE |  | CAMC8700 | COMP: Project Level of Effort Support | LSST Forecast - B57 - B1 | 0 | 0 | 2020-12-18 | 2020-12-18 | 304 |  |  | 52 | 2020-12-18 | 2020-12-18 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 0 | FALSE | Finish Milestone | FALSE | 2020-12-18 | 2020-12-18 |  |  |  |  | 0 | 0 | FALSE | FALSE | None |  | None | [6 empty] | 151 | 0 | 151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01 | Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 3 Milestone | Management/Administration

## 2021 Details
Fuse® Analyst Report
Workbook: Workbook1 - 8168 Activities
Schedule Quality
Created on: 8/5/2019
Created by: brackett
2021: Detailed View | 2021: Detailed View | 2021: Detailed View | 2021: Detailed View | 2021: Detailed View
Missing Logic
Total number of activities that are missing a predecessor, a successor, or both. This number should not exceed 5%.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | Previous Start | Previous Finish | Percent Complete | Previous Remaining Duration | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | IsLevelOfEffort | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | Global_Basis of Estimate | Global_Cobra Cost Class | Cobra PMT (EV Method)_Global | Global_Color of Money | Global_Control Account Manager | Global_Design Maturity | Global_Judgement Factor | Global_Milestone Levels | Global_Project Phase | Global_Funding Source | Global_EDIA Survey | Global_MS Type | Phase | NSF Milestones | Loading Curve | Sensor Vendor | LSST_CA | Summary Schedule | ICD for NSF Input | LSST Camera Critical Paths | CD2 Budget Changes | DOE Reviews | Critical Path (CD Reviews) | LSST WP Summary | Critical Path (Camera Delivery) | AWARD / NEED Sub-System | Final Design Key Links | CP - CAMM2100 | CP - CAMM2130 | CP - CAMM2160 | BNL Work Org | Last ETC Update | BNL WBS | LSST Story List | Sum Sch 01 (Camera) | Sum Sch 02 (IT w/Needs) | Sum Sch 03 (Sensors_RTM_IT) | LSST Raft Particulate Mitigation | LSST RTM
FALSE |  | CAMM1060 | COMP: CD-4, Approve Project Completion | LSST Forecast - B57 - B1 | 0 | 0 | 2021-03-17 | 2021-03-17 | 252 |  |  | 0 | 2021-03-17 | 2021-03-17 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 0 | FALSE | Finish Milestone | TRUE | 2021-03-17 | 2021-03-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | FinishOnOrBefore | 2022-03-31 | None | [6 empty] | 17 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  |  | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.01 | DOE Project Milestones | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 1 Milestone | Management/Administration
FALSE |  | CAMM6120 | DECISION: Reduce Effective Area of the Focal Plane (3) | LSST Forecast - B57 - B1 | 0 | 0 | 2021-03-17 | 2021-03-17 | 252 |  |  | 0 | 2021-03-17 | 2021-03-17 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 0 | FALSE | Finish Milestone | TRUE | 2021-03-17 | 2021-03-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.05 | Upscope/Descope Decision Points | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration
Critical
Number of critical activities
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | Previous Start | Previous Finish | Percent Complete | Previous Remaining Duration | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | IsLevelOfEffort | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | Global_Basis of Estimate | Global_Cobra Cost Class | Cobra PMT (EV Method)_Global | Global_Color of Money | Global_Control Account Manager | Global_Design Maturity | Global_Judgement Factor | Global_Milestone Levels | Global_Project Phase | Global_Funding Source | Global_EDIA Survey | Global_MS Type | Phase | NSF Milestones | Loading Curve | Sensor Vendor | LSST_CA | Summary Schedule | ICD for NSF Input | LSST Camera Critical Paths | CD2 Budget Changes | DOE Reviews | Critical Path (CD Reviews) | LSST WP Summary | Critical Path (Camera Delivery) | AWARD / NEED Sub-System | Final Design Key Links | CP - CAMM2100 | CP - CAMM2130 | CP - CAMM2160 | BNL Work Org | Last ETC Update | BNL WBS | LSST Story List | Sum Sch 01 (Camera) | Sum Sch 02 (IT w/Needs) | Sum Sch 03 (Sensors_RTM_IT) | LSST Raft Particulate Mitigation | LSST RTM
FALSE |  | CAM112840 | CD-4/CRR DOE/SC Team Pre Doc Review | LSST Forecast - B57 - B1 | 10 | 10 | 2020-12-18 | 2021-01-14 | 252 |  |  | 0 | 2020-12-18 | 2021-01-14 | 2022-01-12 | 2022-01-26 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2020-12-18 | 2021-01-14 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 10 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01.01.02 | Reviews & Collaboration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Vincent Riot | (1.10) Task/item is a modification of an existing design | 0% |  | Management/Administration | [14 empty] | Project Management
FALSE |  | CAM112850 | CD-4/CRR DOE/SC Review | LSST Forecast - B57 - B1 | 3 | 3 | 2021-01-15 | 2021-01-19 | 252 |  |  | 0 | 2021-01-15 | 2021-01-19 | 2022-01-27 | 2022-01-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Normal | TRUE | 2021-01-15 | 2021-01-19 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 3 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01.01.02 | Reviews & Collaboration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Vincent Riot | (1.10) Task/item is a modification of an existing design | 0% |  | Management/Administration | [14 empty] | Project Management
FALSE |  | CAMC02850 | COMP: CD-4 Review - Camera Readiness Review | LSST Forecast - B57 - B1 | 0 | 0 | 2021-01-19 | 2021-01-19 | 252 |  |  | 0 | 2021-01-19 | 2021-01-19 | 2022-01-31 | 2022-01-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2021-01-19 | 2021-01-19 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01 | Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 3 Milestone | Management/Administration |  |  |  |  | CD-4 Lehman Review - Readiness Review
FALSE |  | CAM112860 | COMP: Camera Ready for CD4 Approval | LSST Forecast - B57 - B1 | 0 | 0 | 2021-01-19 | 2021-01-19 | 252 |  |  | 0 | 2021-01-19 | 2021-01-19 | 2022-01-31 | 2022-01-31 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2021-01-19 | 2021-01-19 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01.01.02 | Reviews & Collaboration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Vincent Riot | (1.10) Task/item is a modification of an existing design | 0% | Level 4 Milestone | Management/Administration | [14 empty] | Project Management
FALSE |  | CAM112870 | CD-4 Approval Process | LSST Forecast - B57 - B1 | 40 | 40 | 2021-01-20 | 2021-03-17 | 252 |  |  | 0 | 2021-01-20 | 2021-03-17 | 2022-02-01 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 2 | FALSE | Normal | TRUE | 2021-01-20 | 2021-03-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Normal | 40 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01.01.02 | Reviews & Collaboration | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys | Engineering Estimate Based on Similar Items or Procedures |  |  |  | Vincent Riot | (1.10) Task/item is a modification of an existing design | 0% |  | Management/Administration | [14 empty] | Project Management
FALSE |  | CAMM1060 | COMP: CD-4, Approve Project Completion | LSST Forecast - B57 - B1 | 0 | 0 | 2021-03-17 | 2021-03-17 | 252 |  |  | 0 | 2021-03-17 | 2021-03-17 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 0 | FALSE | Finish Milestone | TRUE | 2021-03-17 | 2021-03-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | FinishOnOrBefore | 2022-03-31 | None | [6 empty] | 17 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  |  | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.01 | DOE Project Milestones | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 1 Milestone | Management/Administration
FALSE |  | CAMC02950 | COMP: CD-4, Approve Project Completion (Early) | LSST Forecast - B57 - B1 | 0 | 0 | 2021-03-17 | 2021-03-17 | 252 |  |  | 0 | 2021-03-17 | 2021-03-17 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 1 | FALSE | Finish Milestone | TRUE | 2021-03-17 | 2021-03-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | None |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.01 | Management | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 6% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 3 Milestone | Management/Administration
FALSE |  | CAMM6120 | DECISION: Reduce Effective Area of the Focal Plane (3) | LSST Forecast - B57 - B1 | 0 | 0 | 2021-03-17 | 2021-03-17 | 252 |  |  | 0 | 2021-03-17 | 2021-03-17 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 0 | FALSE | Finish Milestone | TRUE | 2021-03-17 | 2021-03-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | AsLateAsPossible |  | None | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.05 | Upscope/Descope Decision Points | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 6 Milestone | Management/Administration
Number of Lags
Total number of activities that have lags in their predecessors. This number should not exceed 5%.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | Previous Start | Previous Finish | Percent Complete | Previous Remaining Duration | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | IsLevelOfEffort | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | Global_Basis of Estimate | Global_Cobra Cost Class | Cobra PMT (EV Method)_Global | Global_Color of Money | Global_Control Account Manager | Global_Design Maturity | Global_Judgement Factor | Global_Milestone Levels | Global_Project Phase | Global_Funding Source | Global_EDIA Survey | Global_MS Type | Phase | NSF Milestones | Loading Curve | Sensor Vendor | LSST_CA | Summary Schedule | ICD for NSF Input | LSST Camera Critical Paths | CD2 Budget Changes | DOE Reviews | Critical Path (CD Reviews) | LSST WP Summary | Critical Path (Camera Delivery) | AWARD / NEED Sub-System | Final Design Key Links | CP - CAMM2100 | CP - CAMM2130 | CP - CAMM2160 | BNL Work Org | Last ETC Update | BNL WBS | LSST Story List | Sum Sch 01 (Camera) | Sum Sch 02 (IT w/Needs) | Sum Sch 03 (Sensors_RTM_IT) | LSST Raft Particulate Mitigation | LSST RTM
FALSE |  | CAMM1060 | COMP: CD-4, Approve Project Completion | LSST Forecast - B57 - B1 | 0 | 0 | 2021-03-17 | 2021-03-17 | 252 |  |  | 0 | 2021-03-17 | 2021-03-17 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 0 | FALSE | Finish Milestone | TRUE | 2021-03-17 | 2021-03-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | FinishOnOrBefore | 2022-03-31 | None | [6 empty] | 17 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  |  | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.01 | DOE Project Milestones | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 1 Milestone | Management/Administration
Merge Hotspot
The total number of activities with a high number of predecessor links.
Excluded | Annotations | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Total Float | Actual Start | Actual Finish | Free Float | Early Start | Early Finish | Late Start | Late Finish | Baseline Cost | Budget Cost | Actual Cost | Remaining Cost | Total Cost | Number Of Discrete Successors | IsOutOfSequence | Activity Type Ex | Critical | Baseline Start | Baseline Finish | Previous Actual Start | Previous Actual Finish | Previous Start | Previous Finish | Percent Complete | Previous Remaining Duration | External | Longest Path | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Expected Finish | External Early Start | External Late Finish | Suspend Date | Resume Date | Number of Predecessors | Number of External Predecessors | Number of FS Predecessors | Number of SS Predecessors | Number of SF Predecessors | Number of FF Predecessors | Number of Successors | Number of External Successors | Number of FS Successors | Number of SS Successors | Number of SF Successors | Number of FF Successors | Number of Lags | Number of Leads | Number of Successor Lags | Number of Successor Leads | Minimum Lag | Maximum Lag | WBS Level | Number of Resource Assignments | Control Account Wbs | Control Account Obs | CWbs | CObs | IsLevelOfEffort | % | Duration Uncertainty | Use Duration Uncertainty | Duration Uncertainty Distribution | Min Duration | Most Likely Duration | Max Duration | Mean Duration | Min Duration % | Most Likely Duration % | Max Duration % | Mean Duration % | Std Deviation Duration | Cost Uncertainty | Use Cost Uncertainty | Cost Uncertainty Distribution | Min Cost | Most Likely Cost | Max Cost | Mean Cost | Min Cost % | Most Likely Cost % | Max Cost % | Mean Cost % | Std Deviation Cost | Activity Type | Baseline Duration | Actual Duration | Calendar | Activity Status | Percent Complete | Baseline Work | Actual Work | Remaining Work | Total Work | WBS Code | WBS Name | Earned Value Work | Planned Value Work | ACWP (AC) | BCWP (EV) | BCWS (PV) | EAC | Earned Value Technique | Start Percentage | Percent Complete Type | Global_Basis of Estimate | Global_Cobra Cost Class | Cobra PMT (EV Method)_Global | Global_Color of Money | Global_Control Account Manager | Global_Design Maturity | Global_Judgement Factor | Global_Milestone Levels | Global_Project Phase | Global_Funding Source | Global_EDIA Survey | Global_MS Type | Phase | NSF Milestones | Loading Curve | Sensor Vendor | LSST_CA | Summary Schedule | ICD for NSF Input | LSST Camera Critical Paths | CD2 Budget Changes | DOE Reviews | Critical Path (CD Reviews) | LSST WP Summary | Critical Path (Camera Delivery) | AWARD / NEED Sub-System | Final Design Key Links | CP - CAMM2100 | CP - CAMM2130 | CP - CAMM2160 | BNL Work Org | Last ETC Update | BNL WBS | LSST Story List | Sum Sch 01 (Camera) | Sum Sch 02 (IT w/Needs) | Sum Sch 03 (Sensors_RTM_IT) | LSST Raft Particulate Mitigation | LSST RTM
FALSE |  | CAMM1060 | COMP: CD-4, Approve Project Completion | LSST Forecast - B57 - B1 | 0 | 0 | 2021-03-17 | 2021-03-17 | 252 |  |  | 0 | 2021-03-17 | 2021-03-17 | 2022-03-29 | 2022-03-29 | 0 | 0 | 0 | 0 | 0 | 0 | FALSE | Finish Milestone | TRUE | 2021-03-17 | 2021-03-17 |  |  |  |  | 0 | 0 | FALSE | TRUE | FinishOnOrBefore | 2022-03-31 | None | [6 empty] | 17 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  |  | 4 | 0 |  |  |  |  | FALSE | 1 | Off | FALSE | [10 empty] | Off | FALSE | [10 empty] | Milestone | 0 | 0 |  | Planned | 0% | 0 | 0 | 0 | 0 | LSST Forecast - B57 - B1.3.00.01 | DOE Project Milestones | 0 | 0 | 0 | 0 | 0 | 0 | PercentComplete | 4% | CP_Phys |  |  |  |  | Vincent Riot |  |  | Level 1 Milestone | Management/Administration