## Slide 1: Base Facility Jeff Barr Project Architect LSST Telescope & Site Control Account Manager for Facilities NSF/DOE Joint Status Review August 27, 2019

## Slide 2: WBS 4.13 Base Facility
Base Facility (in partnership with NOAO & AURA)
  Plans: Andes Arq., Remodeling: Rencoret Ltda., Construction: GHG Ltda.
  Includes:
  Phase 1:
    Site Preparation and Remodeling of Existing Buildings
  Phase 2:
    Data Center
    New Office Building

## Slide 3
Base Facility Scope
New 2-story Office Building
Reception
Data Center
Existing Refurbished Office/Lab Building
Existing Shops
Relocated Warehouse
Existing Gemini Facility
Exist. Building Refurbished
for Meeting
Rooms
NORTH
Existing Refurbished Office Building
La Serena Base Facility Addition – Birdseye View

## Slide 4
Base Facility Scope – New Buildings
Plans by Andes Arquitectos for buildings under construction by Constructora GHG
Office Building 1st Floor Plan
Data Center Section

## Slide 5: Cost Summary – Base Facility Comprehensive
Phase 1 Project (Rencoret) – Base Site Preparation and remodeling 90% Complete Remaining work is remodeling of old computer rooms – anticipated completion Nov. 2019
Phase 2 Project (GHG) – Base Facility Construction 99% Complete Remaining scope is contract closeout, furnishing and occupancy
Following closeout of all work Base Facility work that is subject to the partnership agreement, the final LSST share will be determined and a contingency request will be submitted to cover accumulated change orders and other cost escalation.

## Slide 6: Earned Value Tracking – All Facilities (Summit and Base)
(All Values in $K)
Schedule Variance reflects lateness in Base Facility.
No project critical path impact anticipated.
Cost Variance mainly due to accumulated change orders in Base Facility remodeling and construction
Application of contingency for change orders on Summit Facility construction

## Slide 7: Cost (CPI) and Schedule (SPI) Performance Tracking All Facilities (Summit and Base)
Contingency applied to cover change orders on Summit Facility construction

## Slide 8: Earned Value Tracking – Base Facility Ongoing & Remaining Work
Phase 1 – Site Prep and Remodeling
Phase 1 – remodeling contract remains to be completed by end of CY 2019. Coverage of change orders for this comprehensive contract will be reconciled at conclusion.
Phase 2 – New office building and Data Center contract to be closed out imminently
Final Cost Variances subject to calculation of partner shares of change order work
Cost Variance of ~$900K (9.5% of total contract) contingency to be requested
Cost Variance of ~$420K (20% of total remodeling contract) to be reconciled at close
Schedule variance stable during hiatus in remodeling work
Phase 2 – New Building Construction

## Slide 9: Base Facility Progress – July, 2019
Front Façade and Front Entry

## Slide 10: Base Facility Progress – July, 2019
LSST Remote Operations Room & Data Center Rack Room

## Slide 11: Base Facility – Future Work
Complete IT cabling and infrastructure
Provide furnishings for offices, workspaces and common areas.
Complete move to new Base facility Offices – September, 2019
Complete remodeling of old computer rooms to conference rooms – December, 2019
Closeout all contracts and reconcile final AURA/LSST/NOAO partnership accounting – early 2020

## Slide 12: Base Facility – Risks and Opportunities
Construction-related risks have been substantially retired.
Risk of damage to critical LSST data processing/storage equipment has been mitigated by seismic isolation of the Data Center
Risks of adequacy of Data Center space and utilities have been substantially retired, as all criteria defined in LSE-239 Base Facility Data Center Requirements have been satisfied.
Future opportunities remain for previously designed - but not implemented - options for addition of public gallery space and photovoltaic power generation panels.

## Slide 13: Base Facility – Safety
Remodeling and new construction work in ~2 ½ years of work have resulted in no serious accidents or incidents.
Continued safety vigilance will be maintained regarding final remodeling to be carried out in proximity of occupied business and residential areas.
Life and health safety issues in Base Facility have been successfully addressed by full compliance of all new and remodeled facilities with all applicable Chilean and International building codes.

## Slide 14: Thank-you