## Slide 1: Summit Facility Jeff Barr Project Architect LSST Telescope & Site Control Account Manager for Facilities NSF/DOE Joint Status Review August 27, 2019

## Slide 2: WBS 4.3 Summit Facility & 4.13 Base Facility
Summit Facility
  Plans: Arcadis -Chile, Main Construction: Besalco Construcciones
  Includes:
  Main Service Building, Lower Enclosure, and Telescope Pier
  Auxiliary Telescope Building and Dome
  Platform Lift (Pflow)
  Pachón Hotel Addition (Proyect, Ltda.)

## Slide 3: Summit Facility Scope
Drone Views (from early 2018 before Dome erection start)
Auxiliary Telescope Building
Service Building Platform Lift Lower Enclosure

## Slide 4: Summit Facility Scope – Telescope Enclosure/Service Bldg.
prevailing
wind
Service Building – 2,630 m2 (28,300 ft2) gross area
1 - Utility Ground Floor: main entry, shop, mech./elect. equip., camera refrigeration
2 - Control Floor: control room, computing, general office/support areas
3 - Maintenance Floor: mirror coating & camera maintenance
4 - Mezzanine Floor: elevated catwalk to telescope, staging platforms, Camera HVAC
5 - Enclosure Ground Floor/Upper Service Floor: connecting level between buildings
- Platform Lift for conveyance of mirrors & camera
Telescope Pier & Enclosure – 16m D & 30m D – 707 m2 (7,600 ft2)
5 - Lower Enclosure Floor: utility access, shop, storage
6 - Pier Intermediate and Upper Floors: electrical, utility access
7 - Dome Floor: access to telescope and dome
8 - Telescope Maintenance Platform: service access to telescope
access road
concrete pier & lower enclosure walls
platform lift
general utility room
optics
base of lower enclosure
machine shop
base of
pier
Maintenance Floor Level 3
rails for mirror cart
Receiving door and truck ramp
camera maintenance area
mirror maintenance area
platform lift
deck
Control Room
Computer
Control Floor Level 2
Open Office
Break
Conf.
Entry
Shop
Mech.
Elec.
Cam
Refrig
OSS
Utility Ground Floor Level 1
Telescope Platform Level 8
Dome Floor Level 7
Dome Floor
hatch
2 pier floor levels
Telescope Platform
platform lift
roof
rails
Enclosure Ground Floor Level 5
0 5 10 20m
north
receiving
Auxiliary Telescope Facility
Level 2
Level 1
pier
enclosure
dome & telescope
on adjacent hill

## Slide 5: Cost Summary – Summit Facility Comprehensive
Summit Facility Construction (Besalco) 100% Complete Contingency was requested and applied to cover an overspend of $2,600K
Platform Lift Contract (Pflow) 100% Complete Pending final closeout & documentation
Lodging addition ~60% complete
Post Construction activities are added by LCR as work is required and executed

## Slide 6: Earned Value Tracking – All Facilities (Summit and Base)
(All Values in $K)
Schedule Variance reflects lateness in Base Facility.
No project critical path impact anticipated.
Cost Variance mainly due to accumulated change orders in Base Facility remodeling and construction
Application of contingency for change orders on Summit Facility construction

## Slide 7: Cost (CPI) and Schedule (SPI) Performance Tracking All Facilities (Summit and Base)
Contingency applied to cover change orders on Summit Facility construction

## Slide 8: Earned Value Tracking – Pachón Lodging Addition Only Remaining Facility Construction Work at Summit
High CPI reflects conservative under-billing by contractor
Low SPI reflects under-billing and foundation/weather delays
Anticipated completion
Sept.
30th
Contract (now 60% done) w/ Proyect Ltda. – well-managed to date by Contractor/LSST team.
Remodeling to create 2 new rooms completed on schedule in ~3 months.
4–Room Addition has been subject to unexpected soil condition and weather delays.
Final Change Order total expected to be ~$40K, less than 10% of overall contract value.
Utilizing this Contractor (Proyect Ltda.) for guard-railing and other work at main summit site.

## Slide 9: Summit Facilities – Accomplishments
Summit Facility Complete – Photo from July, 2019

## Slide 10: Summit Facilities – Accomplishments
Camera Clean/White Rooms Now in use
Entry of M1M3 Cell in Facility July 24, 2019
Platform Lift Raised to maximum height and load tested March 2019

## Slide 11: Summit Facilities – Accomplishments
Calibration Hill Facilities continue in development
Weather tower – DIMM Tower – Aux. Tel. Dome
Warehouse constructed to protect M1M3 Mirror and for future storage

## Slide 12: Summit Facilities – Accomplishments
Pachón Hotel Addition
2 LSST rooms provided by remodeling
4 more rooms under construction in new addition

## Slide 13: Summit Facilities – Future Work
Post Construction Projects
  Enclosure of Camera Refrigeration Room at first level
  Enclosure of Dynalene Chiller room in telescope pier
  Improvements to weather-proofing of first level
  Final improvements to roads and platforms
  Installation of man-lift, pier ring platform in dome area
  Other – as defined, approved and scheduled
Completion of Hotel addition Rooms available by October 2019 to support TMA on-site work and other AIV activities.

## Slide 14
Construction related risks substantially retired
Schedule impact risks retired. Summit Facility complete and ready for integration of all subsystems.
Scope option for constructing warehouse was identified and realized to mitigate M1M3 risk provide benefit for future operations.
Scope option for acquiring previous contractor dining facility and offices have was identified and realized with benefit to AIV efficiency and schedule.
Summit Facilities – Risks and Opportunities

## Slide 15: Summit Facility – Safety
Summit Facility site preparation and construction completed with no major accidents or incidents.
Continued safety vigilance will continue for completion of Hotel addition project and post-construction work.
Life and health safety issues in Summit Facility have been successfully addressed by full compliance of facility with all applicable Chilean and International building codes.

## Slide 16: Thank-you