## Intro
Risk Report Data
This file is the generated report data from the Report Data Python script. Copy the relevant tables into the Word document to create the report.
Overall PWCE: |  | 23190.9
Notes | To obtain the risk matrix used for section 5, go to the following link and take a screenshot (Snipping Tool or Win-Shift-S):
https://jira.lsstcorp.org/projects/RM?selectedItem=com.ja.jira.plugin.report.riskmanagement:RiskManagementTab

## Table 1
Risk Summary
Sub-system | Active Risk/Opportunity | Proposed | Realized | Retired | Expected Labor Risk Exposure (K-USD)* | Expected Non-Labor Risk Exposure | Prob. Weighted Exposure Cost (K-USD)* | Subsystem | Labor Exposure | Nonlabor Exposure | PWE ($K)
Data Management | 66 | 0 | 5 | 18 | 4248.6 | 4130.9775 | 8379.47 | Data Management | 4248.6 | 4130.9775 | 8379.47
Education and Public Outreach | 7 | 2 | 1 | 8 | 362.8 | 167.5 | 530.3 | Education and Public Outreach | 362.8 | 167.5 | 530.3
Project Management Office | 14 | 4 | 0 | 2 | 5025.5 | 1748.5 | 6774 | Project Management Office | 5025.5 | 1748.5 | 6774
Systems Engineering | 25 | 1 | 1 | 8 | 2720.2 | 1447.9 | 4168.1 | Systems Engineering | 2720.2 | 1447.9 | 4168.1
Telescope & Site | 66 | 0 | 3 | 18 | 3473.7 | 2026.225 | 5883.13 | Telescope & Site | 3473.7 | 2026.225 | 5883.13
Totals | 178 | 7 | 10 | 54 | 15830.8 | 9521.1025 | 25735 | Totals | 15830.8 | 9521.1025 | 25735
[8 empty] | Subsystem | Active Risk/Opportunity | Proposed | Realized | Retired
[8 empty] | Data Management | 66 | 0 | 5 | 18
[8 empty] | Education and Public Outreach | 7 | 2 | 1 | 8
[8 empty] | Project Management Office | 14 | 4 | 0 | 2
[8 empty] | Systems Engineering | 25 | 1 | 1 | 8
[8 empty] | Telescope & Site | 66 | 0 | 3 | 18

## Table 2
Opportunity Summary
Sub-system | Active Risk/Opportunity | Proposed | Realized | Retired | Expected Labor Risk Exposure (K-USD)* | Expected Non-Labor Risk Exposure | Prob. Weighted Exposure Cost (K-USD)* | Subsystem | PWE ($K)
Data Management | 2 | 0 | 0 | 3 |  |  | 55 | Data Management | 55
Education and Public Outreach | 0 | 0 | 2 | 0 |  |  | 0 | Project Management Office | 2324.5
Project Management Office | 5 | 0 | 0 | 2 |  |  | 2324.5 | Systems Engineering | 164.6
Systems Engineering | 3 | 0 | 0 | 1 |  |  | 164.6 | Any missing rows indicate all values are 0
Telescope & Site | 0 | 0 | 0 | 0 |  |  | 0 | Any missing rows indicate all values are 0
Totals | 10 | 0 | 2 | 6 |  |  | 2544.1 | Totals | 2544.1
[8 empty] | Subsystem | Active Risk/Opportunity | Realized | Retired
[8 empty] | Data Management | 2 | 0 | 3
[8 empty] | Education and Public Outreach | 0 | 2 | 0
[8 empty] | Project Management Office | 5 | 0 | 2
[8 empty] | Systems Engineering | 3 | 0 | 1

## Table 3
Table 3
Top Risks List
Sort Number | Risk ID # | Subsystem | WBS | Risk Title | Probability Weighted Cost Exposure ($K)
1 | RM-886 | Project Management Office | 01C | Subsystem Milestone Execution | 3717
2 | RM-773 | Data Management | 02C.04 | Computing power required for Data Release Production exceeds estimates by large factor | 1348.1
3 | RM-888 | Project Management Office | 01C | Multi-agency coordination - Camera Delivery | 1332
4 | RM-1938 | Telescope & Site | 04C.04.02.05 | Dome Integration Late | 1036
5 | RM-1935 | Telescope & Site | 04C.05.02.05 | TMA Integration Late | 999
6 | RM-775 | Data Management | 02C.04.06 | Unanticipated characteristics of real data result in poor MultiFit performance (computational) | 962
7 | RM-733 | Systems Engineering | 06C.02 | Discontinuity between subsystem I&T and Commissioning staffing levels | 888
8 | RM-815 | Telescope & Site | 4.14 | Telescope and Site Integration activities underestimated | 851
9 | RM-723 | Data Management | 02C.04 | Object counts exceed expectations, leading to insufficient compute | 822.8
10 | RM-735 | Systems Engineering | 6 | Unstable Camera opto-electronic performance | 740
| Date: | 2019-07-29 |  | Top Ten Total: | 12695.9

## Table 4
Table 4
Top 10 List - Opportunities
Sort Number | Opp ID # | Subsystem | WBS | Title | Probability Weighted Cost Exposure ($K)
1 | RM-628 | Project Management Office | 1.01C.01 | Favorable Chilean Currency Exchange Rate Factor | 1480
2 | RM-629 | Project Management Office | 1.01C | Favorable Personnel Costs | 442
3 | RM-630 | Project Management Office | 1.01C | Favorable Material Estimate Uncertainty | 340
4 | RM-785 | Systems Engineering | 1.06C.05 | Commissioning Finishes Early | 112.5
5 | RM-631 | Project Management Office | 1.01C | Favorable Institutional Overhead Rates | 60
6 | RM-627 | Data Management | 02C.10 | New or different technology provides saving in hardware/effort. | 30
7 | RM-786 | Systems Engineering | 1.06C | Standardizing Common Hardware Across Subsystems | 29.6
8 | RM-624 | Data Management | 02C.04.06 | Exceptional MultiFit Performance | 25
9 | RM-787 | Systems Engineering | 1.06C.05 | Camera Verification On Summit Finishes Early | 22.5
10 | RM-632 | Project Management Office | 1.01C | Purchase Forward Planned Hardware Sooner with Favorable Exchange Rates | 2.5
| Date: | 2019-07-29 |  | Top Ten Total: | 2544.1

## Table 6
JIRA ID | Subsystem | WBS | Summary | PWE ($K) | Proposed Management Response
RM-886 | Project Management Office | 01C | Subsystem Milestone Execution | 3717 | Schedule and contingency will be used along with reworking the integrated plan to deal with subsystem delays

## Table 7
Subsystem | JIRA ID | Summary | WBS | Trigger Date | Probability | Nonlabor Cost | Labor Cost | PWE ($K)
Telescope & Site | RM-881 | Calibration atmospheric telescope dome does not meet automation requirements | 4.8 | 2019-03-01 | 0%-5% | 100 | 120 | 5.5
Telescope & Site | RM-817 | Mount Late Delivery | 4.5 | 2019-05-01 | 25%-50% | 0 | 0 | 169.2
Telescope & Site | RM-814 | Dome Late Delivery | 4.4 | 2019-05-01 | 25%-50% | 0 | 0 | 178.5
Telescope & Site | RM-869 | Telescope mount pier interfaces must be modified | 4.5 | 2019-06-01 | 0%-5% | 100 | 600 | 17.5
Telescope & Site | RM-821 | Summit Integration of dome, mount and telescope causes project delays | 4.1 | 2019-06-01 | 25%-50% | 250 | 160 | 151.7
Telescope & Site | RM-846 | Telescope mount interfaces to camera must be modified | 4.5 | 2019-07-01 | 0%-5% | 200 | 400 | 15
Telescope & Site | RM-871 | Calibration atmospheric telescope refurbishment does not meet performance requirements | 4.8 | 2019-07-31 | 5%-10% | 100 | 120 | 16.5
Systems Engineering | RM-733 | Discontinuity between subsystem I&T and Commissioning staffing levels | 06C.02 | 2019-07-31 | 25%-50% | 0 | 2400 | 888
Telescope & Site | RM-1878 | Dome Maintenance Required before final acceptance | 04C.04 | 2019-08-01 | 25%-50% | 500 | 0 | 185
Telescope & Site | RM-815 | Telescope and Site Integration activities underestimated | 4.14 | 2019-08-01 | 25%-50% | 500 | 1800 | 851
Telescope & Site | RM-1936 | TMA Shipping Late | 04C.05.02.04 | 2019-09-30 | 10%-25% | 0 | 900 | 153
Data Management | RM-813 | Insufficiently reliable network infrastructure at Base Center | 02C.08.01 | 2019-09-30 | 5%-10% | 500 | 0 | 37.5
Systems Engineering | RM-726 | Camera Refrigeration System Maintainability | 06C.01.01 | 2019-09-30 | 50%-75% | 750 | 0 | 472.5
Systems Engineering | RM-746 | System Level Performance Impacts of Compounding Component Optical Defects | 1.06C.01 | 2019-09-30 | 5%-10% | 0 | 180 | 13.5
Telescope & Site | RM-819 | Telescope and Site shipping and logistics scope and budget | 4.12 | 2019-10-01 | 10%-25% | 300 | 0 | 51
Telescope & Site | RM-826 | Dome dynamic performance below specifications | 4.4 | 2019-10-01 | 5%-10% | 300 | 320 | 46.5
Telescope & Site | RM-848 | Dome Flushing Performance below specifications | 4.4 | 2019-11-01 | 5%-10% | 300 | 240 | 40.5
Telescope & Site | RM-849 | Dome Seal performance below specifications | 4.4 | 2019-11-01 | 5%-10% | 280 | 240 | 39
Systems Engineering | RM-731 | Infrastructure Interface between Base Facility and Camera Inadequately defined | 06C.02.02.02 | 2019-11-01 | 0%-1% | 500 | 80 | 2.9
Telescope & Site | RM-820 | AOS Software Late Delivery | 4.11 | 2019-12-01 | 10%-25% | 50 | 80 | 22.1
Telescope & Site | RM-884 | M1M3 mirror damage during summit integration requiring repair | 4.14 | 2019-12-01 | 0%-1% | 200 | 3600 | 19
Telescope & Site | RM-822 | M1M3 cell assembly integration work falls behind schedule | 4.6.4 | 2019-12-31 | 5%-10% | 250 | 200 | 33.75
Telescope & Site | RM-862 | Calibration process for u-band performs below specifications | 4.8 | 2020-01-01 | 0%-5% | 250 | 120 | 9.25
Telescope & Site | RM-868 | M1M3 Hard Point performances below specifications | 4.6.3 | 2020-01-01 | 0%-5% | 100 | 120 | 5.5
Telescope & Site | RM-866 | M1M3 mirror damage during transport between support building &amp; telescope | 4.12 | 2020-01-01 | 0%-5% | 50 | 240 | 7.25
Telescope & Site | RM-885 | Mount dynamic performances below specifications on summit | 4.5 | 2020-01-01 | 5%-10% | 250 | 240 | 36.75
Telescope & Site | RM-839 | M1M3 Axial support bandwidth low | 4.6.3 | 2020-01-01 | 5%-10% | 250 | 180 | 32.25
Telescope & Site | RM-847 | M1M3 overstress due to Coating Chamber Differential Pumping | 4.9 | 2020-01-01 | 5%-10% | 250 | 320 | 42.75
Telescope & Site | RM-853 | M1M3 or M2 surface error found during summit integration due to poor AOS control | 4.14 | 2020-01-01 | 0%-5% | 75 | 400 | 11.88
Telescope & Site | RM-857 | Vacuum Seal between M1M3 Cell and Mirror fails during coating | 4.9 | 2020-01-01 | 0%-5% | 400 | 40 | 11
Telescope & Site | RM-829 | M2 mirror damage during summit integration requiring repair | 4.12 | 2020-01-01 | 0%-1% | 200 | 3600 | 19

## Table 8
Subsystem | ID | Summary | Date | User | Comment
Data Management | RM-674 | New SRD requirements require new DM functionality | 2019-06-25 21:55 | Wil O'Mullane | Reviewed with no changes.
| RM-685 | Science data quality analysis tools inadequate | 2019-06-25 21:53 | Wil O'Mullane | Reviewed with no changes.
| RM-704 | Science Data Quality Assessment unexpected requirements | 2019-06-25 21:55 | Wil O'Mullane | Reviewed with no changes.
| RM-708 | Science Data Quality Assessment - too slow | 2019-06-25 21:58 | Wil O'Mullane | Reviewed with no changes.
| RM-720 | Software framework insufficiently extensible to support addition/removal of algorithms | 2019-06-25 21:59 | Wil O'Mullane | Reviewed with no changes.
| RM-757 | Filesystems fail to scale adequately | 2019-06-25 21:54 | Wil O'Mullane | Reviewed with no changes.
| RM-765 | System and service monitoring tools inadequate | 2019-06-25 21:58 | Wil O'Mullane | Reviewed with no changes.
Education and Public Outreach | RM-805 | Loss of key EPO personnel | 2019-07-23 22:26 | Amanda Bauer | Ben Emmons left Project Jan 2019. We have recovered from this loss by bringing Cathy Petry on at 0.5 FTE to assist with Project Controls. The risk still exists and we will continue work toward maintaining a productive workplace for all team members.
|  |  | 2019-07-23 22:28 | Amanda Bauer | Abbey Yacoe left Project May 2019. We have recovered by hiring Blake Mason for the Web Developer position. This risk still exists and we will continue work toward maintaining a productive workplace for all team members.
Project Management Office | RM-887 | Institutional Overhead Rates | 2019-07-02 23:00 | Victor Krabbendam | This probability has been reduced to a 10-25% exposure as AURA has managed the changes in indirect rates to have minimal impact on LSST Construction. The exposure has also been reduced to half of the 2017 value.
| RM-888 | Multi-agency coordination - Camera Delivery | 2019-07-02 23:12 | Victor Krabbendam | With the latest schedule change in the NSF funded effort, the Camera has gained additional float so the probability of the camera being late is reduced to 25-50%
Telescope & Site | RM-816 | Weather impact on construction schedule | 2019-07-18 15:45 | Victor Krabbendam | Scheduling outside work around the seasons has not been successful. The weather will continue to be a factor for Dome finish work and for the key TMA installation until finished. Some TMA integration work has been planned for installation through the Facility lift and dome crane so that the weather impacts will be minimized.
| RM-820 | AOS Software Late Delivery | 2019-06-27 22:05 | Austin Roberts | Made the schedule recoverable and adjusted to 2 FTE's for 2 months and 50K for vendor support.
| RM-823 | Loss of key Telescope and Site personnel | 2019-07-19 13:57 | Victor Krabbendam | T&S effort is nearing critical completion so exposure reduced to 300k to represent an FTE of consultation if a key staff member left.
| RM-831 | OCS Requirements change | 2019-06-27 21:58 | Austin Roberts | This was realized and the OCS has been re-architected as part of the T&S Software replan.
| RM-833 | Summit facility must be modified to accommodate interfaces | 2019-07-18 04:17 | Victor Krabbendam | System integration is now more compressed and may add demands on the facility that were not originally envisioned so along with critical subsystems (TMA Dome, Camera) that will be delivered through 2020, the trigger date for this risk was extended to Dec 2020.
| RM-836 | Availability of all LSST components to commission OCS system | 2019-07-02 22:33 | Victor Krabbendam | Reviewed with no changes.
| RM-838 | OCS implementation complicated by inability to run system prior to going live | 2019-07-02 22:20 | Victor Krabbendam | Reviewed with no changes.
| RM-843 | Camera Utilities provided from mount top end not adequate | 2019-07-18 15:52 | Victor Krabbendam | Prototypes, ICDs, and requirements have all been managed. This remaining risk exposure will remian until tested with the camera.
| RM-851 | LSST coating chamber performances below specifications | 2019-07-02 22:26 | Austin Roberts | The coating chamber has been accepted from the vendor.
| RM-855 | Mount or Dome Motion Coupling Predicted During Observing | 2019-07-02 21:35 | Austin Roberts | Reviewed with no changes.
| RM-859 | Coating system Magnetron contacting mirror surface | 2019-07-18 20:22 | Victor Krabbendam | Coating Facility has successfully passed it acceptance test and has successfully been used on the M2. The only remaining appreciable risk is for M1M3.
| RM-873 | Camera or M2 Hexapod motion out of range | 2019-07-18 15:35 | Victor Krabbendam | Design and ICD mitigations completed. Remaining risk will now extend until final test of TMA and Hexapod on site.
| RM-878 | Power distribution interruption | 2019-07-18 20:40 | Victor Krabbendam | Power back-up system has been tested. There will continue to be a risk of Lightning damage to the infrastructure
|  |  | 2019-07-19 16:22 | Oliver Wiecha | To minimize the risk of electrical damage due to lightning, the LSST summit facility electrical system has been designed to avoid exposure of UPS power to the elements. UPS power is only distributed inside the facility and it feeds all major systems, except any load located on the rotating enclosure (AKA dome) or outside the building. The dome is generously grounded in several locations providing parallel discharge paths directly to the ground mesh, therefore minimizing the difference in electrical potential resulting from a direct lightning strike. A direct hit to the incoming high voltage power lines would be attenuated by the facility power transformer and the very large TVSS installed right ahead.
| RM-885 | Mount dynamic performances below specifications on summit | 2019-07-02 21:51 | Austin Roberts | Recent testing at vendor shows that the factory control issue has been resolved. Reduced expected dollars to $250K and expected months to 3.

## Table 9
ID | Date | Author | Field | From | To
RM-1 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-1878 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-1932 | 2019-07-02 20:35 | Austin Roberts | Link | 0 | This issue is child task of RM-817
| 2019-07-02 20:42 | Austin Roberts | Link | 0 | This issue is mitigated by RM-1933
| 2019-07-02 20:42 | Austin Roberts | status | Proposed | Active Risk/Opportunity
| 2019-07-02 20:46 | Austin Roberts | Link | 0 | This issue is mitigated by RM-1934
| 2019-07-02 20:55 | Austin Roberts | assignee | William Gressler | Shawn Callahan
| 2019-07-03 16:37 | Austin Roberts | summary | Software Integration Late | TMA Software Integration Late
RM-1935 | 2019-07-02 20:54 | Austin Roberts | Link | 0 | This issue is child task of RM-817
| 2019-07-02 20:55 | Austin Roberts | Handling Actions | 0
|  |  | status | Proposed | Active Risk/Opportunity
| 2019-07-02 20:56 | Austin Roberts | Handling Actions | 0 | RM-1857, RM-1649
|  |  | Link | 0 | This issue is mitigated by RM-1857This issue is mitigated by RM-1649
RM-1936 | 2019-07-02 21:03 | Austin Roberts | Link | 0 | This issue is child task of RM-817
| 2019-07-02 21:03 | Austin Roberts | Handling Actions | 0
|  |  | status | Proposed | Active Risk/Opportunity
RM-1937 | 2019-07-02 21:13 | Austin Roberts | Link | 0 | This issue is child task of RM-814
| 2019-07-02 21:14 | Austin Roberts | Handling Actions | 0
|  |  | status | Proposed | Active Risk/Opportunity
| 2019-07-02 00:18 | Austin Roberts | summary | Contractor Default | Dome Contractor Default
RM-1938 | 2019-07-02 21:18 | Austin Roberts | Link | 0 | This issue is child task of RM-814
| 2019-07-02 21:18 | Austin Roberts | Handling Actions | 0
|  |  | status | Proposed | Active Risk/Opportunity
| 2019-07-02 21:19 | Austin Roberts | Link | 0 | This issue is mitigated by RM-1485This issue is mitigated by RM-1648
| 2019-07-02 21:19 | Austin Roberts | Handling Actions | 0 | RM-1485, RM-1648, RM-1893
|  |  | Link | 0 | This issue is mitigated by RM-1893
RM-1939 | 2019-07-02 22:17 | Austin Roberts | Link | 0 | This issue is parent task of RM-877
| 2019-07-02 22:17 | Austin Roberts | summary | OCS Development isLate | OCS Development is Late
| 2019-07-02 22:18 | Austin Roberts | Link | 0 | This issue is parent task of RM-838
| 2019-07-02 22:18 | Austin Roberts | Link | 0 | This issue is parent task of RM-745This issue is parent task of RM-836
| 2019-07-02 22:24 | Victor Krabbendam | Handling Actions | 0
|  |  | status | Proposed | Active Risk/Opportunity
| 2019-07-25 21:34 | Austin Roberts | Expected Dollars (K$) | 0 | 0
|  |  | Handling Actions | 0
RM-2 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-3 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-4 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-49 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-668 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-671 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-672 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-673 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-674 | 2019-06-25 21:55 | Wil O'Mullane | Last Reviewed (Deprecated) | 31/Jan/18 12:00 AM | 25/Jun/19 9:54 PM
|  |  | status | Active Risk/Opportunity | Active Risk/Opportunity
| 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-675 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-676 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-677 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-678 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-679 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-680 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-683 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-684 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-685 | 2019-06-25 21:53 | Wil O'Mullane | Last Reviewed (Deprecated) | 03/May/19 9:17 PM | 25/Jun/19 9:52 PM
|  |  | status | Active Risk/Opportunity | Active Risk/Opportunity
| 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-686 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-687 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-688 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-689 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-691 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-692 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-694 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-695 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-696 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-697 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-698 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-699 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-700 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-701 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-702 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-703 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-704 | 2019-06-25 21:55 | Wil O'Mullane | Last Reviewed (Deprecated) | 23/Jan/19 3:50 PM | 25/Jun/19 9:55 PM
|  |  | status | Active Risk/Opportunity | Active Risk/Opportunity
| 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-705 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-706 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-707 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-708 | 2019-06-25 21:58 | Wil O'Mullane | Last Reviewed (Deprecated) | 03/May/19 9:48 PM | 25/Jun/19 9:57 PM
|  |  | status | Active Risk/Opportunity | Active Risk/Opportunity
| 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-710 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-711 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-712 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-713 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-714 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-715 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-716 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-717 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-718 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-719 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-720 | 2019-06-25 21:59 | Wil O'Mullane | Last Reviewed (Deprecated) | 03/May/19 9:50 PM | 25/Jun/19 9:58 PM
|  |  | status | Active Risk/Opportunity | Active Risk/Opportunity
| 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-721 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-723 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-725 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-726 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-727 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-728 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-729 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-730 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-731 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-732 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-733 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-734 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-735 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-737 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-738 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-739 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-740 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-741 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-742 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-743 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-745 | 2019-07-02 22:18 | Austin Roberts | Link | 0 | This issue is child task of RM-1939
| 2019-07-03 16:08 | Austin Roberts | Is Parent Risk | 0 | False
RM-746 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-747 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-749 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-752 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-753 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-754 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-755 | 2019-06-25 21:48 | Wil O'Mullane | Current Probability of Occurrence | 0%-5% | 0%-1%
| 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-757 | 2019-06-25 21:54 | Wil O'Mullane | Last Reviewed (Deprecated) | 16/Apr/18 12:00 AM | 25/Jun/19 9:53 PM
|  |  | status | Active Risk/Opportunity | Active Risk/Opportunity
| 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-758 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-759 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-760 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-762 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-763 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-765 | 2019-06-25 21:58 | Wil O'Mullane | Last Reviewed (Deprecated) | 03/May/19 9:56 PM | 25/Jun/19 9:58 PM
|  |  | status | Active Risk/Opportunity | Active Risk/Opportunity
| 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-766 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-768 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-769 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-773 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-774 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-775 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-776 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-780 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-783 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-784 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-802 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-803 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
| 2019-07-24 18:58 | Amanda Bauer | Obligation Date | 1/Sep/21 | 31/Jan/22
RM-804 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
| 2019-07-24 20:13 | Amanda Bauer | Obligation Date | 1/Mar/21 | 1/Mar/22
| 2019-07-24 21:27 | Amanda Bauer | FTE's required | 4 | 3
RM-805 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-806 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-807 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
| 2019-07-24 21:23 | Amanda Bauer | Obligation Date | 1/Oct/20 | 1/Oct/21
RM-808 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-813 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-814 | 2019-07-02 21:13 | Austin Roberts | Link | 0 | This issue is parent task of RM-1937
| 2019-07-02 21:18 | Austin Roberts | Link | 0 | This issue is parent task of RM-1938
| 2019-07-02 21:19 | Austin Roberts | Link | This issue is mitigated by RM-1485 | 0
| 2019-07-02 21:19 | Austin Roberts | Link | This issue is mitigated by RM-1648 | 0
| 2019-07-02 21:19 | Austin Roberts | Link | This issue is mitigated by RM-1893 | 0
| 2019-07-02 21:19 | Austin Roberts | Expected (months) | 1
|  |  | Expected Dollars (K$) | 1500
|  |  | FTE's required | 0
|  |  | Handling Actions | 0
|  |  | Is Parent Risk | 0 | True
| 2019-07-25 21:33 | Austin Roberts | Expected Dollars (K$) | 0 | 0
|  |  | Handling Actions | 0
RM-815 | 2019-06-27 16:51 | Andy Clements | labels |  | Software
| 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-816 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
| 2019-07-18 15:42 | Victor Krabbendam | Obligation Date | 1/Aug/19 | 30/Jan/20
RM-817 | 2019-07-02 20:35 | Austin Roberts | Link | 0 | This issue is parent task of RM-1932
| 2019-07-02 20:54 | Austin Roberts | Link | 0 | This issue is parent task of RM-1935
| 2019-07-02 20:56 | Austin Roberts | Link | This issue is mitigated by RM-1649 | 0
| 2019-07-02 20:56 | Austin Roberts | Link | This issue is mitigated by RM-1857 | 0
| 2019-07-02 21:03 | Austin Roberts | Link | 0 | This issue is parent task of RM-1936
| 2019-07-02 21:04 | Austin Roberts | Expected (months) | 2
|  |  | Expected Dollars (K$) | 0
|  |  | FTE's required | 0
|  |  | Handling Actions | 0
|  |  | Is Parent Risk | 0 | True
| 2019-07-02 21:05 | Austin Roberts | assignee | William Gressler | Shawn Callahan
| 2019-07-25 21:33 | Austin Roberts | Expected Dollars (K$) | 0 | 0
|  |  | Handling Actions | 0
RM-819 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
| 2019-07-18 20:55 | Victor Krabbendam | Expected Dollars (K$) | 750 | 300
|  |  | Notebook 2 | LCR-575 established a work package in WBS 04C.12.8 to fund shipping and logistics activities for M1M3, M2, hexapod and rotator, TMA, and the coating plant. This risk covers the potential cost when the detailed planning activities are schedule. Used 50% of the planned budget ($1.6M) as the target expense. Labor coverage planned to use AURA resources. Jan 2019: reduce exposure to $750k due to M2 and coating plant delivery | LCR-575 established a work package in WBS 04C.12.8 to fund shipping and logistics activities for M1M3, M2, hexapod and rotator, TMA, and the coating plant. This risk covers the potential cost when the detailed planning activities are schedule. Used 50% of the planned budget ($1.6M) as the target expense. Labor coverage planned to use AURA resources. Jan 2019: reduce exposure to $750k due to M2 and coating plant delivery Recent Change request captures all known logistics costs through TMA. only minor unforeseen issues remain for this risk.
|  |  | Obligation Date | 1/Aug/19 | 1/Oct/19
RM-820 | 2019-06-27 16:57 | Andy Clements | labels |  | Software
| 2019-06-27 22:01 | Austin Roberts | FTE's required | 0 | 1
| 2019-06-27 22:02 | Austin Roberts | FTE's required | 1 | 0
| 2019-06-27 22:02 | Austin Roberts | Schedule Recoverable | No | Yes
| 2019-06-27 22:03 | Austin Roberts | FTE's required | 0 | 2
| 2019-06-27 22:03 | Austin Roberts | Expected (months) | 1 | 2
| 2019-06-27 22:04 | Austin Roberts | Expected Dollars (K$) | 0 | 50
| 2019-06-27 22:05 | Austin Roberts | Handling Approach | Mitigate | Accept
| 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-821 | 2019-06-27 17:33 | Andy Clements | labels |  | Software
| 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-822 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
| 2019-07-18 04:03 | Victor Krabbendam | FTE's required | 0 | 5
|  |  | Obligation Date | 1/Aug/19 | 31/Dec/19
|  |  | Schedule Recoverable | No | Yes
|  |  | assignee | William Gressler | Doug Neill
| 2019-07-18 04:03 | Victor Krabbendam | Expected (months) | 1 | 2
|  |  | Expected Dollars (K$) | 0 | 250
RM-823 | 2019-06-27 16:58 | Andy Clements | labels |  | Software
| 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
| 2019-07-19 13:57 | Victor Krabbendam | Expected Dollars (K$) | 500 | 300
RM-824 | 2019-06-27 17:34 | Andy Clements | labels |  | Software
| 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-825 | 2019-06-27 17:35 | Andy Clements | labels |  | Software
| 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-826 | 2019-06-27 17:36 | Andy Clements | labels |  | Software
| 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-827 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
| 2019-07-18 05:29 | Victor Krabbendam | Handling Approach | Mitigate | Accept
|  |  | Proposed Management Response | 0 | Manage early occupancy, delayed decommissioning of old data center.
|  |  | resolution | 0 | Done
|  |  | status | Active Risk/Opportunity | Realized
RM-829 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-830 | 2019-06-27 17:37 | Andy Clements | labels |  | Software
| 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-831 | 2019-06-27 17:37 | Andy Clements | labels |  | Software
| 2019-06-27 21:58 | Austin Roberts | resolution | 0 | Done
|  |  | status | Active Risk/Opportunity | Realized
RM-832 | 2019-06-27 17:38 | Andy Clements | labels |  | Software
| 2019-07-02 21:43 | Austin Roberts | Current Probability of Occurrence | 5%-10% | 0%-5%
| 2019-07-02 21:44 | Austin Roberts | Current Probability of Occurrence | 0%-5% | 5%-10%
| 2019-07-02 21:45 | Austin Roberts | Obligation Date | 1/Dec/19 | 1/Apr/20
| 2019-07-03 16:09 | Austin Roberts | Is Parent Risk | 0 | False
RM-833 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
| 2019-07-18 04:13 | Victor Krabbendam | Obligation Date | 1/Jul/19 | 1/Dec/20
|  |  | assignee | William Gressler | Jeff Barr
RM-834 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
| 2019-07-22 20:15 | Victor Krabbendam | Handling Approach | Mitigate
|  |  | resolution | 0 | Done
|  |  | status | Active Risk/Opportunity | Retired
RM-835 | 2019-06-27 17:39 | Andy Clements | labels |  | Software
| 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-836 | 2019-06-27 17:40 | Andy Clements | labels |  | Software
| 2019-07-02 22:18 | Austin Roberts | Link | 0 | This issue is child task of RM-1939
| 2019-07-02 22:32 | Victor Krabbendam | Random risk/opportunities may occur during | Commissioning only | Both Construction and Commissioning
| 2019-07-02 22:33 | Victor Krabbendam | Last Reviewed (Deprecated) | 23/Oct/18 12:00 AM | 02/Jul/19 10:32 PM
|  |  | status | Active Risk/Opportunity | Active Risk/Opportunity
| 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-837 | 2019-06-27 17:40 | Andy Clements | labels |  | Software
| 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-838 | 2019-06-27 17:41 | Andy Clements | labels |  | Software
| 2019-07-02 22:18 | Austin Roberts | Link | 0 | This issue is child task of RM-1939
| 2019-07-02 22:20 | Victor Krabbendam | Last Reviewed (Deprecated) | 23/Oct/18 12:00 AM | 02/Jul/19 10:20 PM
|  |  | status | Active Risk/Opportunity | Active Risk/Opportunity
| 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-839 | 2019-06-27 17:42 | Andy Clements | labels |  | Software
| 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-840 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
| 2019-07-18 04:08 | Victor Krabbendam | General Notebook 1 | Labor is Chile will be dependent largely on mining conditions and economic outlook. Risk due to TMA erection is mitigated via new scope in fixed price contract. Risk due to dome erection is to be mitigated via scope request in bid solicitation. Reduced risk Oct 2014 as dome bid includes installation. July 2016 update: reduced cost risk to $500k ($1M) Jan 2017 update: reduced cost risk to $350k Oct 2017: move trigger to Oct 2018 | Labor is Chile will be dependent largely on mining conditions and economic outlook. Risk due to TMA erection is mitigated via new scope in fixed price contract. Risk due to dome erection is to be mitigated via scope request in bid solicitation. Reduced risk Oct 2014 as dome bid includes installation. July 2016 update: reduced cost risk to $500k ($1M) Jan 2017 update: reduced cost risk to $350k Oct 2017: move trigger to Oct 2018 July 2019: move trigger date to end of dome work - Jan 2020
|  |  | Obligation Date | 1/Sep/19 | 31/Jan/20
|  |  | assignee | William Gressler | Jeff Barr
RM-841 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-843 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-844 | 2019-06-27 17:44 | Andy Clements | labels |  | Software
| 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
| 2019-07-22 20:04 | Victor Krabbendam | Link | 0 | This issue is mitigated by RM-1941
RM-845 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-846 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-847 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-848 | 2019-06-27 17:46 | Andy Clements | labels |  | Software
| 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-849 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-85 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-850 | 2019-06-27 17:47 | Andy Clements | labels |  | Software
| 2019-07-02 21:38 | Austin Roberts | Expected (months) | 4 | 2
|  |  | FTE's required | 5 | 3
|  |  | Is Parent Risk | 0 | False
RM-851 | 2019-07-02 22:26 | Austin Roberts | resolution | 0 | Done
|  |  | status | Active Risk/Opportunity | Retired
RM-853 | 2019-06-27 17:47 | Andy Clements | labels |  | Software
| 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-854 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-855 | 2019-07-02 21:35 | Austin Roberts | Last Reviewed (Deprecated) | 07/Feb/19 3:14 AM | 02/Jul/19 2:34 PM
|  |  | status | Active Risk/Opportunity | Active Risk/Opportunity
| 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-857 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-858 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-859 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
| 2019-07-18 20:23 | Victor Krabbendam | Obligation Date | 1/Jan/20 | 1/Jan/21
RM-860 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
| 2019-07-18 20:25 | Victor Krabbendam | summary | M1M3 Mirror Cell Cart Hydraulic Lift overtravels and overloads telescope &amp; cell Interface | M1M3 Mirror Cell Cart Hydraulic Lift overtravels and overloads telescope and cell Interface
RM-861 | 2019-06-27 17:49 | Andy Clements | labels |  | Software
| 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-862 | 2019-06-27 17:50 | Andy Clements | labels |  | Software
| 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-863 | 2019-06-27 17:50 | Andy Clements | labels |  | Software
| 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-864 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-866 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
| 2019-07-18 05:19 | Victor Krabbendam | Link | 0 | This issue is mitigated by RM-1940
RM-867 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-868 | 2019-06-27 17:51 | Andy Clements | labels |  | Software
| 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-869 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-870 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-871 | 2019-06-27 17:52 | Andy Clements | labels |  | Software
| 2019-06-27 17:53 | Andy Clements | labels | Software
| 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
| 2019-07-18 05:05 | Victor Krabbendam | General Notebook 1 | The Calypso telescope will be removed from Kitt Peak and refurbished. Update Sept 2014. Calypso hardware successfully removed to NOAO for upgrade. Vendor ACE under contract to provide refurbishment - fixed price effort. | The Calypso telescope will be removed from Kitt Peak and refurbished. Update Sept 2014. Calypso hardware successfully removed to NOAO for upgrade. Vendor ACE under contract to provide refurbishment - fixed price effort. System is on site, assembled and under computer control. Risk trigger date set for Eng. first light.
|  |  | Obligation Date | 1/Mar/19 | 31/Jul/19
RM-872 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-873 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-874 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-876 | 2019-06-27 17:54 | Andy Clements | labels |  | Software
| 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-877 | 2019-06-27 17:54 | Andy Clements | labels |  | Software
| 2019-07-02 22:17 | Austin Roberts | Link | 0 | This issue is child task of RM-1939
| 2019-07-02 22:42 | Victor Krabbendam | assignee | William Gressler | Dave Mills
| 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-878 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
| 2019-07-18 20:42 | Victor Krabbendam | Random occurrences | 10 | 4
|  |  | assignee | William Gressler | Jeff Barr
RM-879 | 2019-06-27 18:00 | Andy Clements | labels |  | Software
| 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-881 | 2019-06-27 18:00 | Andy Clements | labels |  | Software
| 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-883 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-884 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-885 | 2019-06-27 18:03 | Andy Clements | labels |  | Software
| 2019-07-02 21:51 | Austin Roberts | Expected (months) | 6 | 3
|  |  | Expected Dollars (K$) | 500 | 250
|  |  | Is Parent Risk | 0 | False
RM-886 | 2019-06-28 22:02 | Austin Roberts | Link | 0 | This issue is child task of RM-888
| 2019-06-28 22:02 | Austin Roberts | Link | This issue is child task of RM-888 | 0
| 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
| 2019-07-18 15:03 | Victor Krabbendam | General Notebook 1 | The project originally established 13 months of schedule contingency for the project to address schedule risk. This schedule is unfunded in the baseline so any work that extends into that period will need to be funded from either the existing baseline budget or from contingency. | The project originally established 13 months of schedule contingency for the project to address schedule risk. This schedule is unfunded in the baseline so any work that extends into that period will need to be funded from either the existing baseline budget or from contingency. As of July 2019 the Project is now down to 3.5 months of unfunded schedule. The three most significant subsystems that jeopardize the schedule are the TMA, Dome, and Camera. Each has its own risk so this risk captures the project-wide impact.
| 2019-07-18 15:05 | Victor Krabbendam | Expected Dollars (K$) | 1500 | 500
|  |  | FTE's required | 75 | 65
RM-887 | 2019-07-02 23:00 | Victor Krabbendam | Current Probability of Occurrence | 50%-75% | 10%-25%
|  |  | Expected Dollars (K$) | 2000 | 1000
|  |  | Is Parent Risk | 0 | False
RM-888 | 2019-06-28 22:02 | Austin Roberts | Link | 0 | This issue is parent task of RM-886
| 2019-06-28 22:02 | Austin Roberts | Link | This issue is parent task of RM-886 | 0
| 2019-07-02 23:11 | Victor Krabbendam | Current Probability of Occurrence | 50%-75% | 25%-50%
| 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-889 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-890 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-891 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-892 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-893 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-894 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-895 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-896 | 2019-07-03 16:17 | Austin Roberts | Is Parent Risk | 0 | False
RM-897 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-898 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False
RM-899 | 2019-07-03 16:18 | Austin Roberts | Is Parent Risk | 0 | False

## Fig. 1 Running Graph
Date | PMO | DM | T&S | EPO | SE | Total | Top 50
2014-05-16 | 4142 | 14005 | 13925 | 1056 | 4120 | 37248
2014-08-06 | 5669 | 14273 | 13925 | 1056 | 4602 | 39525
2014-08-07 | 6372 | 14273 | 13925 | 1056 | 4894 | 40520
2015-02-24 | 6372 | 14273 | 14142 | 1056 | 7593 | 43436
2015-03-31 | 6372 | 14643 | 14223 | 1056 | 7116 | 43410
2015-04-28 | 6372 | 14799 | 14211 | 1056 | 7116 | 43554
2015-05-26 | 5877.23 | 14799.12 | 14438 | 1055.7 | 7116.1 | 43286.15
2015-06-30 | 5877.23 | 14799.12 | 14438 | 1055.7 | 7116.1 | 43286.15
2015-07-28 | 5877.23 | 14799.12 | 14438 | 1055.7 | 7375.3 | 43545.35
2015-08-25 | 5877.23 | 14799.12 | 14438 | 1055.7 | 7664.2 | 43834.25
2015-09-29 | 5877.23 | 14164.22 | 14438 | 1055.7 | 7664.2 | 43199.35
2015-10-27 | 6700.53 | 14083.37 | 16195.7 | 1085.7 | 7664.2 | 45729.5
2015-11-24 | 6700.53 | 14746.23 | 16191.3 | 1085.7 | 7444.2 | 46167.96
2015-12-29 | 6700.53 | 17409.23 | 16416.3 | 1085.7 | 7634.2 | 49245.96
2016-01-20 | 6701 | 17409 | 16031 | 1086 | 7332 | 48559
2016-02-05 | 5801 | 17409 | 16031 | 1054.9 | 7334.2 | 47630.1
2016-02-29 | 5801 | 17409 | 16031 | 1054.9 | 7334.2 | 47630.1
2016-03-31 | 5801 | 17409 | 16031 | 1055 | 7284 | 47580
2016-04-26 | 5801 | 17409 | 16031 | 1055 | 7284 | 47580
2016-06-01 | 5801 | 17563.98 | 14616.98 | 1055 | 7277.75 | 46314.71
2016-06-06 | 5801 | 17564 | 14971 | 1055 | 7278 | 46669
2016-07-20 | 5442 | 17670 | 15130 | 1149 | 6747 | 46138
2016-10-07 | 5850 | 17670 | 15130 | 1233 | 7250 | 47133
2016-10-31 | 5850 | 17670 | 13642 | 894 | 7250 | 45306
2016-11-29 | 5850 | 22829 | 14790 | 1017 | 7339 | 51825
2017-01-06 | 6180.75 | 22829 | 14790 | 1017 | 8825.95 | 53642.7
2017-01-31 | 6180.75 | 22829 | 14366.33 | 933.77 | 8825.95 | 53135.8
2017-02-28 | 6180.75 | 22602.28 | 14662.33 | 933.77 | 8729.75 | 53108.88
2017-04-27 | 6180.75 | 22602.28 | 13633.4 | 875.97 | 8729.75 | 52022.15
2017-06-05 | 6180.75 | 12003.9 | 12801.8 | 875.97 | 9889.85 | 41752.27
2017-08-11 | 7601 | 12003.9 | 12050 | 1046 | 11819 | 44519.9
2017-10-09 | 7601 | 12000 | 11985 | 1014 | 11832 | 44432
2017-12-30 | 7601 | 11782 | 12726 | 747 | 12947 | 45803
2018-02-28 | 7601 | 11923 | 12726 | 701 | 12947 | 45898
2018-03-29 | 7601 | 12866 | 12942 | 1259 | 13586 | 48254
2018-05-07 | 9616 | 12866 | 12942 | 1182 | 13586 | 50192
2018-05-08 | 9616 | 12866 | 12942 | 1182 | 9210 | 45816 | 37052
2018-05-18 | 9616 | 12866 | 10977 | 1099 | 9210 | 43768 | 37052
2018-07-27 | 8935 | 12866 | 10977 | 1099 | 9210 | 43087 | 35160
2018-11-01 | 8683 | 11920 | 8599 | 1047 | 9210 | 39459 | 32000
2018-12-01 | 8683 | 11920 | 8598 | 1047 | 9162 | 39410 | 32000
2018-12-21 | 8683 | 11920 | 8598 | 1047 | 9162 | 39410 | 32000

## All Active Risks
JIRA ID | Labor Cost | Labor PWE ($K) | Model | Non-labor PWE ($K) | Nonlabor Cost | Probability | Probability Weighted Exposure ($K) | Proposed Management Response | Random Period | Review Date | Status | Subsystem | Summary | Trigger Date | WBS | description | issue_type | mean_probability | score
RM-881 | 120 | 3 | Trigger date | 2.5 | 100 | 0%-5% | 5.5 | Ash dome arrived in Chile (April 2017) and will be assembled onto auxiliary telescope pier in May/June 2017. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Telescope & Site | Calibration atmospheric telescope dome does not meet automation requirements | 2019-03-01 | 4.8 | IF the calibration atmospheric dome does not meet the autonomous performance requirements, THEN the dome design must be improved to ensure automated usage. | RM-Risk | 0.025 | 1
RM-817 | 0 | 0 | Trigger date | 0 | 0 | 25%-50% | 169.2 | Working with vendor to develop logistics plan to minimize schedule risks in shipping. Oversight during the next few months as work focuses on factory integration to support testing campaign. Aug 2017: TMA is now 2 months late, with shipment in July 2018. Jan 2019: TMA is now scheduled to depart Spain in May 2019. Working with Dome and SE to improve parallel work flow. |  | 2019-07-25 21:33 | Active Risk/Opportunity | Telescope & Site | Mount Late Delivery | 2019-05-01 | 4.5 | If the Telescope Mount Assembly is delivered late, THEN overall schedule is impacted | RM-Risk | 0.37 | 0
RM-814 | 0 | 0 | Trigger date | 0 | 0 | 25%-50% | 178.5 | Dome vendor has maintained schedule as of September 2016. The dome vendor is now committed to working through the winter months rather than stop work completely in an attempt to minimize schedule. Embedded plate alignment is much longer than planned...final completion is now OCt 2018, which will interfere with TMA installation. Jan 2019 Update: working to support enclosed dome by May 2019, but need additional contingency funds to support new schedule and cash flow issues. |  | 2019-07-25 21:33 | Active Risk/Opportunity | Telescope & Site | Dome Late Delivery | 2019-05-01 | 4.4 | IF the Dome is delivered late, THEN overall schedule is impacted. | RM-Risk | 0.37 | 0
RM-869 | 600 | 15 | Trigger date | 2.5 | 100 | 0%-5% | 17.5 | TMA pier completed by summit vendor and meets requirements. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Telescope & Site | Telescope mount pier interfaces must be modified | 2019-06-01 | 4.5 | IF the interfaces designed into the telescope mount design prove to not be sufficient to the pier, THEN a contract modification will be required. | RM-Risk | 0.025 | 2
RM-821 | 160 | 59.2 | Trigger date | 92.5 | 250 | 25%-50% | 151.7 | Continue to work to coordinate activities. EIE is now in Chile (April 2017) and has begun to focus on dome integration. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Telescope & Site | Summit Integration of dome, mount and telescope causes project delays | 2019-06-01 | 4.1 | IF the summit integration between the three major components of dome, mount and telescope is late, THEN project schedule delays will increase. | RM-Risk | 0.37 | 4
RM-846 | 400 | 10 | Trigger date | 5 | 200 | 0%-5% | 15 | Final change proposal costs for detailed relocation of compressors and utility line layout coming in mid-2017. |  | 2019-07-03 16:18 | Active Risk/Opportunity | Telescope & Site | Telescope mount interfaces to camera must be modified | 2019-07-01 | 4.5 | IF the interfaces designed into the telescope mount design prove to not be sufficient to the camera, THEN a redesign and contract modification will be required. | RM-Risk | 0.025 | 2
RM-841 | 0 | 0 | Distributed occurrence | 56.25 | 750 | 5%-10% | 56.25 |  |  | 2019-07-03 16:17 | Active Risk/Opportunity | Telescope & Site | Estimate uncertainty on remaining budget procurements | 2019-07-01 | 4.1 | IF there is uncertainty in the basis of estimates used for budgetary planning, THEN there is a risk the remaining budgeted items will have cost variances. | RM-Risk | 0.075 | 4
RM-871 | 120 | 9 | Trigger date | 7.5 | 100 | 5%-10% | 16.5 |  |  | 2019-07-19 05:05 | Active Risk/Opportunity | Telescope & Site | Calibration atmospheric telescope refurbishment does not meet performance requirements | 2019-07-31 | 4.8 | IF the atmospheric telescope refurbishment is not sufficient to meet the performance requirements, THEN additional design improvements must be included. | RM-Risk | 0.075 | 2
RM-733 | 2400 | 888 | Trigger date | 0 | 0 | 25%-50% | 888 |  |  | 2019-07-03 16:18 | Active Risk/Opportunity | Systems Engineering | Discontinuity between subsystem I&T and Commissioning staffing levels | 2019-07-31 | 06C.02 | IF staffing levels between subsystems I&amp;T needs exceeds what is planned for Commissioning THEN key technical skills needed by commissioning activities may leave the project prematurely, causing delays in or incomplete commissioning activities. | RM-Risk | 0.37 | 0
RM-1878 | 0 | 0 | Trigger date | 185 | 500 | 25%-50% | 185 | LSST and EIE will work to determine the status of the dome bogie drive system and necessary adjustments as additional steel loads are added the bogie trucks. | Both Construction and Commissioning | 2019-07-03 16:17 | Active Risk/Opportunity | Telescope & Site | Dome Maintenance Required before final acceptance | 2019-08-01 | 04C.04 | If the Dome's exposed metallic surfaces are not treated, cleaned or protected, then the performance and reliability will be notably degraded. The ring and motor mounting surfaces and hardware are currently experiencing excessive corrosion. This is a challenge since the Dome materials technically still belong to the contractor. However, if an arrangement can not be made to allow Maintenance, then the degradation should be formally analyzed and used as criteria during the acceptance event. | RM-Risk | 0.37 | 4
RM-815 | 1800 | 666 | Trigger date | 185 | 500 | 25%-50% | 851 | The CAMs have been working to update planning packages for work activity which falls &quot;between&quot; subsystems. Budgeted and non-budgeted items have been entered into PMCS and will request funding where needed. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Telescope & Site | Telescope and Site Integration activities underestimated | 2019-08-01 | 4.14 | If the detailed planning of the Telescope and Site integration plan uncovers new scope, THEN the cost and/or schedule of the work package will increase. | RM-Risk | 0.37 | 12
RM-697 | 360 | 61.2 | Distributed occurrence | 0 | 0 | 10%-25% | 61.2 | Proposed response: Improve template generation algorithms. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | Creation of difference imaging templates difficult due to DCR | 2019-08-01 | 02C.03.04 | IF the template generation algorithms cannot sufficiently account for differential chromatic refraction THEN difference images will have artifacts and false or inaccurate alerts will result | RM-Risk | 0.17 | 0
RM-808 | 480 | 177.6 | Distributed occurrence | 0 | 0 | 25%-50% | 177.6 | Increase staffing, collaborate with DM, de-scope planned activities, and look at alternate technology. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Education and Public Outreach | EPO software development effort underestimated | 2019-09-01 | 5 | IF software development takes longer than expected for planned deliverables THEN schedule delays will occur or some deliverables may not be completed. Software. | RM-Risk | 0.37 | 0
RM-1936 | 900 | 153 | Trigger date | 0 | 0 | 10%-25% | 153 |  |  | 2019-07-02 21:03 | Active Risk/Opportunity | Telescope & Site | TMA Shipping Late | 2019-09-30 | 04C.05.02.04 | IF the TMA doe not reach the summit as scheduled THEN the project critical path will be impacted. | RM-Risk | 0.17 | 0
RM-813 | 0 | 0 | Trigger date | 37.5 | 500 | 5%-10% | 37.5 | Developed plan to reduce amount of computing and storage equipment required at Base Data Center, based on relying more on services at LSST Data Facility accessed over high speed network. Residual risk is now based on lower total cost of computing and storage equipment. Liklihood will remain as is until Base Data Center initial configuration in FY19. | Construction only | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | Insufficiently reliable network infrastructure at Base Center | 2019-09-30 | 02C.08.01 | IF the Base Center network infrastructure is insufficiently reliable THEN the transfer of raw and crosstalk corrected images to the Archive Center will be reduced, delaying or preventing the release of data products | RM-Risk | 0.075 | 2
RM-726 | 0 | 0 | Trigger date | 472.5 | 750 | 50%-75% | 472.5 | Focus on a higher performance coating for M2 |  | 2019-07-03 16:18 | Active Risk/Opportunity | Systems Engineering | Camera Refrigeration System Maintainability | 2019-09-30 | 06C.01.01 | IF the refrigeration system does not meet the camera scheduled and/or unscheduled downtime requirements, THEN the observatory operations plan will be impacted. | RM-Risk | 0.63 | 10
RM-746 | 180 | 13.5 | Trigger date | 0 | 0 | 5%-10% | 13.5 | Conduct analysis to understand root causes. Update DM pipeline processing to take out effects. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Systems Engineering | System Level Performance Impacts of Compounding Component Optical Defects | 2019-09-30 | 1.06C.01 | IF the individual optical element defects have compounding effects at the optical system level, THEN overall system optical performance requirements may not be achieved. | RM-Risk | 0.075 | 0
RM-824 | 180 | 30.6 | Distributed occurrence | 85 | 500 | 10%-25% | 115.6 | Focused on internal labor pool assignments and detailed identification of work between hardware and software teams. New job postings out...waiting for qualified candidates. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Telescope & Site | Staffing plan does not support the Telescope and Site work and scope schedule | 2019-10-01 | 4.1 | If the staffing plan does not support the current work scope and schedule, THEN Telescope deliverables will be delayed. | RM-Risk | 0.17 | 6
RM-826 | 320 | 24 | Trigger date | 22.5 | 300 | 5%-10% | 46.5 |  |  | 2019-07-03 16:17 | Active Risk/Opportunity | Telescope & Site | Dome dynamic performance below specifications | 2019-10-01 | 4.4 | IF dome can not reliably achieve acceleration and speed performance necessitated by the cadence of the survey, THEN cadence of the survey will not be achieved. | RM-Risk | 0.075 | 4
RM-819 | 0 | 0 | Trigger date | 51 | 300 | 10%-25% | 51 | No new FTE labor support is required as AURA/Chile does have resources to support logistics issues into Chile. The T&amp;S original labor pool budgeted a separate &quot;logistics coordinator&quot; role. This responsibility has been assumed by current labor support and the available AURA/Chile group. New hire identified and offer being made in early May 2017. Working with TMA and coating plant vendors to solicit bids to provide more shipping scope. |  | 2019-07-18 20:55 | Active Risk/Opportunity | Telescope & Site | Telescope and Site shipping and logistics scope and budget | 2019-10-01 | 4.12 | IF the shipping and logistics requirements for the Telescope and Site subsystems are more complicated than planned THEN additional budget and time allocation may be necessary. | RM-Risk | 0.17 | 3
RM-845 | 80 | 2 | Distributed occurrence | 5 | 200 | 0%-5% | 7 |  |  | 2019-07-03 16:17 | Active Risk/Opportunity | Telescope & Site | Damage to components from rough crane movements | 2019-10-01 | 4.12 | IF crane movements create excessive jerking or rough motion, THEN damage to telescope components may occur. | RM-Risk | 0.025 | 1
RM-848 | 240 | 18 | Trigger date | 22.5 | 300 | 5%-10% | 40.5 |  |  | 2019-07-03 16:17 | Active Risk/Opportunity | Telescope & Site | Dome Flushing Performance below specifications | 2019-11-01 | 4.4 | IF dome fails to provide effective flushing (rate of air-changes) in on-site conditions to the extent that seeing performance of telescope would be compromised, THEN observatory seeing allocation in image quality error budget will not be met. | RM-Risk | 0.075 | 4
RM-849 | 240 | 18 | Trigger date | 21 | 280 | 5%-10% | 39 |  |  | 2019-07-03 16:18 | Active Risk/Opportunity | Telescope & Site | Dome Seal performance below specifications | 2019-11-01 | 4.4 | IF there is a failure of the Dome weather seals, THEN the seal design will need to be changed. | RM-Risk | 0.075 | 4
RM-731 | 80 | 0.4 | Trigger date | 2.5 | 500 | 0%-1% | 2.9 |  |  | 2019-07-03 16:17 | Active Risk/Opportunity | Systems Engineering | Infrastructure Interface between Base Facility and Camera Inadequately defined | 2019-11-01 | 06C.02.02.02 | IF the infrastructure interface between the Base Facility and the Camera subsystem is not adequately defined, THEN the camera team may not have adequate space and utilities to support their needs during commissioning and operations. | RM-Risk | 0.005 | 0
RM-820 | 80 | 13.6 | Trigger date | 8.5 | 50 | 10%-25% | 22.1 | Add additional resources required to avoid slipping AIV and Commissioning. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Telescope & Site | AOS Software Late Delivery | 2019-12-01 | 4.11 | IF the AOS software is delivered late, THEN it will impact T&S AIV completion and Commissioning. | RM-Risk | 0.17 | 3
RM-884 | 3600 | 18 | Trigger date | 1 | 200 | 0%-1% | 19 |  |  | 2019-07-03 16:17 | Active Risk/Opportunity | Telescope & Site | M1M3 mirror damage during summit integration requiring repair | 2019-12-01 | 4.14 | IF the M1M3 is damaged during telescope integration on summit, THEN the mirror must be repaired on site. | RM-Risk | 0.005 | 0
RM-876 | 320 | 8 | Distributed occurrence | 2.5 | 100 | 0%-5% | 10.5 | Detailed T&amp;S and camera technical meetings have advanced the maturity of the camera cable wrap design (April 2017). | Both Construction and Commissioning | 2019-07-03 16:18 | Active Risk/Opportunity | Telescope & Site | Mount Camera Cable Wrap insufficient | 2019-12-01 | 4.2 | IF Telescope camera Cable wrap becomes insufficient due to increase/ change of camera utilities, THEN modifications will have to be implemented with cost and schedule impact. | RM-Risk | 0.025 | 1
RM-718 | 180 | 4.5 | Distributed occurrence | 0 | 0 | 0%-5% | 4.5 | Proposed response: Redesign provenance. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | Provenance capture inadequate | 2019-12-01 | 02C.06 | IF provenance capture is incomplete or unreliable THEN it will not be possible to recreate data products on demand from precursor products, compromising the ability to deliver some data products to users | RM-Risk | 0.025 | 0
RM-822 | 200 | 15 | Trigger date | 18.75 | 250 | 5%-10% | 33.75 | T&amp;S management will need to maintain close connection to the M1M3 assembly team and provide coordinated support to maintain the aggressive schedule. Additional coordination with CAID and the University of Arizona will be required. |  | 2019-07-19 04:03 | Active Risk/Opportunity | Telescope & Site | M1M3 cell assembly integration work falls behind schedule | 2019-12-31 | 4.6.4 | IF the M1M3 integration and test activities take longer than planned, THEN the critical path of the project increases | RM-Risk | 0.075 | 2
RM-868 | 120 | 3 | Trigger date | 2.5 | 100 | 0%-5% | 5.5 | Components fabricated and being assembled at LSST office for testing in May 2017. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Telescope & Site | M1M3 Hard Point performances below specifications | 2020-01-01 | 4.6.3 | IF the M1M3 hardpoint performances are below specifications, THEN M1M3 mirror may take longer to reach its position. | RM-Risk | 0.025 | 1
RM-866 | 240 | 6 | Trigger date | 1.25 | 50 | 0%-5% | 7.25 |  |  | 2019-07-19 05:19 | Active Risk/Opportunity | Telescope & Site | M1M3 mirror damage during transport between support building &amp; telescope | 2020-01-01 | 4.12 | IF the rail surfaces are uneven between telescope and coating chamber, THEN there is risk of damage to mirror. | RM-Risk | 0.025 | 1
RM-885 | 240 | 18 | Trigger date | 18.75 | 250 | 5%-10% | 36.75 | Focus on test procedures to validate performance quickly. |  | 2019-07-02 21:51 | Active Risk/Opportunity | Telescope & Site | Mount dynamic performances below specifications on summit | 2020-01-01 | 4.5 | IF mount can not reach acceleration and speed needed to maintain the cadence of the survey, THEN the cadence of the survey will not be achieved. | RM-Risk | 0.075 | 2
RM-757 | 180 | 13.5 | Distributed occurrence | 77.25 | 1030 | 5%-10% | 90.75 | Proposed response: Partition systems (with resulting inefficiency). Use (less efficient) distributed archive systems instead of filesystems. Reduce pre-operations data production. Evaluate retained data model. | Construction only | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | Filesystems fail to scale adequately | 2020-01-01 | 02C.07.09 | IF filesystems fail to scale to the billions of files needed for LSST DM, THEN production delivery requirements and end-user data access requirements will not be met. | RM-Risk | 0.075 | 6
RM-839 | 180 | 13.5 | Trigger date | 18.75 | 250 | 5%-10% | 32.25 | Detailed simulations validate M1M3 design - full testing to begin in May 2017. The additional flow valves have been included in the mirror support designs. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Telescope & Site | M1M3 Axial support bandwidth low | 2020-01-01 | 4.6.3 | IF M1M3 support response time is too slow to accommodate dynamic loading, THEN the slew and settle requirements may not be met. | RM-Risk | 0.075 | 2
RM-847 | 320 | 24 | Trigger date | 18.75 | 250 | 5%-10% | 42.75 |  |  | 2019-07-03 16:17 | Active Risk/Opportunity | Telescope & Site | M1M3 overstress due to Coating Chamber Differential Pumping | 2020-01-01 | 4.9 | IF there is a pumping differential between the upper chamber and mirror cell, THEN the M1M3 mirror may be overstressed. | RM-Risk | 0.075 | 4
RM-853 | 400 | 10 | Trigger date | 1.875 | 75 | 0%-5% | 11.88 |  |  | 2019-07-03 16:17 | Active Risk/Opportunity | Telescope & Site | M1M3 or M2 surface error found during summit integration due to poor AOS control | 2020-01-01 | 4.14 | IF M1M3 or M2 surface errors are higher than expected during initial alignment due to poor AOS control, THEN it will take longer to properly align the optical system. | RM-Risk | 0.025 | 1
RM-857 | 40 | 1 | Trigger date | 10 | 400 | 0%-5% | 11 |  |  | 2019-07-03 16:18 | Active Risk/Opportunity | Telescope & Site | Vacuum Seal between M1M3 Cell and Mirror fails during coating | 2020-01-01 | 4.9 | IF Seal between M1M3 Cell and Mirror fails, THEN risk of contamination of the coating that will reduce the performance and adhesion of the coating. | RM-Risk | 0.025 | 1
RM-862 | 120 | 3 | Trigger date | 6.25 | 250 | 0%-5% | 9.25 |  |  | 2019-07-03 16:18 | Active Risk/Opportunity | Telescope & Site | Calibration process for u-band performs below specifications | 2020-01-01 | 4.8 | IF the u-band calibration system flux is too low, THEN the calibration plan will not meet the time allocation. | RM-Risk | 0.025 | 1
RM-829 | 3600 | 18 | Trigger date | 1 | 200 | 0%-1% | 19 | Harris has successfully pull tested all mirror pads and integrated the optic into the cell assembly. |  | 2019-07-03 16:18 | Active Risk/Opportunity | Telescope & Site | M2 mirror damage during summit integration requiring repair | 2020-01-01 | 4.12 | IF damage occurs to M2 during summit integration, THEN repair to damages will be required. | RM-Risk | 0.005 | 0
RM-816 | 900 | 153 | Trigger date | 85 | 500 | 10%-25% | 238 | The dome vendor and building contractor are both subject to this risk. EIE is mitigating by scheduling work throughout the winter period and Besalco is focused on enclosing the facility. |  | 2019-07-18 15:45 | Active Risk/Opportunity | Telescope & Site | Weather impact on construction schedule | 2020-01-30 | 4.1 | IF work prohibitive winter weather occurs, THEN it may cause some cost / schedule risk in summit construction. | RM-Risk | 0.17 | 9
RM-840 | 0 | 0 | Trigger date | 26.25 | 350 | 5%-10% | 26.25 |  |  | 2019-07-19 04:08 | Active Risk/Opportunity | Telescope & Site | Steel and erection crew require premium cost | 2020-01-31 | 4.1 | IF hiring steel and erection crew is difficult due to labor shortage (mining), THEN cost for crew will be a premium | RM-Risk | 0.075 | 2
RM-877 | 240 | 6 | Trigger date | 4 | 160 | 0%-5% | 10 | Version 3.5 of DDS is providing stable communications to vendors to date and is being updated as/if bugs arise. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Telescope & Site | Availability of OCS Communications Middleware | 2020-02-01 | 4.1 | IF the OCS communications middleware is not standardized, THEN there may be communications problems with other subsystems and schedule delay. | RM-Risk | 0.025 | 1
RM-830 | 480 | 81.6 | Trigger date | 85 | 500 | 10%-25% | 166.6 | Working with AURA procurement to expedite the purchasing process, especially in Chile. | Both Construction and Commissioning | 2019-07-03 16:17 | Active Risk/Opportunity | Telescope & Site | Contractor default | 2020-02-07 | 4.1 | IF construction contractor insolvency happens, THEN severe cost and schedule impact is possible. | RM-Risk | 0.17 | 6
RM-1938 | 1800 | 666 | Trigger date | 370 | 1000 | 25%-50% | 1036 | LSST will continue to support Dome integration activities. |  | 2019-07-02 21:19 | Active Risk/Opportunity | Telescope & Site | Dome Integration Late | 2020-02-14 | 04C.04.02.05 | IF the Dome integration does not complete as scheduled THEN some critical path activities will be impacted. | RM-Risk | 0.37 | 12
RM-765 | 180 | 13.5 | Distributed occurrence | 0 | 0 | 5%-10% | 13.5 | Proposed response: Improve tools. Add resources for incident response, proactive mitigation, and problem management. Relax system availability requirements (unlikely). Accept operational delays |  | 2019-07-03 16:18 | Active Risk/Opportunity | Data Management | System and service monitoring tools inadequate | 2020-03-01 | 02C.07.06 | IF the tools used to monitor the operation of the Data Management System are inadequate THEN there will be delay in recognizing and responding to operational problems | RM-Risk | 0.075 | 0
RM-742 | 900 | 67.5 | Trigger date | 15 | 200 | 5%-10% | 82.5 |  |  | 2019-07-03 16:17 | Active Risk/Opportunity | Systems Engineering | Common Project-Wide IT Design | 2020-03-01 | 06C04 | IF adequate resources are not assigned to develop a comprehensive project-wide design for IT, THEN the project may have an inadequate IT system for operations OR unplanned resources will have to be expended late in the project to compensate. | RM-Risk | 0.075 | 6
RM-760 | 240 | 18 | Trigger date | 0 | 0 | 5%-10% | 18 | Proposed response: Add resources to other subsystems. Accelerate development after delivery of component. |  | 2019-07-03 16:18 | Active Risk/Opportunity | Data Management | Late appearance of deliverables from other subsystems | 2020-03-01 | 02C.07.06 | IF deliverables on which DM depends from other LSST subsystems (e.g., the SDS client from CAM or the EFD interface from OCS) are late and consequent DM development cannot start THEN incompatibilities may not be discovered in time and milestones may be delayed | RM-Risk | 0.075 | 0
RM-758 | 180 | 13.5 | Distributed occurrence | 0 | 0 | 5%-10% | 13.5 | Proposed response: Test early and test often looking at corner cases. Test bug fixes and other integration type of activities. Devote additional resources to debugging and integration. More robust change management process for deploying software changes into production. | Both Construction and Commissioning | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | Ease of deployment | 2020-03-01 | 02C.07.06 | IF new releases are difficult to construct or deploy into production because of software problems THEN bug fixes and needed functionality may not be available in a timely way, leading to delays in integration or collection of substandard data | RM-Risk | 0.075 | 0
RM-755 | 120 | 0.6 | Trigger date | 7.725 | 1545 | 0%-1% | 8.32 | Proposed response: Purchase higher-quality hardware. Purchase more spares. Reduce complexity of algorithms. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | Insufficiently reliable computing infrastructure | 2020-03-01 | 02C.07.09 | IF the Archive Center computing infrastructure is insufficiently reliable THEN the throughput of data through commissioning, data release production, and other processing campaigns will be reduced, delaying the availability of data products for verification and validation of the instruments and science pipelines, and for early data previews | RM-Risk | 0.005 | 0
RM-763 | 600 | 45 | Trigger date | 0 | 0 | 5%-10% | 45 | Proposed response: Devote additional resources to debugging and integration. |  | 2019-07-03 16:18 | Active Risk/Opportunity | Data Management | Unexpected DM component incompatibilities discovered during integration | 2020-03-01 | 02C.07.06 | IF unexpected incompatibilities between DM system components are encountered during integration THEN services will not be ready to support production use cases | RM-Risk | 0.075 | 0
RM-720 | 180 | 13.5 | Distributed occurrence | 0 | 0 | 5%-10% | 13.5 | Proposed response: Redesign and reimplement application framework. |  | 2019-07-03 16:18 | Active Risk/Opportunity | Data Management | Software framework insufficiently extensible to support addition/removal of algorithms | 2020-03-01 | 02C.03.05, 02C.04.01 | IF the application framework cannot sufficiently support the addition/removal of algorithms THEN experimentation with new algorithms during Construction, Commissioning, and Operations will be slowed and scientific performance will be reduced, and Level 3 to Level 2 migration costs increased | RM-Risk | 0.075 | 0
RM-719 | 180 | 13.5 | Distributed occurrence | 0 | 0 | 5%-10% | 13.5 | Proposed response: Improve file access services. Re-architect software. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | File data access patterns for production change | 2020-03-01 | 02C.06.02 | IF the data access patterns for files required by production algorithms are not as expected, THEN production delivery requirements will not be met. | RM-Risk | 0.075 | 0
RM-688 | 540 | 91.8 | Distributed occurrence | 0 | 0 | 10%-25% | 91.8 | Proposed response: Redesign MOPS algorithms. Use more of existing daytime-idle Alert Production hardware. |  | 2019-07-03 16:18 | Active Risk/Opportunity | Data Management | MOPS algorithm performance | 2020-03-01 | 02C.03.06 | IF MOPS cannot process expected LSST data with required speed, orbit determination efficiency, and accuracy THEN solar system science will be compromised | RM-Risk | 0.17 | 0
RM-703 | 180 | 30.6 | Distributed occurrence | 26.265 | 154.5 | 10%-25% | 56.78 | Proposed response: Reduce synchronization. Simplify algorithms. Purchase additional hardware. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | Distribution of pipeline execution times | 2020-03-01 | 02C.03, 02C.04 | IF the distribution of pipeline execution times has a long tail THEN as the system is scaled up, the overall production execution speed will be disproportionately slowed by the synchronization barriers. | RM-Risk | 0.17 | 3
RM-708 | 360 | 27 | Distributed occurrence | 7.725 | 103 | 5%-10% | 34.72 | Proposed response: Improve algorithms. Purchase additional hardware. | Both Construction and Commissioning | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | Science Data Quality Assessment - too slow | 2020-03-01 | 02C.10 | IF the SDQA system cannot produce its results in a timely manner THEN there will be insufficient verification of data products | RM-Risk | 0.075 | 2
RM-679 | 540 | 199.8 | Distributed occurrence | 0 | 0 | 25%-50% | 199.8 | Proposed response: Improve algorithms. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | Object characterization performance | 2020-03-01 | 02C.04.06 | IF one or more of the object characterization algorithms does not accurately measure galaxy shapes to SRD levels THEN the scientific usefulness of weak lensing analyses and other Level 2 data products will be compromised | RM-Risk | 0.37 | 0
RM-675 | 320 | 118.4 | Distributed occurrence | 114.33 | 309 | 25%-50% | 232.73 | Proposed response: Redesign algorithms. Purchase additional hardware. Relax alert latency requirement. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | Computing power required for Alert Production exceeds estimates by small factor | 2020-03-01 | 02C.03 | IF the computing power required by the Alert Production exceeds the estimate by a small factor THEN the latency of alert processing may exceed specifications, reducing the scientific value of transient alerts | RM-Risk | 0.37 | 8
RM-678 | 540 | 199.8 | Distributed occurrence | 0 | 0 | 25%-50% | 199.8 | Proposed response: Improve algorithms. |  | 2019-07-03 16:18 | Active Risk/Opportunity | Data Management | Selected image differencing algorithm fails to achieve SRD performance | 2020-03-01 | 02C.03.07 | IF the image differencing algorithm used fails to achieve SRD performance levels on the expected data THEN false, missing, or inaccurate alerts will result | RM-Risk | 0.37 | 0
RM-835 | 320 | 54.4 | Distributed occurrence | 34 | 200 | 10%-25% | 88.4 |  |  | 2019-07-03 16:17 | Active Risk/Opportunity | Telescope & Site | Wavefront Estimation Algorithm Performance below requirements | 2020-03-01 | 4.7 | IF wavefront estimation algorithm does not meet performance requirements, THEN image quality error budget may not be met. | RM-Risk | 0.17 | 6
RM-1932 | 60 | 22.2 | Trigger date | 92.5 | 250 | 25%-50% | 114.7 | Apply LSST project resources to support the software development. Investigate incentives to the contractor. |  | 2019-07-03 16:37 | Active Risk/Opportunity | Telescope & Site | TMA Software Integration Late | 2020-04-01 | 04C.05.02.05 | IF the TMA control software has additional design challenges THEN site integration is going to be delayed. | RM-Risk | 0.37 | 4
RM-832 | 480 | 36 | Trigger date | 9 | 120 | 5%-10% | 45 | review testing procedures for FAT |  | 2019-07-03 16:09 | Active Risk/Opportunity | Telescope & Site | Excessive Vibration from Mount Drive System | 2020-04-01 | 4.5 | IF mount motion induced vibrations exceed requirements, THEN image quality error budget may not be met. | RM-Risk | 0.075 | 4
RM-825 | 120 | 20.4 | Trigger date | 25.5 | 150 | 10%-25% | 45.9 |  |  | 2019-07-03 16:17 | Active Risk/Opportunity | Telescope & Site | M1M3 Thermal system does not meet specifications | 2020-06-01 | 4.6.3 | IF M1M3 thermal system is unable to track ambient and to achieve the temperature stability specification, THEN the M1M3 mirror seeing and thermal contribution may exceed the allocation in the image quality error budget. | RM-Risk | 0.17 | 3
RM-692 | 540 | 40.5 | Distributed occurrence | 38.625 | 515 | 5%-10% | 79.13 | Proposed response: Redesign database. Ration database access. Distribute database to non-project providers. Add database hardware. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | Database performance | 2020-06-01 | 02C.06 | IF the science database system does not support the planned pipeline load and query load from users THEN data products will not be delivered on time or fewer user queries will be able to execute. | RM-Risk | 0.075 | 6
RM-775 | 540 | 199.8 | Trigger date | 762.2 | 2060 | 25%-50% | 962 | Proposed response: Improve algorithms. Purchase additional hardware. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | Unanticipated characteristics of real data result in poor MultiFit performance (computational) | 2020-06-01 | 02C.04.06 | IF the real data are more complex or more noisy than anticipated THEN MultiFit may require more computing power to converge to a best fit. | RM-Risk | 0.37 | 12
RM-732 | 0 | 0 | Trigger date | 0 | 0 | 50%-75% | 0 | If the allocated time is not sufficient for the necessary commissioning effort then the project will first allocate additional early integration time with the commissioning camera before the main camera arrives. IF that hardware condition does not satisfy the necessary testing than all three phases of the commissioning will be reviewed with subsystem delivery dates to find a project wide optimization. While the Project plan has 8.5 (as of 12/4/2018) months (was 13) of schedule float, full extension of the project will be a final response. Deeper blending and integration of early commissioning and system verification activities with planned T&S AIV activities can be used to shorten some of the later commissioning activities. As part of the development of the system verification plan (2019) the SIT-COM team will identify verification tests that can be conducted during AIV. SIT-COM will work with the AIV team to integrate these early test with their planned work. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Systems Engineering | Insufficient Commissioning Period | 2020-06-01 | 1.06C.05 | IF the available time allocated for Commissioning following schedule reduction is not sufficient THEN technical verification will not show that the requirements for Operations Readiness have been met . | RM-Risk | 0.63 | 0
RM-738 | 120 | 75.6 | Trigger date | 157.5 | 250 | 50%-75% | 233.1 | Contract additional scientific resources to re-optimize the calibration plan and implied hardware/software with minimal changes to the baseline design. |  | 2019-07-03 16:18 | Active Risk/Opportunity | Systems Engineering | Obtain Instrumental Calibration Data Products | 2020-07-01 | 6 | IF the expected time of acquiring the required calibration data products does not fit into the available time (~3 hours) during a normal 24 hour operational cycle, THEN the calibration process and supporting hardware/software will need to be redesigned. | RM-Risk | 0.63 | 5
RM-870 | 80 | 6 | Trigger date | 11.25 | 150 | 5%-10% | 17.25 | Detailed T&amp;S and camera technical discussions have matured the overall utility line design and layout (April 2017). |  | 2019-07-03 16:18 | Active Risk/Opportunity | Telescope & Site | Camera Refrigerant Flexible Lines and fittings not adequate | 2020-08-01 | 4.5 | IF selected flexible lines and fittings for camera refrigeration system are not adequate, THEN modifications will have to be implemented with cost and schedule impact. | RM-Risk | 0.075 | 2
RM-739 | 40 | 1 | Trigger date | 25 | 1000 | 0%-5% | 26 | If performance degradation is not too large then replacement of filter may be deferred to operations phase. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Systems Engineering | Filter bandpass stability | 2020-08-01 | 6 | IF filter bandpasses are unstable (due to thermal and or mechanical effects) THEN photometric color repeatability requirements will not be met. | RM-Risk | 0.025 | 3
RM-879 | 240 | 6 | Trigger date | 0.25 | 10 | 0%-5% | 6.25 | Recent hardware measurements confirm closed loop response on surrogate mirror assembly. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Telescope & Site | M2 Active Support Control below performances | 2020-08-01 | 4.6.4 | IF the M2 active support control system is below performances, THEN the M2 image quality allocation may not be met and new hardware will be required. | RM-Risk | 0.025 | 1
RM-844 | 80 | 6 | Trigger date | 4.5 | 60 | 5%-10% | 10.5 |  |  | 2019-07-22 20:04 | Active Risk/Opportunity | Telescope & Site | Guiding below performance | 2020-08-01 | 4.2 | IF Guiding is below performance, THEN new centroid and guiding algorithms will have to be designed and tested. | RM-Risk | 0.075 | 2
RM-850 | 120 | 9 | Trigger date | 7.5 | 100 | 5%-10% | 16.5 |  |  | 2019-07-02 21:38 | Active Risk/Opportunity | Telescope & Site | Mount Top End Thermal control below specifications for M2 or camera | 2020-08-01 | 4.5 | IF the top end assembly thermal control system fails to extract heat from M2 or camera to control temperature, THEN the observatory seeing contribution may exceed allocation in image quality error budget. | RM-Risk | 0.075 | 2
RM-861 | 120 | 9 | Trigger date | 18.75 | 250 | 5%-10% | 27.75 | Dome screen design completed to meet wind and seismic requirements. |  | 2019-07-03 16:18 | Active Risk/Opportunity | Telescope & Site | Dome Light/Wind screen Performance below specifications | 2020-08-01 | 4.4 | IF protective light/wind screen fails to meet critical requirements for reliability, rapid positioning of aperture and/or light protection, THEN the stray light requirements will not be met requiring redesign of light/wind screen. | RM-Risk | 0.075 | 2
RM-858 | 320 | 24 | Trigger date | 7.5 | 100 | 5%-10% | 31.5 |  |  | 2019-07-03 16:17 | Active Risk/Opportunity | Telescope & Site | Dome background interior light levels too high for calibration during daytime | 2020-08-01 | 4.4 | IF the dome background light variation is too high for daytime calibration, THEN the calibration plan must be modified. | RM-Risk | 0.075 | 2
RM-1935 | 2700 | 999 | Trigger date | 0 | 0 | 25%-50% | 999 | Look for alternative activities that can be performed in parallel without a completed TMA. |  | 2019-07-02 20:56 | Active Risk/Opportunity | Telescope & Site | TMA Integration Late | 2020-08-03 | 04C.05.02.05 | IF the TMA system integration on site is longer than planned THEN the project critical path will be delayed. | RM-Risk | 0.37 | 0
RM-867 | 640 | 16 | Trigger date | 2.5 | 100 | 0%-5% | 18.5 | Latest design requirements have loosened the overall uniformity requirements and recently the calibration screen design was updated to meet wind/seismic load requirements. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Telescope & Site | Calibration screen uniformity-stability below specifications | 2020-09-01 | 4.8 | IF calibration uniformity-stability requirements are not met by dome calibration screen, THEN photometric calibration requirements may not be met. | RM-Risk | 0.025 | 2
RM-671 | 540 | 91.8 | Trigger date | 262.65 | 1545 | 10%-25% | 354.45 | Proposed response: Reduce complexity of algorithms. Purchase additional hardware. Process only a sample of each night`s data. |  | 2019-07-03 16:18 | Active Risk/Opportunity | Data Management | Computing power required for Alert Production exceeds estimates by large factor | 2020-09-01 | 02C.03 | IF the computing power required by the Alert Production exceeds the estimate by a large factor (factor of 2 or more) THEN processing of images from the telescope will not keep up with the data flow over a 24 hour period. Processing deficit will grow without bound | RM-Risk | 0.17 | 9
RM-672 | 400 | 68 | Distributed occurrence | 262.65 | 1545 | 10%-25% | 330.65 | Proposed response: Reduce complexity of algorithms. Purchase additional hardware. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | Computing power required for Data Release Production exceeds estimates by small factor | 2020-09-01 | 02C.04 | IF the computing power required by the Data Release Production exceeds the baseline estimate by a small factor THEN data release processing will be slowed, resulting in lower probability of producing data releases on time | RM-Risk | 0.17 | 9
RM-843 | 120 | 9 | Trigger date | 11.25 | 150 | 5%-10% | 20.25 | T&amp;S and camera teams focused on detailed design of TMA/camera utilities. Hardware has been fabricated and near final delivery. |  | 2019-07-18 15:52 | Active Risk/Opportunity | Telescope & Site | Camera Utilities provided from mount top end not adequate | 2020-09-01 | 4.2 | IF the utilities delivered to the camera from the mount are not adequate, THEN modifications will have to be implemented with cost and schedule impact. | RM-Risk | 0.075 | 2
RM-715 | 540 | 13.5 | Trigger date | 0 | 0 | 0%-5% | 13.5 | Proposed response: Improve algorithms by using more self-calibration. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | Calibration system compromised | 2020-09-01 | 02C.04.02 | IF the calibration systems (auxiliary telescope and other instruments, dome screen, projector, etc.) do not meet requirements or were inadequately designed THEN the global photometric requirement will not meet the SRD spec. | RM-Risk | 0.025 | 0
RM-717 | 540 | 91.8 | Trigger date | 0 | 0 | 10%-25% | 91.8 | Proposed response: Improve algorithms by using more self-calibration. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | Lab camera characterization measurements are insufficient | 2020-09-01 | 02C.04.02 | IF laboratory characterization of the Camera fails to produce an adequate model of the instrument signature THEN photometric and shape measurements may fail to reach SRD specs | RM-Risk | 0.17 | 0
RM-716 | 180 | 13.5 | Trigger date | 0 | 0 | 5%-10% | 13.5 | Proposed response: Improve models of filter bandpass. Develop alternate calibration algorithms. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | Filter bandpass characterization does not meet spec | 2020-09-01 | 02C.04.02 | IF filter bandpass characterization does not meet the requirements THEN photometric (and possibly astrometric) calibration may fail to reach SRD specs | RM-Risk | 0.075 | 0
RM-696 | 360 | 61.2 | Trigger date | 0 | 0 | 10%-25% | 61.2 | Proposed response: Improve algorithms to remove scattered light. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | Scattered light more significant than anticipated | 2020-09-01 | 02C.03.01, 02C.03.07 | IF the scattered light is more prevalent or significant than anticipated THEN background estimation, image subtraction, photometry and the rates of false positive alerts will be high and the SRD specs may not be achieved | RM-Risk | 0.17 | 0
RM-699 | 360 | 61.2 | Distributed occurrence | 0 | 0 | 10%-25% | 61.2 | Proposed response: Improve PSF estimation algorithm. |  | 2019-07-03 16:18 | Active Risk/Opportunity | Data Management | Insufficient accuracy of PSF estimation algorithm | 2020-09-01 | 02C.04.03 | IF the algorithm (using wavefront sensing and camera metrology) fails to adequately estimate the instrumental component of the PSF THEN the scientific usefulness of measurements in the data products will be reduced | RM-Risk | 0.17 | 0
RM-752 | 1080 | 81 | Trigger date | 270.375 | 3605 | 5%-10% | 351.38 | Proposed response: Reduce complexity of algorithms. Re-architect to fit cheaper hardware. Purchase additional hardware. Reduce pre-operations processing tests. Adjust refresh and new provisioning schedules. Accept delays or incompleteness. | Both Construction and Commissioning | 2019-07-03 16:18 | Active Risk/Opportunity | Data Management | Computing cost performance | 2020-09-01 | 02C.07.09 | IF the growth of computing system price-performance does not match expectations THEN data products will be delayed or incomplete | RM-Risk | 0.075 | 8
RM-837 | 80 | 6 | Trigger date | 15 | 200 | 5%-10% | 21 |  |  | 2019-07-03 16:17 | Active Risk/Opportunity | Telescope & Site | Wavefront Sensor Offset not adequate for active optics system | 2020-09-01 | 4.7 | IF offset between intra and extra focal wavefront sensor is not adequate, THEN modifications of the WFS algorithm/software will have to be implemented with cost and schedule impact. | RM-Risk | 0.075 | 2
RM-873 | 40 | 1 | Trigger date | 2.5 | 100 | 0%-5% | 3.5 |  |  | 2019-07-18 15:35 | Active Risk/Opportunity | Telescope & Site | Camera or M2 Hexapod motion out of range | 2020-10-01 | 4.5 | IF required hexapod motion is out of range limit during operations, THEN modifications will have to be implemented with cost and schedule impact. | RM-Risk | 0.025 | 1
RM-838 | 240 | 18 | Trigger date | 4.5 | 60 | 5%-10% | 22.5 |  |  | 2019-07-03 16:17 | Active Risk/Opportunity | Telescope & Site | OCS implementation complicated by inability to run system prior to going live | 2020-10-01 | 4.1 | IF OCS implementation becomes complicated due to the inability to interact with subsystems, THEN there may be a schedule delay to the start of survey. | RM-Risk | 0.075 | 2
RM-854 | 160 | 12 | Trigger date | 22.5 | 300 | 5%-10% | 34.5 |  |  | 2019-07-03 16:17 | Active Risk/Opportunity | Telescope & Site | Light baffle system does not meet specifications | 2020-10-01 | 4.2 | IF the light baffles do not perform according to specs, THEN the baffles will need to be modified so that stray light requirements are met. | RM-Risk | 0.075 | 2
RM-855 | 40 | 6.8 | Trigger date | 27.2 | 160 | 10%-25% | 34 |  |  | 2019-07-03 16:17 | Active Risk/Opportunity | Telescope & Site | Mount or Dome Motion Coupling Predicted During Observing | 2020-10-01 | 4.5 | IF measurements show that dome motion during an exposure creates vibration coupling between dome and telescope above allocation in error budget, THEN image quality error budget may not be met. | RM-Risk | 0.17 | 3
RM-863 | 180 | 13.5 | Trigger date | 12 | 160 | 5%-10% | 25.5 |  |  | 2019-07-03 16:17 | Active Risk/Opportunity | Telescope & Site | Grounding or noise issues so that Control Systems do not perform to specification | 2020-10-01 | 4.11 | IF control system components do not perform well in real environment, have noise or grounding issues, insufficient accuracy or processing capabilities, THEN additional design efforts will be required. | RM-Risk | 0.075 | 2
RM-780 | 320 | 54.4 | Trigger date | 170 | 1000 | 10%-25% | 224.4 | Management should not accept the performance degradation associated with this risk and make all efforts to implement derived corrections. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Systems Engineering | Active Optics Image Performance Verification | 2020-10-01 | 6 | IF The closed loop active optics system does not accurately reconstruct the alignment errors THEN the image quality performance of the SRD specifications will not be met. | RM-Risk | 0.17 | 9
RM-729 | 120 | 20.4 | Distributed occurrence | 85 | 500 | 10%-25% | 105.4 |  |  | 2019-07-03 16:17 | Active Risk/Opportunity | Systems Engineering | Technical OpsCon not finished in time to impact facility layouts and design decisions | 2020-10-01 | 06C.05.03 | IF the project-wide Technical Operations are not defined and approved soon enough to influence the final designs of the major operational facilities as well as software and hardware designs, THEN operations performed in the commissioning phase may not be optimized, leading to cost impacts. | RM-Risk | 0.17 | 6
RM-700 | 360 | 61.2 | Distributed occurrence | 0 | 0 | 10%-25% | 61.2 | Proposed response: Improve deblending algorithms. |  | 2019-07-03 16:18 | Active Risk/Opportunity | Data Management | Deblending algorithm shapes | 2020-12-01 | 02C.04.05 | IF the deblending algorithm introduces systematic shape measurement errors THEN the SRD requirement on residual ellipticity correlation may not be met. | RM-Risk | 0.17 | 0
RM-833 | 80 | 6 | Trigger date | 22.5 | 300 | 5%-10% | 28.5 | T&amp;S and Camera teams are working to close out the details of camera room utilities and other common interfaces. |  | 2019-07-19 04:17 | Active Risk/Opportunity | Telescope & Site | Summit facility must be modified to accommodate interfaces | 2020-12-01 | 4.3 | IF the early design of the summit facility has not properly anticipated the interfaces and capabilities required by the other LSST subsystems, THEN the summit facility contract will need to be modified to meet the interface requirements. | RM-Risk | 0.075 | 2
RM-743 | 80 | 6 | Trigger date | 37.5 | 500 | 5%-10% | 43.5 |  |  | 2019-07-03 16:17 | Active Risk/Opportunity | Systems Engineering | System ellipticity performance | 2021-01-01 | 06C.04 | IF the ellipticity contributions of the as-built technical specifications of the Camera and the Telescope are not properly controlled, THEN the overall system ellipticity performance will not be met. | RM-Risk | 0.075 | 4
RM-687 | 540 | 91.8 | Trigger date | 0 | 0 | 10%-25% | 91.8 | Proposed response: Develop artifact removal or new calibration algorithms. Acquire additional lab data on sensors. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | Unexpected camera detector behavior | 2021-01-01 | 02C.04 | IF the camera exhibits unexpected behavior (such as complex crosstalk signatures or significant charge trapping or significant high-frequency pixel size variation or time-varying artifacts) THEN the data management system will not be able to reduce some or all of the gathered data, or the reduced data may not be up to SRD specs. | RM-Risk | 0.17 | 0
RM-684 | 360 | 27 | Trigger date | 15.45 | 206 | 5%-10% | 42.45 | Proposed response: Redesign database or production algorithms. Add database hardware. | Commissioning only | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | Unexpected database data access patterns from DM productions | 2021-01-01 | 02C.06 | IF the data access patterns for databases required by production algorithms are not as expected, THEN production delivery requirements may not be met. | RM-Risk | 0.075 | 4
RM-899 | 60 | 0.3 | Distributed occurrence | 1 | 200 | 0%-1% | 1.3 |  |  | 2019-07-03 16:18 | Active Risk/Opportunity | Project Management Office | Annual funding lower than baseline plan | 2021-01-01 | 01C | IF in a given year there is a 5% to 10% reduction to the baseline funding profile THEN the project will need to re-plan the baseline accordingly. | RM-Risk | 0.005 | 0
RM-754 | 120 | 9 | Trigger date | 0 | 0 | 5%-10% | 9 | Proposed response: Utilize multiple data sites (NCSA, Base, and CC-IN2P3) and appropriate technologies to build an environment that will protect the LSST data. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | Data loss due to backup failure | 2021-01-01 | 02C.07.09 | IF disaster recovery stores of science data are incomplete or unusable THEN a major loss of data can occur | RM-Risk | 0.075 | 0
RM-859 | 40 | 3 | Trigger date | 27 | 360 | 5%-10% | 30 |  |  | 2019-07-18 20:23 | Active Risk/Opportunity | Telescope & Site | Coating system Magnetron contacting mirror surface | 2021-01-01 | 4.9 | IF the coating chamber magnetron support system fails, THEN damage to the mirror surface could occur. | RM-Risk | 0.075 | 2
RM-737 | 360 | 133.2 | Trigger date | 0 | 0 | 25%-50% | 133.2 | Perform study to determine performance impact and consider using part of the performance margin. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Systems Engineering | Instrumental Flux Measurements | 2021-02-01 | 6 | IF instrumental flux measurements from the delivered DM pipeline have higher biases and systematic errors than assumed THEN the photometric performance requirement will not be met. | RM-Risk | 0.37 | 0
RM-774 | 720 | 122.4 | Distributed occurrence | 0 | 0 | 10%-25% | 122.4 | Proposed response: Develop additional deliverables or update to meet requirements. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | SRD not flowed down correctly | 2021-02-01 | 02C | IF the Science Requirements Document was not flowed down correctly THEN the data management system may not be able to deliver all required deliverables, or deliver them at the required accuracy/precision levels. | RM-Risk | 0.17 | 0
RM-762 | 180 | 13.5 | Distributed occurrence | 0 | 0 | 5%-10% | 13.5 | Proposed response: Test early and test often looking at corner cases. Devote additional resources to debugging and integration. More robust change management process for deploying software changes into production. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | Inadequate release QA | 2021-03-01 | 02C.07.06 | IF the software release QA system does not perform adequate testing on releases prior to deployment THEN faulty releases may be installed in production, inhibiting integration and commissioning or leading to operations failures | RM-Risk | 0.075 | 0
RM-759 | 240 | 18 | Trigger date | 0 | 0 | 5%-10% | 18 | Proposed response: Add resources to fix integration problems. |  | 2019-07-03 16:18 | Active Risk/Opportunity | Data Management | Unexpected LSST subsystem incompatibilities discovered during integration | 2021-03-01 | 02C.07.06 | IF unexpected incompatibilities with other LSST subsystems are encountered during integration THEN DM will fail to integrate properly and the overall system will not operate when needed. | RM-Risk | 0.075 | 0
RM-713 | 360 | 27 | Trigger date | 0 | 0 | 5%-10% | 27 | Proposed response: Mask victim pixels |  | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | Camera fails to meet cross-talk matrix sparseness requirement | 2021-03-01 | 02C.03.01 | IF there is cross-talk between sensors beyond what is permitted by requirements THEN there will be unidentified cross-talk ghosts and/or measurement errors present in the data. | RM-Risk | 0.075 | 0
RM-701 | 360 | 61.2 | Distributed occurrence | 0 | 0 | 10%-25% | 61.2 | Proposed response: Re-architect software. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | Discovering a need for access or parallelism pattern not supported by the workflow middleware | 2021-03-01 | 02C.06.02.01, 02C.06.03.01, 02C.07.01.02 | IF the science algorithms require a data access or parallelism pattern not supported by the middleware THEN the delivery and/or accuracy of data products may be in jeopardy | RM-Risk | 0.17 | 0
RM-674 | 720 | 54 | Trigger date | 0 | 0 | 5%-10% | 54 | Proposed response: Develop new deliverables or update to meet new requirements. Buy new hardware for additional computation. | Both Construction and Commissioning | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | New SRD requirements require new DM functionality | 2021-03-01 | 02C | IF new requirements are introduced or recognized in the LSST Science Requirements Document that impact Data Management production deliverables THEN some data management deliverables may either be missing or not be at the SRD levels | RM-Risk | 0.075 | 0
RM-677 | 1200 | 204 | Distributed occurrence | 0 | 0 | 10%-25% | 204 | Proposed response: Add resources to handle updates. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | Failure to manage dependencies with other LSST subsystems | 2021-03-01 | 02C | IF there is the wrong level of integration with other LSST subsystems` software (too little or too much) THEN continued development and/or application of bug fixes may be inhibited, resulting in delays and possibly lost or corrupted data | RM-Risk | 0.17 | 0
RM-773 | 720 | 122.4 | Distributed occurrence | 1225.7 | 7210 | 10%-25% | 1348.1 | Proposed response: Reduce sky area or depth. Use StackFit only with concomitant systematic effects. Reduce complexity of algorithms. Purchase additional hardware. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | Computing power required for Data Release Production exceeds estimates by large factor | 2021-03-01 | 02C.04 | IF the computing power required by the Data Release Production algorithms, given projected source behavior, exceeds the baseline estimate by a large factor (factor of 2 or more) THEN early data releases cannot cover the full area and/or depth of the survey | RM-Risk | 0.17 | 12
RM-734 | 0 | 0 | Trigger date | 0 | 0 | 25%-50% | 0 | Allocate additional FTEs. |  | 2019-07-03 16:18 | Active Risk/Opportunity | Systems Engineering | Camera Verification Delays on Summit | 2021-03-01 | 6 | IF on-summit camera verification proceeds more slowly than planned, THEN there will be a delay in the start of Full System Integration and Test, leading to a delay in the ORR. | RM-Risk | 0.37 | 0
RM-740 | 180 | 13.5 | Trigger date | 15 | 200 | 5%-10% | 28.5 | Assign dedicated scientific and engineering resources full time for a duration of 3 months to evaluate issues, come up with a solution, and test/implement the solution. Expedite bringing in additional consulting resources from outside the project as needed. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Systems Engineering | OpSim Fidelity does not reflect Observatory Behavior | 2021-07-15 | 06C.05 | IF the Operations Simulator does not adequately reproduce the expected behavior of the observatory, THEN the assessment of whether the observatory can meet the full-survey requirements and/or successfully address the four science drivers may not be accurate. | RM-Risk | 0.075 | 2
RM-741 | 120 | 44.4 | Trigger date | 92.5 | 250 | 25%-50% | 136.9 | Management should not accept the performance degradation associated with this risk and make proposed corrections. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Systems Engineering | Unstable Illumination Correction | 2021-07-15 | 6 | IF the illumination correction varies (e.g. due to changes in scattered light) on timescales shorter than can be used to derive calibration products THEN the photometric uniformity requirements will not be met OR time to obtain necessary calibration will be taken away from the survey. | RM-Risk | 0.37 | 4
RM-886 | 5400 | 3402 | Distributed occurrence | 315 | 500 | 50%-75% | 3717 | Schedule and contingency will be used along with reworking the integrated plan to deal with subsystem delays | Both Construction and Commissioning | 2019-07-18 15:05 | Active Risk/Opportunity | Project Management Office | Subsystem Milestone Execution | 2021-08-01 | 01C | IF the subsystems do not execute and deliver on Level 1 or Level 2 milestones THEN the overall Project schedule will be delayed and other subsystem activity can be impacted. | RM-Risk | 0.63 | 20
RM-894 | 0 | 0 | Distributed occurrence | 37.5 | 500 | 5%-10% | 37.5 |  |  | 2019-07-03 16:18 | Active Risk/Opportunity | Project Management Office | Escalation Budgeting | 2021-08-01 | 01C | IF actual escalation is not accurately predicted in the PMCS THEN the budget will need to be adjusted. | RM-Risk | 0.075 | 2
RM-1939 | 0 | 0 | Trigger date | 0 | 0 | 10%-25% | 35.5 |  |  | 2019-07-25 21:34 | Active Risk/Opportunity | Telescope & Site | OCS Development is Late | 2021-08-02 | 04C.10.02 | IF the OCS software development and integration does not meet the technical requirements or schedule, THEN the final science verification and validation efforts will be delayed. | RM-Risk | 0.17 | 0
RM-768 | 600 | 222 | Distributed occurrence | 0 | 0 | 25%-50% | 222 | Proposed response: Re-architect software using more standard tools/languages/philosophies. Add resources for maintenance of old architecture. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | LSST DM software architecture incompatible with de-facto community standards | 2021-09-01 | 02C.07.08 | IF the LSST DM software architecture (including tools/libraries, languages, and design philosophies) is excessively custom-built THEN maintenance and changes will be difficult | RM-Risk | 0.37 | 0
RM-673 | 120 | 20.4 | Trigger date | 262.65 | 1545 | 10%-25% | 283.05 | Proposed response: Reduce data stored per object/source/alert. Purchase additional hardware. Reduce number of highly-crowded fields. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | Archive sizing inadequate | 2021-09-01 | 02C.06 | IF there are more objects, sources, or alerts than expected, THEN we will not be able to archive all versions of all data products or access latency requirements will not be met | RM-Risk | 0.17 | 9
RM-889 | 0 | 0 | Distributed occurrence | 595 | 3500 | 10%-25% | 595 | There is no mitigation for this risk. Non-labor purchasing is already set for acquisition as early as possible. |  | 2019-07-03 16:18 | Active Risk/Opportunity | Project Management Office | Chilean currency exchange rate factor | 2021-09-01 | 01C | IF the average currency exchange between the Chilean Peso and the USD is less than when budget was set, THEN there will be a cost increase. | RM-Risk | 0.17 | 12
RM-721 | 540 | 13.5 | Distributed occurrence | 0 | 0 | 0%-5% | 13.5 | Proposed response: Improve algorithms. |  | 2019-07-03 16:18 | Active Risk/Opportunity | Data Management | Astrometric calibration | 2021-09-01 | 02C.03.07 | IF the global astrometric calibration does not achieve the precision and accuracy called for in the SRD THEN the scientific usefulness of the survey will be compromised | RM-Risk | 0.025 | 0
RM-685 | 540 | 91.8 | Distributed occurrence | 0 | 0 | 10%-25% | 91.8 | Proposed response: Improve tools. |  | 2019-07-03 16:18 | Active Risk/Opportunity | Data Management | Science data quality analysis tools inadequate | 2021-09-01 | 02C.10 | IF the tools available to scientists to analyze the data quality are inadequate THEN data quality problems may go unrecognized, if the system fails to identify defects in the recorded raw data in an accurate and timely manner THEN failures in upstream systems may be missed, resulting in the failure to perform necessary repairs or adjustments and the recording of substandard data | RM-Risk | 0.17 | 0
RM-683 | 540 | 91.8 | Trigger date | 35.02 | 206 | 10%-25% | 126.82 | Proposed response: Redesign database. Ration database access. Distribute database to non-project providers. Add database hardware. Redesign here ould be major piece of work and some investigation is merited. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | Unexpected database data access patterns from science users | 2021-09-01 | 02C.06 | IF the data access patterns for databases required by analyses by scientists are not as expected, THEN end-user data access desires may not be met. | RM-Risk | 0.17 | 6
RM-689 | 540 | 91.8 | Trigger date | 0 | 0 | 10%-25% | 91.8 | Proposed response: Redesign MOPS algorithms. Use more of existing daytime-idle Alert Production hardware. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | Transient rates exceed expectations (impact on MOPS) | 2021-09-01 | 02C.03.06 | IF the transient rates exceed expectations by a significant factor THEN the tracklet-track-orbit based MOPS algorithm will be overwhelmed with potential candidates and unable to find real asteroids. | RM-Risk | 0.17 | 0
RM-691 | 240 | 40.8 | Trigger date | 0 | 0 | 10%-25% | 40.8 | Proposed response: Redesign workflow. |  | 2019-07-03 16:18 | Active Risk/Opportunity | Data Management | Selected DRP workflow fails to support required science cases | 2021-09-01 | 02C.04 | IF the overall Data Release Production workflow structure (including the sequence and organization of pipeline executions) is incorrect (especially in the face of real data) THEN some types of intermediate data will not be available and scientific performance will be reduced | RM-Risk | 0.17 | 0
RM-686 | 540 | 91.8 | Distributed occurrence | 0 | 0 | 10%-25% | 91.8 | Proposed response: Improve algorithms. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | Photometric calibration | 2021-09-01 | 02C.03.07, 02C.04.07 | IF the global photometric calibration does not achieve the precision and accuracy called for in the SRD THEN the scientific usefulness of the survey will be compromised | RM-Risk | 0.17 | 0
RM-712 | 540 | 40.5 | Trigger date | 0 | 0 | 5%-10% | 40.5 | Proposed response: Improve deblending, detection, and measurement algorithms. Avoid highly-crowded fields. |  | 2019-07-03 16:18 | Active Risk/Opportunity | Data Management | Source density too high for detection/measurement | 2021-09-01 | 02C.03.01, 02C.04.05, 02C.04.06 | IF the assumptions about typical on-sky source density are incorrect THEN existing source detection and measurement algorithms may fail in areas where they were assumed to function. | RM-Risk | 0.075 | 0
RM-711 | 540 | 40.5 | Trigger date | 0 | 0 | 5%-10% | 40.5 | Proposed response: Redesign MOPS algorithms. Use more of existing daytime-idle Alert Production hardware. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | Numbers of detected moving objects exceed expectations (MOPS) | 2021-09-01 | 02C.03.06 | IF the number of moving objects exceeds expectations by a significant factor THEN the pre-covery and ephemeris calculation MOPS components may not be able to finish in time. | RM-Risk | 0.075 | 0
RM-710 | 180 | 30.6 | Trigger date | 0 | 0 | 10%-25% | 30.6 | Proposed response: Improve file access services. Re-architect software. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | File data access patterns for science analysis change | 2021-09-01 | 02C.06.02 | IF the data access patterns for files required by analyses by scientists are not as expected, THEN end-user data access requirements will not be met. | RM-Risk | 0.17 | 0
RM-714 | 360 | 27 | Trigger date | 0 | 0 | 5%-10% | 27 | Proposed response: Improve deblending algorithms. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | Deblending algorithm - splitting | 2021-09-01 | 02C.04 | IF the morphology or complexity of blends is higher than anticipated THEN the selected deblending algorithm will not be able to deblend faint sources, jeopardizing extragalactic and dark energy science. | RM-Risk | 0.075 | 0
RM-694 | 400 | 68 | Distributed occurrence | 0 | 0 | 10%-25% | 68 | Proposed response: Accelerate development and testing of Data Release Production software. |  | 2019-07-03 16:18 | Active Risk/Opportunity | Data Management | Rate of software updates required by Data Release Production | 2021-09-01 | 02C.04 | IF the Data Release Production is insufficiently mature when operations begin THEN the rate of software enhancements and bug fixes will preclude the production of a Data Release with a single version of the software, reducing the scientific integrity of the Data Release | RM-Risk | 0.17 | 0
RM-695 | 360 | 61.2 | Distributed occurrence | 0 | 0 | 10%-25% | 61.2 | Proposed response: Redesign algorithms. Relax alert latency requirement. |  | 2019-07-03 16:18 | Active Risk/Opportunity | Data Management | Alert Production algorithm scaling and predictability of performance | 2021-09-01 | 02C.03 | IF the DM algorithms in alert production prove to have a high sensitivity to crowded fields, occasional corrupted upstream data, or other features of the data THEN there may be excessive failures to meet the alert delivery requirement. | RM-Risk | 0.17 | 0
RM-698 | 360 | 61.2 | Distributed occurrence | 0 | 0 | 10%-25% | 61.2 | Proposed response: Improve algorithms. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | Instrumental PSF magnitude measurement exceeds allocated error budget | 2021-09-01 | 02C.04.03 | IF point source flux estimation algorithms fail to operate within the assigned error budget (currently 3mmag), THEN the total photometric calibration error may exceed SRD specifications. | RM-Risk | 0.17 | 0
RM-749 | 1200 | 6 | Random occurrence(s) | 5.15 | 1030 | 0%-1% | 11.15 | Proposed response: Move hardware to Base during Commissioning. Add secure tunnel infrastructure over existing networks or use tape/disk/SSD shipping instead of networks. | Both Construction and Commissioning | 2019-07-03 16:18 | Active Risk/Opportunity | Systems Engineering | Security vulnerabilities - inter-site links | 2021-09-01 | 1.06.01 | IF security issues arise affecting the links between production sites THEN the multi-site data production model may be compromised and Archive Site resources not able to be fully exploited. | RM-Risk | 0.005 | 0
RM-702 | 360 | 61.2 | Distributed occurrence | 0 | 0 | 10%-25% | 61.2 | Proposed response: Improve algorithms and reanalyze past releases. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | Science Data Quality Assessment - miscategorization of data | 2021-09-01 | 02C.10 | IF the quality assessments by SDQA are insufficiently reliable or accurate, and good data are classified as bad, or the reverse, THEN the efficiency or scientific usefulness of the survey may be compromised, or inadequacies in DM productions may be missed | RM-Risk | 0.17 | 0
RM-706 | 540 | 40.5 | Trigger date | 0 | 0 | 5%-10% | 40.5 | Proposed response: Implement better PSF models. Improve difference imaging algorithms. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | Selected image differencing algorithm performs poorly with real images | 2021-09-01 | 02C.03.07 | IF the real PSF is significantly different from the one assumed during algorithm development and tuning THEN the results of image differencing may contain many artifacts due to imperfect subtraction resulting in increased false positive rates. | RM-Risk | 0.075 | 0
RM-707 | 360 | 27 | Distributed occurrence | 7.725 | 103 | 5%-10% | 34.72 | Proposed response: Re-architect software. Add SUI hardware. All sky maps are a particular area of concern - we could look into existing tools in this area. |  | 2019-07-03 16:18 | Active Risk/Opportunity | Data Management | LSST Science Platform architecture fails to scale | 2021-09-01 | 02C.05 | IF the LSST Science Platform architecture fails to scale to the actual load THEN scientists will encounter delays and/or failures, or access will have to be rationed | RM-Risk | 0.075 | 2
RM-705 | 240 | 40.8 | Trigger date | 0 | 0 | 10%-25% | 40.8 | Proposed response: Develop additional quality metrics. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | Science Data Quality Assessment unexpected metrics required | 2021-09-01 | 02C.10 | IF real-world data turns out to have characteristics that require additional quality metrics, THEN there will be insufficient verification of data products | RM-Risk | 0.17 | 0
RM-704 | 240 | 40.8 | Trigger date | 0 | 0 | 10%-25% | 40.8 | Proposed response: Develop additional quality metrics. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | Science Data Quality Assessment unexpected requirements | 2021-09-01 | 02C.10 | IF additional requirements are added, THEN there will be insufficient time to build the correct system | RM-Risk | 0.17 | 0
RM-680 | 540 | 199.8 | Trigger date | 0 | 0 | 25%-50% | 199.8 | Proposed response: Improve algorithms. | Both Construction and Commissioning | 2019-07-03 16:18 | Active Risk/Opportunity | Data Management | Unanticipated characteristics of real data result in poor MultiFit performance (scientific) | 2021-09-01 | 02C.04.06 | IF the real data is not well fit by models and assumptions made by MultiFit THEN the produced measurements may not be scientifically useful. | RM-Risk | 0.37 | 0
RM-676 | 360 | 226.8 | Trigger date | 0 | 0 | 50%-75% | 226.8 | Proposed response: Filter alerts. Improve algorithms. |  | 2019-07-03 16:18 | Active Risk/Opportunity | Data Management | Alert false alarm rate | 2021-09-01 | 02C.03 | IF the alert false alarm rate exceeds a tolerable level THEN the scientific usefulness of alerts will be compromised | RM-Risk | 0.63 | 0
RM-807 | 240 | 1.2 | Trigger date | 1 | 200 | 0%-1% | 2.2 | Fix vulnerabilities |  | 2019-07-24 21:23 | Active Risk/Opportunity | Education and Public Outreach | EPO security vulnerabilities discovered late | 2021-10-01 | 5 | Discovery of security vulnerabilities are discovered prior to Operations. Software. | RM-Risk | 0.005 | 0
RM-784 | 0 | 0 | Trigger date | 0.75 | 30 | 0%-5% | 0.75 |  |  | 2019-07-03 16:17 | Active Risk/Opportunity | Systems Engineering | Camera Reflective Surfaces Cause Noise Issues | 2021-12-01 | 1.06C.02 | IF the unpainted camera surfaces result in excessive light scattering within the main beam THEN background noise will increase, resulting in reduced source signal-to-noise ratio thereby reducing the survey efficiency. | RM-Risk | 0.025 | 1
RM-735 | 1800 | 666 | Trigger date | 74 | 200 | 25%-50% | 740 | If this risk is realized, it will take up some of the schedule float. It may be possible to incorporate some of the mitigation during scheduled engineering time blocks. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Systems Engineering | Unstable Camera opto-electronic performance | 2021-12-01 | 6 | IF the camera opto-electronic performance requirements used to derive calibration products is unstable on the mountain (e.g. amplifier gain and sensor y-band QE) THEN photometric repeatability requirements will not be met. | RM-Risk | 0.37 | 12
RM-802 | 40 | 1 | Random occurrence(s) | 0 | 0 | 0%-5% | 1 | Make changes to system to reflect updated web standards and trends. | Commissioning only | 2019-07-03 16:18 | Active Risk/Opportunity | Education and Public Outreach | EPO external standards change | 2022-01-01 | 5 | IF EPO team is not keeping on top of changes in external tools or standards THEN user interfaces become unsupported or lack of integration with community tools or unmaintainable interface to EPO products. Software. | RM-Risk | 0.025 | 0
RM-803 | 240 | 40.8 | Distributed occurrence | 0 | 0 | 10%-25% | 40.8 | Modify web interfaces in response to user testing. |  | 2019-07-24 18:58 | Active Risk/Opportunity | Education and Public Outreach | EPO user interface too complex | 2022-01-31 | 5 | IF user testing on EPO products is not frequent enough or thorough enough THEN the user interface will not be intuitive, responsive enough or easy to use for primary audiences of general public. The worst case scenario if users have an unpleasant first experience, leave the site and don't return. Usability. | RM-Risk | 0.17 | 0
RM-723 | 720 | 122.4 | Trigger date | 700.4 | 4120 | 10%-25% | 822.8 | Proposed response: Improve algorithms. Purchase additional hardware. Reduce sky area or depth. | Commissioning only | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | Object counts exceed expectations, leading to insufficient compute | 2022-03-01 | 02C.04 | IF the detected number of objects exceeds expectation by a significant factor THEN there will not be enough computational capacity for DRP. | RM-Risk | 0.17 | 12
RM-804 | 360 | 61.2 | Trigger date | 25.5 | 150 | 10%-25% | 86.7 | Proposed response: Devote additional resources to debugging and integration. |  | 2019-07-24 21:27 | Active Risk/Opportunity | Education and Public Outreach | EPO and DM Integration Incompatibilities | 2022-03-01 | 5 | Incompatibilities between DM and EPO during integration and commissioning. DM Integration | RM-Risk | 0.17 | 6
RM-1937 | 120 | 20.4 | Random occurrence(s) | 85 | 500 | 10%-25% | 105.4 | LSST will become the general contractor. | Construction only | 2019-07-03 00:18 | Active Risk/Opportunity | Telescope & Site | Dome Contractor Default |  | 04C.04.02 | IF the Dome contractor defaults THEN LSST will have to bring the Dome development effort in house. | RM-Risk | 0.17 | 6
RM-872 | 80 | 2 | Distributed occurrence | 2.5 | 100 | 0%-5% | 4.5 | Working on design of roof actuator and integration sequence to avoid schedule impacts. |  | 2019-07-03 16:18 | Active Risk/Opportunity | Telescope & Site | Summit Facility Platform lift is not working during summit integration |  | 4.14 | IF the platform lift is not working during integration, THEN integration schedule will be delayed. | RM-Risk | 0.025 | 1
RM-823 | 80 | 29.6 | Random occurrence(s) | 111 | 300 | 25%-50% | 140.6 |  | Both Construction and Commissioning | 2019-07-19 13:57 | Active Risk/Opportunity | Telescope & Site | Loss of key Telescope and Site personnel |  | 4.1 | IF there is an unplanned loss of key personnel in the Telescope and Site group THEN there will be schedule loss and recruitment efforts will be required. | RM-Risk | 0.37 | 4
RM-769 | 1200 | 6 | Random occurrence(s) | 5.15 | 1030 | 0%-1% | 11.15 | Proposed response: Work with ISO to implement information security incident response procedures | Both Construction and Commissioning | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | Security vulnerabilities - inter-site links |  | 02C.07.07 | IF security issues arise affecting the links between production sites THEN the multi-site data production model may be compromised and Archive Site resources not able to be fully exploited. | RM-Risk | 0.005 | 0
RM-766 | 120 | 3 | Random occurrence(s) | 3.8625 | 154.5 | 0%-5% | 6.85 | Proposed response: Work with ISO to implement information security incident response procedures. | Both Construction and Commissioning | 2019-07-03 16:17 | Active Risk/Opportunity | Data Management | Security vulnerabilities and user data access |  | 02C.07.07 | IF security vulnerabilities are discovered THEN outside access to science data may need to be limited until the vulnerabilities are fixed | RM-Risk | 0.025 | 1
RM-745 | 100 | 17 | Distributed occurrence | 0 | 0 | 10%-25% | 17 | Subsystem managers support optimized redesign activities on both sides of the interface. |  | 2019-07-03 16:08 | Active Risk/Opportunity | Systems Engineering | OCS Architecture Changes Impact on Interfaces |  | 6 | IF the OCS ISDs and OCS-to-subsystem ICDs impact subsystem interfaces, THEN systems engineering will have to initiate and negotiate unplanned technical change orders for vendor contracts or in-house designs. | RM-Risk | 0.17 | 0
RM-888 | 3600 | 1332 | Trigger date | 0 | 0 | 25%-50% | 1332 | At this time the NSF and DOE efforts are on the critical path. ComCam reduces the direct dependency of late Camera delivery but with an 80% confidence of delivery within 5 months of due date this risk covers the residual impact of the camera being later that ComCam can stay efficient. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Project Management Office | Multi-agency coordination - Camera Delivery |  | 01C | IF Camera is delivered later than ComCam usefulness THEN the resulting project inefficiencies will need to be paid for with contingency funds. | RM-Risk | 0.37 | 0
RM-890 | 1200 | 90 | Random occurrence(s) | 75 | 1000 | 5%-10% | 165 | Earthquake damage must be corrected. | Both Construction and Commissioning | 2019-07-03 16:17 | Active Risk/Opportunity | Project Management Office | Earthquake of moderate severity at summit and/or base |  | 01C | IF there is an earthquake of moderate severity (in accordance with an Operable Seismic event as defined in OSS-REQ-0345) resulting in significant damage (defined as any damage that cannot be repaired within the statistical allocation of the unscheduled down time), THEN there will be an interruption of the normal work schedule to repair damage to equipment, resulting in a cost impact. | RM-Risk | 0.075 | 6
RM-887 | 0 | 0 | Random occurrence(s) | 170 | 1000 | 10%-25% | 170 | AURA was chosen as the basis because very little can be done in response to a rate change. AURA centers, including NOAO are subject to NSF approval so changes are well understood and will come with significant advanced warning. | Both Construction and Commissioning | 2019-07-02 23:00 | Active Risk/Opportunity | Project Management Office | Institutional Overhead Rates |  | 01C | IF institutional overhead rates increase THEN LSST could be faced with additional expenditures for work performed at that location. | RM-Risk | 0.17 | 6
RM-883 | 0 | 0 | Distributed occurrence | 2.5 | 100 | 0%-5% | 2.5 |  |  | 2019-07-03 16:17 | Active Risk/Opportunity | Telescope & Site | M1M3 damaged during vacuum lifting/installation |  | 4.6 | If lift and installation procedures are not followed during M1M3 integration in Tucson, THEN damage may occur to the M1M3 system | RM-Risk | 0.025 | 1
RM-891 | 0 | 0 | Random occurrence(s) | 340 | 2000 | 10%-25% | 340 |  | Both Construction and Commissioning | 2019-07-03 16:17 | Active Risk/Opportunity | Project Management Office | Unfavorable Non-Labor Estimate Uncertainty |  | 01C | IF the project underestimates the cost of material goods and other non-labor, or the Project has not planned for sufficient quantities to execute the plan, THEN the project will incur a cost increase. | RM-Risk | 0.17 | 9
RM-725 | 960 | 355.2 | Random occurrence(s) | 55.5 | 150 | 25%-50% | 410.7 | Management must accept this risk and actively implement the recommended mitigation activities. | Commissioning only | 2019-07-03 16:17 | Active Risk/Opportunity | Systems Engineering | Maintaining Engineering Staff Through Commissioning |  | 6 | IF the project cannot retain key engineering and technical staff through the commissioning phase THEN the successful completion of commissioning will be delayed or compromised. | RM-Risk | 0.37 | 12
RM-727 | 1800 | 306 | Random occurrence(s) | 0 | 0 | 10%-25% | 306 | This is beyond control of management and delay must be accepted. | Commissioning only | 2019-07-03 16:18 | Active Risk/Opportunity | Systems Engineering | Significant weather events delay commissioning effort |  | 6 | IF there is a long period of poor weather in either the System Integration and Test or Commissioning phase THEN there will be a delay in system first light and/or operation readiness. | RM-Risk | 0.17 | 0
RM-878 | 120 | 3 | Random occurrence(s) | 2.5 | 100 | 0%-5% | 5.5 |  | Both Construction and Commissioning | 2019-07-19 16:22 | Active Risk/Opportunity | Telescope & Site | Power distribution interruption |  | 4.12 | IF lightning strikes the facility, THEN power distribution interruptions may occur. | RM-Risk | 0.025 | 1
RM-874 | 200 | 5 | Random occurrence(s) | 2.5 | 100 | 0%-5% | 7.5 | Unavoidable cost | Both Construction and Commissioning | 2019-07-03 16:17 | Active Risk/Opportunity | Telescope & Site | Labor dispute at construction site |  | 4.1 | If there is a labor dispute on site during construction, THEN there will be schedule loss and additional labor costs | RM-Risk | 0.025 | 1
RM-783 | 80 | 29.6 | Distributed occurrence | 0 | 0 | 25%-50% | 29.6 | Subsystem managers support optimized redesign activities on both sides of the interface. |  | 2019-07-03 16:17 | Active Risk/Opportunity | Systems Engineering | Camera-Telescope Interface Development Synchronization |  | 6 | IF the Camera-Telescope ICDs are not synchronized prior to the earliest Phase 3 need dates, THEN systems engineering will have to initiate and negotiate unplanned technical change orders for vendor contracts or in-house designs. | RM-Risk | 0.37 | 0
RM-892 | 0 | 0 | Random occurrence(s) | 153 | 900 | 10%-25% | 153 | Plans for earlier hiring processes or allowing sufficient time to find staff on the right schedule is a necessary response to the staff positions that pose such risk in the working climate. | Construction only | 2019-07-03 16:17 | Active Risk/Opportunity | Project Management Office | Staffing Availability |  | 1.01C.01 | If staffing is not available for hire on the planned schedule, at the planned FTE, or at the expected level of expertise, or if it is under resourced in the baseline plan, then the costs for labor to accomplish the Programmed effort will change. | RM-Risk | 0.17 | 6
RM-893 | 120 | 44.4 | Random occurrence(s) | 0 | 0 | 25%-50% | 44.4 | Add more staff | Both Construction and Commissioning | 2019-07-03 16:17 | Active Risk/Opportunity | Project Management Office | Administrative Audit and Reporting Support |  | 01C.01 | IF the Government continues escalation of audit frequency and detail or reporting requirements THEN the Project Office may need additional Staffing | RM-Risk | 0.37 | 0
RM-897 | 80 | 6 | Random occurrence(s) | 10.5 | 140 | 5%-10% | 16.5 |  | Both Construction and Commissioning | 2019-07-03 16:18 | Active Risk/Opportunity | Project Management Office | Contract litigations |  | 01C.01 | If potential litigation issues associated with construction contracts happen, THEN severe impact to construction schedule is possible | RM-Risk | 0.075 | 2
RM-895 | 1800 | 135 | Random occurrence(s) | 0 | 0 | 5%-10% | 135 |  | Both Construction and Commissioning | 2019-07-03 16:18 | Active Risk/Opportunity | Project Management Office | Serious accident or fatality(ies) of personnel |  | 01C.03 | IF serious accident or fatality of personnel happens THEN the schedule will be delayed due to work stoppage, investigation and implementation of corrective actions | RM-Risk | 0.075 | 0
RM-896 | 40 | 6.8 | Random occurrence(s) | 42.5 | 250 | 10%-25% | 49.3 | The succession plan clearly indicates how responsibility and authority are transferred for key personnel. Recruitment would begin immediately and possible temporary staff will be found within the organization or collaborating organizations to find temporary support. | Both Construction and Commissioning | 2019-07-03 16:17 | Active Risk/Opportunity | Project Management Office | Loss of Key PMO Personnel |  | 01C.01 | IF there is an unplanned loss of key personnel in the PMO THEN there will be a loss of momentum and new recruitment will be required. | RM-Risk | 0.17 | 3
RM-898 | 120 | 9 | Random occurrence(s) | 9 | 120 | 5%-10% | 18 |  | Both Construction and Commissioning | 2019-07-03 16:18 | Active Risk/Opportunity | Project Management Office | Road safety - accidents |  | 01C.03 | IF Vehicular traffic accidents occur - especially on unpaved mountain road to Pachon, THEN minor cost impact is possible. | RM-Risk | 0.075 | 2
RM-805 | 100 | 63 | Random occurrence(s) | 126 | 200 | 50%-75% | 189 | Proposed response: Incentivize personnel to stay (e.g. science time, community visibility, growing responsibilities). Hire replacements (likely at additional cost), seek alternative options for developing deliverables, or activate descope options as appropriate. 2018 Oct 1: Have implemented 20% science time for scientific staff position. |  | 2019-07-23 22:28 | Active Risk/Opportunity | Education and Public Outreach | Loss of key EPO personnel |  | 5 | IF one or more key EPO personnel are lost to the Project through the end of commissioning or are not in the correct geographical location THEN some milestones may slip. Staffing. | RM-Risk | 0.63 | 5
RM-806 | 240 | 18 | Random occurrence(s) | 15 | 200 | 5%-10% | 33 | Replace obsolete packages with what has replaced them (likely better and easier to use anyway) | Both Construction and Commissioning | 2019-07-03 16:17 | Active Risk/Opportunity | Education and Public Outreach | Required EPO software packages not available |  | 5 | IF EPO's ongoing mitigation plan for choosing widely supported external software packages and staying up to date with changes and updates to external software THEN EPO programs become unsupported, obsolete, or unusable by community members. Examples include 3d javascript library and the graphing library d3.js. Software. | RM-Risk | 0.075 | 2
RM-747 | 100 | 7.5 | Random occurrence(s) | 0 | 0 | 5%-10% | 7.5 | Subsystem managers support optimized redesign activities on both sides of the interface. | Both Construction and Commissioning | 2019-07-03 16:18 | Active Risk/Opportunity | Systems Engineering | Camera-Data Management Interface Development Synchronization |  | 6 | IF the Camera-Data Management ICDs are not synchronized prior to the earliest Phase 3 need dates, THEN systems engineering will have to initiate and negotiate unplanned technical change orders for vendor contracts or in-house designs. | RM-Risk | 0.075 | 0
RM-753 | 120 | 0.6 | Random occurrence(s) | 7.725 | 1545 | 0%-1% | 8.32 | &lt;br&gt;Proposed response: Purchase more energy-efficient hardware. Reduce sky area or depth. Use StackFit only. Reduce complexity of algorithm. | Both Construction and Commissioning | 2019-07-03 16:18 | Active Risk/Opportunity | Data Management | New environmental regulations affecting data centers |  | 02C.07.09 | IF new environmental regulations require data centers to be more energy efficient than the baseline, THEN less capacity will be available at the Archive Center, leading to delays in processing campaigns for development and integration, commissioning, and early data previews | RM-Risk | 0.005 | 0
RM-860 | 240 | 6 | Random occurrence(s) | 4 | 160 | 0%-5% | 10 |  | Commissioning only | 2019-07-18 20:25 | Active Risk/Opportunity | Telescope & Site | M1M3 Mirror Cell Cart Hydraulic Lift overtravels and overloads telescope and cell Interface |  | 4.12 | IF M1M3 cart hydraulic lift overtravels and overloads the telescope and cell interface, THEN damage may occur to the interface. | RM-Risk | 0.025 | 1
RM-864 | 180 | 4.5 | Random occurrence(s) | 6.25 | 250 | 0%-5% | 10.75 |  | Commissioning only | 2019-07-03 16:17 | Active Risk/Opportunity | Telescope & Site | M2 surface damage during camera maintenance during commissioning |  | 4.12 | IF routine camera maintenance or filter change procedures fail, THEN there is risk of damage to M2 mirror. | RM-Risk | 0.025 | 1
RM-836 | 320 | 54.4 | Random occurrence(s) | 28.9 | 170 | 10%-25% | 83.3 |  | Both Construction and Commissioning | 2019-07-03 16:17 | Active Risk/Opportunity | Telescope & Site | Availability of all LSST components to commission OCS system |  | 4.1 | IF there is complication in commissioning of the OCS system with each of the other LSST components, THEN there may be schedule delays. | RM-Risk | 0.17 | 3
RM-776 | 240 | 88.8 | Random occurrence(s) | 0 | 0 | 25%-50% | 88.8 | Proposed response: Incentivize personnel to stay (e.g. science time, community visibility, growing responsibilities). Hire replacements (likely at additional cost). 2014.9.9: Have implemented 20% science time for all scientific staff positions. | Both Construction and Commissioning | 2019-07-03 16:18 | Active Risk/Opportunity | Data Management | Loss of key DM personnel |  | 02C.01 | IF one or more key data management personnel are lost to the project through the end of commissioning or are not in the correct geographical location THEN some milestones may slip | RM-Risk | 0.37 | 0
RM-728 | 40 | 3 | Random occurrence(s) | 150 | 2000 | 5%-10% | 153 | Initiate procurement of replacement filter asap, acknowledging that filter delivery may come after Operations Readiness Review (ORR). | Commissioning only | 2019-07-03 16:18 | Active Risk/Opportunity | Systems Engineering | Filter breakage |  | 6 | IF a filter is broken during early I&amp;T and Science Verification THEN the initial survey requirements for 6 filters will not be met. | RM-Risk | 0.075 | 6
RM-730 | 160 | 12 | Random occurrence(s) | 90 | 1200 | 5%-10% | 102 | Management must accept this risk cost. | Both Construction and Commissioning | 2019-07-03 16:17 | Active Risk/Opportunity | Systems Engineering | Vendor Support During Integration |  | 06C.03 | IF vendor supplied components fail during integration and the vendor does not provide adequate post-acceptance support, THEN the project may be required to spend resources to reverse engineer and fix the component. | RM-Risk | 0.075 | 6