## Slide 1: Camera responses to 2nd day questions NSF/DOE Joint Director’s Review August 7, 2019

## Slide 2: Remaining work
WBS (L2,L3) | Number of Control Accounts | Closed Control Accounts | Delivery as of July | ETC (May19) | FTE year for ETC (May19)
3.01 Management | 3 | 0 |  | $1,664 | 3.7
3.02 Systems Integration | 2 | 0 |  | $903 | 2.4
3.03 Science Sensors | 5 | 2 | Complete | $13 | 0.0
3.04.01 Science Raft Systems | 7 | 4 | Complete | $490 | 0.0
3.04.02 Corner Raft Systems | 5 | 2 | Complete | $74 | 0.0
3.05 Optics | 4 | 0 |  | $4,608 | 1.2
3.06.01 Camera Body | 2 | 0 |  | $120 | 0.3
3.06.02 Shutter | 2 | 0 |  | $224 | 0.4
3.06.04 Cryostat | 6 | 2 |  | $133 | 0.3
3.06.05 Utility Trunk | 2 | 0 |  | $356 | 0.7
3.07.01 Control System | 3 | 0 |  | $461 | 0.6
3.07.02 Data Acq Sys | 2 | 0 |  | $210 | 0.4
3.07.03 Aux Elec | 2 | 0 | Complete | $99 | 0.0
3.08 Integration and Test (3.08.06 ComCam) | 6 | 1 | ComCam Complete | $2,870 | 10.2
Total | 51 | 11 |  | $12,224 | 20.3

## Slide 3: There are no single procurements larger than $50K remaining to be awarded
WBS | Total procurement | % Completed | % Awarded in progress | % Not awarded but locked | % Not awarded
3.03 Science Sensors | $25,338K | 100.0% | 0.0% | 0.0% | 0.0%
3.04.01 Science Raft Systems | $4,549K | 100.0% | 0.0% | 0.0% | 0.0%
3.04.02 Corner Raft Systems | $3,096K | 100.0% | 0.0% | 0.0% | 0.0%
3.05 Optics | $19,439K | 85.2% | 14.8% | 0.0% | 0.0%
3.06.01 Camera Body | $555K | 100.0% | 0.0% | 0.0% | 0.0%
3.06.02 Shutter | $848K | 91.5% | 8.5% | 0.0% | 0.0%
3.06.04 Cryostat | $6,028K | 97.0% | 1.3% | 0.0% | 1.7%
3.06.05 Utility Trunk | $165K | 24.1% | 18.5% | 0.0% | 57.3%
3.07.01 Control System | $576K | 61.7% | 1.4% | 0.0% | 36.9%
3.07.02 Data Acq Sys | $1,515K | 100.0% | 0.0% | 0.0% | 0.0%
3.07.03 Aux Elec | $515K | 100.0% | 0.0% | 0.0% | 0.0%
3.08 Integration and Test | $2,901K | 90.9% | 3.9% | 0.0% | 5.2%
Total (as of May 2019) | $65,525K | 94.3% | 4.8% | 0.0% | 0.9%
Total (as of May 2018) | 83% | 11% | 2% | 4%