## Slide 1: LSST Camera DAQ Acquisition System (DAQ) Status Michael Huffer (SLAC) LSST Camera DAQ System Manager NSF/DOE Joint Status Review August 27–30, 2019
V1.3

## Slide 2: Outline
Introduction & Overview
  Requirements
  Architecture
  Major functional blocks
Status (technical)
  Major hardware/firmware functional blocks
  Major software functional blocks
  DAQ support for Camera and project development
Status (programmatic)
  Organizational structure
  Cost and schedule performance
  Risks
  Hazards
Transition to Commissioning and Operation
Summary
Supporting Material
  Key Documents
  Past reviews and response to recommendations
  BCR and EAC summaries

## Slide 3: The DAQ both acquires & buffers image data
In cryostat Sensors & Electronics, organized in modular units of Rafts
Commodity processors on both summit & base
Client & DAQ separated by a commodity Network
Major requirements (design drivers):
Data delivered to multiple, concurrent clients at read-out rate, in “real-time”
  Read-out rate is ~3.7 Gigabytes/second
Access to raft electronics for the purpose of configuration, monitoring and control
Common system clock & synchronous timing
Provide telescope guiding data
The DAQ is comprised of hardware, firmware and software!

## Slide 4: The DAQ’s major components and its clients
Source Communication Interface (SCI)
Read/Out
System
Image Store
Telescope
Guiding
API
Telescope
Adaptive control
API
QA &
diagnostics
API
Forwarding
(Alert processing & archiving)
API
Cryostat
Summit
Computer Room
Summit & Base
Facilities
TCS
CCS
DM
ROI
Wavefront
Wavefront & Science
Guiding Data System (GDS)

## Slide 5: An aside (The Camera’s FPA by the numbers)
The Focal Plane Array (FPA) is divided physically into 25 rafts
  21 science rafts in the center and 4 corner rafts
A raft’s electronics are organized in units of Raft-Electronics-Boards (REBs)
  A science raft contains three identical REBs
  A corner raft contains two REBs, a Guider REB and a Wavefront REB
Each REB manages a set of sensors
  Science REB manages three (3) sensors
  Guider REB manages two (2) sensors
  Wave-front REB manages one (1) sensor
From a DAQ perspective all sensors are relatively identical, they…
  contain ~16 Megapixels
  are read-out in parallel through 16 amplifiers
  contain pixels digitized with 18-bits of precision
Nominal cadence for science & wave-front sensors is a…
  15 second exposure followed by a 2 second readout
The guide sensors provide windowed data at roughly 9 Hz

## Slide 6: Acquired data buffered for as long as seven days
Requirement is derived from Observatory’s requirement to continue operation even with interruption of service between summit and base facility
  2 days covers Mean-Time-To-Repair for summit/base communication
  7 days covers MTTR for base/NCSA communication
For purposes of reliability at altitude flash, not rotational media is used
  Multiple, parallel drives to scale read performance (240)
  ~60 Gigabytes/second of external I/O capacity
Baseline is 240 Terabytes of storage
  Comfortably fits within ops plan for both day & night activity
  Also includes 2 days of simulation
The flash + its management system (hardware & software) is the Image-Store
  The Image Store is modeled as Network-Attached-Storage (NAS)
This was 2 days originally

## Slide 7: Block diagram of the DAQ System
Increasing distance
from Camera
Shaded brown indicates firmware or software

## Slide 8: Hardware/firmware

## Slide 9: The REB (Raft-Electronics-Board) and its FPGA
This is where it all starts (DAQ’s first functional block)
Each REB, regardless of type contains an identical FPGA
FPGA firmware is partitioned into two components separated by interface
  The SCI (Source-Communication-Interface)
  SSL (Sensor-Specific-Logic)
DAQ is also responsible for choice of:
  Data connector and its pin-out
  Cabling from connector downwards
Mini-SAS
(Signal connector)
3M Twin-ax
(to OTM)
FPGA

## Slide 10: The SCI (Source-Communication-Interface)
A small, lightweight, self-contained set of Core IP sharing the FPGA with its SSL
Employs high speed (3.125 Gbits/sec) point-to-point, serial, high-speed communication protocol (PGP)
  Protocol assures QOS through four Virtual Channels
The SCI Has four principal functions:
  Provide stable, system reference clock and synchronous commands
  Reliably encode & transmit 18-bit pixel data to CDS
  Reliably encode & transmit 18-bit diagnostic data to CDS
  Provides a mechanism for external configuration, control & monitoring of the REB’s sensor electronics
Sensor- specific Logic

## Slide 11: Cables between SCI & OTM
3M Twin Axial cable
  Longitudinal aluminum shield
  2 ground wires connected to shield
  4 pairs for high speed signals
    Impedance : 100 Ohm
    Propagation delay : 4.95 ns/m
    Intra-pair skew : <10 ps @ 3 m
    Attenuation : -4.9 dB/m @ 10 GHz
  4 single ended “sideband” signals
  1 mm minimum bend radius
High speed pairs (PGP primary & redundant)
4 single ended wires (used as 2 LVDS pairs)
Terminations:
  REB side uses Mini-SAS connector
  OTM side soldered directly to OTM
Cross- section of 3M cable

## Slide 12: The OTM (Optical-Transition-Module)
Has two functions:
  Converts signal paths from copper to fiber & fiber to copper
  Serves as cryostat penetration
Its a PCB board which also serves as the cryostat penetration
  Located on a flange
  Partly on “vacuum” side and partly on “air” side
Two transceivers (one “warm” and the other a cold spare)
  MTTF of both transceivers on any OTM is ~90,000 years @ 40C
One OTM services 12 SCIs (total system has 6)
3M Twin Axial soldered here
Fiber-optic transceiver(s)
“air” side
“vacuum” side

## Slide 13: Fiber run between Camera & Observatory computer room
The fiber run from the Camera boundary to the CDS is 145m (including contingency)
  Endpoint disconnects shown at the Camera (a) and CDS in the computer room (e)
Observatory operations and maintenance require the fiber run to be split in three places
  The boundary between the Camera Cable wrap and the spider vanes (b)
  At both ends of the maypole cable wrap (c) and (d)
Both Camera and Observatory have agreed to the:
  Number and type of fibers
  Number of spares
  Number of disconnects
  Connectors used at the Camera-Observatory interfaces

## Slide 14: Camera Telescope Interface
The Camera/integrating structure disconnect
  Marks the division between Camera and Observatory provided cables
  Allows the assembly of the integrating structure
  Space has been allocated on the interface plate which contains all camera utilities
  The DAQ will have two 1 x 6 MPT adapters, one for each side of the six OTMs (A/B)
  Cables originate on the OTMs & pass through the Utility Trunk to the camera side of the interface plate
This interface has been specified in an ICD between Camera and site
  ICD is released and under configuration control

## Slide 15: Camera Telescope Interface

## Slide 16: The CDS (Camera-Data-System) is an ATCA shelf
A front-board is a COB (Cluster-On-Board)
Each COB is paired with an RTM
  FPA-RTM (SCIs)
  SSD-RTM (Storage Array)
COBs are partitioned into two sets:
  3 service the FPA
  11 service the Store
COBs contain Reconfigurable-Cluster Elements (RCE)
An RCE is a processor executing server code
The CDS also contains:
  Timing Distribution
  112 port 10-Gigabit Ethernet
14 Slots with full-mesh backplane containing Front-boards and RTMs
RDS,IMS,RMS,DSS
SSD-RTM
FPA-RTM
Ethernet backbone (SFP+)
XDS

## Slide 17: ATCA 14 Slot Full-Mesh Shelf
External Ethernet
Shelf manager
Power supplies
Fans
RTM
Shelf Front
COB
Shelf Rear

## Slide 18: Cluster-On-Board (COB)
CI (32 port 10-GE switch)
DTM
1 of 4
DPM bays
Eight (8)
10-GE SFP+
1 of 2 RCEs
Zone 3
Front Board
RTM
Zone 2
Zone 1

## Slide 19: The Reconfigurable-Cluster-Element (RCE)
Based on System-On-Chip (SOC) technology
The RCE is a a generic computational node
It’s an FPGA, It’s a DSP, It’s a Processor:
  Dual-core (A-9) ARM processor (@ 1 GHZ)
  1 GByte of DDR3 RAM
  Up to 64 Gigabytes of flash
  Memory subsystem has > 6 GBytes/sec of I/O capacity
  Real-Time kernel (RTEMS)
  Full TCP/IP stack
RCE’s host all Server software

## Slide 20: FPA-RTM
CXP transceiver
(12 full-duplex channels)
P3
To (up to) 12 SCI’s on 1 to 4 rafts
To/From COB (its RCEs)
GPS receiver & Time-Of-Day

## Slide 21: SSD-RTM
One of 2 layers (8 drives)
Layer’s
power conversion
Bottom layer mated directly on RTM
1 Terabyte 1.5” SATA SSD
To/From COB (its RCEs)

## Slide 22: Software

## Slide 23: The bucket is the unit in which data are stored
The Image Store buffers Images
Data accessible only after committed
Images sort naturally into 2 epochs:
  While filling (only one)
  While resident (many)
Access is provided in either epoch:
  Filling satisfies real-time, low latency requirements
  Resident images are randomly accessible through an image catalog
Should be 7 days!

## Slide 24: The sources of an image are stored in parallel
source0
source1
Sourcem-1
sourcem
Imagename
Image
Source
Pixels
t0
t2
in parallel
in parallel
Slicen-1
Slice0
Slice1
Slicen
Slicen-1
Slice0
Slice1
Slicen
Slicen-1
Slice0
Slice1
Slicen
Slicen-1
Slice0
Slice1
Slicen
in parallel
in parallel
in parallel

## Slide 25: Software Services
Services are the software expression of the DAQ system’s capabilities
  Any one service contains multiple functions (as classes & methods)
There are five principal services. These are:
Raft Management:
  Access to raft electronics for the purposes of
  configuration, monitoring & control
Raft Data Acquisition:
  Acquires raft-based data (both pixel & metadata)
  Commits that data to the Image-Store
Image Management:
  Initiates and orchestrates image creation
  Manages image catalog
Storage Access:
  Provides access to the Image-Store
  Manages the allocation/de-allocations of buckets
  Provides both read & write access to the data of a bucket
Emulation facility
  API to create emulated images
  Facility to “playback” images (emulated or otherwise)
For purposes of development the five services are implemented through 25 different packages

## Slide 26: A service follows a Client/Server pattern
Two processors separated by a network
  Server performs work (the Service)
  Client uses its results
Server & Client hide the mechanics of accessing network behind interfaces
Server code executes exclusively on RCEs (within the CDS)
  Employs an Open-Source Real-Time kernel (RTEMS)
Server code is stored on each RCE’s configuration flash
Servers start automatically on RCE boot
Client code executes on either hosts or RCEs
  It’s designed to be portable across both Linux & RTEMS
Client applications are built by linking against client libraries

## Slide 27: Technical status

## Slide 28: Status (major hardware/firmware blocks)
REB (hardware interface)
  Connector pin-out stable and in use by all boards
  Connector shown to be vacuum compliant
SCI (firmware + interface)
  Development is complete and in use in the field
Timing distribution hardware and firmware
  Development is complete and in use in the field
OTM + vacuum cables:
  Production is complete & all OTMs are in the cryostat
Fiber-Runs (Telescope/Camera ICD):
  Telescope is performing acquisition based on agreed ICD
ATCA shelves
  Qualified one vendor, procurement is complete
COB
  Production is complete ( > 200 boards)
FPA-RTM
  Production is complete ( 18 boards)
SSD-RTM
  Production is complete (18 boards)
  Testing remains underway
SATA Firmware
  Development is complete
Includes NCSA system, ComCam, AuxTel as well as the camera

## Slide 29: Status (System Software)
Release | Hardware | Firmware | Software Services | Comments | Status
V1 | REB COB Hybrid RTM | SCI PGP-V1 | Raft Management Service Raft Data Storage Service Image Management Service Distributed Storage Service | GEN-III prototype interfaces 3-REB readout no synchronization “soft” Image Store | Complete
V2 |  | Timing firmware, PGP-V2 | Implementation changes for RDS & IMS. | Synchronized timing and commands | Complete
V3 | SSD-RTM | SATA-II firmware | SATA-II driver support. Implementation changes in XDS, RDS & IMS | “hard” Image Store | Complete
V4 | FPA-RTM |  | EMU Emulation Service | Emulation Services | Complete
V5 | “New” COB FPA-RTM | Cross-talk correction firmware | Implementation changes for IMS | Cross-Talk correction | Not yet started.
  From software services & a hardware/firmware substrate Systems are composed…
  Baseline proposed five different system releases, timed to match camera and project needs
Integration of “glue” software (necessary to transit from soft to hard store) remains…

## Slide 30: Status (Engineering-Test-Unit (ETU))
Designed to explore and validate scaling laws. It’s a:
Platform to simulate 50% of the FPA & DAQ System:
  SCIs
  OTMs
  CDS
  Storage-Array
Platform to simulate up to 16 hosts and their clients
Status: Complete
6-slot CDS
Cluster of up to 16 hosts

## Slide 31: Status (SCI board)
Single FPGA which contains 12 independent SCIs
  Connects to all 12 channels of an OTM
  Has a separate high frequency, high precision clock
Uses
  Test synchronous commanding over an entire OTM
  Simulate 12 REBs
  Testing production data path…
  including observatory fiber-optic cable plant without either Camera or ComCam
Used …
  To test V1 DAQ installation for TS-8 at BNL
  For functional tests of OTM
Status
  Complete
  3 in hand

## Slide 32: Support for camera & project development
  In use…
    BNL (Raft production & sensor development)
    Paris-IN2P3 (Sensor development)
    SLAC-CCS (DAQ/CCS integration)
    SLAC-I&T (Raft acceptance)
    NCSA (DAQ/DM integration)
    Tucson (TCS/DAQ integration)
    Harvard/Tucson (Aux Telescope)
    Commissioning Camera
  NCSA production system ready to ship…
    Increases both its functionality & performance
    Exact copy of system used by camera

## Slide 33: Programmatic Status

## Slide 34: Organization chart
SLAC
  Michael Huffer (CAM & Subsystem manager)
  Gregg Thayer (Deputy)
  Stefano Russo
  Sergio Maldonado
Engineering support from Gunther Haller’s division (TID):
Ryan Herbst’s group for board and FPGA design
Lupe Salgado’s group for board production
Their work is complete and they are now off-project
Their work is complete and they are now off-project

## Slide 35: DAQ Performance as of May 2019
DAQ cumulative SPI = 0.94
DAQ cumulative CPI = 0.88
Control Account | BCWS | BCWP | ACWP | SV | SPI | CV | CPI | BAC | EAC | % Comp
3.07.02 Data Acquisition System | $5,657 | $5,301 | $6,011 | ($356) | 0.94 | ($710) | 0.88 | $5,688 | $6,222 | 93%

## Slide 36: DAQ performance trend
SPI has been in decline due to delays in SATA firmware development
CPI has been on a slow decline due to unanticipated labor in developing new COB
Both SPI and CPI have now stabilize as the above issues have now been resolved

## Slide 37: DAQ Variance Analysis
DAQ has one reportable negative schedule variance due to:
  Unanticipated delay to layout new COB PCB
  Unanticipated delay to producing SATA firmware for V3
DAQ raft has three reportable, negative cost variances
  $250K The review committee for the DAQ FDR remarked that the labor required to meet the schedule for V1 was under-estimated and as a tier-1 action requested an additional FTE. This FTE was found (Joanne Bogart) and applied with the result that V1 was delivered on time. This cost was included in the last ETC.
  $35K. The DAQ system, through its OTM, became the pathfinder for all Camera vacuum processing and the costs associated with this role were never scoped. This cost was included in the last ETC.
  $211K. The Raft Electronics Board turned out be incapable of producing its own address with in the Camera mosaic. As a consequence a distributed, highly performing database needed to be added to the DAQ system. The technical complexity associated with this task was grossly underestimated. This variance represents the labor necessary to add this functionality.

## Slide 38: DAQ Estimate to complete status
Comprehensive estimate at completion performed on 10/2018 (performed yearly)
An additional update was done in the month of January
EAC key drivers:
Additional, one 1 year FTE as requested by FDR committee (~ -$250K)
Over-run (Additional vacuum processing labor (~-$35K))
Over-run (Necessary re-spin of new COB (~-$80K))
Savings found in elimination of unnecessary scope (~$20K)
Control Account | BAC | EAC | VAC | %Comp
DAQ Management | 1,079,615 | 1,275,095 | -195,480 | N/A
DAQ Hardware & software | 4,608,259 | 4,946419 | -338,160 | 93%

## Slide 39: Definition of Risk and Risk Analysis
Risk can be defined as an undesirable event during project execution that negatively affects program goals for performance, cost or schedule.
Risk management is the ongoing process of comprehensively assessing project risks.
Camera Risk Management Plan (LCA-29-A) defines the methodology to manage our risks
Quasi-quantitative process to assign objective values to probability of occurrence and impact of occurrence aspects of risk.
Total Impact:
(0.50*Cost Impact) + (0.33*Schedule Impact) + (0.33*Performance Impact)
Risk Score:
Risk Probability * Total Impact
Pts | Severity of Impact | Description of Impact
Cost Impact |  | 
1 | Insignificant | Overrun of cost of < $30K, recoverable with project contingency
2 | Minor | Overrun of cost of $30k - $200K, recoverable with project contingency
3 | Moderate | Overrun of cost of 200k - $1.5M, with significant impact on contingency
4 | High | Overrun of baseline cost of $1.5M - $10M, with re-baseline required
5 | Critical | Overrun of baseline cost of >$10M, with project in jeopardy
Schedule Impact |  | 
1 | Insignificant | Degradation of schedule margin to project critical path by < 2 wks
2 | Minor | Degradation of schedule margin to project critical path by 2 wks to 1.5 months
3 | Moderate | Degradation of schedule margin to project critical path by 1.5 to 3 months
4 | High | Degradation of schedule margin to project critical path by 3 to 6 months
5 | Critical | Degradation of schedule margin to project critical path by > 6 months
Performance Impact |  | 
1 | Insignificant | No effect on ability to meet requirements; minor design changes needed
2 | Minor | Minor excursion from subsystem requirement, but compensated elsewhere
3 | Moderate | Level 2 and/or SRD design specification exceeded
4 | High | Level 1 and/or SRD minimum specification exceeded
5 | Critical | Unable to achieve any of the primary science missions
Pts | Likelihood of Occurrence | Approximate Probability | Description of Probability
1 | Rare | <1% | Likelihood of occurrence is not credible
2 | Unlikely | 1-5% | Not reasonably expected to occur
3 | Possible | 5-25% | Possible, or difficult to assess the chance of occurrence
4 | Likely | 25-67% | Very likely that an adverse event will occur
5 | Highly Probable | >67% | High probability that an adverse event will come to pass
Definition of Risk Probability
Definition of Risk Impact

## Slide 40: Standardized risk management processes used to manage DAQ risks
Risks are tracked in the Camera Risk registry, Document LCA-29
Risk exposure is assessed and tracked at regular intervals since 2010
Actively planning mitigation to burn down risks and monitor progress
  Current status: 10 total risks identified
    1 risks is actively being mitigated
    9 are closed or accepted due to design changes or mitigation completion
Mitigations are budgeted in the scope of work
After budgeted mitigation (Post-Mitigation) is performed, residual risk is analyzed
The last remaining active risk will be retired at the next risk management meeting…
  Does DAQ have enough man-power to not impact the camera schedule? :
  Target requirement was delivery of V4 and completion of hardware production….
    done

## Slide 41: Hazard Overview
For LSST hazards are defined as a failure of a component, system or function that could lead to personnel injury or damage to hardware (Hazards are not risks).

## Slide 42: DAQ Hazards
In general the DAQ system can be considered hazard free
  For both personnel and equipment
Equipment exceptions are ESD related:
  ATCA boards, RTMs and OTMs
Personnel exceptions are ATCA shelf power related:
  Low voltage supply (48 VDC), but high current
  Input is at rear of shelf with minimum exposure
    Shelves are housed in summit facility supplied racks
These are all well-understood, conventional, occupational hazards
  Mitigation will be administrative
    Well identified procedures and training
    Follow accepted ESD plan for handling electronic boards, devices & equipment

## Slide 43: Transition to commissioning & operations
Installed early version of DAQ system at NCSA
  Emulation allows DAQ/DM API to be exercised in the Camera’s absence
  Later this summer NCSA system will grow to become a copy of summit system
DAQ is an integral partner in the project-wide “path-finding” exercises led by Michael Reuter from Project Systems-Engineering.
DAQ is a founding member of Jeff Kantor’s “tiger-team” which coordinates shared infrastructure & networking on summit.
ComCam uses a DAQ system identical to the Camera
The Calibration Telescope uses a DAQ system identical to the Camera’s
DAQ has planned its own specific early summit integration exercises:
  Validate telescope fiber-optic installation
  Validate use of DWDM equipment between summit & base
  Commission and verify networking infrastructure before Camera(s) summit arrival
A significant effort has gone into into integration of the DAQ on the summit…
Data Management is DAQ’s principal client

## Slide 44: Summary
Major Accomplishments:
  ETU & SCI board complete & operational
  All hardware/firmware for DAQ Versions 1-4 complete
  Emulation & playback facility complete
  Deployed full hardware + DAQ Version 4 to camera (in IR-2)
  Deployed DAQ test-stand support to seven different sites
  Completed OTM production and successful integration with cryostat
  Completed SATA II Firmware
  Completed COB + RTM production
6 Month look-a-head goals:
  Deploy V4 + corresponding hardware to NCSA
  Complete GDS
  Port “soft” to “hard” storage system
  Perform early summit integration
  Continue to support deployed DAQ systems
6-slot CDS
6-slot CDS
6-slot CDS

## Slide 45: End of Presentation

## Slide 46: Supporting Material

## Slide 47: Key Documents are available on “Additional Docs” Tab in Confluence
Key Documents & Reviews for the corner raft subsystem can be found at (contact the Camera point of contact for access):
  https://confluence.slac.stanford.edu/display/LSSTCAMREV/Home
This site contains:
  Project Documents
  Design and Allocated Baseline Documents
    Specifications
    ICDs
    Design Documents
  Cost and Schedule Baseline
  Design Reviews & Relevant Presentations
    Preliminary Design Review
    Other reviews
  Focused Topics

## Slide 48: DAQ WBS (Management + Hardware)
WBS | Title | Key Deliverable
3.07.02 | DAQ | Management, development design, engineering, production, assembly and testing effort to produce the DAQ system hardware and software.
3.07.02.01 | DAQ Integration & Management | Management effort and travel including overall system design for all the DAQ Hardware and Software.
3.07.02.02 | DAQ Hardware & Software | Hardware and software design, engineering, production, assembly and testing effort to deliver the DAQ hardware and software
WBS | Title | Key Deliverable
3.07.02.02.01 | OTM and Cabling | Development, design, engineering, production, assembly & testing effort to produce the Optical Transition Module &associated cabling.
3.07.02.02.02 | DAQ COB | Development, design, engineering, production, assembly and testing effort to produce the COB main modules with associated daughter modules (DPM, DTM).
3.07.02.02.03 | FPA/SSD RTM | Development design, engineering, production, assembly & testing effort to produce the FPA/SSD RTM for communication and storage.
3.07.02.02.04 | FPA RTM | Development design, engineering, production, assembly & testing effort to produce the FPA/RTM for communication.
3.07.02.02.05 | SSD-RTM | Development design, engineering, production, assembly and testing effort to produce the SSD Rear Transition Module for data storage.
3.07.02.02.06 | ATCA Shelves | Summarizes the purchase & testing effort to produce ATCA shelves.

## Slide 49: DAQ WBS (Management + Hardware)
WBS | Title | Key Deliverable
3.07.02.02.07 | SCI Firmware | Development, design, engineering and testing effort to produce the Source Communication Interface Firmware.
3.07.02.02.08 | Crosstalk Correction Firmware | Development, design, engineering and testing effort to produce the Crosstalk Correction Firmware.
3.07.02.02.09 | Image Management Services | Development design, engineering and testing effort to produce the Raft Management/Data Server/Image Management Server Software (RMS/RDS/IMS).
3.07.02.02.10 | Timing Distribution Server Hardware and Software (TDS) | Development design, engineering, production, assembly and testing effort to produce the Timing Distribution Server Hardware and Software (TDS).
3.07.02.02.11 | FPA Emulation Server Software (FES/FEC) | Development design, engineering and testing effort to produce the FPA Emulation Server Software.
3.07.02.02.12 | Storage Array Software (SAS/SAC) | Development design, engineering and testing effort to produce the ATCA shelves. Storage Array Software (SAS/SAC)
WBS | Title | Key Deliverable
3.07.02.02.13 | DAQ Systems | Development design, engineering, production, assembly and testing effort to produce all the test stands for the subsystem efforts for the Science raft testing (BNL, France), the Corner raft testing (SLAC, Harvard), for I&T at SLAC, and for the Commissioning Camera. This WBS also includes the full production DAQ system to be delivered to the Camera. Development, design, assembly & testing effort to produce the Engineering-Test-Unit. The ETU is designed to explore the performance scaling envelope and functions of the DAQ system before introduction on the summit.

## Slide 50: Reviews
Response to CD-3 Review
  No DAQ-specific recommendations
Response to recent Final Design Review
  DAQ FDR (June 1, 2015)
  No Tier 1 action items

## Slide 51: DAQ Baseline Changes since CD-2 (major changes 1)
BCR-002: Schedule update (Work Sequencing/Resource Allocation)
  No Major changes, total Cost change ($150)
BCR-011 #2: Schedule update (Work Sequencing)
  Re-planned DAQ/CCS V1.0 and V2.0 work going to Science Raft Test Stand 8.
  Total Cost change $558
BCR-013 #2: Removed DAQ V3.1
  DAQ V3.1 no longer an official release version.
  Moved all DAQ V3.1 work into DAQ V3.0.
  Total Cost change $998
BCR-031 #3 DAQ Re-plan
  Total Cost change $8,099

## Slide 52: DAQ Baseline Changes since CD-2 (Major changes 2)
BCR-056 #2 DAQ SATA Firmware
  Labor required more effort then planned
  Total Cost change $44,367
BCR-066 #2 COB Hardware Components
  Total Cost change $105,358
BCR-070 #1 DAQ Guiding Data System
  New scope added to DAQ WBS
  Total Cost change $168,397
BCR-081 #1 DAQ Programming of REB FPGA
  New scope added to DAQ WBS (multi-boot support)
  Total Cost change $76,590
BCR-081 #2 DAQ New Layout for the COB
  New scope added to WBS (add 32 port switch to COB)
  Total Cost change $70,668

## Slide 53: DAQ Baseline Changes since CD-2 (rate updates)
BCR-001: FY15 Rate update
  No Major changes, total cost change ($12786)
BCR-021 #3: FY16 Rate update
  No Major changes, total cost change $15,807
BCR-039 LSST Camera Re-org
  No Major changes, total cost change ($16,563)
BCR-044 January 2017 FY17 Rate Update
  No Major changes, total cost change $20,790
BCR-067 FY18 Rate Updates
  No Major changes, total cost change $4,092
BCR-083 FY19 Rate Updates
  No Major changes, total cost change $5,558

## Slide 54: DAQ Baseline Changes since CD-2 (planning packages 1)
BCR-022 #1: Planning Package Schedule update
  No Major changes, total Cost change $10,075
BCR-024 #2: Planning Package Schedule update
  No Major changes, total Cost change $2,588
BCR-028 #7: Planning Package Schedule update
  No Major changes, total Cost change $8,099
BCR-031 #4 Planning Package Updates
  No Major changes, total Cost change $19,064
BCR-041 #3 Planning Package Updates
  No Major changes, total Cost change $1,493
BCR-047 #3 Planning Package Updates
  No Major changes, total Cost change $1,952

## Slide 55: DAQ Baseline Changes since CD-2 (planning packages 2)
BCR-054 #3 Planning Package Updates
  No Major changes, total Cost change $966
BCR-059 #3 Planning Package Updates
  No Major changes, total Cost change $291
BCR-061 #5 Planning Package Updates
  No Major changes, total Cost change $0
BCR-072 #5 Planning Package Updates
  No Major changes, total Cost change $0
BCR-074 #1 Planning Package Updates
  No Major changes, total Cost change ($164)